## Data ETL Task Status
UID | WBS | EMAIL SENT | TASK COMPLETION | STATUS | Task Name | Duration (Hrs) | Start | Finish | BaseLine Start | Resource Names | Team | Predecessors | Tag Status | Defect | Comments | Actual Resources | Start IST | Big3 Check | Cutover Change Required | Defect - cutover | Defect - cutover - Description | Cutover Change Status | Updated Resources | Base Line Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Status to be updated | #start | #issue | #done | There
94411 | WBS.2.1.10.2.1.5 | N | N | Planned | Execute Extracts from MP2 for master data and non open item transaction data conversions | 6 | 2021-01-17 21:45 | 2021-01-18 07:00 | 2021-01-18 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2021-01-18 08:15 | [6 empty] | 1 | 1: 93067 - Planned | #done | FALSE | FALSE | TRUE | TRUE
3968 | WBS.2.1.10.2.6.11 | N | N | Planned | Execute Extracts from AS8 (PTM) for master data and non open item transaction data conversions | 4 | 2021-01-18 01:00 | 2021-01-18 05:00 | 2021-01-18 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2021-01-18 11:30 | [7 empty] | 1: 93067 - Planned | #done | FALSE | FALSE | TRUE | TRUE
3967 | WBS.2.1.10.2.6.10 | N | N | Planned | Execute Extracts from Maintelligence for master data and non open item transaction data conversions | 2 | 2021-01-18 01:00 | 2021-01-18 03:00 | 2021-01-18 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2021-01-18 11:30 | [7 empty] | 1: 93067 - Planned | #done | FALSE | FALSE | TRUE | TRUE
3966 | WBS.2.1.10.2.6.4 | N | N | Planned | Execute Extracts from AS8 for master data and non open item transaction data conversions | 6 | 2021-01-18 01:00 | 2021-01-18 07:00 | 2021-01-18 | ANJALI SINHA | DATA | 93067 | #done |  |  | ANJALI SINHA | 2021-01-18 11:30 | [7 empty] | 1: 93067 - Planned | #done | FALSE | FALSE | TRUE | TRUE
3964 | WBS.2.2.1.7.13.3 | N | N | Planned | Execute Extracts from ECC for master data - confirm completed | 5 | 2021-01-18 01:00 | 2021-01-18 06:00 | 2021-01-18 | ANJALI SINHA | Data | 93067 | #done |  |  | ANJALI SINHA | 2021-01-18 11:30 | [7 empty] | 1: 93067 - Planned | #done | FALSE | FALSE | TRUE | TRUE
82569 |  | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - AC | 0.5 | 2021-01-18 01:00 | 2021-01-18 01:30 | 2021-01-18 | JASPREET SINGH | DATA | 4063 | #done |  |  | JASPREET SINGH | 2021-01-18 11:30 | [7 empty] | 1: 4063 - Planned | #done | FALSE | FALSE | TRUE | TRUE
82566 | WBS.2.1.4.1.1.9 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - SCM | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | 2021-01-18 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2021-01-18 16:45 | [7 empty] | 1: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82567 | WBS.2.1.4.1.3.8 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - EWM | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | 2021-01-18 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2021-01-18 16:45 | Material | [6 empty] | 1: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82574 | WBS.2.1.10.2.6.3 | N | N | Planned | MC Task ¦ Create HDBODBC Connection And Validate For QA | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | 2021-01-18 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2021-01-18 16:45 | [7 empty] | 1: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82575 | WBS.2.1.10.2.6.5 | N | N | Planned | MC Task ¦ Sanity Testing of Job Execution In BODS QA | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | 2021-01-18 | JASPREET SINGH | DATA | 36501 | #done |  |  | JASPREET SINGH | 2021-01-18 16:45 | [7 empty] | 1: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82561 | WBS.2.1.4.1.1.4 | N | N | Planned | Create XREF Table Indices In HANA DB | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | 2021-01-18 | ANKIT AGARWAL | DATA | 36501 | #done |  |  | ANKIT AGARWAL | 2021-01-18 16:45 | [7 empty] | 1: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10137 | WBS.2.1.15.17.1.8 | N | N | Planned | MDG_C0098 - Execute DQ job to identify in-scope AS8 Procured materials | 4 | 2021-01-18 06:45 | 2021-01-18 10:45 | 2021-01-18 | PRADEEP CHEEDALLA | DATA | 4229,36501 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-18 17:15 | [7 empty] | 1: 4229 - Planned; 2: 36501 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82570 | WBS.2.1.10.2.6.1 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - PTP | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | 2021-01-18 | JASPREET SINGH | DATA | 80788 | #done |  |  | JASPREET SINGH | 2021-01-18 17:15 | [7 empty] | 1: 80788 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89984 | WBS.2.1.15.9.1.20 | N | N | Planned | PTM_C0245 - Execute Preload - TAPPI ID conversion | 2 | 2021-01-18 07:15 | 2021-01-18 09:15 | 2021-01-18 | PRADEEP CHEEDALLA | DATA | 89985 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-18 17:45 | [6 empty] | 1 | 1: 89985 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
97821 | WBS.2.2.1.7.16.5 | N | N | Planned | CSR - Assignment of a special procurement key to a material | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | 2021-01-18 | SHANKAR RAMNARAYANAN | Data | 7819 | Yet to receive |  |  | SHANKAR RAMNARAYANAN | 2021-01-18 18:45 | [7 empty] | 1: 7819 - Planned | Yet to receive |  |  |  | FALSE
92780 | WBS.2.1.15.23.1.1 | N | N | Planned | Execute Preload ITR_C0016.1 - Convert Functional Locations - MP2 | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | 2021-01-18 | JASPREET SINGH | DATA | 92781,5782 | #done |  |  | JASPREET SINGH | 2021-01-18 19:00 | [6 empty] | 1 | 1: 92781 - Planned; 2: 5782 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5390 | WBS.2.1.15.20.1.1 | N | N | Planned | ITR_C0016 - Execute Preload - Convert Functional Locations - AS8 | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | 2021-01-18 | JASPREET SINGH | DATA | 5782 | #done |  |  | Sourabhi Mandal | 2021-01-18 19:00 | [6 empty] | 1 | 1: 5782 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89675 | WBS.2.1.8.2.2.2 | N | N | Planned | Update Vendor cross reference and Vendor In-Scope | 2 | 2021-01-18 08:45 | 2021-01-18 10:45 | 2021-01-18 | ANJALI SINHA | DATA | 89679 | #done |  |  | ANJALI SINHA | 2021-01-18 19:15 | Material | [6 empty] | 1: 89679 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82565 | WBS.2.1.4.1.1.5 | N | N | Planned | MDG_C0098 - Maintain XREF Values In BODS For Procured Materials Conversion | 0.5 | 2021-01-18 08:45 | 2021-01-18 09:15 | 2021-01-18 | JASPREET SINGH | DATA | 9125 | #done |  |  | JASPREET SINGH | 2021-01-18 19:15 | [7 empty] | 1: 9125 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89674 | WBS.2.1.4.1.1.11 | N | N | Planned | Update Material cross reference and In-Scope tables | 1 | 2021-01-18 08:45 | 2021-01-18 09:45 | 2021-01-18 | DEEPA SAW | DATA | 36501,9125 | #done |  |  | DEEPA SAW | 2021-01-18 19:15 | [7 empty] | 1: 36501 - Planned; 2: 9125 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5084 | WBS.2.1.10.2.6.8 | N | N | Planned | MDG_C0098 - Execute Transform program for AS8 Procured materials | 4 | 2021-01-18 08:45 | 2021-01-18 12:45 | 2021-01-18 | DEEPA SAW | DATA | 4229,9125 | #done |  |  | DEEPA SAW | 2021-01-18 19:15 | [7 empty] | 1: 4229 - Planned; 2: 9125 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90888 | WBS.2.2.1.7.13.24 | N | N | Planned | MDG_C0098 - Execute Preload for ZUNB materials manual load file | 2 | 2021-01-18 09:15 | 2021-01-18 11:15 | 2021-01-18 | PRADEEP CHEEDALLA | Data | 90886,90887,3976,4229 | #done |  |  | Aarthi | 2021-01-18 19:45 | [7 empty] | 1: 90886 - Planned; 2: 90887 - Planned; 3: 3976 - Planned; 4: 4229 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89982 | WBS.2.1.8.2.2.1 | N | N | Planned | PTM_C0245 - Execute Load program - TAPPI ID conversion | 3 | 2021-01-18 09:30 | 2021-01-18 12:30 | 2021-01-18 | ANURAG ANAND | DATA | 89983 | #done |  |  | ANURAG ANAND | 2021-01-18 20:00 | Material | [6 empty] | 1: 89983 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5387 | WBS.2.1.15.6.1.4 | N | N | Planned | ITR_C0064 - Execute Load program - Convert Code And Code Groups | 1 | 2021-01-18 10:00 | 2021-01-18 11:00 | 2021-01-18 | VENKATESH GANESHAN | DATA | 4091,3995 | #done |  |  | VENKATESH GANESHAN | 2021-01-18 20:30 | [6 empty] | 1 | 1: 4091 - Planned; 2: 3995 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5381 | WBS.2.1.15.15.1.12 | N | N | Planned | ITR_C0070 - Execute Load program - Convert Characteristics - AS8 and MP2 | 1 | 2021-01-18 10:00 | 2021-01-18 11:00 | 2021-01-18 | ANURAG ANAND | DATA | 3992,4091 | #done |  |  | ANURAG ANAND | 2021-01-18 20:30 | [7 empty] | 1: 3992 - Planned; 2: 4091 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5233 | WBS.2.1.9.29.1.3 | N | N | Planned | PTP_C0001 - Execute Transform program - Convert PTP contracts | 2 | 2021-01-18 10:45 | 2021-01-18 12:45 | 2021-01-18 | ANKIT AGARWAL | DATA | 89679,89675,3964,82570,97452 | #done |  |  | Ishaq | 2021-01-18 21:15 | [6 empty] | 1 | 1: 89679 - Planned; 2: 89675 - Planned; 3: 3964 - Planned; 4: 82570 - Planned; 5: 97452 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5243 | WBS.2.1.8.1.1.58 | N | N | Planned | PTP_C0008 - Execute Transform program - Convert Purchase Info Record - ECC | 1 | 2021-01-18 10:45 | 2021-01-18 11:45 | 2021-01-18 | ANJALI SINHA | DATA | 89675,89679,3964,82570,97452 | #done |  |  | ANJALI SINHA | 2021-01-18 21:15 | Material | [6 empty] | 1: 89675 - Planned; 2: 89679 - Planned; 3: 3964 - Planned; 4: 82570 - Planned; 5: 97452 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5392 | WBS.2.1.8.2.1.22 | N | N | Planned | ITR_C0016 - Execute Load program - Convert Functional Locations - AS8 | 5 | 2021-01-18 11:00 | 2021-01-18 16:00 | 2021-01-18 | JASPREET SINGH | DATA | 5391 | #done |  |  | Sourabhi Mandal | 2021-01-18 21:30 | Material | [6 empty] | 1: 5391 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5384 | WBS.2.1.15.15.1.9 | N | N | Planned | ITR_C0069 - Execute Load program - Convert Classes - AS8 and MP2 | 1 | 2021-01-18 11:30 | 2021-01-18 12:30 | 2021-01-18 | ANURAG ANAND | DATA | 5382 | #done |  |  | ANURAG ANAND | 2021-01-18 22:00 | [7 empty] | 1: 5382 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92778 | WBS.2.1.15.19.1.1 | N | N | Planned | Execute Load ITR_C0016.1 - Convert Functional Locations - MP2 | 3 | 2021-01-18 11:30 | 2021-01-18 14:30 | 2021-01-18 | JASPREET SINGH | DATA | 92779 | #done |  |  | JASPREET SINGH | 2021-01-18 22:00 | [7 empty] | 1: 92779 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10116 | WBS.2.1.15.8.1.4 | N | N | Planned | PTM_C0079 - Execute transformation for Work Center Conversion | 1 | 2021-01-18 12:00 | 2021-01-18 13:00 | 2021-01-18 | ANURAG ANAND | DATA | 89610,92229,92244,93067,91838,4667,94432,96559 | #done |  |  | ANURAG ANAND | 2021-01-18 22:30 | [7 empty] | 89610 - Planned | 92229 - Planned | 92244 - Planned | 93067 - Planned | 91838 - Planned | 4667 - Planned | 94432 - Planned | 96559 - Planned |  |  |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
9174 | WBS.2.2.1.7.13.22 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS semi-finished materials manual load file | 3 | 2021-01-18 12:45 | 2021-01-18 15:45 | 2021-01-18 | PRADEEP CHEEDALLA | Data | 3976,9851,9852,4229 | #done |  |  | Aarthi | 2021-01-18 23:15 | [7 empty] | 1: 3976 - Planned; 2: 9851 - Planned; 3: 9852 - Planned; 4: 4229 - Planned | #start | FALSE | FALSE | TRUE | TRUE
10138 | WBS.2.1.9.11.1.1 | N | N | Planned | MDG_C0098 - Compare DQ and ETL filtered in-scope AS8 Procured Materials and analyze/report differences | 3 | 2021-01-18 12:45 | 2021-01-18 15:45 | 2021-01-18 | PRADEEP CHEEDALLA | DATA | 10137,5084 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-18 23:15 | [7 empty] | 1: 10137 - Planned; 2: 5084 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10492 | WBS.2.1.9.6.1.2 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Basic View | 1 | 2021-01-18 12:45 | 2021-01-18 13:45 | 2021-01-18 | DEEPA SAW | DATA | 5084 | #done |  |  | DEEPA SAW | 2021-01-18 23:15 | Customer | [6 empty] | 1: 5084 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
95364 | WBS.2.2.1.7.16.5 | N | N | Planned | PTP_C0008 - To perform deletion of FG PIRs - Convert Purchase Info Record - ECC | 1 | 2021-01-18 12:45 | 2021-01-18 13:45 | 2021-01-18 | ANJALI SINHA | DATA | 95365 | #done |  |  | ANURAG ANAND | 2021-01-18 23:15 | [7 empty] | 1: 95365 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10493 |  | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Purchasing/MRP View | 1 | 2021-01-18 13:45 | 2021-01-18 14:45 | 2021-01-18 | DEEPA SAW | DATA | 10492 | #done |  |  | DEEPA SAW | 2021-01-19 00:15 | Material | [6 empty] | 1: 10492 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10494 | WBS.2.1.10.2.6.6 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Accounting view | 1 | 2021-01-18 14:45 | 2021-01-18 15:45 | 2021-01-18 | DEEPA SAW | DATA | 10493 | #done |  |  | DEEPA SAW | 2021-01-19 01:15 | [7 empty] | 1: 10493 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5235 | WBS.2.1.15.7.1.2 | N | N | Planned | PTP_C0001 - Execute Load program - Contracts (Before load, manually create one contract but do not save) | 3 | 2021-01-18 14:45 | 2021-01-18 17:45 | 2021-01-18 | PHANI GHANTASALA | DATA | 5234 | #done |  |  | PHANI GHANTASALA | 2021-01-19 01:15 | [7 empty] | 1: 5234 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92785 | WBS.2.1.9.30.1.3 | N | N | Planned | Execute Preload ITR_C0018.1 - Convert equipment – MP2 | 1 | 2021-01-18 15:30 | 2021-01-18 16:30 | 2021-01-18 | VENKATESH GANESHAN | DATA | 92784,92777 | #done |  |  | DEBRAJ PAL | 2021-01-19 02:00 | [7 empty] | 1: 92784 - Planned; 2: 92777 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
83323 | WBS.2.2.1.7.13.23 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - SPECS semi finished material load file (all views) | 2 | 2021-01-18 15:45 | 2021-01-18 17:45 | 2021-01-18 | PRADEEP CHEEDALLA | Data | 9174 | #done |  |  | Aarthi | 2021-01-19 02:15 | [7 empty] | 1: 9174 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10495 | WBS.2.1.10.2.6.7 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Storage view | 1 | 2021-01-18 15:45 | 2021-01-18 16:45 | 2021-01-18 | DEEPA SAW | DATA | 10494 | #done |  |  | DEEPA SAW | 2021-01-19 02:15 | [7 empty] | 1: 10494 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10496 | WBS.2.1.8.1.1.5 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Sales View | 1 | 2021-01-18 16:45 | 2021-01-18 17:45 | 2021-01-18 | DEEPA SAW | DATA | 10495 | #done |  |  | DEEPA SAW | 2021-01-19 03:15 | Material | [6 empty] | 1: 10495 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
8807 | WBS.2.1.15.25.1.1 | N | N | Planned | ITR_C0030 - Execute Transformation program - Convert Functional Location Classification Values – AS8 | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | 2021-01-18 | ANJALI SINHA | DATA | 5385,5393,3966,82569 | #done |  |  | ANJALI SINHA | 2021-01-19 05:00 | [7 empty] | 1: 5385 - Planned; 2: 5393 - Planned; 3: 3966 - Planned; 4: 82569 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82903 | WBS.2.1.15.16.1.8 | N | N | Planned | ITR_C0038 - Execute Transform program - Convert Task Lists – Functional Location Conversion - PTM | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | 2021-01-18 | ANKIT AGARWAL | DATA | 5393,3968,82569 | #done |  |  | ANKIT AGARWAL | 2021-01-19 05:00 | [7 empty] | 1: 5393 - Planned; 2: 3968 - Planned; 3: 82569 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5427 | WBS.2.1.15.26.1.3 | N | N | Planned | ITR_C0055 - Execute Transform program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | 2021-01-18 | JASPREET SINGH | DATA | 5382,5388,5393,3967,82569 | #done |  |  | Ishaq | 2021-01-19 05:00 | [6 empty] | 1 | 1: 5382 - Planned; 2: 5388 - Planned; 3: 5393 - Planned; 4: 3967 - Planned; 5: 82569 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92787 | WBS.2.1.9.8.1.10 | N | N | Planned | Execute Load ITR_C0018.1 - Convert equipment – MP2 | 1 | 2021-01-18 18:30 | 2021-01-18 19:30 | 2021-01-18 | VENKATESH GANESHAN | DATA | 92786 | #done |  |  | VENKATESH GANESHAN | 2021-01-19 05:00 | [7 empty] | 1: 92786 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5405 | WBS.2.1.9.26.1.4 | N | N | Planned | ITR_C0071 - Execute Transform program - Convert Documents | 2 | 2021-01-18 19:00 | 2021-01-18 21:00 | 2021-01-18 | ANKIT AGARWAL | DATA | 5393,3966,82569,90491,94411 | #done |  |  | Ishaq | 2021-01-19 05:30 | [7 empty] | 1: 5393 - Planned; 2: 3966 - Planned; 3: 82569 - Planned; 4: 90491 - Planned; 5: 94411 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90055 | WBS.2.1.8.1.1.23 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.5 | 2021-01-18 19:30 | 2021-01-18 20:00 | 2021-01-18 | PHANI GHANTASALA | DATA | 90082 | #done |  |  | PHANI GHANTASALA | 2021-01-19 06:00 | Material | [6 empty] | 1: 90082 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
83325 | WBS.2.1.9.1.1.2 | N | N | Planned | Execute load for SPECS semi-finished materials manual load file (Including ZSOURCE characteristic) | 2.5 | 2021-01-18 20:00 | 2021-01-19 06:30 | 2021-01-19 | ANURAG ANAND | DATA | 90055,90054,90067,10371,92829 | #done |  |  | ANURAG ANAND | 2021-01-19 06:30 | [7 empty] | 1: 90055 - Planned; 2: 90054 - Planned; 3: 90067 - Planned; 4: 10371 - Planned; 5: 92829 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90890 | WBS.2.1.9.12.1.1 | N | N | Planned | MDG_C0098 - Execute load for ZUNB materials (Including ZSOURCE characteristic) | 2 | 2021-01-18 20:00 | 2021-01-18 22:00 | 2021-01-18 | ANURAG ANAND | DATA | 90889,90055,90054,90067,10371,92829 | #done |  |  | ANURAG ANAND | 2021-01-19 06:30 | [7 empty] | 1: 90889 - Planned; 2: 90055 - Planned; 3: 90054 - Planned; 4: 90067 - Planned; 5: 10371 - Planned; 6: 92829 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5090 | WBS.2.1.8.1.1.4 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Basic View | 2 | 2021-01-18 20:00 | 2021-01-18 22:00 | 2021-01-18 | DEBRAJ PAL | DATA | 90055,90054,10425,92114,92115,92829 | #done |  |  | DEBRAJ PAL | 2021-01-19 06:30 | Material | [6 empty] | 1: 90055 - Planned; 2: 90054 - Planned; 3: 10425 - Planned; 4: 92114 - Planned; 5: 92115 - Planned; 6: 92829 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82901 | WBS.2.1.15.25.1.3 | N | N | Planned | ITR_C0038 - Execute Load program - Convert Task Lists – Functional Location Conversion - PTM | 1 | 2021-01-18 21:00 | 2021-01-18 22:00 | 2021-01-18 | DEBRAJ PAL | DATA | 82902 | #done |  |  | DEBRAJ PAL | 2021-01-19 07:30 | [7 empty] | 1: 82902 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5440 | WBS.2.1.15.24.1.1 | N | N | Planned | ITR_C0030 - Execute Load program - Convert Functional Location Classification Values – AS8 | 2 | 2021-01-18 21:00 | 2021-01-19 07:00 | 2021-01-19 | VENKATESH GANESHAN | DATA | 8808 | #done |  |  | VENKATESH GANESHAN | 2021-01-19 07:30 | [6 empty] | 1 | 1: 8808 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92806 | WBS.2.1.9.28.1.3 | N | N | Planned | Execute Preload ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2021-01-18 21:30 | 2021-01-19 06:30 | 2021-01-19 | ANKIT AGARWAL | DATA | 94411,92777,92788 | #done |  |  | ANKIT AGARWAL | 2021-01-19 08:00 | [7 empty] | 1: 94411 - Planned; 2: 92777 - Planned; 3: 92788 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5407 | WBS.2.2.1.7.13.15 | N | N | Planned | ITR_C0071 - Execute Load program - Convert Documents | 2 | 2021-01-18 21:30 | 2021-01-19 07:30 | 2021-01-19 | VENKATESH GANESHAN | Data | 5406 | #done |  |  | VENKATESH GANESHAN | 2021-01-19 08:00 | [7 empty] | 1: 5406 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5096 | WBS.2.1.9.14.1.1 | N | N | Planned | MDG_C0098 - Execute Transform program for Materials - Classifications View | 3 | 2021-01-19 06:00 | 2021-01-19 09:00 | 2021-01-19 | ANJALI SINHA | DATA | 5090 | #done |  |  | Krishna | 2021-01-19 16:30 | [7 empty] | 1: 5090 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10498 | WBS.2.2.1.7.13.20 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Basic View | 2 | 2021-01-19 06:00 | 2021-01-19 08:00 | 2021-01-19 | ANJALI SINHA | Data | 5090 | #done |  |  | ANJALI SINHA | 2021-01-19 16:30 | [7 empty] | 1: 5090 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9148 | WBS.2.1.9.6.1.3 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Plant, MRP, Purchasing & Quality (MRO) | 4 | 2021-01-19 06:00 | 2021-01-19 10:00 | 2021-01-19 | DEBRAJ PAL | DATA | 5090,10418 | #done |  |  | DEBRAJ PAL | 2021-01-19 16:30 | [7 empty] | 1: 5090 - Planned; 2: 10418 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
83324 | WBS.2.2.1.7.13.19 | N | N | Planned | Generate Post Load Validation report - SPECS semi-finished materials load file | 4 | 2021-01-19 06:30 | 2021-01-19 10:30 | 2021-01-19 | PRADEEP CHEEDALLA | Data | 83325 | #done |  |  | Aarthi | 2021-01-19 17:00 | [7 empty] | 1: 83325 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5429 | WBS.2.2.1.7.13.9 | N | N | Planned | ITR_C0055 - Execute Load program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2021-01-19 06:30 | 2021-01-19 08:30 | 2021-01-19 | PHANI GHANTASALA | Data | 5428 | #done |  |  | PHANI GHANTASALA | 2021-01-19 17:00 | [7 empty] | 1: 5428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92808 | WBS.2.1.15.18.1.3 | N | N | Planned | Execute Load ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2021-01-19 07:15 | 2021-01-19 08:15 | 2021-01-19 | VENKATESH GANESHAN | DATA | 92807 | #done |  |  | VENKATESH GANESHAN | 2021-01-19 17:45 | [6 empty] | 1 | 1: 92807 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10118 | WBS.2.1.15.21.1.2 | N | N | Planned | PTM_C0079 - Execute Smoke test load for Work Center Conversion | 1 | 2021-01-19 08:15 | 2021-01-19 09:15 | 2021-01-19 | ANURAG ANAND | DATA | 89613,7913 | #done |  |  | ANURAG ANAND | 2021-01-19 18:45 | [6 empty] | 1 | 1: 89613 - Planned; 2: 7913 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10472 | WBS.2.1.15.28.1.1 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points Classification | 2 | 2021-01-19 08:30 | 2021-01-19 10:30 | 2021-01-19 | JASPREET SINGH | DATA | 5429,82569 | #done |  |  | Ishaq | 2021-01-19 19:00 | [6 empty] | 1 | 1: 5429 - Planned; 2: 82569 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10526 | WBS.2.1.13.1.1.8 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - Procured materials - Classification view | 1 | 2021-01-19 09:00 | 2021-01-19 10:00 | 2021-01-19 | ANJALI SINHA | DATA | 5096 | #done |  |  | Krishna | 2021-01-19 19:30 | Vendor | [6 empty] | 1: 5096 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9149 | WBS.2.1.10.2.6.2 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Accounting/Costing Views | 4 | 2021-01-19 10:00 | 2021-01-19 14:00 | 2021-01-19 | DEBRAJ PAL | DATA | 9148,10412 | #done |  |  | DEBRAJ PAL | 2021-01-19 20:30 | Material | [6 empty] | 1: 9148 - Planned; 2: 10412 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5177 | WBS.2.1.15.21.1.4 | N | N | Planned | PTM_C0079 - Execute Load program - PPDS Convert Work Centers | 2 | 2021-01-19 10:15 | 2021-01-19 12:15 | 2021-01-19 | ANURAG ANAND | DATA | 89612,36996,4667,94432,96559 | #done |  |  | ANURAG ANAND | 2021-01-19 20:45 | [6 empty] | 1 | 1: 89612 - Planned; 2: 36996 - Planned; 3: 4667 - Planned; 4: 94432 - Planned; 5: 96559 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5453 | WBS.2.1.8.2.1.13 | N | N | Planned | ITR_C0038.2 - Execute Transform program - Convert Task Lists – Functional Location Conversion - Maintelligence | 4 | 2021-01-19 10:30 | 2021-01-19 14:30 | 2021-01-19 | ANKIT AGARWAL | Data | 5393,3967,82569,82900 | #done |  |  | Sourabhi Mandal | 2021-01-19 21:00 | [6 empty] | 1 | 1: 5393 - Planned; 2: 3967 - Planned; 3: 82569 - Planned; 4: 82900 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10473 | WBS.2.1.15.28.1.3 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points Classification | 1 | 2021-01-19 10:30 | 2021-01-19 11:30 | 2021-01-19 | PHANI GHANTASALA | DATA | 10472 | #done |  |  | PHANI GHANTASALA | 2021-01-19 21:00 | [7 empty] | 1: 10472 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90767 | WBS.2.1.15.17.1.8 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS extension semi-finished materials and generate report | 2.5 | 2021-01-19 11:30 | 2021-01-19 14:00 | 2021-01-19 | PRADEEP CHEEDALLA | DATA | 9186,90768 | #done |  |  | Aarthi | 2021-01-19 22:00 | Material | [6 empty] | 1: 9186 - Planned; 2: 90768 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
68443 | WBS.2.1.15.16.1.3 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points-Entry List | 1 | 2021-01-19 11:30 | 2021-01-19 12:30 | 2021-01-19 | JASPREET SINGH | DATA | 5382,5388,5393,10473 | #done |  |  | Sourabhi Mandal | 2021-01-19 22:00 | [6 empty] | 1 | 1: 5382 - Planned; 2: 5388 - Planned; 3: 5393 - Planned; 4: 10473 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
68444 | WBS.2.1.15.16.1.7 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points-Entry List | 1 | 2021-01-19 12:30 | 2021-01-19 13:30 | 2021-01-19 | PHANI GHANTASALA | DATA | 68443 | #done |  |  | PHANI GHANTASALA | 2021-01-19 23:00 | [6 empty] | 1 | 1: 68443 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9150 | WBS.2.1.9.1.1.4 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Storage View | 4 | 2021-01-19 14:00 | 2021-01-19 18:00 | 2021-01-19 | DEBRAJ PAL | DATA | 9149,10306 | #done |  |  | DEBRAJ PAL | 2021-01-20 00:30 | [7 empty] | 1: 9149 - Planned; 2: 10306 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10499 | WBS.2.2.1.7.13.5 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Plant/Purchasing & Accounting/Costing Views | 3 | 2021-01-19 14:00 | 2021-01-19 17:00 | 2021-01-19 | ANJALI SINHA | Data | 9148,9149 | #done |  |  | ANJALI SINHA | 2021-01-20 00:30 | [7 empty] | 1: 9148 - Planned; 2: 9149 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10120 | WBS.2.2.1.7.13.16 | N | N | Planned | PTM_C0079 - Execute load for Work Center Hierarchy | 2 | 2021-01-19 14:15 | 2021-01-19 16:15 | 2021-01-19 | ANURAG ANAND | Data | 89619 | #done |  |  | ANURAG ANAND | 2021-01-20 00:45 | [7 empty] | 1: 89619 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90765 | WBS.2.1.9.10.1.2 | N | N | Planned | Execute load for SPECS extension semi-finished materials manual load file (Including ZSOURCE characteristic) MDG_C0098 | 3 | 2021-01-19 15:00 | 2021-01-19 18:00 | 2021-01-19 | ANURAG ANAND | DATA | 90766 | #done |  |  | ANURAG ANAND | 2021-01-20 01:30 | [7 empty] | 1: 90766 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
95508 | WBS.2.2.1.7.16.5 | N | N | Planned | Execute Transform program - PTM_C0094 Convert Setup groups / Setup Matrix | 4 | 2021-01-19 15:45 | 2021-01-19 19:45 | 2021-01-19 | PRADEEP CHEEDALLA | DATA | 95509,95510 | #done |  |  | Ishaq/Krishna | 2021-01-20 02:15 | [7 empty] | 1: 95509 - Planned; 2: 95510 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5455 | WBS.2.1.8.2.1.24 | N | N | Planned | ITR_C0038.2 - Execute Load program - Convert Task Lists – Functional Location Conversion - Maintelligence | 1 | 2021-01-19 16:30 | 2021-01-19 17:30 | 2021-01-19 | DEBRAJ PAL | DATA | 5454 | #done |  |  | DEBRAJ PAL | 2021-01-20 03:00 | Material | [5 empty] | 1 | 1: 5454 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82908 | WBS.2.1.15.8.1.2 | N | N | Planned | ITR_C0175 - Execute Transform program - Convert Documents for measuring points | 1 | 2021-01-19 17:30 | 2021-01-19 18:30 | 2021-01-19 | JASPREET SINGH | DATA | 5430 | #done |  |  | Sourabhi Mandal | 2021-01-20 04:00 | [7 empty] | 1: 5430 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9151 | WBS.2.1.15.11.1.1 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Sales View | 3 | 2021-01-19 18:00 | 2021-01-19 21:00 | 2021-01-19 | DEBRAJ PAL | DATA | 9150,10431 | #done |  |  | DEBRAJ PAL | 2021-01-20 04:30 | [7 empty] | 1: 9150 - Planned; 2: 10431 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10501 | WBS.2.1.9.10.1.4 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Storage View | 2 | 2021-01-19 18:00 | 2021-01-19 20:00 | 2021-01-19 | ANJALI SINHA | DATA | 9150 | #done |  |  | ANJALI SINHA | 2021-01-20 04:30 | [7 empty] | 1: 9150 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
94770 | WBS.2.1.9.19.1.7 | N | N | Planned | Replicate changes for Unit of Issue and Printed boards master data updates needed for BOMs | 1 | 2021-01-19 18:15 | 2021-01-19 19:15 | 2021-01-19 | PHANI GHANTASALA | DATA | 94769 | #done |  |  | PHANI GHANTASALA | 2021-01-20 04:45 | [7 empty] | 1: 94769 - Planned | Yet to receive | FALSE | TRUE | TRUE | TRUE
10110 | WBS.2.1.8.1.1.47 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Bill of Materials (MBOMS) | 8 | 2021-01-19 19:15 | 2021-01-20 11:15 | 2021-01-20 | PRADEEP CHEEDALLA | DATA | 10372,80758,94770,94724 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-20 05:45 | Material | [6 empty] | 1: 10372 - Planned; 2: 80758 - Planned; 3: 94770 - Planned; 4: 94724 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9798 | WBS.2.1.9.18.1.1 | N | N | Planned | PTM_C0080 - Execute Transform - Upload for Repetitive Manufacturing | 5 | 2021-01-19 19:15 | 2021-01-20 08:15 | 2021-01-20 | PRADEEP CHEEDALLA | DATA | 9797,10372,94770 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-20 05:45 | [7 empty] | 1: 9797 - Planned; 2: 10372 - Planned; 3: 94770 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89712 | WBS.2.1.9.25.1.1 | N | N | Planned | Replicate SPECS and ZUNB materials from MDG to S4 using t-code BD10 | 3 | 2021-01-19 19:45 | 2021-01-20 06:45 | 2021-01-20 | PHANI GHANTASALA | DATA | 10372,90891,92582,92830 | #done |  |  | PHANI GHANTASALA | 2021-01-20 06:15 | [7 empty] | 1: 10372 - Planned; 2: 90891 - Planned; 3: 92582 - Planned; 4: 92830 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5478 | WBS.2.2.1.7.13.8 | N | N | Planned | ITR_C0050.1 - Execute Transform program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2021-01-19 20:15 | 2021-01-20 06:15 | 2021-01-20 | ANKIT AGARWAL | Data | 9400,5430 | #done |  |  | Ishaq | 2021-01-20 06:45 | [7 empty] | 1: 9400 - Planned; 2: 5430 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
95506 | WBS.2.2.1.7.1.7 | N | N | Planned | Execute Load program - PTM_C0094 Convert Setup groups / Setup Matrix | 1 | 2021-01-19 20:45 | 2021-01-19 21:45 | 2021-01-19 | PRADEEP CHEEDALLA | DATA | 95507 | #done |  |  | Ishaq/Krishna | 2021-01-20 07:15 | [7 empty] | 1: 95507 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5100 | WBS.2.1.8.1.1.16 | N | N | Planned | MDG_C0098 - Execute Load in MDG - Materials - Classification View (ECC & AS8) | 4.5 | 2021-01-19 21:00 | 2021-01-20 09:30 | 2021-01-20 | ANJALI SINHA | DATA | 10423,9151 | #done |  |  | Krishna | 2021-01-20 07:30 | Material | [6 empty] | 1: 10423 - Planned; 2: 9151 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10502 | WBS.2.1.15.12.1.1 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Sales View | 2 | 2021-01-19 21:00 | 2021-01-20 07:00 | 2021-01-20 | ANJALI SINHA | DATA | 9151 | #done |  |  | ANJALI SINHA | 2021-01-20 07:30 | [7 empty] | 1: 9151 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9928 | WBS.2.1.8.1.1.15 | N | N | Planned | MDG_C0098 - Generate In-Scope list and AS8 / S/4HANA material Xref and upload to SharePoint | 1 | 2021-01-19 21:00 | 2021-01-19 22:00 | 2021-01-19 | DEEPA SAW | DATA | 9151 | #done |  |  | DEEPA SAW | 2021-01-20 07:30 | Material | [6 empty] | 1: 9151 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89711 | WBS.2.1.8.1.1.28 | N | N | Planned | Generate Replication Validation reports - SPECS and ZUNB materials | 2 | 2021-01-20 06:45 | 2021-01-20 08:45 | 2021-01-20 | ANKIT AGARWAL | DATA | 89712 | #done |  |  | Ishaq | 2021-01-20 17:15 | Material | [6 empty] | 1: 89712 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5480 | WBS.2.1.15.24.1.3 | N | N | Planned | ITR_C0050.1 - Execute Load program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2021-01-20 07:45 | 2021-01-20 09:45 | 2021-01-20 | VENKATESH GANESHAN | DATA | 5479 | #done |  |  | VENKATESH GANESHAN | 2021-01-20 18:15 | [6 empty] | 1 | 1: 5479 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82906 | WBS.2.1.9.26.1.6 | N | N | Planned | ITR_C0175 - Execute Load program - Convert Documents for measuring points | 1 | 2021-01-20 08:00 | 2021-01-20 09:00 | 2021-01-20 | VENKATESH GANESHAN | DATA | 82907 | #done |  |  | VENKATESH GANESHAN | 2021-01-20 18:30 | [7 empty] | 1: 82907 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10528 | WBS.2.1.8.1.1.20 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - Procured materials - Classification View | 1 | 2021-01-20 09:30 | 2021-01-20 10:30 | 2021-01-20 | ANJALI SINHA | DATA | 5100 | #done |  |  | Krishna | 2021-01-20 20:00 | Material | [6 empty] | 1: 5100 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10023 | WBS.2.1.9.8.1.7 | N | N | Planned | PTM_C0082 - Execute Preload for Convert Routing (simulation mode) | 2 | 2021-01-20 10:00 | 2021-01-20 12:00 | 2021-01-20 | ANURAG ANAND | DATA | 89709,80758,89619 | #done |  |  | ANURAG ANAND | 2021-01-20 20:30 | [7 empty] | 1: 89709 - Planned; 2: 80758 - Planned; 3: 89619 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9804 | WBS.2.2.1.7.13.21 | N | N | Planned | PTM_C0082 - Execute Preload - upload routes for Repetitive Manufacturing (Simulation Mode) | 3 | 2021-01-20 10:00 | 2021-01-20 13:00 | 2021-01-20 | ANURAG ANAND | Data | 9803,10120,89709,89619 | #done |  |  | ANURAG ANAND | 2021-01-20 20:30 | [7 empty] | 1: 9803 - Planned; 2: 10120 - Planned; 3: 89709 - Planned; 4: 89619 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5121 | WBS.2.1.9.19.1.1 | N | N | Planned | Replicate Asset Suite Procured Materials from MDG to S/4HANA using t-code BD10 | 9 | 2021-01-20 10:30 | 2021-01-20 19:30 | 2021-01-20 | PHANI GHANTASALA | DATA | 10307,10414,10413,10424,10430,68525,92582,92830 | #done |  |  | PHANI GHANTASALA | 2021-01-20 21:00 | [7 empty] | 10307 - Planned | 10414 - Planned | 10413 - Planned | 10424 - Planned | 10430 - Planned | 68525 - Planned | 92582 - Planned | 92830 - Planned |  |  |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
90050 | WBS.2.1.8.1.1.46 | N | N | Planned | Change BOM partner profile to collect mode in MDG | 0.25 | 2021-01-20 12:15 | 2021-01-20 12:30 | 2021-01-20 | PHANI GHANTASALA | DATA | 9799,10111 | #done |  |  | PHANI GHANTASALA | 2021-01-20 22:45 | Material | [6 empty] | 1: 9799 - Planned; 2: 10111 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9800 | WBS.2.1.8.1.1.48 | N | N | Planned | PTM_C0080 - Execute Load in MDG - upload for Repetitive Manufacturing | 3 | 2021-01-20 12:45 | 2021-01-20 15:45 | 2021-01-20 | PRADEEP CHEEDALLA | DATA | 90050,9799,90084 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-20 23:15 | Material | [6 empty] | 1: 90050 - Planned; 2: 9799 - Planned; 3: 90084 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5183 | WBS.2.1.9.4.1.10 | N | N | Planned | PTM_C0080 - Execute Load in MDG - Convert Bill of Materials (MBOMS) | 8 | 2021-01-20 12:45 | 2021-01-20 20:45 | 2021-01-20 | PRADEEP CHEEDALLA | DATA | 90050,10111,90084,94724 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-20 23:15 | Material | [6 empty] | 1: 90050 - Planned; 2: 10111 - Planned; 3: 90084 - Planned; 4: 94724 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5193 | WBS.2.1.8.1.1.51 | N | N | Planned | PTM_C0082 - Execute Actual Load - Convert Routings | 4 | 2021-01-20 13:00 | 2021-01-20 17:00 | 2021-01-20 | ANURAG ANAND | DATA | 10024 | #done |  |  | ANURAG ANAND | 2021-01-20 23:30 | Material | [6 empty] | 1: 10024 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
82854 | WBS.2.1.8.1.1.54 | N | N | Planned | PTM_C0082 - Execute Load in S/4 - upload routings for Repetitive Manufacturing | 1 | 2021-01-20 14:00 | 2021-01-20 15:00 | 2021-01-20 | ANURAG ANAND | DATA | 82855,92189 | #done |  |  | ANURAG ANAND | 2021-01-21 00:30 | Material | [6 empty] | 1: 82855 - Planned; 2: 92189 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10503 | WBS.2.1.9.16.1.1 | N | N | Planned | Generate Replication Validation reports - AS8 Procured materials (Basic, Plant, Storage Location, Sales views) | 2 | 2021-01-20 19:30 | 2021-01-20 21:30 | 2021-01-20 | ANKIT AGARWAL | DATA | 5121 | #done |  |  | Ishaq | 2021-01-21 06:00 | [7 empty] | 1: 5121 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5122 | WBS.2.1.9.15.1.1 | N | N | Planned | Replicate Materials Quality View from MDG to S/4HANA | 0.5 | 2021-01-20 19:30 | 2021-01-20 20:00 | 2021-01-20 | PHANI GHANTASALA | DATA | 5121,10413 | #done |  |  | PHANI GHANTASALA | 2021-01-21 06:00 | [7 empty] | 1: 5121 - Planned; 2: 10413 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5415 | WBS.2.2.1.7.13.7 | N | N | Planned | IT ITR_C0020 - Execute Transform Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2021-01-21 07:00 | 2021-01-21 11:00 | 2021-01-21 | DEEPA SAW | Data | 5393,5408,10428 | #done |  |  | DEEPA SAW | 2021-01-21 17:30 | [7 empty] | 1: 5393 - Planned; 2: 5408 - Planned; 3: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
89766 | WBS.2.2.1.7.16.5 | N | N | Planned | Provide MARA and MARC extracts after materials sign-off to help prepare file for Procurement MDM | 1 | 2021-01-21 07:00 | 2021-01-21 08:00 | 2021-01-21 | PRADEEP CHEEDALLA | DATA | 10428 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-21 17:30 | [7 empty] | 1: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5395 | WBS.2.1.9.21.1.4 | N | N | Planned | ITR_C0018 - Execute Preload - Convert equipment – AS8 | 4 | 2021-01-21 07:00 | 2021-01-21 11:00 | 2021-01-21 | VENKATESH GANESHAN | DATA | 5393,82989,10428 | #done |  |  | VENKATESH GANESHAN | 2021-01-21 17:30 | [6 empty] | 1 | 1: 5393 - Planned; 2: 82989 - Planned; 3: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5248 | WBS.2.2.1.7.13.35 | N | N | Planned | PTP_C0008.1 - Execute Transform program - Convert Purchase Info Record - AS8 | 3 | 2021-01-21 07:00 | 2021-01-21 10:00 | 2021-01-21 | JASPREET SINGH | Data | 10428,89675,89679 | #done |  |  | JASPREET SINGH | 2021-01-21 17:30 | [7 empty] | 1: 10428 - Planned; 2: 89675 - Planned; 3: 89679 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5448 | WBS.2.1.9.19.1.5 | N | N | Planned | ITR_C0038.1 - Execute Transform program - Convert Task Lists – Functional Location – AS8 | 2 | 2021-01-21 07:00 | 2021-01-21 09:00 | 2021-01-21 | ANKIT AGARWAL | DATA | 5393,5408,10428,5456,82900 | #done |  |  | ANKIT AGARWAL | 2021-01-21 17:30 | [7 empty] | 1: 5393 - Planned; 2: 5408 - Planned; 3: 10428 - Planned; 4: 5456 - Planned; 5: 82900 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92867 | WBS.2.1.9.31.1.1 | N | N | Planned | Execute Preload ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2021-01-21 07:00 | 2021-01-21 08:00 | 2021-01-21 | ANKIT AGARWAL | DATA | 92777,92809,10428 | #done |  |  | ANKIT AGARWAL | 2021-01-21 17:30 | [6 empty] | 1 | 1: 92777 - Planned; 2: 92809 - Planned; 3: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5468 | WBS.2.2.1.7.13.6 | N | N | Planned | ITR_C0038.6 - Execute Transform program - Convert Task Lists - General Conversion – AS8 | 2 | 2021-01-21 07:00 | 2021-01-21 09:00 | 2021-01-21 | JASPREET SINGH | Data | 5408,10428 | #done |  |  | Ishaq | 2021-01-21 17:30 | [7 empty] | 1: 5408 - Planned; 2: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
80859 | WBS.2.1.9.17.1.1 | N | N | Planned | Replicate AS8 Procured Materials Classifiation View from MDG to S/4HANA using change pointers | 14 | 2021-01-21 07:00 | 2021-01-21 21:00 | 2021-01-21 | PHANI GHANTASALA | DATA | 10429,10428 | #done |  |  | PHANI GHANTASALA | 2021-01-21 17:30 | [7 empty] | 1: 10429 - Planned; 2: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5186 | WBS.2.2.1.7.16.5 | N | N | Planned | Replicate MBOMs (including Repetitive MFG BOMs from RTR) from MDG to S/4HANA | 4 | 2021-01-21 08:00 | 2021-01-21 12:00 | 2021-01-21 | PHANI GHANTASALA | DATA | 10334,9801 | #done |  |  | PHANI GHANTASALA | 2021-01-21 18:30 | [7 empty] | 1: 10334 - Planned; 2: 9801 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92869 | WBS.2.1.15.16.1.4 | N | N | Planned | Execute Load ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2021-01-21 10:00 | 2021-01-21 11:00 | 2021-01-21 | DEBRAJ PAL | DATA | 92868 | #done |  |  | DEBRAJ PAL | 2021-01-21 20:30 | [7 empty] | 1: 92868 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5450 | WBS.2.1.8.1.1.17 | N | N | Planned | ITR_C0038.1 - Execute Load program - Convert Task Lists – Functional Location – AS8 | 5 | 2021-01-21 10:00 | 2021-01-21 15:00 | 2021-01-21 | DEBRAJ PAL | DATA | 5449 | #done |  |  | DEBRAJ PAL | 2021-01-21 20:30 | Material | [6 empty] | 1: 5449 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5470 | WBS.2.1.8.1.1.29 | N | N | Planned | ITR_C0038.6 - Execute Load program - Convert Task Lists - General Conversion – AS8 | 1 | 2021-01-21 10:45 | 2021-01-21 11:45 | 2021-01-21 | DEBRAJ PAL | DATA | 5469 | #done |  |  | DEBRAJ PAL | 2021-01-21 21:15 | Material | [6 empty] | 1: 5469 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5397 | WBS.2.1.9.18.1.3 | N | N | Planned | ITR_C0018 - Execute Load program - Convert equipment – AS8 | 5 | 2021-01-21 12:00 | 2021-01-21 17:00 | 2021-01-21 | VENKATESH GANESHAN | DATA | 5396 | #done |  |  | VENKATESH GANESHAN | 2021-01-21 22:30 | [7 empty] | 1: 5396 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5250 | WBS.2.1.8.1.1.76 | N | N | Planned | PTP_C0008.1 - Execute Load program - Convert Purchase Info Record - AS8 | 13 | 2021-01-21 12:00 | 2021-01-22 09:00 | 2021-01-22 | JASPREET SINGH | DATA | 5249 | #done |  |  | JASPREET SINGH | 2021-01-21 22:30 | Material | [6 empty] | 1: 5249 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90049 | WBS.2.1.8.1.1.30 | N | N | Planned | Change BOM partner profile to pass immediately in MDG | 0.25 | 2021-01-21 12:30 | 2021-01-21 12:45 | 2021-01-21 | PHANI GHANTASALA | DATA | 9801,10334,9802 | #done |  |  | PHANI GHANTASALA | 2021-01-21 23:00 | Material | [6 empty] | 1: 9801 - Planned; 2: 10334 - Planned; 3: 9802 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10114 | WBS.2.2.1.7.13.17 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions for Repetitive Manufacturing | 2 | 2021-01-21 12:30 | 2021-01-21 14:30 | 2021-01-21 | PRADEEP CHEEDALLA | Data | 9809,9807,9802 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-21 23:00 | [7 empty] | 1: 9809 - Planned; 2: 9807 - Planned; 3: 9802 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92874 | WBS.2.1.15.19.1.3 | N | N | Planned | Execute Preload ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2021-01-21 13:00 | 2021-01-21 14:00 | 2021-01-21 | ANKIT AGARWAL | DATA | 92870 | #done |  |  | Ishaq | 2021-01-21 23:30 | [6 empty] | 1 | 1: 92870 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10022 | WBS.2.1.9.28.1.1 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions | 2 | 2021-01-21 14:00 | 2021-01-21 16:00 | 2021-01-21 | PRADEEP CHEEDALLA | DATA | 5195,10334,5187,80758 | #done |  |  | PRADEEP CHEEDALLA | 2021-01-22 00:30 | [7 empty] | 1: 5195 - Planned; 2: 10334 - Planned; 3: 5187 - Planned; 4: 80758 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
9810 | WBS.2.1.15.30.1.1 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production Versions for Repetitive Manufacturing | 2 | 2021-01-21 14:45 | 2021-01-21 16:45 | 2021-01-21 | PHANI GHANTASALA | DATA | 10115 | #done |  |  | PHANI GHANTASALA | 2021-01-22 01:15 | [7 empty] | 1: 10115 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92876 | WBS.2.1.9.31.1.3 | N | N | Planned | Execute Load ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2021-01-21 16:00 | 2021-01-21 17:00 | 2021-01-21 | VENKATESH GANESHAN | DATA | 92875 | #done |  |  | VENKATESH GANESHAN | 2021-01-22 02:30 | [6 empty] | 1 | 1: 92875 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5417 | WBS.2.1.9.30.1.1 | N | N | Planned | ITR_C0020 - Execute Load Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2021-01-21 16:45 | 2021-01-21 20:45 | 2021-01-21 | PHANI GHANTASALA | DATA | 5416 | #done |  |  | PHANI GHANTASALA | 2021-01-22 03:15 | [7 empty] | 1: 5416 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5201 | WBS.2.1.9.29.1.1 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production versions | 1.5 | 2021-01-21 18:00 | 2021-01-21 19:30 | 2021-01-21 | PHANI GHANTASALA | DATA | 10021 | #done |  |  | PHANI GHANTASALA | 2021-01-22 04:30 | [6 empty] | 1 | 1: 10021 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10112 | WBS.2.1.8.2.1.18 | N | N | Planned | ITR_C0028 - Execute Transform program - Convert Equipment Classification values - AS8 | 2 | 2021-01-21 18:00 | 2021-01-21 20:00 | 2021-01-21 | ANJALI SINHA | DATA | 5385,5398 | #done |  |  | ANJALI SINHA | 2021-01-22 04:30 | Material | [6 empty] | 1: 5385 - Planned; 2: 5398 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5473 | WBS.2.1.9.8.1.5 | N | N | Planned | ITR_C0050 - Execute Transform Program - Convert Maintenance Plans Conversion – AS8 | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | 2021-01-21 | JASPREET SINGH | DATA | 5451,5471 | #done |  |  | Sourabhi Mandal | 2021-01-22 05:30 | [7 empty] | 1: 5451 - Planned; 2: 5471 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5437 | WBS.2.1.15.7.1.4 | N | N | Planned | ITR_C0028 - Execute Load program - Convert Equipment Classification Values – AS8 | 1 | 2021-01-21 20:20 | 2021-01-21 21:20 | 2021-01-21 | VENKATESH GANESHAN | DATA | 10113 | #done |  |  | VENKATESH GANESHAN | 2021-01-22 06:50 | [6 empty] | 1 | 1: 10113 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
80860 | WBS.2.1.15.11.1.3 | N | N | Planned | Generate Replication Validation reports - AS8 Procured Materials Classification view | 2 | 2021-01-21 21:00 | 2021-01-22 07:00 | 2021-01-22 | ANKIT AGARWAL | DATA | 80859 | #done |  |  | Ishaq | 2021-01-22 07:30 | [7 empty] | 1: 80859 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10032 | WBS.2.2.1.7.13.34 | N | N | Planned | PTM_C0205 - Execute Transform Program - Convert Product Master | 5 | 2021-01-22 06:00 | 2021-01-22 11:00 | 2021-01-22 | DEEPA SAW | Data | 10428,3956,8861,8862,94302,94305,96567,96568,96699,96700 | #done |  |  | Krishna | 2021-01-22 16:30 | [7 empty] | 10428 - Planned | 3956 - Planned | 8861 - Planned | 8862 - Planned | 94302 - Planned | 94305 - Planned | 96567 - Planned | 96568 - Planned | 96699 - Planned | 96700 - Planned |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
5400 | WBS.2.1.9.4.1.8 | N | N | Planned | ITR_C0024 - Execute Transform Program - Convert BOM - Material / Assemblies Conversion – AS8 | 2 | 2021-01-22 07:15 | 2021-01-22 09:15 | 2021-01-22 | PRADEEP CHEEDALLA | DATA | 5408,10428,5418 | #done |  |  | Aarthi | 2021-01-22 17:45 | Material | [6 empty] | 1: 5408 - Planned; 2: 10428 - Planned; 3: 5418 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5475 | WBS.2.1.9.19.1.6 | N | N | Planned | ITR_C0050 - Execute Load Program - Convert Maintenance Plans Conversion – AS8 | 2 | 2021-01-22 08:00 | 2021-01-22 10:00 | 2021-01-22 | VENKATESH GANESHAN | DATA | 5474,95484 | #done |  |  | VENKATESH GANESHAN | 2021-01-22 18:30 | [7 empty] | 1: 5474 - Planned; 2: 95484 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90052 | WBS.2.1.9.8.1.3 | N | N | Planned | Turn ON DRFOUT, Turn OFF Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.25 | 2021-01-22 09:00 | 2021-01-22 09:15 | 2021-01-22 | PHANI GHANTASALA | DATA | 10428,89709,10427,90079 | #done |  |  | PHANI GHANTASALA | 2021-01-22 19:30 | [7 empty] | 1: 10428 - Planned; 2: 89709 - Planned; 3: 10427 - Planned; 4: 90079 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90959 | WBS.2.1.9.28.1.3 | N | N | Planned | Identify changes in material master in MDG not made by conversion | 3 | 2021-01-22 09:15 | 2021-01-22 12:15 | 2021-01-22 | SHANKAR RAMNARAYANAN | DATA | 90052 | #done |  |  | SHANKAR RAMNARAYANAN | 2021-01-22 19:45 | [7 empty] | 1: 90052 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5402 | WBS.2.1.15.17.1.8 | N | N | Planned | ITR_C0024 - Execute Load Program - Convert BOM - Material / Assemblies Conversion – AS8 | 5 | 2021-01-22 10:15 | 2021-01-22 15:15 | 2021-01-22 | PRADEEP CHEEDALLA | DATA | 5401 | #done |  |  | Aarthi | 2021-01-22 20:45 | Material | [6 empty] | 1: 5401 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5253 | WBS.2.1.8.1.1.77 | N | N | Planned | PTP_C0200 - Execute Transform Program - Source List Conversion - AS8 | 2 | 2021-01-22 11:00 | 2021-01-22 13:00 | 2021-01-22 | ANJALI SINHA | DATA | 5251,10428 | #done |  |  | Krishna | 2021-01-22 21:30 | Material | [6 empty] | 1: 5251 - Planned; 2: 10428 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5245 | WBS.2.1.8.1.1.57 | N | N | Planned | PTP_C0008 - Execute Load program - Convert Purchase Info Record - ECC | 4 | 2021-01-22 11:00 | 2021-01-22 15:00 | 2021-01-22 | ANJALI SINHA | DATA | 5244,5251,95364 | #done |  |  | ANJALI SINHA | 2021-01-22 21:30 | Material | [6 empty] | 1: 5244 - Planned; 2: 5251 - Planned; 3: 95364 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
90960 | WBS.2.1.9.28.1.3 | N | N | Planned | Replicate changes in material master not made by conversion from MDG to S4 | 2 | 2021-01-22 12:15 | 2021-01-22 14:15 | 2021-01-22 | SHANKAR RAMNARAYANAN | DATA | 90959 | #done |  |  | SHANKAR RAMNARAYANAN | 2021-01-22 22:45 | [7 empty] | 1: 90959 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5255 | WBS.2.1.8.1.1.65 | N | N | Planned | PTP_C0200 - Execute Load Program - Source List Conversion - AS8 | 3 | 2021-01-22 14:00 | 2021-01-22 17:00 | 2021-01-22 | ANJALI SINHA | DATA | 5254 | #done |  |  | Krishna | 2021-01-23 00:30 | Material | [6 empty] | 1: 5254 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5229 | WBS.2.1.8.1.1.71 | N | N | Planned | PTM_C0205 - Execute Load Program - Convert Product Master | 10 | 2021-01-22 16:00 | 2021-01-25 10:00 | 2021-01-25 | DEEPA SAW | DATA | 10033,94316,94315,94312,94311,96569,96570,96701,96702 | #done |  |  | Krishna | 2021-01-23 02:30 | Material | [6 empty] | 10033 - Planned | 94316 - Planned | 94315 - Planned | 94312 - Planned | 94311 - Planned | 96569 - Planned | 96570 - Planned | 96701 - Planned | 96702 - Planned |  |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
5215 | WBS.2.1.8.2.1.23 | N | N | Planned | PTM_C0092 - Execute Load Program - Convert Product Cost Collectors - PE | 1 | 2021-01-22 17:00 | 2021-01-22 18:00 | 2021-01-22 | PHANI GHANTASALA | DATA | 4056,11032 | #done |  |  | PHANI GHANTASALA | 2021-01-23 03:30 | Material | [6 empty] | 1: 4056 - Planned; 2: 11032 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5258 | WBS.2.1.8.1.1.64 | N | N | Planned | PTP_C0200.1 - Execute Transform Program - Convert Source List - ECC | 2 | 2021-01-22 17:00 | 2021-01-22 19:00 | 2021-01-22 | JASPREET SINGH | DATA | 5236,5246 | #done |  |  | JASPREET SINGH | 2021-01-23 03:30 | Material | [6 empty] | 1: 5236 - Planned; 2: 5246 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5260 | WBS.2.1.15.23.1.3 | N | N | Planned | PTP_C0200.1 - Execute Load Program - Convert Source List - ECC | 2 | 2021-01-22 20:00 | 2021-01-22 22:00 | 2021-01-22 | JASPREET SINGH | DATA | 5259 | #done |  |  | JASPREET SINGH | 2021-01-23 06:30 | [6 empty] | 1 | 1: 5259 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
4971 | WBS.2.1.8.1.1.70 | N | N | Planned | DAT_C0234 - Execute Transform Program -Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2021-01-25 11:15 | 2021-01-25 13:15 | 2021-01-25 | ANJALI SINHA | DATA | 9101,93067,91838 | Yet to receive |  |  | ANJALI SINHA | 2021-01-25 21:45 | Material | [6 empty] | 1: 9101 - Planned; 2: 93067 - Planned; 3: 91838 - Planned | Yet to receive |  |  |  | FALSE
95038 | WBS.2.2.1.7.16.5 | N | N | Planned | Update Material Master for ECC Facilities as Provided by PTP Team | 4 | 2021-01-25 12:15 | 2021-01-25 16:15 | 2021-01-25 | SHANKAR RAMNARAYANAN | DATA | 95037 | Yet to receive |  |  | SHANKAR RAMNARAYANAN | 2021-01-25 22:45 | [7 empty] | 1: 95037 - Planned | Yet to receive |  |  |  | FALSE
4973 | WBS.2.1.8.2.1.10 | N | N | Planned | DAT_C0234 - Execute Load Program - Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2021-01-25 13:30 | 2021-01-25 15:30 | 2021-01-25 | ANURAG ANAND | DATA | 4972 | Yet to receive |  |  | ANURAG ANAND | 2021-01-26 | Material | [6 empty] | 1: 4972 - Planned | Yet to receive |  |  |  | FALSE
10474 | WBS.2.1.15.15.1.2 | N | N | Planned | ITR_C0061 - Execute Preload - Convert Work Center - HR assignments | 1 | 2021-01-25 18:00 | 2021-01-25 19:00 | 2021-01-25 | VENKATESH GANESHAN | DATA | 4974 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-01-26 04:30 | [7 empty] | 1: 4974 - Planned | Yet to receive |  |  |  | FALSE
5378 | WBS.2.1.15.6.1.2 | N | N | Planned | ITR_C0061 - Execute Load program - Convert Work Center - HR assignments | 4 | 2021-01-25 19:20 | 2021-01-26 07:20 | 2021-01-26 | VENKATESH GANESHAN | DATA | 10475 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-01-26 05:50 | [6 empty] | 1 | 1: 10475 - Planned | Yet to receive |  |  |  | FALSE
89987 | WBS.2.1.8.2.2.8 | N | N | Planned | Execute T-4 Extracts for Asset Suite | 2.5 | 2021-01-26 06:30 | 2021-01-26 09:00 | 2021-01-26 | ANJALI SINHA | DATA | 89967,5254 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 17:00 | Material | [6 empty] | 1: 89967 - Planned; 2: 5254 - Planned | Yet to receive |  |  |  | FALSE
82771 | WBS.2.1.8.1.1.3 | N | N | Planned | MDG_C0098 - Execute Extracts from AS8 for Delta load of AS8 Procured materials | 6 | 2021-01-26 06:30 | 2021-01-26 12:30 | 2021-01-26 | ANJALI SINHA | DATA | 10428,10854,89967,5254 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 17:00 | Material | [6 empty] | 1: 10428 - Planned; 2: 10854 - Planned; 3: 89967 - Planned; 4: 5254 - Planned | Yet to receive |  |  |  | FALSE
95613 |  | N | N |  | Run routing component allocation logic after BOM replication to S4 | 2 | 2021-01-26 07:15 | 2021-01-26 09:15 | 2021-01-26 | ANURAG ANAND | DATA | 5187,5193,10854,97456 | Yet to receive |  |  | ANURAG ANAND | 2021-01-26 17:45 | [7 empty] | 1: 5187 - Planned; 2: 5193 - Planned; 3: 10854 - Planned; 4: 97456 - Planned | Yet to receive |  |  |  | FALSE
94400 | WBS.2.1.8.2.2.3 | N | N | Planned | Execute T-4 Extracts for MP2 | 2.5 | 2021-01-26 07:15 | 2021-01-26 09:45 | 2021-01-26 | ANJALI SINHA | DATA | 94359 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 17:45 | Material | [6 empty] | 1: 94359 - Planned | Yet to receive |  |  |  | FALSE
92846 | WBS.2.2.1.7.28.3 | N | N | Planned | Execute Preload ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2021-01-26 09:45 | 2021-01-26 10:45 | 2021-01-26 | ANJALI SINHA | DATA | 94359,94400,92777,92788,92809 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 20:15 | [7 empty] | 1: 94359 - Planned; 2: 94400 - Planned; 3: 92777 - Planned; 4: 92788 - Planned; 5: 92809 - Planned | Yet to receive |  |  |  | FALSE
94357 | WBS.2.2.1.7.26.1 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2021-01-26 09:45 | 2021-01-26 10:45 | 2021-01-26 | JASPREET SINGH | DATA | 94359,94400,92877 | Yet to receive |  |  | JASPREET SINGH | 2021-01-26 20:15 | [7 empty] | 1: 94359 - Planned; 2: 94400 - Planned; 3: 92877 - Planned | Yet to receive |  |  |  | FALSE
5760 | WBS.2.1.15.12.1.3 | N | N | Planned | ITR_C0032 - Execute Transform program - Convert Open work orders – Asset Suite | 2 | 2021-01-26 10:15 | 2021-01-26 12:15 | 2021-01-26 | ANJALI SINHA | DATA | 10428,5398,5408,89967,89987,90973,94400 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 20:45 | [6 empty] | 1 | 1: 10428 - Planned; 2: 5398 - Planned; 3: 5408 - Planned; 4: 89967 - Planned; 5: 89987 - Planned; 6: 90973 - Planned; 7: 94400 - Planned | Yet to receive |  |  |  | FALSE
89993 | WBS.2.2.1.7.13.14 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 15 | 2021-01-26 10:15 | 2021-01-26 12:15 | 2021-01-26 | ANKIT AGARWAL | Data | 89987,90973,94400,5476 | Yet to receive |  |  | ANKIT AGARWAL | 2021-01-26 20:45 | [7 empty] | 1: 89987 - Planned; 2: 90973 - Planned; 3: 94400 - Planned; 4: 5476 - Planned | Yet to receive |  |  |  | FALSE
92844 | WBS.2.2.1.7.26.5 | N | N | Planned | Execute Load ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2021-01-26 12:15 | 2021-01-26 13:15 | 2021-01-26 | ANJALI SINHA | DATA | 92845 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 22:45 | [7 empty] | 1: 92845 - Planned | Yet to receive |  |  |  | FALSE
82772 | WBS.2.1.8.1.1.33 | N | N | Planned | Execute Transform program for DELTA Asset Suite Procured materials | 4 | 2021-01-26 12:30 | 2021-01-26 16:30 | 2021-01-26 | DEEPA SAW | DATA | 82771 | Yet to receive |  |  | DEEPA SAW | 2021-01-26 23:00 | Material | [6 empty] | 1: 82771 - Planned | Yet to receive |  |  |  | FALSE
89994 | WBS.2.1.15.15.1.6 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 2 | 2021-01-26 12:35 | 2021-01-26 14:35 | 2021-01-26 | ANKIT AGARWAL | DATA | 89996 | Yet to receive |  |  | ANKIT AGARWAL | 2021-01-26 23:05 | [7 empty] | 1: 89996 - Planned | Yet to receive |  |  |  | FALSE
94355 | WBS.2.2.1.7.28.1 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2021-01-26 12:45 | 2021-01-26 13:45 | 2021-01-26 | JASPREET SINGH | DATA | 94356 | Yet to receive |  |  | JASPREET SINGH | 2021-01-26 23:15 | [7 empty] | 1: 94356 - Planned | Yet to receive |  |  |  | FALSE
5762 | WBS.2.1.15.26.1.1 | N | N | Planned | ITR_C0032 - Execute Load program - Convert Open work orders – Asset Suite | 4 | 2021-01-26 13:15 | 2021-01-26 17:15 | 2021-01-26 | ANJALI SINHA | DATA | 5761 | Yet to receive |  |  | ANJALI SINHA | 2021-01-26 23:45 | [6 empty] | 1 | 1: 5761 - Planned | Yet to receive |  |  |  | FALSE
92813 | WBS.2.1.15.20.1.3 | N | N | Planned | Execute Preload ITR_C0247 - NRX 3D Enterprise Document Conversion | 4 | 2021-01-26 16:00 | 2021-01-26 20:00 | 2021-01-26 | ANJALI SINHA | DATA | 92777,5393,5398,92788,10428,95626 | Yet to receive |  |  | ANJALI SINHA | 2021-01-27 02:30 | [6 empty] | 1 | 1: 92777 - Planned; 2: 5393 - Planned; 3: 5398 - Planned; 4: 92788 - Planned; 5: 10428 - Planned; 6: 95626 - Planned | Yet to receive |  |  |  | FALSE
82773 | WBS.2.1.9.25.1.3 | N | N | Planned | Generate Preload validation reports - DELTA AS8 Procured materials - All Views | 4 | 2021-01-26 16:30 | 2021-01-26 20:30 | 2021-01-26 | DEEPA SAW | DATA | 82772 | Yet to receive |  |  | DEEPA SAW | 2021-01-27 03:00 | [7 empty] | 1: 82772 - Planned | Yet to receive |  |  |  | FALSE
92815 | WBS.2.1.8.2.1.17 | N | N | Planned | Execute Load ITR_C0247 - NRX 3D Enterprise Document Conversion | 8 | 2021-01-27 07:00 | 2021-01-27 15:00 | 2021-01-27 | DEBRAJ PAL | DATA | 92814 | Yet to receive |  |  | DEBRAJ PAL | 2021-01-27 17:30 | Material | [6 empty] | 1: 92814 - Planned | Yet to receive |  |  |  | FALSE
82777 | WBS.2.1.15.15.1.1 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change pointers for CLFMAS, MATMAS, MATQM in MDG for DELTA Procured Materials load | 0.5 | 2021-01-27 09:30 | 2021-01-27 10:00 | 2021-01-27 | PHANI GHANTASALA | DATA | 92471 | Yet to receive |  |  | PHANI GHANTASALA | 2021-01-27 20:00 | [7 empty] | 1: 92471 - Planned | Yet to receive |  |  |  | FALSE
82778 | WBS.2.1.9.6.1.5 | N | N | Planned | Execute Load in MDG - DELTA AS8 Procured Materials - All Views | 4 | 2021-01-27 10:00 | 2021-01-27 14:00 | 2021-01-27 | DEBRAJ PAL | DATA | 82774,82775,82776,82777,92124,92628 | Yet to receive |  |  | DEBRAJ PAL | 2021-01-27 20:30 | [7 empty] | 1: 82774 - Planned; 2: 82775 - Planned; 3: 82776 - Planned; 4: 82777 - Planned; 5: 92124 - Planned; 6: 92628 - Planned | Yet to receive |  |  |  | FALSE
90681 | WBS.2.1.9.17.1.3 | N | N | Planned | MDG_C0098 - Execute Transform for DELTA AS8 Materials - Classifications View and generate validation report | 2 | 2021-01-27 14:00 | 2021-01-27 16:00 | 2021-01-27 | ANJALI SINHA | DATA | 82778 | Yet to receive |  |  | Krishna | 2021-01-28 00:30 | [7 empty] | 1: 82778 - Planned | Yet to receive |  |  |  | FALSE
82779 | WBS.2.1.9.21.1.2 | N | N | Planned | Generate Post Load Validation report - DELTA AS8 Procured materials - All Views | 3 | 2021-01-27 14:00 | 2021-01-27 17:00 | 2021-01-27 | ANJALI SINHA | DATA | 82778 | Yet to receive |  |  | Aarthi | 2021-01-28 00:30 | [6 empty] | 1 | 1: 82778 - Planned | Yet to receive |  |  |  | FALSE
90679 | WBS.2.1.8.1.1.7 | N | N | Planned | MDG_C0098 - Execute Load in MDG - DELTA AS8 Materials - Classification View and generate validation report | 1 | 2021-01-27 17:00 | 2021-01-27 18:00 | 2021-01-27 | ANJALI SINHA | DATA | 90680 | Yet to receive |  |  | Krishna | 2021-01-28 03:30 | Material | [6 empty] | 1: 90680 - Planned | Yet to receive |  |  |  | FALSE
82798 | WBS.2.1.9.16.1.3 | N | N | Planned | Replicate DELTA AS8 Procured materials from MDG to S/4HANA | 1.5 | 2021-01-27 19:15 | 2021-01-27 20:45 | 2021-01-27 | PHANI GHANTASALA | DATA | 82780,82781,82782,92627 | Yet to receive |  |  | PHANI GHANTASALA | 2021-01-28 05:45 | [7 empty] | 1: 82780 - Planned; 2: 82781 - Planned; 3: 82782 - Planned; 4: 92627 - Planned | Yet to receive |  |  |  | FALSE
90677 | WBS.2.1.9.19.1.3 | N | N | Planned | Replicate DELTA AS8 Procured material classifications from MDG to S4 and generate report | 2 | 2021-01-27 19:15 | 2021-01-27 21:15 | 2021-01-27 | PHANI GHANTASALA | DATA | 90678,92627 | Yet to receive |  |  | PHANI GHANTASALA | 2021-01-28 05:45 | [7 empty] | 1: 90678 - Planned; 2: 92627 - Planned | Yet to receive |  |  |  | FALSE
82799 | WBS.2.1.9.15.1.3 | N | N | Planned | Generate Replication validation report for DELTA AS8 Procured materials - All Views | 2 | 2021-01-27 20:45 | 2021-01-28 06:45 | 2021-01-28 | ANKIT AGARWAL | DATA | 82798 | Yet to receive |  |  | Ishaq | 2021-01-28 07:15 | [7 empty] | 1: 82798 - Planned | Yet to receive |  |  |  | FALSE
82804 | WBS.2.1.9.19.1.4 | N | N | Planned | Turn-ON DRFOUT, Turn OFF Change pointers for CLFMAS, MATMAS, MATQM in MDG after DELTA AS8 material signoff | 0.5 | 2021-01-28 09:45 | 2021-01-28 10:15 | 2021-01-28 | PHANI GHANTASALA | DATA | 92473 | Yet to receive |  |  | PHANI GHANTASALA | 2021-01-28 20:15 | [7 empty] | 1: 92473 - Planned | Yet to receive |  |  |  | FALSE
81155 | WBS.2.2.1.7.13.10 | N | N | Planned | Execute Extracts from AS8 for PTP_C0005.1, ITR_C0062 | 7.5 | 2021-01-30 21:15 | 2021-01-31 04:45 | 2021-01-31 | ANKIT AGARWAL | Data | 5251,3968,82187 | Yet to receive |  |  | ANKIT AGARWAL | 2021-01-31 07:45 | [7 empty] | 1: 5251 - Planned; 2: 3968 - Planned; 3: 82187 - Planned | Yet to receive |  |  |  | FALSE
97761 | WBS.2.2.1.7.16.5 | N | N | Planned | Dump check tables for PTM_C0201 | 1 | 2021-01-30 21:15 | 2021-01-30 22:15 | 2021-01-30 | DEEPA SAW | DATA | 82187 | Yet to receive |  |  | DEEPA SAW | 2021-01-31 07:45 | [7 empty] | 1: 82187 - Planned | Yet to receive |  |  |  | FALSE
94412 | WBS.2.1.15.30.1.1 | N | N | Planned | Execute FCW Extracts from MP2 for ITR_C0067.1 and ITR_C0062.1 | 3.5 | 2021-01-31 01:15 | 2021-01-31 04:45 | 2021-01-31 | ANJALI SINHA | DATA | 36505 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 36505 - Planned | Yet to receive |  |  |  | FALSE
81154 | WBS.2.1.16.4.2.16 | N | N | Planned | Execute Final Cutover Extracts from AS8 - for PTM_C0201, ITR_0035, ITR_C0067 | 3 | 2021-01-31 01:15 | 2021-01-31 04:15 | 2021-01-31 | ANJALI SINHA | DATA | 3968,36505 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 3968 - Planned; 2: 36505 - Planned | Yet to receive |  |  |  | FALSE
96720 | WBS.2.2.1.7.20.3 | N | N | Planned | RVG - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | 2021-01-31 | ANJALI SINHA | DATA | 36505,68450,96704 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 36505 - Planned; 2: 68450 - Planned; 3: 96704 - Planned | Yet to receive |  |  |  | FALSE
8874 | WBS.2.2.1.7.13.13 | N | N | Planned | PTH - PTM_C0201 - Execute Inventory Extracts From Elixir | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | 2021-01-31 | ANJALI SINHA | Data | 8864,36505,68450 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 8864 - Planned; 2: 36505 - Planned; 3: 68450 - Planned | Yet to receive |  |  |  | FALSE
94450 | WBS.2.1.13.1.1.12 | N | N | Planned | SCH - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | 2021-01-31 | ANJALI SINHA | DATA | 5231,36505,68450 | #done |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 5231 - Planned; 2: 36505 - Planned; 3: 68450 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
29564 | WBS.2.2.1.7.11.1 | N | N | Planned | Extract MAP (Moving Average Price) values from AS8 for Costing/AUP as of Cutoff date | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | 2021-01-31 | ANJALI SINHA | DATA | 36505 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 36505 - Planned | Yet to receive |  |  |  | FALSE
96719 | WBS.2.2.1.7.9.1 | N | N | Planned | RNC - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | 2021-01-31 | ANJALI SINHA | DATA | 36505,68450,96703 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 11:45 | [7 empty] | 1: 36505 - Planned; 2: 68450 - Planned; 3: 96703 - Planned | Yet to receive |  |  |  | FALSE
29567 | WBS.2.2.1.7.22.6 | N | N | Planned | Extract MAP (Moving Average Price values) from ECC for Procured Materials as of cutoff date | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | 2021-01-31 | ANJALI SINHA | DATA | 36505,95439 | #done |  |  | ANJALI SINHA | 2021-01-31 12:15 | [7 empty] | 1: 36505 - Planned; 2: 95439 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
81152 | WBS.2.2.1.7.1.19 | N | N | Planned | Execute Final Cutover Extracts from ECC - Small | 2.5 | 2021-01-31 02:30 | 2021-01-31 05:00 | 2021-01-31 | ANJALI SINHA | DATA | 3964,3966,3967,3968,36505,95439,97813,97547 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 13:00 | [7 empty] | 3964 - Planned | 3966 - Planned | 3967 - Planned | 3968 - Planned | 36505 - Planned | 95439 - Planned | 97813 - Planned | 97547 - Planned |  |  |  |  | Yet to receive |  |  |  | FALSE
81153 | WBS.2.2.1.7.20.1 | N | N | Planned | Execute Final Cutover Extracts from ECC - Large (Sales Orders, Pricing Records, Pricing Agrmts., Inventory) | 3.5 | 2021-01-31 02:30 | 2021-01-31 06:00 | 2021-01-31 | ANJALI SINHA | DATA | 3964,36505,95439,97813,97547 | Yet to receive |  |  | ANJALI SINHA | 2021-01-31 13:00 | [7 empty] | 1: 3964 - Planned; 2: 36505 - Planned; 3: 95439 - Planned; 4: 97813 - Planned; 5: 97547 - Planned | Yet to receive |  |  |  | FALSE
10039 | WBS.2.2.1.7.1.12 | N | N | Planned | PTH - PTM_C0201 - Extract E80 Storage Bins and Batches | 1 | 2021-01-31 03:30 | 2021-01-31 04:30 | 2021-01-31 | DEBRAJ PAL | DATA | 8874,89987,97835 | Yet to receive |  |  | DEBRAJ PAL | 2021-01-31 14:00 | [7 empty] | 1: 8874 - Planned; 2: 89987 - Planned; 3: 97835 - Planned | Yet to receive |  |  |  | FALSE
94452 | WBS.2.2.1.7.1.14 | N | N | Planned | PTM_C0201-Extract Storage bins and batches for all sources(PTH,RNC,RVG,SCH,HTB,BWG) | 2 | 2021-01-31 06:00 | 2021-01-31 08:00 | 2021-01-31 | DEEPA SAW | DATA | 94450,8874,96719,96720,81154,81152,81153,97761 | #done |  |  | DEEPA SAW | 2021-01-31 16:30 | [7 empty] | 94450 - Planned | 8874 - Planned | 96719 - Planned | 96720 - Planned | 81154 - Planned | 81152 - Planned | 81153 - Planned | 97761 - Planned |  |  |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
92169 | WBS.2.1.8.2.2.15 | N | N | Planned | Turn OFF DRFOUT in MDG for all Material Updates | 0.25 | 2021-01-31 10:30 | 2021-01-31 10:45 | 2021-01-31 | PHANI GHANTASALA | DATA | 91471,36505,92752,96892 | #done |  |  | MADAN | 2021-01-31 21:00 | Material | [6 empty] | 1: 91471 - Planned; 2: 36505 - Planned; 3: 92752 - Planned; 4: 96892 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
80925 | WBS.2.2.1.6.1.2 | N | N | Planned | Update Material Cross Reference (Xref) due to dual maintenance after initial conversion | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | 2021-01-31 | DEEPA SAW | DATA | 36505,94798,96903 | #done |  |  | DEEPA SAW | 2021-02-01 04:00 | Material | [6 empty] | 1: 36505 - Planned; 2: 94798 - Planned; 3: 96903 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5770 | WBS.2.2.1.7.29.3 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans – Asset suite | 4 | 2021-01-31 17:30 | 2021-01-31 21:30 | 2021-01-31 | ANKIT AGARWAL | DATA | 81154,5476,96903 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 04:00 | [7 empty] | 1: 81154 - Planned; 2: 5476 - Planned; 3: 96903 - Planned | Yet to receive |  |  |  | FALSE
92840 | WBS.2.2.1.7.23.17 | N | N | Planned | Execute Preload ITR_C0062.1 Convert Work order history – MP2 | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | 2021-01-31 | ANKIT AGARWAL | DATA | 94412,36505,96903 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 04:00 | [7 empty] | 1: 94412 - Planned; 2: 36505 - Planned; 3: 96903 - Planned | Yet to receive |  |  |  | FALSE
5486 | WBS.2.2.1.7.23.8 | N | N | Planned | ITR_C0062 - Execute Transform Program - Convert Work Order History - AS8 | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | 2021-01-31 | ANKIT AGARWAL | DATA | 5393,5398,81155,81706,36505,96903 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 04:00 | [7 empty] | 1: 5393 - Planned; 2: 5398 - Planned; 3: 81155 - Planned; 4: 81706 - Planned; 5: 36505 - Planned; 6: 96903 - Planned | Yet to receive |  |  |  | FALSE
80928 | WBS.2.2.1.7.13.1 | N | N | Planned | Provide preload file for AS8 MAP (Moving Average Price)/Inventory validation | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | 2021-01-31 | PRADEEP CHEEDALLA | Data | 29564,96903 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2021-02-01 04:00 | [7 empty] | 1: 29564 - Planned; 2: 96903 - Planned | Yet to receive |  |  |  | FALSE
91850 | WBS.2.2.1.7.13.32 | N | N | Planned | Execute DQ report to compare PO, Material and PIR units of measure | 1.5 | 2021-01-31 17:30 | 2021-01-31 19:00 | 2021-01-31 | PRADEEP CHEEDALLA | Data | 89675,81152,90972,96903 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2021-02-01 04:00 | [7 empty] | 1: 89675 - Planned; 2: 81152 - Planned; 3: 90972 - Planned; 4: 96903 - Planned | Yet to receive |  |  |  | FALSE
5698 | WBS.2.2.1.4.3.3 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Convert Open Purchase Orders | 3 | 2021-01-31 17:30 | 2021-01-31 20:30 | 2021-01-31 | ANJALI SINHA | DATA | 81155,82626,89675,81154,96903 | Yet to receive |  |  | ANJALI SINHA | 2021-02-01 04:00 | Customer | [6 empty] | 1: 81155 - Planned; 2: 82626 - Planned; 3: 89675 - Planned; 4: 81154 - Planned; 5: 96903 - Planned | Yet to receive |  |  |  | FALSE
10027 | WBS.2.2.1.7.5.4 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Service Purchase Orders | 4 | 2021-01-31 17:30 | 2021-01-31 21:30 | 2021-01-31 | ANJALI SINHA | DATA | 81155,82626,89675,81154,96903 | Yet to receive |  |  | ANJALI SINHA | 2021-02-01 04:00 | [7 empty] | 1: 81155 - Planned; 2: 82626 - Planned; 3: 89675 - Planned; 4: 81154 - Planned; 5: 96903 - Planned | Yet to receive |  |  |  | FALSE
5765 | WBS.2.2.1.7.15.2 | N | N | Planned | ITR_C0035 - Execute Transform program - Convert Open Notifications – Asset Suite | 1.5 | 2021-01-31 17:30 | 2021-01-31 19:00 | 2021-01-31 | JASPREET SINGH | DATA | 5395,81154,5438,89987,94400,96903 | Yet to receive |  |  | JASPREET SINGH | 2021-02-01 04:00 | [7 empty] | 1: 5395 - Planned; 2: 81154 - Planned; 3: 5438 - Planned; 4: 89987 - Planned; 5: 94400 - Planned; 6: 96903 - Planned | Yet to receive |  |  |  | FALSE
92834 | WBS.2.2.1.7.5.7 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | 2021-01-31 | JASPREET SINGH | DATA | 94412,36505,92877,96903 | Yet to receive |  |  | JASPREET SINGH | 2021-02-01 04:00 | [7 empty] | 1: 94412 - Planned; 2: 36505 - Planned; 3: 92877 - Planned; 4: 96903 - Planned | Yet to receive |  |  |  | FALSE
96347 | WBS.2.2.1.7.16.5 | N | N | Planned | IM Sites - PTM_C0201 - Execute Transform For ECC IM Inventory | 3 | 2021-01-31 17:30 | 2021-01-31 20:30 | 2021-01-31 | DEEPA SAW | DATA | 81153,96903 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 04:00 | [7 empty] | 1: 81153 - Planned; 2: 96903 - Planned | Yet to receive |  |  |  | FALSE
94469 | WBS.2.2.1.7.13.28 | N | N | Planned | PTH - PTM_C0201 - Execute Transform For AS8 MRO Inventory | 2 | 2021-01-31 17:45 | 2021-01-31 19:45 | 2021-01-31 | DEEPA SAW | Data | 10038,81154,5230,96903 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 04:15 | [7 empty] | 1: 10038 - Planned; 2: 81154 - Planned; 3: 5230 - Planned; 4: 96903 - Planned | Yet to receive |  |  |  | FALSE
94467 | WBS.2.2.1.7.13.2 | N | N | Planned | HBG and BG - PTM_C0201 - Execute Transform For ECC MRO Inventory | 2 | 2021-01-31 17:45 | 2021-01-31 19:45 | 2021-01-31 | DEEPA SAW | DATA | 10038,94323,81153,96572,96903 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 04:15 | [7 empty] | 1: 10038 - Planned; 2: 94323 - Planned; 3: 81153 - Planned; 4: 96572 - Planned; 5: 96903 - Planned | Yet to receive |  |  |  | FALSE
94476 | WBS.2.2.1.7.16.5 | N | N | Planned | PTH - PTM_C0201 - Execute preload for E80 Inventory Load file (FG) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | 2021-01-31 | DEBRAJ PAL | DATA | 9091,10038,8864,10039 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 04:30 | [7 empty] | 1: 9091 - Planned; 2: 10038 - Planned; 3: 8864 - Planned; 4: 10039 - Planned | Yet to receive |  |  |  | FALSE
90407 | WBS.2.2.1.7.27.1 | N | N | Planned | PTH - PTM_C0201 - Execute Transform For Elixir Inventory | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | 2021-01-31 | DEEPA SAW | DATA | 5231,9091,10038,8874,8864,96703,96704 | #done |  |  | DEEPA SAW | 2021-02-01 04:30 | [7 empty] | 1: 5231 - Planned; 2: 9091 - Planned; 3: 10038 - Planned; 4: 8874 - Planned; 5: 8864 - Planned; 6: 96703 - Planned; 7: 96704 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
97173 | WBS.2.2.1.15.1.5 | N | N | Planned | BG (FG/PR) - PTM_C0201 - Execute Transform for SAP-WM Inventory | 2.5 | 2021-01-31 18:00 | 2021-01-31 20:30 | 2021-01-31 | DEEPA SAW | DATA | 10038,9091,96571 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 04:30 | Customer | [6 empty] | 1: 10038 - Planned; 2: 9091 - Planned; 3: 96571 - Planned | Yet to receive |  |  |  | FALSE
96692 | WBS.2.2.1.7.23.9 | N | N | Planned | RNC, RVG AND SCH - PTM_C0201 - Execute Transform For JDA Inventory | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | 2021-01-31 | DEEPA SAW | DATA | 5231,9091,10038,8874,8864,96703,96704 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 04:30 | [7 empty] | 1: 5231 - Planned; 2: 9091 - Planned; 3: 10038 - Planned; 4: 8874 - Planned; 5: 8864 - Planned; 6: 96703 - Planned; 7: 96704 - Planned | Yet to receive |  |  |  | FALSE
5684 | WBS.2.2.1.7.13.26 | N | N | Planned | PTM_C0202 - Execute Load program - Convert Truck/Transportation Load Data | 3 | 2021-01-31 19:00 | 2021-01-31 22:00 | 2021-01-31 | ANURAG ANAND | Data | 5218,92152,93004,94329,96651,96749,96750,97478 | #done |  |  | ANURAG ANAND | 2021-02-01 05:30 | [7 empty] | 5218 - Planned | 92152 - Planned | 93004 - Planned | 94329 - Planned | 96651 - Planned | 96749 - Planned | 96750 - Planned | 97478 - Planned |  |  |  |  | Yet to receive | FALSE | FALSE | TRUE | TRUE
90147 | WBS.2.1.15.30.1.1 | N | N | Planned | Replicate materials with EP/Production SLOC & Frozen Horizon updates from MDG to S4 & Also replicate the loading group changes | 3 | 2021-01-31 19:15 | 2021-01-31 22:15 | 2021-01-31 | PHANI GHANTASALA | DATA | 90038,90068,90851,92742,94725,97705 | #done |  |  | PHANI GHANTASALA | 2021-02-01 05:45 | [7 empty] | 1: 90038 - Planned; 2: 90068 - Planned; 3: 90851 - Planned; 4: 92742 - Planned; 5: 94725 - Planned; 6: 97705 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
5767 | WBS.2.2.1.7.4.5 | N | N | Planned | ITR_C0035 - Execute Load program - Convert Open Notifications – Asset Suite | 1 | 2021-01-31 19:20 | 2021-01-31 20:20 | 2021-01-31 | JASPREET SINGH | DATA | 5766 | Yet to receive |  |  | JASPREET SINGH | 2021-02-01 05:50 | [7 empty] | 1: 5766 - Planned | Yet to receive |  |  |  | FALSE
80929 | WBS.2.2.1.7.23.10 | N | N | Planned | Provide preload file for ECC MAP (Moving Average Price)/Inventory validation | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | 2021-01-31 | PRADEEP CHEEDALLA | DATA | 29567,96903,80928 | #done |  |  | PRADEEP CHEEDALLA | 2021-02-01 06:00 | [7 empty] | 1: 29567 - Planned; 2: 96903 - Planned; 3: 80928 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
94478 | WBS.2.2.1.7.16.5 | N | N | Planned | PTH - PTM_C0201 - Execute Load for E80 FG Inventory | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | 2021-01-31 | DEBRAJ PAL | DATA | 94477,95429 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 06:00 | [7 empty] | 1: 94477 - Planned; 2: 95429 - Planned | Yet to receive |  |  |  | FALSE
90894 | WBS.2.1.15.30.1.1 | N | N | Planned | Replicate materials with Order UOM updates from MDG to S4 for PO conversion | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | 2021-01-31 | PHANI GHANTASALA | DATA | 90893 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 06:30 | [7 empty] | 1: 90893 - Planned | Yet to receive |  |  |  | FALSE
5488 | WBS.2.2.1.7.15.1 | N | N | Planned | ITR_C0062 - Execute Load Program - Convert Work Order History - AS8 | 2 | 2021-01-31 20:15 | 2021-01-31 22:15 | 2021-01-31 | ANKIT AGARWAL | DATA | 5487 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 06:45 | [7 empty] | 1: 5487 - Planned | Yet to receive |  |  |  | FALSE
92832 | WBS.2.2.1.7.4.11 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | 2021-01-31 | JASPREET SINGH | DATA | 92833 | Yet to receive |  |  | JASPREET SINGH | 2021-02-01 07:00 | [7 empty] | 1: 92833 - Planned | Yet to receive |  |  |  | FALSE
92838 | WBS.2.2.1.7.22.12 | N | N | Planned | Execute Load ITR_C0062.1 Convert Work order history – MP2 | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | 2021-01-31 | ANKIT AGARWAL | DATA | 92839 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 07:00 | [7 empty] | 1: 92839 - Planned | Yet to receive |  |  |  | FALSE
29570 | WBS.2.2.1.7.18.2 | N | N | Planned | Load Moving Average Prices for AS8 | 6 | 2021-01-31 20:30 | 2021-02-01 02:30 | 2021-02-01 | DEBRAJ PAL | DATA | 29566,92152 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 07:00 | [7 empty] | 1: 29566 - Planned; 2: 92152 - Planned | Yet to receive |  |  |  | FALSE
94486 | WBS.2.2.1.7.23.1 | N | N | Planned | SCH - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | 2021-02-01 | DEBRAJ PAL | DATA | 92152,94479,95429,95685,95686,95687 | #done |  |  | VENKATESH GANESHAN | 2021-02-01 08:00 | [7 empty] | 1: 92152 - Planned; 2: 94479 - Planned; 3: 95429 - Planned; 4: 95685 - Planned; 5: 95686 - Planned; 6: 95687 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
96728 | WBS.2.2.1.7.16.5 | N | N | Planned | RNC - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | 2021-02-01 | DEBRAJ PAL | DATA | 96727,92152,95429,95685,95686,95687 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-02-01 08:00 | [7 empty] | 1: 96727 - Planned; 2: 92152 - Planned; 3: 95429 - Planned; 4: 95685 - Planned; 5: 95686 - Planned; 6: 95687 - Planned | Yet to receive |  |  |  | FALSE
96735 | WBS.2.2.1.7.16.5 | N | N | Planned | RVG - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | 2021-02-01 | DEBRAJ PAL | DATA | 96734,92152,95429,95685,95686,95687 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-02-01 08:00 | [7 empty] | 1: 96734 - Planned; 2: 92152 - Planned; 3: 95429 - Planned; 4: 95685 - Planned; 5: 95686 - Planned; 6: 95687 - Planned | Yet to receive |  |  |  | FALSE
5772 | WBS.2.2.1.7.26.6 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans – Asset suite | 2 | 2021-01-31 22:00 | 2021-02-01 | 2021-02-01 | ANKIT AGARWAL | DATA | 5771,92152 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-01 08:30 | [7 empty] | 1: 5771 - Planned; 2: 92152 - Planned | Yet to receive |  |  |  | FALSE
5693 | WBS.2.2.1.15.1.3 | N | N | Planned | PTP_C0005 - Execute Transform program - Convert Open Purchase Orders - ECC | 2 | 2021-01-31 22:15 | 2021-02-01 00:15 | 2021-02-01 | JASPREET SINGH | DATA | 81152,89675,90894,90972,91849,90147 | Yet to receive |  |  | JASPREET SINGH | 2021-02-01 08:45 | Material | [6 empty] | 1: 81152 - Planned; 2: 89675 - Planned; 3: 90894 - Planned; 4: 90972 - Planned; 5: 91849 - Planned; 6: 90147 - Planned | Yet to receive |  |  |  | FALSE
96670 | WBS.2.2.1.7.8.1 | N | N | Planned | REX - PTM_C0201 - Execute Load program for REX SAP IM (ECC) Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | 2021-02-01 | DEEPA SAW | DATA | 96669,95429 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 09:00 | [7 empty] | 1: 96669 - Planned; 2: 95429 - Planned | Yet to receive |  |  |  | FALSE
96666 | WBS.2.2.1.7.1.15 | N | N | Planned | SAT - PTM_C0201 - Execute Load program for SAT SAP IM (ECC) Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | 2021-02-01 | DEEPA SAW | DATA | 96665,95429 | Yet to receive |  |  | DEEPA SAW | 2021-02-01 09:00 | [7 empty] | 1: 96665 - Planned; 2: 95429 - Planned | Yet to receive |  |  |  | FALSE
96689 | WBS.2.2.1.7.16.5 | N | N | Planned | BG (FG/SFG) - PTM_C0201 - Execute Load for SAP-WM FG/SFG Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | 2021-02-01 | VENKATESH GANESHAN | DATA | 96688,96565,95429 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-02-01 09:00 | [7 empty] | 1: 96688 - Planned; 2: 96565 - Planned; 3: 95429 - Planned | Yet to receive |  |  |  | FALSE
29571 | WBS.2.1.10.2.14.7 | N | N | Planned | Load Moving Average Prices for ECC (procured material) | 2 | 2021-01-31 23:30 | 2021-02-01 01:30 | 2021-02-01 | DEBRAJ PAL | DATA | 29569,92152 | #done |  |  | DEBRAJ PAL | 2021-02-01 10:00 | [7 empty] | 1: 29569 - Planned; 2: 92152 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
10029 | WBS.2.2.1.7.20.5 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Service Purchase Orders | 2 | 2021-02-01 00:30 | 2021-02-01 02:30 | 2021-02-01 | PHANI GHANTASALA | DATA | 10028,82656,82766,92152 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 11:00 | [7 empty] | 1: 10028 - Planned; 2: 82656 - Planned; 3: 82766 - Planned; 4: 92152 - Planned | Yet to receive |  |  |  | FALSE
89764 | WBS.2.2.1.7.20.11 | N | N | Planned | PTP_C0005.1 - AS8 - Turn on the enhancement | 0.5 | 2021-02-01 00:30 | 2021-02-01 01:00 | 2021-02-01 | PHANI GHANTASALA | DATA | 10028,82656 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 11:00 | [7 empty] | 1: 10028 - Planned; 2: 82656 - Planned | Yet to receive |  |  |  | FALSE
5700 | WBS.2.2.1.7.13.30 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Convert Open Purchase Orders | 6 | 2021-02-01 00:30 | 2021-02-01 06:30 | 2021-02-01 | PHANI GHANTASALA | Data | 5699,82657,82766,92152 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 11:00 | [7 empty] | 1: 5699 - Planned; 2: 82657 - Planned; 3: 82766 - Planned; 4: 92152 - Planned | Yet to receive |  |  |  | FALSE
94491 | WBS.2.2.1.7.13.33 | N | N | Planned | HBG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2021-02-01 03:30 | 2021-02-01 06:30 | 2021-02-01 | DEBRAJ PAL | Data | 94471,92152,29567,29571,93904,95429 | Yet to receive |  |  | VENKATESH GANESHAN | 2021-02-01 14:00 | [7 empty] | 1: 94471 - Planned; 2: 92152 - Planned; 3: 29567 - Planned; 4: 29571 - Planned; 5: 93904 - Planned; 6: 95429 - Planned | Yet to receive |  |  |  | FALSE
8883 | WBS.2.2.1.7.23.2 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for Elixir Inventory | 5 | 2021-02-01 03:30 | 2021-02-01 08:30 | 2021-02-01 | DEBRAJ PAL | DATA | 5671,92152,93138,93321,95429,97618 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 14:00 | [7 empty] | 1: 5671 - Planned; 2: 92152 - Planned; 3: 93138 - Planned; 4: 93321 - Planned; 5: 95429 - Planned; 6: 97618 - Planned | Yet to receive |  |  |  | FALSE
96682 | WBS.2.2.1.7.16.5 | N | N | Planned | BG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2021-02-01 04:30 | 2021-02-01 07:30 | 2021-02-01 | DEBRAJ PAL | DATA | 96681,92152,29567,29571,96631,95429 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 15:00 | [7 empty] | 1: 96681 - Planned; 2: 92152 - Planned; 3: 29567 - Planned; 4: 29571 - Planned; 5: 96631 - Planned; 6: 95429 - Planned | Yet to receive |  |  |  | FALSE
5695 | WBS.2.2.1.7.13.36 | N | N | Planned | PTP_C0005 - Execute Load program - Convert Open Purchase Orders - ECC | 3 | 2021-02-01 05:15 | 2021-02-01 08:15 | 2021-02-01 | JASPREET SINGH | Data | 5694,82646,82766,92152,82340,90147 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 15:45 | [7 empty] | 1: 5694 - Planned; 2: 82646 - Planned; 3: 82766 - Planned; 4: 92152 - Planned; 5: 82340 - Planned; 6: 90147 - Planned | Yet to receive |  |  |  | FALSE
94493 | WBS.2.2.1.7.26.2 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for AS8 Inventory (MRO) | 4 | 2021-02-01 05:30 | 2021-02-01 09:30 | 2021-02-01 | DEBRAJ PAL | DATA | 29564,29570,68331,94473,92152,95429 | Yet to receive |  |  | DEBRAJ PAL | 2021-02-01 16:00 | [7 empty] | 1: 29564 - Planned; 2: 29570 - Planned; 3: 68331 - Planned; 4: 94473 - Planned; 5: 92152 - Planned; 6: 95429 - Planned | Yet to receive |  |  |  | FALSE
89763 | WBS.2.2.1.7.21.5 | N | N | Planned | PTP_C0005.1 - AS8 - Turn off the enhancement | 0.5 | 2021-02-01 12:15 | 2021-02-01 12:45 | 2021-02-01 | PHANI GHANTASALA | DATA | 10029,5696,10030 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 22:45 | [7 empty] | 1: 10029 - Planned; 2: 5696 - Planned; 3: 10030 - Planned | Yet to receive |  |  |  | FALSE
9657 | WBS.2.2.1.7.9.3 | N | N | Planned | PTP_C0236 - Execute Transform program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 13:00 | 2021-02-01 14:00 | 2021-02-01 | ANURAG ANAND | DATA | 80747,82480,5701,5696,82661,82652,94291 | Yet to receive |  |  | ANURAG ANAND | 2021-02-01 23:30 | [7 empty] | 1: 80747 - Planned; 2: 82480 - Planned; 3: 5701 - Planned; 4: 5696 - Planned; 5: 82661 - Planned; 6: 82652 - Planned; 7: 94291 - Planned | Yet to receive |  |  |  | FALSE
90896 | WBS.2.2.1.7.13.11 | N | N | Planned | Replicate materials after reverting order UOM and AUOM updates from MDG to S4 | 5 | 2021-02-01 13:15 | 2021-02-01 18:15 | 2021-02-01 | PHANI GHANTASALA | Data | 90895 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-01 23:45 | [7 empty] | 1: 90895 - Planned | Yet to receive |  |  |  | FALSE
97523 |  |  |  |  | HBG - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 2020-12-14 16:15 | 2021-02-01 16:00 | 2021-02-01 17:00 | 2021-02-01 | ANURAG ANAND | DATA | 9658,68402,80748,5696,5701,92152,95281,94777 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 02:30 | [7 empty] | 9658 - Planned | 68402 - Planned | 80748 - Planned | 5696 - Planned | 5701 - Planned | 92152 - Planned | 95281 - Planned | 94777 - Planned |  |  |  |  | Yet to receive |  |  |  | FALSE
97529 |  |  |  |  | BG - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 2020-12-14 16:15 | 2021-02-01 16:00 | 2021-02-01 17:00 | 2021-02-01 | ANURAG ANAND | DATA | 9658,68402,80748,5696,5701,92152,96645,96646 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 02:30 | [7 empty] | 9658 - Planned | 68402 - Planned | 80748 - Planned | 5696 - Planned | 5701 - Planned | 92152 - Planned | 96645 - Planned | 96646 - Planned |  |  |  |  | Yet to receive |  |  |  | FALSE
9659 | WBS.2.2.1.7.8.3 | N | N | Planned | PTH - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | 2021-02-01 | ANURAG ANAND | DATA | 9658,68402,80748,5696,5701,68331,92152,94779,94780 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 02:30 | [7 empty] | 9658 - Planned | 68402 - Planned | 80748 - Planned | 5696 - Planned | 5701 - Planned | 68331 - Planned | 92152 - Planned | 94779 - Planned | 94780 - Planned |  |  |  | Yet to receive |  |  |  | FALSE
92172 | WBS.2.2.1.7.13.12 | N | N | Planned | Turn ON DRFOUT in MDG after All Material Updates | 0.25 | 2021-02-01 18:15 | 2021-02-01 18:30 | 2021-02-01 | PHANI GHANTASALA | Data | 90894,90895,90896 | #done |  |  | PHANI GHANTASALA | 2021-02-02 04:45 | [7 empty] | 1: 90894 - Planned; 2: 90895 - Planned; 3: 90896 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
92396 | WBS.2.1.9.28.1.3 | N | N | Planned | Check for Material Change Requests and Manually Updated Materials that may not have Replicated Downstream | 1 | 2021-02-01 18:30 | 2021-02-01 19:30 | 2021-02-01 | SHANKAR RAMNARAYANAN | DATA | 92172,95766 | #done |  |  | SHANKAR RAMNARAYANAN | 2021-02-02 05:00 | [7 empty] | 1: 92172 - Planned; 2: 95766 - Planned | Yet to receive | FALSE | FALSE | TRUE | TRUE
97532 |  |  |  |  | HBG - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 2020-12-14 16:15 | 2021-02-01 19:00 | 2021-02-01 20:00 | 2021-02-01 | ANURAG ANAND | DATA | 82481,36505,97525 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 05:30 | [7 empty] | 1: 82481 - Planned; 2: 36505 - Planned; 3: 97525 - Planned | Yet to receive |  |  |  | FALSE
97540 |  |  |  |  | BG - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 2020-12-14 16:15 | 2021-02-01 19:00 | 2021-02-01 20:00 | 2021-02-01 | ANURAG ANAND | DATA | 82481,36505,97531 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 05:30 | [7 empty] | 1: 82481 - Planned; 2: 36505 - Planned; 3: 97531 - Planned | Yet to receive |  |  |  | FALSE
9661 | WBS.2.2.1.7.27.3 | N | N | Planned | PTH - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-01 19:00 | 2021-02-01 20:00 | 2021-02-01 | ANURAG ANAND | DATA | 82361,82481,36505 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 05:30 | [7 empty] | 1: 82361 - Planned; 2: 82481 - Planned; 3: 36505 - Planned | Yet to receive |  |  |  | FALSE
97542 |  |  |  |  | BG - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2020-12-14 16:15 | 2021-02-01 22:00 | 2021-02-02 | 2021-02-02 | ANURAG ANAND | DATA | 97541,92152,97530 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 08:30 | [7 empty] | 1: 97541 - Planned; 2: 92152 - Planned; 3: 97530 - Planned | Yet to receive |  |  |  | FALSE
97534 |  |  |  |  | HBG - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2020-12-14 16:15 | 2021-02-01 22:00 | 2021-02-02 | 2021-02-02 | ANURAG ANAND | DATA | 97533,92152,97524 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 08:30 | [7 empty] | 1: 97533 - Planned; 2: 92152 - Planned; 3: 97524 - Planned | Yet to receive |  |  |  | FALSE
9663 | WBS.2.2.1.7.23.9 | N | N | Planned | PTH - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 22:00 | 2021-02-02 | 2021-02-02 | ANURAG ANAND | DATA | 9662,9660,92152 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 08:30 | [7 empty] | 1: 9662 - Planned; 2: 9660 - Planned; 3: 92152 - Planned | Yet to receive |  |  |  | FALSE
8788 | WBS.2.2.1.7.13.4 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Costing BOMs | 2 | 2021-02-02 08:45 | 2021-02-02 10:45 | 2021-02-02 | PRADEEP CHEEDALLA | DATA | 7882 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2021-02-02 19:15 | [7 empty] | 1: 7882 - Planned | Yet to receive |  |  |  | FALSE
8790 | WBS.2.2.1.7.18.4 | N | N | Planned | PTM_C0082 - Execute Preload - Convert Costing Routing (Simulation Mode) | 1 | 2021-02-02 09:00 | 2021-02-02 10:00 | 2021-02-02 | ANURAG ANAND | DATA | 7883 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 19:30 | [7 empty] | 1: 7883 - Planned | Yet to receive |  |  |  | FALSE
8792 | WBS.2.1.15.17.1.8 | N | N | Planned | PTM_C0082 - Execute Load program - Costing Routing | 1 | 2021-02-02 10:15 | 2021-02-02 11:15 | 2021-02-02 | ANURAG ANAND | DATA | 8791 | Yet to receive |  |  | ANURAG ANAND | 2021-02-02 20:45 | [7 empty] | 1: 8791 - Planned | Yet to receive |  |  |  | FALSE
5190 | WBS.2.2.1.7.11.13 | N | N | Planned | PTM_C0080 - Execute Load in S/4HANA - for Costing BOMS | 3 | 2021-02-02 11:15 | 2021-02-02 14:15 | 2021-02-02 | PRADEEP CHEEDALLA | DATA | 8789 | Yet to receive |  |  | PRADEEP CHEEDALLA | 2021-02-02 21:45 | [7 empty] | 1: 8789 - Planned | Yet to receive |  |  |  | FALSE
8797 | WBS.2.2.1.7.15.4 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Costing Production Versions (Simulation Mode) | 2 | 2021-02-02 16:15 | 2021-02-02 18:15 | 2021-02-02 | ANKIT AGARWAL | DATA | 7886 | Yet to receive |  |  | ANKIT AGARWAL | 2021-02-03 02:45 | [7 empty] | 1: 7886 - Planned | Yet to receive |  |  |  | FALSE
8799 | WBS.2.2.1.7.16.5 | N | N | Planned | PTM_C0085 - Execute Load Program - Convert Costing Production Versions | 1 | 2021-02-02 18:30 | 2021-02-02 19:30 | 2021-02-02 | PHANI GHANTASALA | DATA | 8798 | Yet to receive |  |  | PHANI GHANTASALA | 2021-02-03 05:00 | [7 empty] | 1: 8798 - Planned | Yet to receive |  |  |  | FALSE

## Sheet1
UID | Tag Status
94411 | #done
3968 | #done
3967 | #done
3966 | #done
3964 | #done
82569 | #done
82566 | Yet to receive
82567 | Yet to receive
82574 | Yet to receive
82575 | Yet to receive
82561 | Yet to receive
10137 | Yet to receive
82570 | Yet to receive
89984 | Yet to receive
92780 | Yet to receive
5390 | Yet to receive
89675 | Yet to receive
82565 | Yet to receive
89674 | Yet to receive
5084 | Yet to receive
90888 | Yet to receive
89982 | Yet to receive
5387 | Yet to receive
5381 | Yet to receive
5233 | Yet to receive
5243 | Yet to receive
5392 | Yet to receive
5384 | Yet to receive
92778 | Yet to receive
10116 | Yet to receive
9174 | #start
10138 | Yet to receive
10492 | Yet to receive
95364 | Yet to receive
10493 | Yet to receive
10494 | Yet to receive
5235 | Yet to receive
92785 | Yet to receive
83323 | Yet to receive
10495 | Yet to receive
10496 | Yet to receive
8807 | Yet to receive
82903 | Yet to receive
5427 | Yet to receive
92787 | Yet to receive
5405 | Yet to receive
90055 | Yet to receive
83325 | Yet to receive
90890 | Yet to receive
5090 | Yet to receive
82901 | Yet to receive
5440 | Yet to receive
92806 | Yet to receive
5407 | Yet to receive
5096 | Yet to receive
10498 | Yet to receive
9148 | Yet to receive
83324 | Yet to receive
5429 | Yet to receive
92808 | Yet to receive
10118 | Yet to receive
10472 | Yet to receive
10526 | Yet to receive
9149 | Yet to receive
5177 | Yet to receive
5453 | Yet to receive
10473 | Yet to receive
90767 | Yet to receive
68443 | Yet to receive
68444 | Yet to receive
9150 | Yet to receive
10499 | Yet to receive
10120 | Yet to receive
90765 | Yet to receive
95508 | Yet to receive
5455 | Yet to receive
82908 | Yet to receive
9151 | Yet to receive
10501 | Yet to receive
94770 | Yet to receive
10110 | Yet to receive
9798 | Yet to receive
89712 | Yet to receive
5478 | Yet to receive
95506 | Yet to receive
5100 | Yet to receive
10502 | Yet to receive
9928 | Yet to receive
89711 | Yet to receive
5480 | Yet to receive
82906 | Yet to receive
10528 | Yet to receive
10023 | Yet to receive
9804 | Yet to receive
5121 | Yet to receive
90050 | Yet to receive
9800 | Yet to receive
5183 | Yet to receive
5193 | Yet to receive
82854 | Yet to receive
10503 | Yet to receive
5122 | Yet to receive
5415 | Yet to receive
89766 | Yet to receive
5395 | Yet to receive
5248 | Yet to receive
5448 | Yet to receive
92867 | Yet to receive
5468 | Yet to receive
80859 | Yet to receive
5186 | Yet to receive
92869 | Yet to receive
5450 | Yet to receive
5470 | Yet to receive
5397 | Yet to receive
5250 | Yet to receive
90049 | Yet to receive
10114 | Yet to receive
92874 | Yet to receive
10022 | Yet to receive
9810 | Yet to receive
92876 | Yet to receive
5417 | Yet to receive
5201 | Yet to receive
10112 | Yet to receive
5473 | Yet to receive
5437 | Yet to receive
80860 | Yet to receive
10032 | Yet to receive
5400 | Yet to receive
5475 | Yet to receive
90052 | Yet to receive
90959 | Yet to receive
5402 | Yet to receive
5253 | Yet to receive
5245 | Yet to receive
90960 | Yet to receive
5255 | Yet to receive
5229 | Yet to receive
5215 | Yet to receive
5258 | Yet to receive
5260 | Yet to receive
4971 | Yet to receive
4973 | Yet to receive
10474 | Yet to receive
5378 | Yet to receive
89987 | Yet to receive
82771 | Yet to receive
95613 | Yet to receive
94400 | Yet to receive
92846 | Yet to receive
94357 | Yet to receive
5760 | Yet to receive
89993 | Yet to receive
92844 | Yet to receive
82772 | Yet to receive
89994 | Yet to receive
94355 | Yet to receive
5762 | Yet to receive
92813 | Yet to receive
82773 | Yet to receive
92815 | Yet to receive
82777 | Yet to receive
82778 | Yet to receive
90681 | Yet to receive
82779 | Yet to receive
90679 | Yet to receive
82798 | Yet to receive
90677 | Yet to receive
82799 | Yet to receive
82804 | Yet to receive
81155 | Yet to receive
94412 | Yet to receive
81154 | Yet to receive
96720 | Yet to receive
8874 | Yet to receive
94450 | Yet to receive
29564 | Yet to receive
96719 | Yet to receive
29567 | Yet to receive
10039 | Yet to receive
81152 | Yet to receive
81153 | Yet to receive
94452 | Yet to receive
92169 | Yet to receive
80925 | Yet to receive
5770 | Yet to receive
92840 | Yet to receive
5486 | Yet to receive
80928 | Yet to receive
91850 | Yet to receive
5698 | Yet to receive
10027 | Yet to receive
5765 | Yet to receive
92834 | Yet to receive
96347 | Yet to receive
94469 | Yet to receive
94467 | Yet to receive
94476 | Yet to receive
90407 | Yet to receive
97173 | Yet to receive
96692 | Yet to receive
5684 | Yet to receive
90147 | Yet to receive
5767 | Yet to receive
80929 | Yet to receive
94478 | Yet to receive
90894 | Yet to receive
5488 | Yet to receive
92832 | Yet to receive
92838 | Yet to receive
29570 | Yet to receive
94486 | Yet to receive
96728 | Yet to receive
96735 | Yet to receive
5772 | Yet to receive
5693 | Yet to receive
96670 | Yet to receive
96666 | Yet to receive
96689 | Yet to receive
29571 | Yet to receive
10029 | Yet to receive
89764 | Yet to receive
5700 | Yet to receive
94491 | Yet to receive
8883 | Yet to receive
96682 | Yet to receive
5695 | Yet to receive
94493 | Yet to receive
89763 | Yet to receive
9657 | Yet to receive
90896 | Yet to receive
97523 | Yet to receive
97529 | Yet to receive
9659 | Yet to receive
92172 | Yet to receive
92396 | Yet to receive
97532 | Yet to receive
97540 | Yet to receive
9661 | Yet to receive
97542 | Yet to receive
97534 | Yet to receive
9663 | Yet to receive
8788 | Yet to receive
8790 | Yet to receive
8792 | Yet to receive
5190 | Yet to receive
8797 | Yet to receive
8799 | Yet to receive
95038 | Yet to receive
97821 | Yet to receive
97761 | Yet to receive
Yet to receive

## Cutover Plan
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27
Unique ID | WBS | E-mail Sent | Task Completion | Status | Task Name | Duration (Hrs) | Start | Finish | Resource Names | Resource Name Email | Secondary Resource Name | Secondary Resource E-Mail | Team | Predecessor | Actual Start | Actual Finish | Constraint Type | Constraint Date | Baseline Start | Baseline Finish | Sub-Team | Location | Finish Date | Baseline Finish (Calc) | Baseline week | Phase | SOW
3931 | WBS.1 | N | N |  | TC ¦ Milestones | 223 | 2021-01-17 05:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control | 2021-01-17
91536 | WBS.1.1 | N | N |  | TC ¦ Milestones - Tasks Control | 223 | 2021-01-17 05:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91551 | WBS.1.1.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness | 223 | 2021-01-17 05:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91553 | WBS.1.1.1.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates | 222.5 | 2021-01-17 05:00 | 2021-02-02 08:00 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-02-02 08:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91554 | WBS.1.1.1.1.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp Down | 180.25 | 2021-01-17 05:00 | 2021-01-30 23:45 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-01-30 23:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Task Control
91556 | WBS.1.1.1.1.1.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp Down - System | 2.75 | 2021-01-17 21:30 | 2021-01-18 06:15 | [8 empty] | * |  | 2021-01-17 21:30 | 2021-01-18 06:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Task Control
93067 | WBS.1.1.1.1.1.1.1 | N | N | Planned | Predecessor for Technical Cutover Tasks - Sunday | 0.25 | 2021-01-17 21:30 | 2021-01-17 21:45 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI |  |  |  |  | 2021-01-17 21:30 | 2021-01-17 21:30 | 2021-01-17 21:45 | SAI | CROSS | 2021-01-17 | 2021-01-17 | 1 | Task Control
36501 | WBS.1.1.1.1.1.1.2 | N | N | Planned | Gate 1 - Technical Go-Live & Data Preparation - Monday | 0.25 | 2021-01-18 06:00 | 2021-01-18 06:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;CHRISTIAN KESSLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CKESSLER@DELOITTE.COM | SAI |  |  |  |  | 2021-01-18 06:00 | 2021-01-18 06:00 | 2021-01-18 06:15 | SAI | CROSS | 2021-01-18 | 2021-01-18 | 1 | Task Control
91555 | WBS.1.1.1.1.1.2 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp Down - Business | 180.25 | 2021-01-17 05:00 | 2021-01-30 23:45 | [8 empty] | * |  | 2021-01-17 05:00 | 2021-01-30 23:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Task Control
10531 | WBS.1.1.1.1.1.2.1 | N | N | Planned | Trigger Business Ramp Down Cutover Tasks | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SAI | CROSS | 2021-01-18 | 2021-01-18 | 1 | Task Control
10846 | WBS.1.1.1.1.1.2.2 | N | N | Planned | Predecessor For T-2 Weeks Task | 0.25 | 2021-01-18 06:00 | 2021-01-18 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-18 06:00 | 2021-01-18 06:00 | 2021-01-18 06:15 | SAI | CROSS | 2021-01-18 | 2021-01-18 | 1 | Task Control
10845 | WBS.1.1.1.1.1.2.3 | N | N | Planned | Predecessor For T-5 Days Task | 0.25 | 2021-01-25 06:00 | 2021-01-25 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-25 06:00 | 2021-01-25 06:00 | 2021-01-25 06:15 | SAI | CROSS | 2021-01-25 | 2021-01-25 | 2 | Task Control
10854 | WBS.1.1.1.1.1.2.4 | N | N | Planned | Predecessor For T-4 Day Task | 0.25 | 2021-01-26 06:00 | 2021-01-26 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-26 06:00 | 2021-01-26 06:00 | 2021-01-26 06:15 | SAI | CROSS | 2021-01-26 | 2021-01-26 | 2 | Task Control
10853 | WBS.1.1.1.1.1.2.5 | N | N | Planned | Predecessor For T-3 Day Task | 0.25 | 2021-01-27 06:00 | 2021-01-27 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-27 06:00 | 2021-01-27 06:00 | 2021-01-27 06:15 | SAI | CROSS | 2021-01-27 | 2021-01-27 | 2 | Task Control
97621 | WBS.1.1.1.1.1.2.16 | N | N | Planned | Send Communication about System Unavailabilty of EHANA & SLT | 0.25 | 2021-01-17 05:00 | 2021-01-17 05:15 | KELLY HINSON | KSHINSON@GAPAC.COM | PRAVEENA REDDY;DWIGHT WORREL;KYNDAL CODY;DANI SIMMONS;MAMIE TREZVANT;SUVENDU KUMAR;NAVJOT SHARMA;SAI TEAM | PRAVEENA.REDDY@GAPAC.COM;*;KYNDAL.CODY@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RPT |  |  |  |  | 2021-01-17 05:00 | 2021-01-17 05:00 | 2021-01-17 05:15 | RPT | ALL | 2021-01-17 | 2021-01-17 | 1 | Task Control
97410 | WBS.1.1.1.1.1.2.15 | N | N | Planned | Send Communication about System Unavailabilty of S4/MDG/PO/GW | 0.25 | 2021-01-24 05:00 | 2021-01-24 05:15 | KELLY HINSON | KSHINSON@GAPAC.COM | KYNDAL CODY;DANI SIMMONS;MAMIE TREZVANT;SUVENDU KUMAR;NAVJOT SHARMA;SAI TEAM | KYNDAL.CODY@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 05:15 | DEV | ALL | 2021-01-24 | 2021-01-24 | 2 | Task Control
97746 | WBS.1.1.1.1.1.2.18 | N | N | Planned | Send Communication about System Unavailability (2nd Weekend) S4/MDG/PO/GW | 0.25 | 2021-01-21 09:00 | 2021-01-21 09:15 | KELLY HINSON | KSHINSON@GAPAC.COM | KYNDAL CODY;DANI SIMMONS;MAMIE TREZVANT;SUVENDU KUMAR;NAVJOT SHARMA;SAI TEAM | KYNDAL.CODY@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI |  |  |  |  | 2021-01-21 09:00 | 2021-01-21 09:00 | 2021-01-21 09:15 | SAI | ALL | 2021-01-21 | 2021-01-21 | 1 | Task Control
10852 | WBS.1.1.1.1.1.2.6 | N | N | Planned | Predecessor For T-2 Day Task | 0.25 | 2021-01-28 06:00 | 2021-01-28 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-28 06:00 | 2021-01-28 06:00 | 2021-01-28 06:15 | SAI | CROSS | 2021-01-28 | 2021-01-28 | 2 | Task Control
10851 | WBS.1.1.1.1.1.2.7 | N | N | Planned | Predecessor For T-1 Day AM Task | 0.25 | 2021-01-29 06:00 | 2021-01-29 06:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-29 06:00 | 2021-01-29 06:00 | 2021-01-29 06:15 | SAI | CROSS | 2021-01-29 | 2021-01-29 | 2 | Task Control
81706 | WBS.1.1.1.1.1.2.8 | N | N | Planned | Predecessor For T-1 Day PM Task | 0.25 | 2021-01-29 12:00 | 2021-01-29 12:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-29 12:00 | 2021-01-29 12:00 | 2021-01-29 12:15 | SAI | CROSS | 2021-01-29 | 2021-01-29 | 2 | Task Control
12178 | WBS.1.1.1.1.1.2.9 | N | N | Planned | Predecessor For T-0 Day AM Task | 0.25 | 2021-01-30 12:00 | 2021-01-30 12:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-30 12:00 | 2021-01-30 12:00 | 2021-01-30 12:15 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Task Control
90821 | WBS.1.1.1.1.1.2.10 | N | N | Planned | Predecessor For T-0 Day PM Task | 0.25 | 2021-01-30 18:00 | 2021-01-30 18:15 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-30 18:00 | 2021-01-30 18:00 | 2021-01-30 18:15 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Task Control
92449 | WBS.1.1.1.1.1.2.11 | N | N | Planned | Predecessor For T-0 Day 2 Hrs prior to FCW | 0.25 | 2021-01-30 22:30 | 2021-01-30 22:45 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM;MARTHONY HOBGOOD | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MHOBGOOD@DELOITTE.COM | SAI |  |  |  |  | 2021-01-30 22:30 | 2021-01-30 22:30 | 2021-01-30 22:45 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Task Control
95633 | WBS.1.1.1.1.1.2.13 | N | N | Planned | Predecessor For T-0 Day 1 Hr prior to FCW | 0.25 | 2021-01-30 23:30 | 2021-01-30 23:45 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | SAI TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI |  |  |  |  | 2021-01-30 23:30 | 2021-01-30 23:30 | 2021-01-30 23:45 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Task Control
97346 | WBS.1.1.1.1.1.2.14 | N | N | Planned | Predecessor For 1/24 DEV Tasks | 0.25 | 2021-01-24 03:45 | 2021-01-24 04:00 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI |  |  |  |  | 2021-01-24 03:45 | 2021-01-24 03:45 | 2021-01-24 04:00 | SAI | ALL | 2021-01-24 | 2021-01-24 | 2 | Task Control
91558 | WBS.1.1.1.1.2 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - FCW - System | 55 | 2021-01-31 01:00 | 2021-02-02 08:00 | [8 empty] | * |  | 2021-01-31 01:00 | 2021-02-02 08:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
92418 | WBS.1.1.1.1.2.1 | N | N |  | Gate 2 - Final Cutover Window Go No Go Decision | 18.25 | 2021-01-31 01:00 | 2021-01-31 19:15 | [8 empty] | * |  | 2021-01-31 01:00 | 2021-01-31 19:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Task Control
95429 | WBS.1.1.1.1.2.1.12 | N | N | Planned | Predecessor for Period Cut-Off | 0.25 | 2021-01-31 19:00 | 2021-01-31 19:15 | DON ABBOTT | DON.ABBOTT@GAPAC.COM | JOHN CASABURRI;MARTHONY HOBGOOD;SAI TEAM | JOHN.CASABURRI@GAPAC.COM;MHOBGOOD@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  |  | 2021-01-31 19:00 | 2021-01-31 19:00 | 2021-01-31 19:15 | SAI | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
36505 | WBS.1.1.1.1.2.1.1 | N | N | Planned | Gate 2 - Final Cutover Window Go No Go Decision | 0.25 | 2021-01-31 01:00 | 2021-01-31 01:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;JOHN CASABURRI;DON ABBOTT;CHRISTIAN KESSLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;CKESSLER@DELOITTE.COM | SAI | 5230,5231,8864,5261,5438,82090,82089,5476,81661,82501,92328,94320,94323,92415,96571,96572,96703,96704,96895,96889,96882,97494,92148,89797,97450,83019,96809,96594,94735,96597,97183,97181,92414,82183,93807,97151,97152,97153,97155,97157,97158,95906,95940,9... |  |  |  | 2021-01-31 01:00 | 2021-01-31 01:00 | 2021-01-31 01:15 | SAI | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
94538 | WBS.1.1.1.1.2.1.2 | N | N | Planned | Communicate Gate 2 - Final Cutover Window Go No Go Decision | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | PMO | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
92466 | WBS.1.1.1.1.2.2 | N | N |  | Milestone 1 - Deployed Sites Resume Processes | 0.75 | 2021-01-31 19:00 | 2021-01-31 19:45 | [8 empty] | * |  | 2021-01-31 19:00 | 2021-01-31 19:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Task Control
92467 | WBS.1.1.1.1.2.2.1 | N | N | Planned | Milestone 1 - Deployed Sites Resume Processes | 0.25 | 2021-01-31 19:00 | 2021-01-31 19:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 92152,92153,93403 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:15 | SAI | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
92593 | WBS.1.1.1.1.2.2.2 | N | N | Planned | Communicate Milestone 1 - Deployed Sites Resume Processes | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | PMO | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
96654 | WBS.1.1.1.1.2.2.3 | N | N | Planned | Trigger for Smoke Test for Already Deployed Sites | 0.25 | 2021-01-31 19:30 | 2021-01-31 19:45 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 19:45 | SAI | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
92280 | WBS.1.1.1.1.2.3 | N | N |  | PTH Milestone 2 - Begin Inventory Transactions | 3.25 | 2021-02-01 16:15 | 2021-02-01 19:30 | [8 empty] | * |  | 2021-02-01 16:15 | 2021-02-01 19:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
92427 | WBS.1.1.1.1.2.3.1 | N | N | Planned | PTH Milestone 2 - Begin Inventory Transactions (Non MRO) | 0.25 | 2021-02-01 19:00 | 2021-02-01 19:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,94781,95652,95654,95666,95668 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 19:15 | SAI | PTH | 2021-02-01 | 2021-02-01 | 3 | Task Control
95166 | WBS.1.1.1.1.2.3.2 | N | N | Planned | PTH Milestone 2 - Begin Inventory Transactions (MRO) | 0.25 | 2021-02-01 16:15 | 2021-02-01 16:30 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,93327 |  |  | * |  | 2021-02-01 16:15 | 2021-02-01 16:30 | SAI | PTH | 2021-02-01 | 2021-02-01 | 3 | Task Control
92594 | WBS.1.1.1.1.2.3.3 | N | N | Planned | Communicate PTH Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 19:15 | 2021-02-01 19:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 92427 |  |  | * |  | 2021-02-01 19:15 | 2021-02-01 19:30 | PMO | PTH | 2021-02-01 | 2021-02-01 | 3 | Task Control
95242 | WBS.1.1.1.1.2.5 | N | N |  | HBG Milestone 2 - Begin Inventory Transactions | 1 | 2021-02-01 14:00 | 2021-02-01 15:00 | [8 empty] | * |  | 2021-02-01 14:00 | 2021-02-01 15:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
95158 | WBS.1.1.1.1.2.5.1 | N | N | Planned | HBG Milestone 2 - Begin Inventory Transactions (Non MRO) | 0.25 | 2021-02-01 14:30 | 2021-02-01 14:45 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,93916,95658,95660,95672,95674 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 14:45 | SAI | HBG | 2021-02-01 | 2021-02-01 | 3 | Task Control
95284 | WBS.1.1.1.1.2.5.2 | N | N | Planned | HBG Milestone 2 - Begin Inventory Transactions (MRO) | 0.25 | 2021-02-01 14:00 | 2021-02-01 14:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,95282 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 14:15 | SAI | HBG | 2021-02-01 | 2021-02-01 | 3 | Task Control
95159 | WBS.1.1.1.1.2.5.3 | N | N | Planned | Communicate HBG Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 14:45 | 2021-02-01 15:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95158 |  |  | * |  | 2021-02-01 14:45 | 2021-02-01 15:00 | PMO | HBG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96479 | WBS.1.1.1.1.2.23 | N | N |  | BG Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 15:00 | 2021-02-01 15:30 | [8 empty] | * |  | 2021-02-01 15:00 | 2021-02-01 15:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96478 | WBS.1.1.1.1.2.23.4 | N | N | Planned | BG Milestone 2 - Begin Inventory Transactions (Non MRO) | 0.25 | 2021-02-01 15:00 | 2021-02-01 15:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96547,96548,96549,96550,96647 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:15 | SAI | BG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96477 | WBS.1.1.1.1.2.23.5 | N | N | Planned | BG Milestone 2 - Begin Inventory Transactions (MRO) | 0.25 | 2021-02-01 15:00 | 2021-02-01 15:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96648 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:15 | SAI | BG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96476 | WBS.1.1.1.1.2.23.6 | N | N | Planned | Communicate BG Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 15:15 | 2021-02-01 15:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96478 |  |  | * |  | 2021-02-01 15:15 | 2021-02-01 15:30 | PMO | BG | 2021-02-01 | 2021-02-01 | 3 | Task Control
95245 | WBS.1.1.1.1.2.7 | N | N |  | SCH Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 09:01 | 2021-02-01 09:31 | [8 empty] | * |  | 2021-02-01 09:01 | 2021-02-01 09:31 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
95164 | WBS.1.1.1.1.2.7.1 | N | N | Planned | SCH Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:01 | 2021-02-01 09:16 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,95197 |  |  | * |  | 2021-02-01 09:01 | 2021-02-01 09:16 | SAI | SCH | 2021-02-01 | 2021-02-01 | 3 | Task Control
95165 | WBS.1.1.1.1.2.7.2 | N | N | Planned | Communicate SCH Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:16 | 2021-02-01 09:31 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95164 |  |  | * |  | 2021-02-01 09:16 | 2021-02-01 09:31 | PMO | SCH | 2021-02-01 | 2021-02-01 | 3 | Task Control
96463 | WBS.1.1.1.1.2.20 | N | N |  | RNC Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 09:00 | 2021-02-01 09:30 | [8 empty] | * |  | 2021-02-01 09:00 | 2021-02-01 09:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96462 | WBS.1.1.1.1.2.20.3 | N | N | Planned | RNC Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:00 | 2021-02-01 09:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96716 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 09:15 | SAI | RNC | 2021-02-01 | 2021-02-01 | 3 | Task Control
96461 | WBS.1.1.1.1.2.20.4 | N | N | Planned | Communicate RNC Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:15 | 2021-02-01 09:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96462 |  |  | * |  | 2021-02-01 09:15 | 2021-02-01 09:30 | PMO | RNC | 2021-02-01 | 2021-02-01 | 3 | Task Control
96460 | WBS.1.1.1.1.2.21 | N | N |  | RVG Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 09:00 | 2021-02-01 09:30 | [8 empty] | * |  | 2021-02-01 09:00 | 2021-02-01 09:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96459 | WBS.1.1.1.1.2.21.3 | N | N | Planned | RVG Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:00 | 2021-02-01 09:15 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96718 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 09:15 | SAI | RVG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96458 | WBS.1.1.1.1.2.21.4 | N | N | Planned | Communicate RVG Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 09:15 | 2021-02-01 09:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96459 |  |  | * |  | 2021-02-01 09:15 | 2021-02-01 09:30 | PMO | RVG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96491 | WBS.1.1.1.1.2.25 | N | N |  | SAT Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 04:30 | 2021-02-01 05:00 | [8 empty] | * |  | 2021-02-01 04:30 | 2021-02-01 05:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96490 | WBS.1.1.1.1.2.25.3 | N | N | Planned | SAT Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 04:30 | 2021-02-01 04:45 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96674 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 04:45 | SAI | SAT | 2021-02-01 | 2021-02-01 | 3 | Task Control
96489 | WBS.1.1.1.1.2.25.4 | N | N | Planned | Communicate SAT Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 04:45 | 2021-02-01 05:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96490 |  |  | * |  | 2021-02-01 04:45 | 2021-02-01 05:00 | PMO | SAT | 2021-02-01 | 2021-02-01 | 3 | Task Control
96485 | WBS.1.1.1.1.2.27 | N | N |  | REX Milestone 2 - Begin Inventory Transactions | 0.5 | 2021-02-01 04:30 | 2021-02-01 05:00 | [8 empty] | * |  | 2021-02-01 04:30 | 2021-02-01 05:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96484 | WBS.1.1.1.1.2.27.3 | N | N | Planned | REX Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 04:30 | 2021-02-01 04:45 | PMO TEAM | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM | CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96673 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 04:45 | SAI | REX | 2021-02-01 | 2021-02-01 | 3 | Task Control
96483 | WBS.1.1.1.1.2.27.4 | N | N | Planned | Communicate REX Milestone 2 - Begin Inventory Transactions | 0.25 | 2021-02-01 04:45 | 2021-02-01 05:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96484 |  |  | * |  | 2021-02-01 04:45 | 2021-02-01 05:00 | PMO | REX | 2021-02-01 | 2021-02-01 | 3 | Task Control
95080 | WBS.1.1.1.1.2.8 | N | N |  | SCH Gate 3 - Resume Shipping/Receiving | 41.76 | 2021-01-31 01:15 | 2021-02-01 19:01 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 19:01 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
95069 | WBS.1.1.1.1.2.8.1 | N | N | Planned | Start SCH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 3964,36505,81706 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | SCH | 2021-01-31 | 2021-01-31 | 3 | Task Control
95070 | WBS.1.1.1.1.2.8.2 | N | N | Planned | Govern SCH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 14:01 | 2021-02-01 14:16 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 90107,92999,93049,93048,93047 |  |  | * |  | 2021-02-01 14:01 | 2021-02-01 14:16 | SAI | SCH | 2021-02-01 | 2021-02-01 | 3 | Task Control
95071 | WBS.1.1.1.1.2.8.3 | N | N | Planned | Communicate SCH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 18:46 | 2021-02-01 19:01 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 92995,95426,95070,92996 |  |  | * |  | 2021-02-01 18:46 | 2021-02-01 19:01 | SAI | SCH | 2021-02-01 | 2021-02-01 | 3 | Task Control
96455 | WBS.1.1.1.1.2.9 | N | N |  | RNC Gate 3 - Resume Shipping/Receiving | 41.75 | 2021-01-31 01:15 | 2021-02-01 19:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 19:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96454 | WBS.1.1.1.1.2.9.1 | N | N | Planned | Start RNC Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 3964,36505,81706 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | RNC | 2021-01-31 | 2021-01-31 | 3 | Task Control
96453 | WBS.1.1.1.1.2.9.2 | N | N | Planned | Govern RNC Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 14:00 | 2021-02-01 14:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96721,96422,96421,96419,96423 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 14:15 | SAI | RNC | 2021-02-01 | 2021-02-01 | 3 | Task Control
96452 | WBS.1.1.1.1.2.9.3 | N | N | Planned | Communicate RNC Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96383,96453,96764,96384 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | SAI | RNC | 2021-02-01 | 2021-02-01 | 3 | Task Control
96451 | WBS.1.1.1.1.2.10 | N | N |  | RVG Gate 3 - Resume Shipping/Receiving | 41.75 | 2021-01-31 01:15 | 2021-02-01 19:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 19:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96450 | WBS.1.1.1.1.2.10.1 | N | N | Planned | Start RVG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | RVG | 2021-01-31 | 2021-01-31 | 3 | Task Control
96449 | WBS.1.1.1.1.2.10.2 | N | N | Planned | Govern RVG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 14:00 | 2021-02-01 14:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96416,96415,96414,96412,96722 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 14:15 | SAI | RVG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96448 | WBS.1.1.1.1.2.10.3 | N | N | Planned | Communicate RVG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96449,96763,96380,96379 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | SAI | RVG | 2021-02-01 | 2021-02-01 | 3 | Task Control
95081 | WBS.1.1.1.1.2.11 | N | N |  | PTH Gate 3 - Resume Shipping/Receiving | 53.75 | 2021-01-31 01:15 | 2021-02-02 07:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 07:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
95066 | WBS.1.1.1.1.2.11.1 | N | N | Planned | Start PTH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 3964,36505,81706 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | PTH | 2021-01-31 | 2021-01-31 | 3 | Task Control
95067 | WBS.1.1.1.1.2.11.2 | N | N | Planned | Govern PTH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-02 01:00 | 2021-02-02 01:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95094,94561,93350,93349,94554,94919,94915,93345,93352,93347,93346,94856,94853,95628 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 01:15 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
95068 | WBS.1.1.1.1.2.11.3 | N | N | Planned | Communicate PTH Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-02 06:45 | 2021-02-02 07:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93344,93340,93339,95425,95067 |  |  | * |  | 2021-02-02 06:45 | 2021-02-02 07:00 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
95087 | WBS.1.1.1.1.2.13 | N | N |  | HBG Gate 3 - Resume Shipping/Receiving | 48.75 | 2021-01-31 01:15 | 2021-02-02 02:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 02:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
95088 | WBS.1.1.1.1.2.13.1 | N | N | Planned | Start HBG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 3964,36505,81706 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | HBG | 2021-01-31 | 2021-01-31 | 3 | Task Control
95089 | WBS.1.1.1.1.2.13.2 | N | N | Planned | Govern HBG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 20:00 | 2021-02-01 20:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95092,94563,94393,94917,94913,93938,93935,93941,95246,95247,93937 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 20:15 | SAI | HBG | 2021-02-01 | 2021-02-01 | 3 | Task Control
95090 | WBS.1.1.1.1.2.13.3 | N | N | Planned | Communicate HBG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-02 01:45 | 2021-02-02 02:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93933,93932,95217,95423,95089 |  |  | * |  | 2021-02-02 01:45 | 2021-02-02 02:00 | SAI | HBG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96498 | WBS.1.1.1.1.2.29 | N | N |  | BG Gate 3 - Resume Shipping/Receiving | 49.75 | 2021-01-31 01:15 | 2021-02-02 03:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 03:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
96497 | WBS.1.1.1.1.2.29.4 | N | N | Planned | Start BG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | BG | 2021-01-31 | 2021-01-31 | 3 | Task Control
96496 | WBS.1.1.1.1.2.29.5 | N | N | Planned | Govern BG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 22:00 | 2021-02-01 22:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96636,96647,96550,96549,96548,96547,96799,96797,96796,96795,96794,96793,96404,96402 |  |  | * |  | 2021-02-01 22:00 | 2021-02-01 22:15 | SAI | BG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96495 | WBS.1.1.1.1.2.29.6 | N | N | Planned | Communicate BG Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-02 02:45 | 2021-02-02 03:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96496,96632,96391 |  |  | * |  | 2021-02-02 02:45 | 2021-02-02 03:00 | SAI | BG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96514 | WBS.1.1.1.1.2.31 | N | N |  | SAT Gate 3 - Resume Shipping/Receiving | 28.75 | 2021-01-31 01:15 | 2021-02-01 06:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 06:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96513 | WBS.1.1.1.1.2.31.4 | N | N | Planned | Start SAT Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | SAT | 2021-01-31 | 2021-01-31 | 3 | Task Control
96512 | WBS.1.1.1.1.2.31.5 | N | N | Planned | Govern SAT Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 05:30 | 2021-02-01 05:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96334,96668,97124,96490 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 05:45 | SAI | SAT | 2021-02-01 | 2021-02-01 | 3 | Task Control
96511 | WBS.1.1.1.1.2.31.6 | N | N | Planned | Communicate SAT Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 05:45 | 2021-02-01 06:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96512 |  |  | * |  | 2021-02-01 05:45 | 2021-02-01 06:00 | SAI | SAT | 2021-02-01 | 2021-02-01 | 3 | Task Control
96506 | WBS.1.1.1.1.2.33 | N | N |  | REX Gate 3 - Resume Shipping/Receiving | 29.75 | 2021-01-31 01:15 | 2021-02-01 07:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 07:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
96505 | WBS.1.1.1.1.2.33.4 | N | N | Planned | Start REX Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | REX | 2021-01-31 | 2021-01-31 | 3 | Task Control
96504 | WBS.1.1.1.1.2.33.5 | N | N | Planned | Govern REX Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 06:30 | 2021-02-01 06:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96322,96672,97125 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 06:45 | SAI | REX | 2021-02-01 | 2021-02-01 | 3 | Task Control
96503 | WBS.1.1.1.1.2.33.6 | N | N | Planned | Communicate REX Gate 3 - Resume Shipping/Receiving | 0.25 | 2021-02-01 06:45 | 2021-02-01 07:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96504 |  |  | * |  | 2021-02-01 06:45 | 2021-02-01 07:00 | SAI | REX | 2021-02-01 | 2021-02-01 | 3 | Task Control
95176 | WBS.1.1.1.1.2.15 | N | N |  | PTH Gate 4 - Resume PO Creation, Receiving | 4.5 | 2021-02-02 03:30 | 2021-02-02 08:00 | [8 empty] | * |  | 2021-02-02 03:30 | 2021-02-02 08:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
95254 | WBS.1.1.1.1.2.15.1 | N | N | Planned | Start PTH Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 07:00 | 2021-02-02 07:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95068 |  |  | * |  | 2021-02-02 07:00 | 2021-02-02 07:15 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
95119 | WBS.1.1.1.1.2.15.2 | N | N | Planned | Govern PTH Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 03:30 | 2021-02-02 03:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 8860,92931,92930,92929,92928,80839,92507,93329,95067 |  |  | * |  | 2021-02-02 03:30 | 2021-02-02 03:45 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
95099 | WBS.1.1.1.1.2.15.3 | N | N | Planned | Communicate PTH Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 07:45 | 2021-02-02 08:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93263,92914,95119,95560,95561,95562,95563 |  |  | * |  | 2021-02-02 07:45 | 2021-02-02 08:00 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
95239 | WBS.1.1.1.1.2.17 | N | N |  | HBG Gate 4 - Resume PO Creation, Receiving | 6 | 2021-02-02 02:00 | 2021-02-02 08:00 | [8 empty] | * |  | 2021-02-02 02:00 | 2021-02-02 08:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
95250 | WBS.1.1.1.1.2.17.1 | N | N | Planned | Start HBG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 02:00 | 2021-02-02 02:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 95090 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 02:15 | SAI | HBG | 2021-02-02 | 2021-02-02 | 3 | Task Control
95117 | WBS.1.1.1.1.2.17.2 | N | N | Planned | Govern HBG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 03:30 | 2021-02-02 03:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 8860,93926,93925,92507,93918,95089,97520 |  |  | * |  | 2021-02-02 03:30 | 2021-02-02 03:45 | SAI | HBG | 2021-02-02 | 2021-02-02 | 3 | Task Control
95097 | WBS.1.1.1.1.2.17.3 | N | N | Planned | Communicate HBG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 07:45 | 2021-02-02 08:00 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93906,93921,93930,93929,93928,93927,95117 |  |  | * |  | 2021-02-02 07:45 | 2021-02-02 08:00 | SAI | HBG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96475 | WBS.1.1.1.1.2.22 | N | N |  | BG Gate 4 - Resume PO Creation, Receiving | 2.5 | 2021-02-02 03:00 | 2021-02-02 05:30 | [8 empty] | * |  | 2021-02-02 03:00 | 2021-02-02 05:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
96474 | WBS.1.1.1.1.2.22.4 | N | N | Planned | Start BG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 03:00 | 2021-02-02 03:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96495 |  |  | * |  | 2021-02-02 03:00 | 2021-02-02 03:15 | SAI | BG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96473 | WBS.1.1.1.1.2.22.5 | N | N | Planned | Govern BG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 03:30 | 2021-02-02 03:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,8860,92507,96496,96409,96408,96407,96406,96653,97522 |  |  | * |  | 2021-02-02 03:30 | 2021-02-02 03:45 | SAI | BG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96472 | WBS.1.1.1.1.2.22.6 | N | N | Planned | Communicate BG Gate 4 - Resume PO Creation, Receiving | 0.25 | 2021-02-02 05:15 | 2021-02-02 05:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96473,96387,96392 |  |  | * |  | 2021-02-02 05:15 | 2021-02-02 05:30 | SAI | BG | 2021-02-02 | 2021-02-02 | 3 | Task Control
92439 | WBS.1.1.1.1.2.19 | N | N |  | Business Role Confirmation | 0.5 | 2021-02-01 08:00 | 2021-02-01 08:30 | [8 empty] | * |  | 2021-02-01 08:00 | 2021-02-01 08:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Task Control
82553 | WBS.1.1.1.1.2.19.1 | N | N | Planned | Trigger for unlocking pilot and catchup users (cutover team to check first site to complete golden transactions) | 0.25 | 2021-02-01 08:00 | 2021-02-01 08:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 8853,8879,8922,5844,5843,5848,5850,5851,82749,93405 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 08:15 | SAI | CROSS | 2021-02-01 | 2021-02-01 | 3 | Task Control
82629 | WBS.1.1.1.1.2.19.2 | N | N | Planned | Unlock Pilot and Catch-Up Transaction Users | 0.25 | 2021-02-01 08:15 | 2021-02-01 08:30 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | SAI TEAM;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 82553 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 08:30 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Task Control
91562 | WBS.1.1.1.1.3 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - FCW - Business | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Task Control
92457 | WBS.1.1.1.1.3.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - FCW - Business | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Task Control
21147 | WBS.1.1.1.1.3.1.1 | N | N | Planned | Trigger Business FCW / Shutdown Cutover Tasks | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SAI | CROSS | 2021-01-31 | 2021-01-31 | 3 | Task Control
91560 | WBS.1.1.1.2 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp Up | 0.5 | 2021-02-02 08:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91561 | WBS.1.1.1.2.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp Up - System | 0.5 | 2021-02-02 08:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
92459 | WBS.1.1.1.2.1.1 | N | N |  | Gate 5 - Open for Business | 0.5 | 2021-02-02 08:00 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:00 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
36654 | WBS.1.1.1.2.1.1.1 | N | N | Planned | Govern Gate 5 - Ramp-Up Tasks - Open for Business | 0.25 | 2021-02-02 08:00 | 2021-02-02 08:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 81215,95068,95071,95090,95097,95099,96472,96495,96448,96452,96511,96503 |  |  | * |  | 2021-02-02 08:00 | 2021-02-02 08:15 | SAI | CROSS | 2021-02-02 | 2021-02-02 | 3 | Task Control
92460 | WBS.1.1.1.2.1.1.2 | N | N | Planned | Communicate Gate 5 - Ramp-Up Tasks - Open for Business | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | MELISSA COLLIER | MELISSA.COLLIER@GAPAC.COM | PMO TEAM;KERRI FOGEL;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;kerri.fogel@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 | SAI | CROSS | 2021-02-02 | 2021-02-02 | 3 | Task Control
92463 | WBS.1.1.1.2.1.2 | N | N |  | Ramp up ¦ T+ days Task | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
92291 | WBS.1.1.1.2.1.2.1 | N | N | Planned | Ramp up ¦ T+10 days | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | SAI TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36654 |  |  |  | 2021-02-02 06:00 | 2021-02-02 08:15 | 2021-02-02 08:30 | SAI | CROSS | 2021-02-02 | 2021-02-02 | 3 | Task Control
91557 | WBS.1.1.1.2.2 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp up - Business | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
92464 | WBS.1.1.1.2.2.1 | N | N |  | TC ¦ Milestones - Tasks Control - Readiness - Phase Gates - Ramp up - Business | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
21148 | WBS.1.1.1.2.2.1.1 | N | N | Planned | Trigger Business Ramp Up Cutover Tasks | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | JOHN CASABURRI | JOHN.CASABURRI@GAPAC.COM | DON ABBOTT;SAI TEAM | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 | SAI | CROSS | 2021-02-02 | 2021-02-02 | 3 | Task Control
91539 | WBS.1.1.2 | N | N |  | TC ¦ Milestones - Key Business Milestones | 26.25 | 2021-02-01 06:00 | 2021-02-02 08:15 | [8 empty] | * |  | 2021-02-01 06:00 | 2021-02-02 08:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91541 | WBS.1.1.2.1 | N | N |  | TC ¦ Milestones - Facility Milestones - All Sites | 26.25 | 2021-02-01 06:00 | 2021-02-02 08:15 | [8 empty] | * |  | 2021-02-01 06:00 | 2021-02-02 08:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Task Control
91782 | WBS.1.1.2.1.1 | N | N |  | TC ¦ Milestones - Key Business Milestones - All Sites - Back to Business | 26.25 | 2021-02-01 06:00 | 2021-02-02 08:15 | [8 empty] | * |  | 2021-02-01 06:00 | 2021-02-02 08:15 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Task Control
91783 | WBS.1.1.2.1.1.1 | N | N |  | TC ¦ Milestones - Key Business Milestones - All Sites - Back to Business | 26.25 | 2021-02-01 06:00 | 2021-02-02 08:15 | [8 empty] | * |  | 2021-02-01 06:00 | 2021-02-02 08:15 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Task Control
91784 | WBS.1.1.2.1.1.1.1 | N | N | Planned | Milestone ¦ Back to Business Achieved for Port Hudson | 0.25 | 2021-02-02 08:00 | 2021-02-02 08:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93344,93263,92914,93340,93339,95068,95099,95562,95560,95561,95563 |  |  | * |  | 2021-02-02 08:00 | 2021-02-02 08:15 | SAI | PTH | 2021-02-02 | 2021-02-02 | 3 | Task Control
94416 | WBS.1.1.2.1.1.1.3 | N | N | Planned | Milestone ¦ Back to Business Achieved for Hattiesburg | 0.25 | 2021-02-02 08:00 | 2021-02-02 08:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93906,93921,93930,93929,93928,93927,93933,93932,95217,95090,95097 |  |  | * |  | 2021-02-02 08:00 | 2021-02-02 08:15 | SAI | HBG | 2021-02-02 | 2021-02-02 | 3 | Task Control
94415 | WBS.1.1.2.1.1.1.4 | N | N | Planned | Milestone ¦ Back to Business Achieved for South Chicago | 0.25 | 2021-02-01 19:01 | 2021-02-01 19:16 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 92995,92996,95071 |  |  | * |  | 2021-02-01 19:01 | 2021-02-01 19:16 | SAI | SCH | 2021-02-01 | 2021-02-01 | 3 | Task Control
96465 | WBS.1.1.2.1.1.1.7 | N | N | Planned | Milestone ¦ Back to Business Achieved for Rancho | 0.25 | 2021-02-01 19:00 | 2021-02-01 19:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96452,96384,96383 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 19:15 | SAI | RNC | 2021-02-01 | 2021-02-01 | 3 | Task Control
96464 | WBS.1.1.2.1.1.1.6 | N | N | Planned | Milestone ¦ Back to Business Achieved for Rivergate | 0.25 | 2021-02-01 19:00 | 2021-02-01 19:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 96448,96380,96379,96528 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 19:15 | SAI | RVG | 2021-02-01 | 2021-02-01 | 3 | Task Control
96466 | WBS.1.1.2.1.1.1.8 | N | N | Planned | Milestone ¦ Back to Business Achieved for Bowling Green | 0.25 | 2021-02-02 05:30 | 2021-02-02 05:45 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96495,96472,96391,96392,96387 |  |  | * |  | 2021-02-02 05:30 | 2021-02-02 05:45 | SAI | BG | 2021-02-02 | 2021-02-02 | 3 | Task Control
96470 | WBS.1.1.2.1.1.1.12 | N | N | Planned | Milestone ¦ Back to Business Achieved for South Atlantic | 0.25 | 2021-02-01 06:00 | 2021-02-01 06:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96511 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 06:15 | SAI | SAT | 2021-02-01 | 2021-02-01 | 3 | Task Control
96468 | WBS.1.1.2.1.1.1.10 | N | N | Planned | Milestone ¦ Back to Business Achieved for Rexdale Dominion | 0.25 | 2021-02-01 07:00 | 2021-02-01 07:15 | BERNHARD MERTES | BERNHARD.MERTES@KOCHGS.COM | PMO TEAM;SAI TEAM | BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505,96503 |  |  | * |  | 2021-02-01 07:00 | 2021-02-01 07:15 | SAI | REX | 2021-02-01 | 2021-02-01 | 3 | Task Control
3947 | WBS.2 | N | N |  | D4 Production Cutover | 271 | 2021-01-16 10:00 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-02-05 08:30 |  |  | 2021-02-05 | 2021-02-05 | 3 | Task Control
3948 | WBS.2.1 | N | N |  | Ramp Down ¦ Phase | 189.25 | 2021-01-16 10:00 | 2021-01-31 08:45 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-02-01 06:30 |  | CROSS | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
4065 | WBS.2.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions | 170.5 | 2021-01-16 10:00 | 2021-01-30 14:00 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-01-30 14:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
4066 | WBS.2.1.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports | 21.5 | 2021-01-17 03:15 | 2021-01-18 00:45 | [8 empty] | * |  | 2021-01-17 03:15 | 2021-01-18 00:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91101 | WBS.2.1.1.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups | 21.5 | 2021-01-17 03:15 | 2021-01-18 00:45 | [8 empty] | * |  | 2021-01-17 03:15 | 2021-01-18 00:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91233 | WBS.2.1.1.1.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - S/4HANA | 3 | 2021-01-17 21:45 | 2021-01-18 00:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 00:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4067 | WBS.2.1.1.1.1.1.1 | N | N | Planned | Backup S/4HANA System - Pre-Transports | 3 | 2021-01-17 21:45 | 2021-01-18 00:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-18 00:45 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91102 | WBS.2.1.1.1.1.2 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP BW | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4073 | WBS.2.1.1.1.1.2.1 | N | N | Planned | Backup BW System - Pre-Transports | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91097 | WBS.2.1.1.1.1.3 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP CRM | 0.75 | 2021-01-17 21:45 | 2021-01-17 22:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:30 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4072 | WBS.2.1.1.1.1.3.1 | N | N | Planned | Backup CRM System - Pre-Transports | 0.75 | 2021-01-17 21:45 | 2021-01-17 22:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:30 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91096 | WBS.2.1.1.1.1.4 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP GRC | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4074 | WBS.2.1.1.1.1.4.1 | N | N | Planned | Backup GRC System - Pre-Transports | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91098 | WBS.2.1.1.1.1.5 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP GW | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4071 | WBS.2.1.1.1.1.5.1 | N | N | Planned | Backup GW System - Pre-Transports | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91100 | WBS.2.1.1.1.1.6 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP MDG | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4068 | WBS.2.1.1.1.1.6.1 | N | N | Planned | Backup MDG System - Pre-Transports | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91099 | WBS.2.1.1.1.1.7 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - SAP PO | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4069 | WBS.2.1.1.1.1.7.1 | N | N | Planned | Backup PO System - Pre-Transports | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92191 | WBS.2.1.1.1.1.9 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups - EHANA | 2.75 | 2021-01-17 03:15 | 2021-01-17 06:00 | [8 empty] | * |  | 2021-01-17 03:15 | 2021-01-17 06:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92190 | WBS.2.1.1.1.1.9.1 | N | N | Planned | Backup EHANA System - Pre-Transports | 2.75 | 2021-01-17 03:15 | 2021-01-17 06:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV |  |  |  |  | 2021-01-17 03:15 | 2021-01-17 03:15 | 2021-01-17 06:00 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90907 | WBS.2.1.1.2 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Transports | 6.5 | 2021-01-17 10:00 | 2021-01-18 10:00 | [8 empty] | * |  | 2021-01-17 10:00 | 2021-01-18 10:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90906 | WBS.2.1.1.2.1 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports | 6.5 | 2021-01-17 10:00 | 2021-01-18 10:00 | [8 empty] | * |  | 2021-01-17 10:00 | 2021-01-18 10:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91234 | WBS.2.1.1.2.1.1 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - S/4HANA | 6.5 | 2021-01-17 10:00 | 2021-01-18 10:00 | [8 empty] | * |  | 2021-01-17 10:00 | 2021-01-18 10:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89765 | WBS.2.1.1.2.1.1.1 | N | N | Planned | MC Task ¦ Adjust Key Value Mapping For Business Partners in MDG and S4 | 1 | 2021-01-17 21:45 | 2021-01-17 22:45 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | DENISE ROBINSON;DATA ETL TEAM;DON ABBOTT;SAI TEAM;PRERNA BODKHE;PHANI GHANTASALA;AMY EL-BASSIONI | DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PRERNA.BODKHE@KOCHTC.COM;PGHANTASALA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:45 | DATA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
8813 | WBS.2.1.1.2.1.1.2 | N | N | Planned | Prepare/Validate Access Control Listing (Cutover Users, Dev/UIUX/Basis For Each In-Scope System) | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | SAI | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
8812 | WBS.2.1.1.2.1.1.3 | N | N | Planned | Receive List of SYSTEM, 3rd Party PO Users And RFC User IDs To Be Created In All Systems Along With Desired Password. This Should Include ABAP, JAVA, HANA, BODS, PO etc. | 1.5 | 2021-01-17 21:45 | 2021-01-17 23:15 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 23:15 | SECURITY | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90671 | WBS.2.1.1.2.1.1.4 | N | N | Planned | Validate Script In EHANA (HA2) System For S/4HANA (S4Q) | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SHARATH RENIKUNTA;FAROOQ SYED;DON ABBOTT;SUVENDU KUMAR;SAI TEAM;DEV TEAM | SRENIKUNTA@DELOITTE.COM;SYFAROOQ@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92631 | WBS.2.1.1.2.1.1.5 | N | N | Planned | Import SLT Transports Post Upgrade Data Conversion | 1 | 2021-01-17 10:00 | 2021-01-17 11:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | DEV TEAM;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97254 |  |  | * |  | 2021-01-17 10:00 | 2021-01-17 11:00 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90605 | WBS.2.1.1.2.1.1.6 | N | N | Planned | Import S/4HANA Transports With Basis Team - For Data Load Only | 1.5 | 2021-01-18 00:45 | 2021-01-18 02:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4067,93067,7867 |  |  | * |  | 2021-01-18 00:45 | 2021-01-18 02:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91838 | WBS.2.1.1.2.1.1.7 | N | N | Planned | Send S/4HANA Transport Results to Business / Teams | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;TED ZEIDLER;DEV TEAM | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4424,7867,90605,93067 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92634 | WBS.2.1.1.2.1.1.8 | N | N | Planned | Validate - Set Inboud Queue Parameter in S4 Application Server | 1 | 2021-01-18 06:00 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90605 |  |  | * |  | 2021-01-18 06:00 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
81550 | WBS.2.1.1.2.1.1.9 | N | N | Planned | Validate Serialization partner profile for SUBMAS in S/4HANA & MDG systems | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM | CHIRAG GUPTA;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CHIRGUPTA@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4084 | WBS.2.1.1.2.1.1.10 | N | N | Planned | Open S/4HANA Client | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SUVENDU KUMAR;DEV TEAM;PRASHANTH TUMMALA;SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;TED ZEIDLER | SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9951 | WBS.2.1.1.2.1.1.11 | N | N | Planned | MC Task ¦ Configure/Validate SSO from Tableau to EHANA database | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM;SUVENDU KUMAR;DEV TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90310 | WBS.2.1.1.2.1.1.12 | N | N | Planned | Confirm S/4HANA Client Is Closed | 0.25 | 2021-01-18 09:45 | 2021-01-18 10:00 | SRINIVAS KAKUTURU | SKAKUTURU@DELOITTE.COM | US GP BASIS;SAI TEAM;DEV TEAM | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 9866,9865,4624,4629,4634,9920,9921,4572,4579,4560,4575,4573 |  |  | * |  | 2021-01-18 09:45 | 2021-01-18 10:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92342 | WBS.2.1.1.2.1.2 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SAP BW | 0.75 | 2021-01-18 06:15 | 2021-01-18 07:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 07:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92201 | WBS.2.1.1.2.1.2.1 | N | N | Planned | Send BW/CRM Transport results to TPM | 0.75 | 2021-01-18 06:15 | 2021-01-18 07:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;TED ZEIDLER;DEV TEAM | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4424,7867,90605,93067 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90981 | WBS.2.1.1.2.1.3 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SAP MDG | 2.5 | 2021-01-17 22:15 | 2021-01-18 06:45 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-18 06:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4228 | WBS.2.1.1.2.1.3.1 | N | N | Planned | SAP MDG - Import transport(s) with Basis Team - for Data Load Only | 1 | 2021-01-17 22:15 | 2021-01-17 23:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4068,93067 |  |  | * |  | 2021-01-17 22:15 | 2021-01-17 23:15 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4229 | WBS.2.1.1.2.1.3.2 | N | N | Planned | Send SAP MDG Transport Results to Team | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;TED ZEIDLER;DEV TEAM | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4228,4424,7867,93067 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90980 | WBS.2.1.1.2.1.4 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SAP PO | 2.5 | 2021-01-17 22:00 | 2021-01-18 06:30 | [8 empty] | * |  | 2021-01-17 22:00 | 2021-01-18 06:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4245 | WBS.2.1.1.2.1.4.1 | N | N | Planned | SAP PO - Import Transport(s) with Basis Team | 1 | 2021-01-17 22:00 | 2021-01-17 23:00 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;TED ZEIDLER;SAI TEAM;HEMACHANDAN AS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;US GP BASIS;DEV TEAM | RADHRASTOGI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;HEMACAS@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4069,93067 |  |  | * |  | 2021-01-17 22:00 | 2021-01-17 23:00 | INT | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
9410 | WBS.2.1.1.2.1.4.2 | N | N | Planned | SAP PO - Import Certificate In SAP PO | 0.25 | 2021-01-17 23:00 | 2021-01-17 23:15 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | HEMACHANDAN AS;DANI SIMMONS;NAVJOT SHARMA;TED ZEIDLER;SAI TEAM;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER;RADHIKA RASTOGI | HEMACAS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM | DEV | 4245,93067 |  |  | * |  | 2021-01-17 23:00 | 2021-01-17 23:15 | INT | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4246 | WBS.2.1.1.2.1.4.3 | N | N | Planned | Send SAP-PO Transport Results To Teams | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4245,4424,7867,93067 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92228 | WBS.2.1.1.2.1.5 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SAP CRM | 1 | 2021-01-17 22:00 | 2021-01-17 23:00 | [8 empty] | * |  | 2021-01-17 22:00 | 2021-01-17 23:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92225 | WBS.2.1.1.2.1.5.1 | N | N | Planned | Import Transport(s) For SAP CRM | 1 | 2021-01-17 22:00 | 2021-01-17 23:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4069,93067 |  |  | * |  | 2021-01-17 22:00 | 2021-01-17 23:00 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90983 | WBS.2.1.1.3 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports | 11.5 | 2021-01-17 22:00 | 2021-01-18 15:30 | [8 empty] | * |  | 2021-01-17 22:00 | 2021-01-18 15:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91236 | WBS.2.1.1.3.1 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports | 8.75 | 2021-01-18 06:45 | 2021-01-18 15:30 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 15:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4085 | WBS.2.1.1.3.1.1 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - AC | 3.25 | 2021-01-18 06:45 | 2021-01-18 10:00 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 10:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4091 | WBS.2.1.1.3.1.1.1 | N | N | Planned | Validate S/4HANA Configuration Transports - AC | 3.25 | 2021-01-18 06:45 | 2021-01-18 10:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;JASON RAMSEY;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 10:00 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90908 | WBS.2.1.1.3.1.2 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - RTR | 8.75 | 2021-01-18 06:45 | 2021-01-18 15:30 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 15:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4098 | WBS.2.1.1.3.1.2.1 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - PS | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;AFSAR ALI MD;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;md.afsarali@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7819 | WBS.2.1.1.3.1.2.2 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - GL | 1.5 | 2021-01-18 06:45 | 2021-01-18 08:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 08:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7820 | WBS.2.1.1.3.1.2.3 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - CO | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7823 | WBS.2.1.1.3.1.2.4 | N | N | Planned | Validate Config Transports for Cutover - PC | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97765 | WBS.2.1.1.3.1.2.10 | N | N | Planned | Central Storeroom #1840 Set Material Ledger Active | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95762 | WBS.2.1.1.3.1.2.5 | N | N | Planned | Add New Plants to PLC tables | 0.5 | 2021-01-18 07:00 | 2021-01-18 07:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7823 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:30 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95763 | WBS.2.1.1.3.1.2.6 | N | N | Planned | Provide List of Users for Plant User Groups | 1 | 2021-01-18 07:30 | 2021-01-18 08:30 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95762 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 08:30 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95764 | WBS.2.1.1.3.1.2.7 | N | N | Planned | Add New Plant User Groups to PLC and Populate with Users | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95763,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96915 | WBS.2.1.1.3.1.2.8 | N | N | Planned | Execute Transactions FINS_CUST_CONS_CHK (gp00/1000 to 4505) and FINSC_CO_CD_TEMPLAT | 0.25 | 2021-01-18 07:45 | 2021-01-18 08:00 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7820 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 08:00 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90909 | WBS.2.1.1.3.1.3 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - OTC | 2.25 | 2021-01-18 06:45 | 2021-01-18 09:00 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 09:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7826 | WBS.2.1.1.3.1.3.1 | N | N | Planned | Validate S/4HANA Configuration Transports - OTC | 2 | 2021-01-18 06:45 | 2021-01-18 08:45 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | MICHELLE SADLER;TRISHUL BUDDHA;SAI TEAM;OTC TEAM;KYNDAL CODY;ONI BORCHERS | BMSADLER@GAPAC.COM;TBUDDHA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 08:45 | OTC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96914 | WBS.2.1.1.3.1.3.3 | N | N | Planned | Activate enhancement E0413 and add delivery types to BRF DT_OTC_DEL_TYP | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | TRISHUL BUDDHA;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | TBUDDHA@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 7826 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | OTC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90910 | WBS.2.1.1.3.1.4 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - EWM | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4100 | WBS.2.1.1.3.1.4.1 | N | N | Planned | Validate S/4HANA Configuration Transports For WM - EWM | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALISON SMITH | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ALISON.SMITH@GAPAC.COM | EWM | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90911 | WBS.2.1.1.3.1.5 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - PTP | 1.5 | 2021-01-18 06:45 | 2021-01-18 08:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 08:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
83006 | WBS.2.1.1.3.1.5.1 | N | N | Planned | Validate S/4HANA Configuration Transports - PTP | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;DOROTHY RUSSELL;SAI TEAM;SRUTHI SRINIVASAN;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36959 | WBS.2.1.1.3.1.5.2 | N | N | Planned | Validate AIF and BRF+ Tables For Interim Interfaces | 1 | 2021-01-18 07:15 | 2021-01-18 08:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 83006,93067 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 08:15 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90912 | WBS.2.1.1.3.1.6 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - SEC | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4086 | WBS.2.1.1.3.1.6.2 | N | N | Planned | Validate S/4HANA Security Transports - SEC | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8814 | WBS.2.1.1.3.1.6.3 | N | N | Planned | Validate SLT Security Transports - SEC | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90974 | WBS.2.1.1.3.1.7 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transportss - MDG - Data | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8815 | WBS.2.1.1.3.1.7.1 | N | N | Planned | Validate Security Transports For MDG | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 93067,4229 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95461 | WBS.2.1.1.3.1.8 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - SCM | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95462 | WBS.2.1.1.3.1.8.1 | N | N | Planned | Validate S/4HANA Configuration Transports - SCM | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SCM TEAM;SAI TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95514 | WBS.2.1.1.3.1.9 | N | N |  | Ramp Down ¦ Tech Build Activities - Pre-Conversions - Post Transports - Validate Transports - CRM and BW | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | [8 empty] | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95513 | WBS.2.1.1.3.1.9.1 | N | N | Planned | Validate Security Transports For CRM & BW | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 92201,93067 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91070 | WBS.2.1.1.3.2 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - System Back-Ups | 9.5 | 2021-01-17 22:00 | 2021-01-18 13:30 | [8 empty] | * |  | 2021-01-17 22:00 | 2021-01-18 13:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91117 | WBS.2.1.1.3.2.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - BW | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91038 | WBS.2.1.1.3.2.1.1 | N | N | Planned | Backup BW System - Pre-Data Big 3 Conversions | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4228,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91118 | WBS.2.1.1.3.2.2 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - S/4HANA | 3 | 2021-01-18 10:30 | 2021-01-18 13:30 | [8 empty] | * |  | 2021-01-18 10:30 | 2021-01-18 13:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91039 | WBS.2.1.1.3.2.2.1 | N | N | Planned | Backup S/4HANA System - Pre-Data Big 3 Conversions | 3 | 2021-01-18 10:30 | 2021-01-18 13:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 81550,68330,4629,4625,9866,9865,9920,9921,4579,4560,4575,4648,9389,9391,9390,4649 |  |  | * |  | 2021-01-18 10:30 | 2021-01-18 13:30 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91119 | WBS.2.1.1.3.2.3 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - MDG | 0.5 | 2021-01-17 22:00 | 2021-01-17 22:30 | [8 empty] | * |  | 2021-01-17 22:00 | 2021-01-17 22:30 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91040 | WBS.2.1.1.3.2.3.1 | N | N | Planned | Backup MDG System - Pre-Data Big 3 Conversions | 0.5 | 2021-01-17 22:00 | 2021-01-17 22:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 9401 |  |  | * |  | 2021-01-17 22:00 | 2021-01-17 22:30 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91120 | WBS.2.1.1.3.2.4 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - PO | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91041 | WBS.2.1.1.3.2.4.1 | N | N | Planned | Backup PO System - Pre-Data Big 3 Conversions | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4228,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91121 | WBS.2.1.1.3.2.5 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - GW | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91042 | WBS.2.1.1.3.2.5.1 | N | N | Planned | Backup GW System - Pre-Data Big 3 Conversions | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4228,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91122 | WBS.2.1.1.3.2.6 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - CRM | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91043 | WBS.2.1.1.3.2.6.1 | N | N | Planned | Backup CRM System - Pre-Data Big 3 Conversions | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4228,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91123 | WBS.2.1.1.3.2.7 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Post Transports - GRC | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91044 | WBS.2.1.1.3.2.7.1 | N | N | Planned | Backup GRC System - Pre-Data Big 3 Conversions | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10101 | WBS.2.1.1.4 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Technical Activity | 99.5 | 2021-01-17 23:00 | 2021-01-26 08:30 | [8 empty] | * |  | 2021-01-17 23:00 | 2021-01-26 08:30 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
4108 | WBS.2.1.1.4.1 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - General | 97.75 | 2021-01-18 06:15 | 2021-01-26 08:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 08:00 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
91573 | WBS.2.1.1.4.1.1 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - General - Multi-System | 97.75 | 2021-01-18 06:15 | 2021-01-26 08:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 08:00 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92601 | WBS.2.1.1.4.1.1.1 | N | N | Planned | Validate PDF export in Prod ADS | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92604 | WBS.2.1.1.4.1.1.2 | N | N | Planned | Validate/Create WE21 port in S4Q | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89750 | WBS.2.1.1.4.1.1.3 | N | N | Planned | Provide Handheld and Vehicle Mount URL to RF configuration team | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;SAI TEAM;SUVENDU KUMAR;DEV TEAM | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7879 | WBS.2.1.1.4.1.1.4 | N | N | Planned | Generate Distribution Model | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4119 | WBS.2.1.1.4.1.1.5 | N | N | Planned | Validate Parallel processing app server .group . | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4159 | WBS.2.1.1.4.1.1.6 | N | N | Planned | Validate Port/RFC config for ALE from S/4HANA to MDG for data objects | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4160 | WBS.2.1.1.4.1.1.7 | N | N | Planned | Switch to operation mode "DATA LOAD" in S/4HANA system | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4124 | WBS.2.1.1.4.1.1.8 | N | N | Planned | Create & Activate Integration Model for Maintenance order - PPDS | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9948 | WBS.2.1.1.4.1.1.9 | N | N | Planned | Activate Quality Inspection | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9946 | WBS.2.1.1.4.1.1.10 | N | N | Planned | Wave Templates & Wave template Determination Set up | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 91838,36501 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94849 | WBS.2.1.1.4.1.1.11 | N | N | Planned | HBG - Build and validate list of Business Processors for Contractors & GP employees | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97203 | WBS.2.1.1.4.1.1.25 | N | N | Planned | PTH - Build and validate list of Business Processors for Contractors & GP employees | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;SAI TEAM;EWM TEAM;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96552 | WBS.2.1.1.4.1.1.20 | N | N | Planned | BG - Build and validate list of Business Processors for Contractors & non-CPG employees and Generic IDs | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | JEANA HARRER;SAI TEAM;DEAN PIPER;EWM TEAM | Jeana.Harrer@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94847 | WBS.2.1.1.4.1.1.13 | N | N | Planned | SCH -Build and validate list of Business Processors for Contractors & GP employees | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96693 | WBS.2.1.1.4.1.1.22 | N | N | Planned | RNC - Build and validate list of Business Processors for Contractors & GP employees | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96694 | WBS.2.1.1.4.1.1.23 | N | N | Planned | RVG - Build and validate list of Business Processors for Contractors & GP employees | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97204 | WBS.2.1.1.4.1.1.26 | N | N | Planned | Get list of 'USERS' from all the 'Business Processor for Contractor' files from Teams and validate against table USR02 | 2 | 2021-01-18 08:30 | 2021-01-18 10:30 | NIKHIL NEGI | nikhnegi@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4573,91838,36501 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:30 | EWM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9945 | WBS.2.1.1.4.1.1.14 | N | N | Planned | Sort Bins for Activity Areas | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | Shefali Kushwaha | shefkushwaha@deloitte.com | DEEPAK SABNANI;AVINASH TALREJA;MICHAEL MATTHEWS;SAI TEAM;DOUG STANISLAWSKI;VINOD MADHANU;JEFFREY GOLDMUNTZ;EWM TEAM | DSABNANI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VMADHANU@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5218,10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:30 | EWM | CROSS | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
9947 | WBS.2.1.1.4.1.1.15 | N | N | Planned | PTH - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;Mohaideen Feroze;SAI TEAM;EWM TEAM;AJIT GOLE;AVINASH TALREJA;KUMAR SATYAM;DOUG STANISLAWSKI | VKUPPILI@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95310 | WBS.2.1.1.4.1.1.17 | N | N | Planned | HBG - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;Mohaideen Feroze;SAI TEAM;EWM TEAM;TEJAS THORAT;AVINASH TALREJA;KUMAR SATYAM;DOUG STANISLAWSKI;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TTHORAT@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96553 | WBS.2.1.1.4.1.1.21 | N | N | Planned | BG - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;Mohaideen Feroze;SAI TEAM;EWM TEAM;RATUL CHAKRABORTY;PRAJWAL K S;AVINASH TALREJA;KUMAR SATYAM;DOUG STANISLAWSKI | VKUPPILI@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ratchakraborty@deloitte.com;prajks@deloitte.com;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95307 | WBS.2.1.1.4.1.1.19 | N | N | Planned | SCH - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;Mohaideen Feroze;SAI TEAM;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA;AVINASH TALREJA;KUMAR SATYAM;DOUG STANISLAWSKI;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | SCH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
4080 | WBS.2.1.1.4.2 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems | 99.5 | 2021-01-17 23:00 | 2021-01-26 08:30 | [8 empty] | * |  | 2021-01-17 23:00 | 2021-01-26 08:30 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
91235 | WBS.2.1.1.4.2.1 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - S/4HANA | 98.25 | 2021-01-18 06:15 | 2021-01-26 08:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 08:30 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96695 | WBS.2.1.1.4.2.1.6 | N | N | Planned | RNC - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;Mohaideen Feroze;SAI TEAM;EWM TEAM;RASHI KUCHYA;GAYATHRI BATTALA;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;GBATTALA@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | RNC | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
97783 | WBS.2.1.1.4.2.1.8 | N | N | Planned | RCU- Verify all users have processors | 0.5 | 2021-01-26 08:00 | 2021-01-26 08:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;LOCKLIN HINTON;DAVID ALENCASTRO;JEREMY RAY;EWM TEAM;SAI TEAM | DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;LOCKLIN.HINTON@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96695 |  |  | * |  | 2021-01-26 08:00 | 2021-01-26 08:30 | EWM | RNC | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96696 | WBS.2.1.1.4.2.1.7 | N | N | Planned | RVG - Create Processors and assign users for Labor Management | 6 | 2021-01-25 18:00 | 2021-01-26 08:00 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 4501,4973,4974,93400,97204 |  |  | * |  | 2021-01-25 18:00 | 2021-01-26 08:00 | EWM | RVG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
97814 | WBS.2.1.1.4.2.1.9 | N | N | Planned | Creating processor for RFC Userid specific to 1369 ( Rivergate ) | 0.5 | 2021-01-26 08:00 | 2021-01-26 08:30 | GAYATHRI BATALA | gbattala@deloitte.com | V Kuppi;AVINASH TALREJA;DEEPAK SABNANI;MICHAEL MATTHEWS;ARNAB DEY;K Satyam;AQUIL HUSAIN;smshah@deloitte.com;SAI TEAM | *;AVTALREJA@DELOITTE.COM;DSABNANI@DELOITTE.COM;MMATTHEWS@DELOITTE.COM;ADEY@DELOITTE.COM;*;AQHUSAIN@DELOITTE.COM;*;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96696 |  |  | * |  | 2021-01-26 08:00 | 2021-01-26 08:30 | EWM | RVG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90486 | WBS.2.1.1.4.2.1.1 | N | N | Planned | Validate Activated SCPI RFCs | 0.33 | 2021-01-18 06:15 | 2021-01-18 06:35 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:35 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
83024 | WBS.2.1.1.4.2.1.2 | N | N | Planned | Validation D4 Printers In S/4HANA | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90488 | WBS.2.1.1.4.2.1.3 | N | N | Planned | Validate/Set-Up Consumer Proxy (Validation) - Vistex | 0.75 | 2021-01-18 06:15 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4142 | WBS.2.1.1.4.2.1.4 | N | N | Planned | Validate Check Printer Set-Up | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | SRINIVAS KATA;SUVENDU KUMAR;SAI TEAM;NAVJOT SHARMA;BRIAN DOBASH;DEV TEAM;TED ZEIDLER | SKATA@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
80759 | WBS.2.1.1.4.2.1.5 | N | N | Planned | Validate Autocash setup | 1.5 | 2021-01-18 06:45 | 2021-01-18 08:15 | NAVEEN CHEPURI | NAVCHEPURI@DELOITTE.COM | RAKESH MAKKAPATI;ARUN GANGADHARAN;MANOHAR VELMANOHAR;DON ABBOTT;SUVENDU KUMAR;SAI TEAM;DEV TEAM | RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;VELMANOHAR@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 08:15 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82560 | WBS.2.1.1.4.2.2 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - BODS / Data ETL | 3.25 | 2021-01-18 01:00 | 2021-01-18 09:15 | [8 empty] | * |  | 2021-01-18 01:00 | 2021-01-18 09:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82574 | WBS.2.1.1.4.2.2.1 | N | N | Planned | MC Task ¦ Create HDBODBC Connection And Validate For QA | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82575 | WBS.2.1.1.4.2.2.2 | N | N | Planned | MC Task ¦ Sanity Testing of Job Execution In BODS QA | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82561 | WBS.2.1.1.4.2.2.3 | N | N | Planned | Create XREF Table Indices In HANA DB | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82566 | WBS.2.1.1.4.2.2.4 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - SCM | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82567 | WBS.2.1.1.4.2.2.5 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - EWM | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82569 | WBS.2.1.1.4.2.2.6 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - AC | 0.5 | 2021-01-18 01:00 | 2021-01-18 01:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 4063 |  |  | * |  | 2021-01-18 01:00 | 2021-01-18 01:30 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82570 | WBS.2.1.1.4.2.2.7 | N | N | Planned | Maintain XREF Values In BODS For Data Conversions - PTP | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 80788 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82565 | WBS.2.1.1.4.2.2.8 | N | N | Planned | MDG_C0098 - Maintain XREF Values In BODS For Procured Materials Conversion | 0.5 | 2021-01-18 08:45 | 2021-01-18 09:15 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | PHANI GHANTASALA;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | PGHANTASALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 9125 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:15 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82576 | WBS.2.1.1.4.2.3 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - SAP HR | 82.5 | 2021-01-18 07:45 | 2021-01-25 10:15 | [8 empty] | * |  | 2021-01-18 07:45 | 2021-01-25 10:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96554 | WBS.2.1.1.4.2.3.15 | N | N | Planned | BG - Provide Initial List of Contractors To Be Created | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | JEANA HARRER;SAI TEAM;DEAN PIPER | Jeana.Harrer@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com | Business | 10846,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | RTR - PS | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96555 | WBS.2.1.1.4.2.3.16 | N | N | Planned | BG - Provide List of Activity Type Assignments For EE's And Contractors | 2 | 2021-01-25 08:15 | 2021-01-25 10:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | JEANA HARRER;SAI TEAM;DEAN PIPER | Jeana.Harrer@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com | Business | 96554,10845 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 10:15 | RTR - PS | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94742 | WBS.2.1.1.4.2.3.3 | N | N | Planned | Transfer Projects Along With WBS Structure For Deploying Site(s) From Ecosys To S/4HANA | 1 | 2021-01-19 19:15 | 2021-01-19 20:15 | LLOYD GRAFF | LLOYD.GRAFF@GAPAC.COM | PETER HENTGES;SAI TEAM;BRENDA STAGGS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | PETER.HENTGES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENDA.STAGGS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95449 |  |  | * |  | 2021-01-19 19:15 | 2021-01-19 20:15 | RTR - PS | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94741 | WBS.2.1.1.4.2.3.4 | N | N | Planned | Validation of Active Projects Along With WBS Structure For Deploying Site(s) From Ecosys To S/4HANA | 2.5 | 2021-01-20 12:15 | 2021-01-20 14:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;JOSHUA PENA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOSHUA.PENA@GAPAC.COM | RTR | 95448 |  |  | * |  | 2021-01-20 12:15 | 2021-01-20 14:45 | RTR - PS | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95449 | WBS.2.1.1.4.2.3.5 | N | N | Planned | Lowering pooling interval for channel - CC_FILE_Snd_ProjectInfo to 300 sec | 0.25 | 2021-01-19 19:00 | 2021-01-19 19:15 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SAMIKSHA KOTIAN;RADHIKA RASTOGI;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | samiksha.vijaykumarkotian@kochtc.com;RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 4250 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:15 | INT | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95448 | WBS.2.1.1.4.2.3.6 | N | N | Planned | Monitor processing of Projects and WBS Structure Replication From Ecosys To S/4HANA | 8 | 2021-01-19 20:15 | 2021-01-20 12:15 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;JOSHUA PENA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOSHUA.PENA@GAPAC.COM | RTR | 94742 |  |  | * |  | 2021-01-19 20:15 | 2021-01-20 12:15 | RTR - PS | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95447 | WBS.2.1.1.4.2.3.7 | N | N | Planned | Returning pooling interval for channel - CC_FILE_Snd_ProjectInfo to default(900 sec) | 0.25 | 2021-01-20 14:45 | 2021-01-20 15:00 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SAMIKSHA KOTIAN;RADHIKA RASTOGI;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | samiksha.vijaykumarkotian@kochtc.com;RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 94741 |  |  | * |  | 2021-01-20 14:45 | 2021-01-20 15:00 | INT | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
92136 | WBS.2.1.1.4.2.3.8 | N | N | Planned | Prepare and Upload Settlement rules for CapEx projects with conversion account and 'From/To Period' as Cutover period | 2 | 2021-01-20 14:45 | 2021-01-20 16:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DON ABBOTT;SAI TEAM;RTR TEAM;JOSHUA PENA | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOSHUA.PENA@GAPAC.COM | RTR | 94741 |  |  | * |  | 2021-01-20 14:45 | 2021-01-20 16:45 | RTR - PS | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95191 | WBS.2.1.1.4.2.3.9 | N | N | Planned | Create Variants for CJ8G CIP settlement jobs for deploying sites for current and prior periods | 0.75 | 2021-01-18 07:45 | 2021-01-18 08:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;AFSAR ALI MD;BRENDA STAGGS;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;md.afsarali@kochtc.com;BRENDA.STAGGS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4098 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 08:30 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95192 | WBS.2.1.1.4.2.3.10 | N | N | Planned | Add applicable deploying company codes to CJ8G variants: ZMRTRTASD and ZRTRTASD_PP | 0.25 | 2021-01-18 08:30 | 2021-01-18 08:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;AFSAR ALI MD;BRENDA STAGGS;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;md.afsarali@kochtc.com;BRENDA.STAGGS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95191 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 08:45 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95193 | WBS.2.1.1.4.2.3.11 | N | N | Planned | Request CJ8G CIP settlement jobs to be scheduled in Stone Branch | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;AFSAR ALI MD;BRENDA STAGGS;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;md.afsarali@kochtc.com;BRENDA.STAGGS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95192 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94759 | WBS.2.1.1.4.2.3.12 | N | N | Planned | Identify Interim Engineering Support projects for deploying sites to be closed and submit to Central Accounting Services | 0.5 | 2021-01-20 14:45 | 2021-01-20 15:15 | DAMON KIENITZ | DAMON.KIENITZ@GAPAC.COM | CHARLEE VANG;BRENDA STAGGS;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;LAWRENCE BOATENG | CHARLEE.VANG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 94741 |  |  | * |  | 2021-01-20 14:45 | 2021-01-20 15:15 | RTR - PS | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
92137 | WBS.2.1.1.4.2.3.13 | N | N | Planned | Execute SE38 for CapEx projects to add 'From Period/Year' to cost center settlement rule as Go-Live month. | 1 | 2021-01-20 16:45 | 2021-01-20 17:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DON ABBOTT;SAI TEAM;RTR TEAM;JOSHUA PENA | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOSHUA.PENA@GAPAC.COM | RTR | 92136 |  |  | * |  | 2021-01-20 16:45 | 2021-01-20 17:45 | RTR - PS | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
4226 | WBS.2.1.1.4.2.4 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - SAP MDG | 1.25 | 2021-01-18 06:45 | 2021-01-18 08:00 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 08:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4230 | WBS.2.1.1.4.2.4.2 | N | N | Planned | Confirm MDG Client Is Open | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4229 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4239 | WBS.2.1.1.4.2.4.3 | N | N | Planned | Switch To Operation Mode "DATA LOAD" In MDG System | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4229 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82244 | WBS.2.1.1.4.2.4.4 | N | N | Planned | Validate Gateway On MDG System | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RAKESH MAKKAPATI;SANDEEP THARWANI;ARUN GANGADHARAN;DIGITAL CORE UX TEAM;SAI TEAM;SUVENDU KUMAR;DEV TEAM | RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;DIGITALCOREUXTEAM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | UX | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90875 | WBS.2.1.1.4.2.4.5 | N | N | Planned | MC Task - Provide Web Server Addresses To CTM | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | ARLENE WALL;SAI TEAM;DEV TEAM | AKWALL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4230 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4244 | WBS.2.1.1.4.2.5 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - SAP PO | 30.5 | 2021-01-17 23:00 | 2021-01-19 19:30 | [8 empty] | * |  | 2021-01-17 23:00 | 2021-01-19 19:30 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
4250 | WBS.2.1.1.4.2.5.1 | N | N | Planned | SAP PO - Configure Channels To Connected Applications | 30 | 2021-01-17 23:00 | 2021-01-19 19:00 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;SAI TEAM;TED ZEIDLER;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 4245 |  |  | * |  | 2021-01-17 23:00 | 2021-01-19 19:00 | INT | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
4252 | WBS.2.1.1.4.2.5.2 | N | N | Planned | SAP PO - Configure Value Mappings | 4 | 2021-01-18 06:30 | 2021-01-18 10:30 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;HEMACHANDAN AS;SAI TEAM;TED ZEIDLER;ARUN GANGADHARAN;RAKESH MAKKAPATI;DEV TEAM | RADHRASTOGI@DELOITTE.COM;HEMACAS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4246 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 10:30 | INT | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4256 | WBS.2.1.1.4.2.5.3 | N | N | Planned | MC Task ¦ SAP PO - Validate Folders For Interfaces In S/4HANA System | 3.5 | 2021-01-18 06:30 | 2021-01-18 10:00 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;SAI TEAM;TED ZEIDLER;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 4246 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 10:00 | INT | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9413 | WBS.2.1.1.4.2.5.4 | N | N | Planned | RTR_I0102 - Maintain BRF+ table ZDT_PO_PARTNER for RTR_I0102 with system related PO partner | 0.75 | 2021-01-18 06:45 | 2021-01-18 07:30 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | GUNEET ARORA;SRINIVAS KATA;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | GUNEARORA@DELOITTE.COM;SKATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:30 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9414 | WBS.2.1.1.4.2.5.5 | N | N | Planned | Validate variant for D4 for Production orders output triggering program - RCCLORD | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;VENKATESH GANESHAN;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89630 | WBS.2.1.1.4.2.5.6 | N | N | Planned | Middleware provide S4Q API for E80 and Markem Image | 0.5 | 2021-01-19 19:00 | 2021-01-19 19:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | ANKIT SONI;BRIAN DOBASH;SANDEEP THARWANI;DON ABBOTT;SUVENDU KUMAR;SAI TEAM;DEV TEAM;ARUN GANGADHARAN;RAKESH MAKKAPATI;TED ZEIDLER | ANKISONI@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 4250 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:30 | INT | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
89643 | WBS.2.1.1.4.2.6 | N | N |  | Ramp Down ¦ Tech Build - Pre-Conversions - Post Transports - Technical Activity - SAP Systems - SAP PI | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90707 | WBS.2.1.1.4.2.6.1 | N | N | Planned | SCP PI - Import transport(s) with Basis Team | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | ANKIT SONI | ANKISONI@DELOITTE.COM | RADHIKA RASTOGI;DANI SIMMONS;NAVJOT SHARMA;RAMYA IYER;SAI TEAM;TED ZEIDLER;SUVENDU KUMAR;DEV TEAM | RADHRASTOGI@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;RAMYIYER@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | INT | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9403 | WBS.2.1.1.4.2.6.2 | N | N | Planned | SCP PI - SAP Cloud Connector Validation for S/4HANA | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | HEMACHANDAN AS | HEMACAS@DELOITTE.COM | TED ZEIDLER;NAVJOT SHARMA;DANI SIMMONS;ANKIT SONI;SANDEEP THARWANI;ANTHONY GORDON;SAI TEAM;US GP BASIS;SUVENDU KUMAR;ARUN GANGADHARAN;RAKESH MAKKAPATI;DEV TEAM;RADHIKA RASTOGI | TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ADGORDON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RADHRASTOGI@DELOITTE.COM | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | INT | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9405 | WBS.2.1.1.4.2.6.3 | N | N | Planned | SCP-PI Configure channels to connected applications | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | HEMACHANDAN AS | HEMACAS@DELOITTE.COM | TED ZEIDLER;NAVJOT SHARMA;DANI SIMMONS;ANKIT SONI;SANDEEP THARWANI;ANTHONY GORDON;SAI TEAM;ARUN GANGADHARAN;RAKESH MAKKAPATI;PAYEL GHOSH;SUVENDU KUMAR;DEV TEAM;RADHIKA RASTOGI;RAMYA IYER | TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ADGORDON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RADHRASTOGI@DELOITTE.COM;RAMYIYER@DELOITTE.COM | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | INT | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96812 | WBS.2.1.1.5 | N | N |  | Ramp Down ¦ Tech Activities - Technical System Upgrade Activity | 170.5 | 2021-01-16 10:00 | 2021-01-30 14:00 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-01-30 14:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96814 | WBS.2.1.1.5.3 | N | N |  | Ramp Down ¦ Tech Activities - Technical System Upgrade Tasks | 170.5 | 2021-01-16 10:00 | 2021-01-30 14:00 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-01-30 14:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96813 | WBS.2.1.1.5.3.1 | N | N |  | Ramp Down ¦ Tech Activities - Technical System Upgrade Tasks First Weekend | 25 | 2021-01-16 10:00 | 2021-01-17 11:00 | [8 empty] | * |  | 2021-01-16 10:00 | 2021-01-17 11:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97315 | WBS.2.1.1.5.3.1.139 | N | N | Planned | DB - Preparation - System unavailability - DB Upgrade Notification to be sent out for EHANA | 0.25 | 2021-01-17 06:00 | 2021-01-17 06:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92190 |  |  | * |  | 2021-01-17 06:00 | 2021-01-17 06:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97316 | WBS.2.1.1.5.3.1.140 | N | N | Planned | DB - Preparation - Stop HANA Replication(HSR) EHANA | 0.25 | 2021-01-17 06:00 | 2021-01-17 06:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92190 |  |  | * |  | 2021-01-17 06:00 | 2021-01-17 06:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97554 | WBS.2.1.1.5.3.1.184 | N | N | Planned | STOP Stone Branch Jobs for EHANA | 1 | 2021-01-17 05:00 | 2021-01-17 06:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;KELLY HINSON;SAI TEAM;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;KSHINSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH |  |  |  |  | 2021-01-17 05:00 | 2021-01-17 05:00 | 2021-01-17 06:00 | BATCH | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97553 | WBS.2.1.1.5.3.1.183 | N | N | Planned | STOP SLT Replication | 0.25 | 2021-01-17 06:00 | 2021-01-17 06:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92190 |  |  | * |  | 2021-01-17 06:00 | 2021-01-17 06:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97319 | WBS.2.1.1.5.3.1.143 | N | N | Planned | DB - Downtime - perform DB upgrade on primary - EHANA | 2 | 2021-01-17 06:15 | 2021-01-17 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97315,97553,97554,97316,92190 |  |  | * |  | 2021-01-17 06:15 | 2021-01-17 08:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97317 | WBS.2.1.1.5.3.1.141 | N | N | Planned | DB - Preparation - perform DB upgrade on Secondary - EHANA | 1.5 | 2021-01-17 08:15 | 2021-01-17 09:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97315,97316,97554,97553,92190,97319 |  |  | * |  | 2021-01-17 08:15 | 2021-01-17 09:45 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97556 | WBS.2.1.1.5.3.1.186 | N | N | Planned | Validation by Reporting Team - Post EHANA Upgrade | 0.5 | 2021-01-17 08:15 | 2021-01-17 08:45 | SMRITI SONI | SMRITI.SONI@KOCHTC.COM | BRIAN RIDENHOUR;LISA HEROLD;DWIGHT WORRELL;PRAVEENA REDDY;SAI TEAM;Atul Agnihotri | BRIAN.RIDENHOUR@GAPAC.COM;LISA.HEROLD@GAPAC.COM;DLWORREL@GAPAC.COM;PRAVEENA.REDDY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;atagnihotri@deloitte.com | RPT | 97319 |  |  | * |  | 2021-01-17 08:15 | 2021-01-17 08:45 | RPT | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97747 | WBS.2.1.1.5.3.1.189 | N | N | Planned | Send Communcation when EHANNA and SLT are available to users after upgrade | 0.25 | 2021-01-17 10:45 | 2021-01-17 11:00 | KELLY HINSON | KSHINSON@GAPAC.COM | PRAVEENA REDDY;DWIGHT WORREL;KYNDAL CODY;DANI SIMMONS;MAMIE TREZVANT;SUVENDU KUMAR;NAVJOT SHARMA;SAI TEAM | PRAVEENA.REDDY@GAPAC.COM;*;KYNDAL.CODY@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RPT | 97556,97626 |  |  | * |  | 2021-01-17 10:45 | 2021-01-17 11:00 | RPT | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97555 | WBS.2.1.1.5.3.1.185 | N | N | Planned | START Stone Branch Jobs for EHANA | 0.25 | 2021-01-17 08:45 | 2021-01-17 09:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;KELLY HINSON;SAI TEAM;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;KSHINSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 97319,97556 |  |  | * |  | 2021-01-17 08:45 | 2021-01-17 09:00 | BATCH | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97557 | WBS.2.1.1.5.3.1.187 | N | N | Planned | START SLT Replication | 0.25 | 2021-01-17 10:00 | 2021-01-17 10:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97319,97556,97255,97253 |  |  | * |  | 2021-01-17 10:00 | 2021-01-17 10:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97626 | WBS.2.1.1.5.3.1.188 | N | N | Planned | Validation by Reporting Team - EHANA after SLT Upgrade | 0.5 | 2021-01-17 10:15 | 2021-01-17 10:45 | SMRITI SONI | SMRITI.SONI@KOCHTC.COM | BRIAN RIDENHOUR;LISA HEROLD;DWIGHT WORRELL;PRAVEENA REDDY;SAI TEAM;Atul Agnihotri | BRIAN.RIDENHOUR@GAPAC.COM;LISA.HEROLD@GAPAC.COM;DLWORREL@GAPAC.COM;PRAVEENA.REDDY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;atagnihotri@deloitte.com | RPT | 97319,97557 |  |  | * |  | 2021-01-17 10:15 | 2021-01-17 10:45 | RPT | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97322 | WBS.2.1.1.5.3.1.146 | N | N | Planned | DB - Uptime - Start HANA Replication(HSR) EHANA | 0.25 | 2021-01-17 08:45 | 2021-01-17 09:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97315,97556,97319 |  |  | * |  | 2021-01-17 08:45 | 2021-01-17 09:00 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97325 | WBS.2.1.1.5.3.1.149 | N | N | Planned | SDI Agent Upgrade | 2 | 2021-01-17 06:15 | 2021-01-17 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97553 |  |  | * |  | 2021-01-17 06:15 | 2021-01-17 08:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97326 | WBS.2.1.1.5.3.1.150 | N | N | Planned | Cloud Connector Upgrade | 2 | 2021-01-17 06:15 | 2021-01-17 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97553 |  |  | * |  | 2021-01-17 06:15 | 2021-01-17 08:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97327 | WBS.2.1.1.5.3.1.151 | N | N | Planned | DS Agent Upgrade | 2 | 2021-01-17 06:15 | 2021-01-17 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97553 |  |  | * |  | 2021-01-17 06:15 | 2021-01-17 08:15 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97510 | WBS.2.1.1.5.3.1.182 | N | N | Planned | Validate File Path for the interfaces in DS Agent ( SAPEFS/SAPEFSPROD ) & Config File Parameters for Memory/Timeout | 0.5 | 2021-01-17 08:15 | 2021-01-17 08:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97327 |  |  | * |  | 2021-01-17 08:15 | 2021-01-17 08:45 | DEV - INFRA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
96871 | WBS.2.1.1.5.3.1.57 | N | N | Planned | DB - Preparation - System unavailability - DB Upgrade Notification to be sent out for S/4, MDG, PO, GW | 0.5 | 2021-01-17 04:15 | 2021-01-17 04:45 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-17 04:15 | 2021-01-17 04:15 | 2021-01-17 04:45 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
96870 | WBS.2.1.1.5.3.1.56 | N | N | Planned | DB - Preparation - Post System Message in SAP for System Unavailability for S/4, MDG, PO, GW | 0.25 | 2021-01-17 04:45 | 2021-01-17 05:00 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96871 |  |  | * |  | 2021-01-17 04:45 | 2021-01-17 05:00 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97246 | WBS.2.1.1.5.3.1.79 | N | N | Planned | Downtime - Patch DS Agent | 0.5 | 2021-01-17 06:15 | 2021-01-17 06:45 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97553 |  |  | * |  | 2021-01-17 06:15 | 2021-01-17 06:45 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97262 | WBS.2.1.1.5.3.1.95 | N | N | Planned | Preparation - Backup for SLT - Before Starting Application Upgrade | 0.5 | 2021-01-16 10:00 | 2021-01-16 10:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-16 10:00 | 2021-01-16 10:00 | 2021-01-16 10:30 | DEV - INFRA | ALL | 2021-01-16 | 2021-01-16 | 1 | Ramp Down
97260 | WBS.2.1.1.5.3.1.93 | N | N | Planned | Preparation - Import Pre Upgrade TRs (SLT) | 0.5 | 2021-01-16 10:30 | 2021-01-16 11:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97262 |  |  | * |  | 2021-01-16 10:30 | 2021-01-16 11:00 | DEV - INFRA | ALL | 2021-01-16 | 2021-01-16 | 1 | Ramp Down
97259 | WBS.2.1.1.5.3.1.92 | N | N | Planned | Preparation - Validate Pre Upgrade TRs (SLT) | 0.5 | 2021-01-16 11:00 | 2021-01-16 11:30 | VINOTH NAGARAJAN | VINAGARAJAN@DELOITTE.COM | RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97260 |  |  | * |  | 2021-01-16 11:00 | 2021-01-16 11:30 | DEV | ALL | 2021-01-16 | 2021-01-16 | 1 | Ramp Down
97258 | WBS.2.1.1.5.3.1.91 | N | N | Planned | Preparation - Extract SUM tool and kick start - SLT | 2 | 2021-01-16 11:30 | 2021-01-16 13:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97259 |  |  | * |  | 2021-01-16 11:30 | 2021-01-16 13:30 | DEV - INFRA | ALL | 2021-01-16 | 2021-01-16 | 1 | Ramp Down
97257 | WBS.2.1.1.5.3.1.90 | N | N | Planned | Pre-Processing - Start Preprocessing stage for SLT | 16 | 2021-01-16 13:30 | 2021-01-17 05:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97258 |  |  | * |  | 2021-01-16 13:30 | 2021-01-17 05:30 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97256 | WBS.2.1.1.5.3.1.89 | N | N | Planned | Pre-Processing - SUM and DB Backup before start downtime for SLT | 0.5 | 2021-01-17 05:30 | 2021-01-17 06:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97257 |  |  | * |  | 2021-01-17 05:30 | 2021-01-17 06:00 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97255 | WBS.2.1.1.5.3.1.88 | N | N | Planned | Downtime - Downtime phase - Monitor for import of SPAU TR SLT | 3 | 2021-01-17 06:00 | 2021-01-17 09:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | LOKESH KAMANA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97256 |  |  | * |  | 2021-01-17 06:00 | 2021-01-17 09:00 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97254 | WBS.2.1.1.5.3.1.87 | N | N | Planned | Downtime - Validate SPAU TR and SPAU, SPAU_ENH Transactions SLT | 1 | 2021-01-17 09:00 | 2021-01-17 10:00 | VINOTH NAGARAJAN | VINAGARAJAN@DELOITTE.COM | RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97255 |  |  | * |  | 2021-01-17 09:00 | 2021-01-17 10:00 | DEV - INFRA | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97253 | WBS.2.1.1.5.3.1.86 | N | N | Planned | Downtime - DMIS Addon in Legacy systems (ECC, BW) | 1 | 2021-01-17 09:00 | 2021-01-17 10:00 | PRASHANT NAMBIAR | PRASHANT.NAMBIAR@KOCHTC.COM | MELVIN REBERRO;GP BASIS/KTC BASIS;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | melvin.reberro@kochtc.com;*;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97255 |  |  | * |  | 2021-01-17 09:00 | 2021-01-17 10:00 | GP-BASIS | ALL | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97832 | WBS.2.1.1.5.3.1.190 | N | N | Planned | Downtime - DMIS Addon BW, CRM | 1.5 | 2021-01-17 09:00 | 2021-01-17 10:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97255 |  |  | * |  | 2021-01-17 09:00 | 2021-01-17 10:30 | GP-BASIS | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
97570 | WBS.2.1.1.5.3.3 |  |  |  | Ramp Down ¦ Tech Activities - Technical System Upgrade Tasks Second Weekend | 160 | 2021-01-23 22:00 | 2021-01-30 14:00 | [8 empty] | * |  | 2021-01-23 22:00 | 2021-01-30 14:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97329 | WBS.2.1.1.5.3.3.153 | N | N | Planned | WebDispatcher Upgrade | 2 | 2021-01-24 06:00 | 2021-01-24 08:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV |  |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:00 | 2021-01-24 08:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97244 | WBS.2.1.1.5.3.3.77 | N | N | Planned | Downtime - Patch Web Dispatcher | 0.5 | 2021-01-24 06:00 | 2021-01-24 06:30 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:00 | 2021-01-24 06:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96869 | WBS.2.1.1.5.3.3.2 | N | N | Planned | DB - Preparation - Backup of S/4 | 3.75 | 2021-01-24 02:00 | 2021-01-24 05:45 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-24 02:00 | 2021-01-24 02:00 | 2021-01-24 05:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96868 | WBS.2.1.1.5.3.3.54 | N | N | Planned | DB - Preparation - Stop Stonebranch Jobs - S/4 | 1 | 2021-01-24 05:00 | 2021-01-24 06:00 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH |  |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 06:00 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97567 | WBS.2.1.1.5.3.3.196 | N | N | Planned | DB - Downtime STOP EDI Integration for S/4 | 1 | 2021-01-24 05:00 | 2021-01-24 06:00 | NAVEEN BODDU | NAVEEN.BODDU@KOCHTC.COM | SAI TEAM;DEV EDI TEAM;GRP_CPBSEDIDEVELOPERS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PATRICK.HERRING@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;IZKHAN@DELOITTE.COM;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM;CYNDI.HOTTENSTINE@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM;NAVEEN.BODDU@KOCHTC.COM;ABRADLEY@GAPAC.COM;GRP_CPBSEDIDEVELOPERS@GAPAC.COM | EDI |  |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 06:00 | EDI | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97563 | WBS.2.1.1.5.3.3.193 | N | N | Planned | DB - Downtime STOP PO Channels for S/4 & MDG | 0.25 | 2021-01-24 06:00 | 2021-01-24 06:15 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV |  |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:00 | 2021-01-24 06:15 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97562 | WBS.2.1.1.5.3.3.192 | N | N | Planned | DB - Downtime STOP SLT Integration S4 | 0.25 | 2021-01-24 05:45 | 2021-01-24 06:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96869 |  |  |  | 2021-01-24 05:45 | 2021-01-24 05:45 | 2021-01-24 06:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96867 | WBS.2.1.1.5.3.3.53 | N | N | Planned | DB - Preparation - Stop HANA Replication(HSR) - S/4 | 0.25 | 2021-01-23 22:00 | 2021-01-23 22:15 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-23 22:00 | 2021-01-23 22:00 | 2021-01-23 22:15 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96866 | WBS.2.1.1.5.3.3.52 | N | N | Planned | DB - Preparation - perform DB upgrade on Secondary - S/4 | 1.5 | 2021-01-23 22:15 | 2021-01-23 23:45 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96867 |  |  | * |  | 2021-01-23 22:15 | 2021-01-23 23:45 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96865 | WBS.2.1.1.5.3.3.51 | N | N | Planned | DB - Preparation - Start HANA Replication(HSR) - S/4 | 6 | 2021-01-23 23:45 | 2021-01-24 05:45 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96866 |  |  | * |  | 2021-01-23 23:45 | 2021-01-24 05:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96864 | WBS.2.1.1.5.3.3.50 | N | N | Planned | DB - Downtime - failover DB to secondary - S/4 | 0.25 | 2021-01-24 06:15 | 2021-01-24 06:30 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96865,97567,97563,97562 |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:15 | 2021-01-24 06:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97748 | WBS.2.1.1.5.3.3.201 | N | N | Planned | Send Communication that S4/MDG/PO/GW is now available after upgrade | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | KELLY HINSON | KSHINSON@GAPAC.COM | KYNDAL CODY;DANI SIMMONS;MAMIE TREZVANT;SUVENDU KUMAR;NAVJOT SHARMA;SAI TEAM | KYNDAL.CODY@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | DEV | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97754 | WBS.2.1.1.5.3.3.200 | N | N | Planned | Validate cashapp after DB upgrade | 0.5 | 2021-01-24 06:30 | 2021-01-24 07:00 | NAVEEN CHEPURI | NAVCHEPURI@DELOITTE.COM | SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;VENKATESH GANESHAN;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 07:00 | DEV | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97569 | WBS.2.1.1.5.3.3.197 | N | N | Planned | DB - Downtime START EDI Integration for S/4 | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | NAVEEN BODDU | NAVEEN.BODDU@KOCHTC.COM | SAI TEAM;DEV EDI TEAM;GRP_CPBSEDIDEVELOPERS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PATRICK.HERRING@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;IZKHAN@DELOITTE.COM;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM;CYNDI.HOTTENSTINE@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM;NAVEEN.BODDU@KOCHTC.COM;ABRADLEY@GAPAC.COM;GRP_CPBSEDIDEVELOPERS@GAPAC.COM | EDI | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | EDI | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97564 | WBS.2.1.1.5.3.3.194 | N | N | Planned | DB - Uptime START SLT Integration S/4 | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97565 | WBS.2.1.1.5.3.3.195 | N | N | Planned | DB - Uptime START PO Channels for S/4 & MDG | 0.25 | 2021-01-24 06:45 | 2021-01-24 07:00 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96864,96834,96854 |  |  | * |  | 2021-01-24 06:45 | 2021-01-24 07:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96860 | WBS.2.1.1.5.3.3.46 | N | N | Planned | DB - Uptime - Start Stonebranch Jobs - S/4 | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96863 | WBS.2.1.1.5.3.3.49 | N | N | Planned | DB - Uptime - Stop HANA Replication(HSR) - S/4 | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96864 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96862 | WBS.2.1.1.5.3.3.48 | N | N | Planned | DB - Uptime - perform DB upgrade on Primary - S/4 | 1.5 | 2021-01-24 07:00 | 2021-01-24 08:30 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96863,96868,97564,97565,97567,97569 |  |  | * |  | 2021-01-24 07:00 | 2021-01-24 08:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96861 | WBS.2.1.1.5.3.3.47 | N | N | Planned | DB - Uptime - Start HANA Replication(HSR) - S/4 | 6 | 2021-01-24 08:30 | 2021-01-24 14:30 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96862 |  |  | * |  | 2021-01-24 08:30 | 2021-01-24 14:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96859 | WBS.2.1.1.5.3.3.45 | N | N | Planned | DB - Preparation - Backup of MDG | 1.5 | 2021-01-24 04:00 | 2021-01-24 05:30 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96871,97346 |  |  | * |  | 2021-01-24 04:00 | 2021-01-24 05:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96858 | WBS.2.1.1.5.3.3.44 | N | N | Planned | DB - Preparation - Stop StoneBranch Jobs - MDG | 1 | 2021-01-24 05:00 | 2021-01-24 06:00 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH |  |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 06:00 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97558 | WBS.2.1.1.5.3.3.188 | N | N | Planned | DB - Downtime STOP SLT Integration MDG | 0.25 | 2021-01-24 05:45 | 2021-01-24 06:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97346,96859 |  |  |  | 2021-01-24 05:45 | 2021-01-24 05:45 | 2021-01-24 06:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96857 | WBS.2.1.1.5.3.3.43 | N | N | Planned | DB - Preparation - Stop HANA Replication(HSR) - MDG | 0.25 | 2021-01-23 22:00 | 2021-01-23 22:15 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-23 22:00 | 2021-01-23 22:00 | 2021-01-23 22:15 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96856 | WBS.2.1.1.5.3.3.42 | N | N | Planned | DB - Preparation - perform DB upgrade on Secondary - MDG | 1.5 | 2021-01-23 22:15 | 2021-01-23 23:45 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96857 |  |  | * |  | 2021-01-23 22:15 | 2021-01-23 23:45 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96855 | WBS.2.1.1.5.3.3.41 | N | N | Planned | DB - Preparation - Start HANA Replication(HSR) - MDG | 6 | 2021-01-23 23:45 | 2021-01-24 05:45 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96856 |  |  | * |  | 2021-01-23 23:45 | 2021-01-24 05:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96854 | WBS.2.1.1.5.3.3.40 | N | N | Planned | DB - Downtime - failover DB to secondary - MDG | 0.25 | 2021-01-24 06:15 | 2021-01-24 06:30 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96855,96858,97558,97563 |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:15 | 2021-01-24 06:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97560 | WBS.2.1.1.5.3.3.190 | N | N | Planned | DB - Downtime START SLT Integration MDG | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96854 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96850 | WBS.2.1.1.5.3.3.36 | N | N | Planned | DB - Uptime - Start Stonebranch Jobs - MDG | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96854 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96853 | WBS.2.1.1.5.3.3.39 | N | N | Planned | DB - Uptime - Stop HANA Replication(HSR) - MDG | 0.25 | 2021-01-24 06:30 | 2021-01-24 06:45 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | DEV | 96854 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 06:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96852 | WBS.2.1.1.5.3.3.38 | N | N | Planned | DB - Uptime - perform DB upgrade on Primary - MDG | 1.5 | 2021-01-24 06:45 | 2021-01-24 08:15 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96853,97560 |  |  | * |  | 2021-01-24 06:45 | 2021-01-24 08:15 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96851 | WBS.2.1.1.5.3.3.37 | N | N | Planned | DB - Uptime - Start HANA Replication(HSR) - MDG | 6 | 2021-01-24 08:15 | 2021-01-24 14:15 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96852 |  |  | * |  | 2021-01-24 08:15 | 2021-01-24 14:15 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96849 | WBS.2.1.1.5.3.3.35 | N | N | Planned | DB - Preparation - Backup of GW | 1 | 2021-01-24 04:00 | 2021-01-24 05:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96871,97346 |  |  | * |  | 2021-01-24 04:00 | 2021-01-24 05:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96848 | WBS.2.1.1.5.3.3.34 | N | N | Planned | DB - Preparation - Stop Stonebranch Jobs - GW | 1 | 2021-01-24 05:00 | 2021-01-24 06:00 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96849 |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 06:00 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96847 | WBS.2.1.1.5.3.3.33 | N | N | Planned | DB - Preparation - Stop HANA Replication(HSR) - GW | 0.25 | 2021-01-23 22:00 | 2021-01-23 22:15 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-23 22:00 | 2021-01-23 22:00 | 2021-01-23 22:15 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96846 | WBS.2.1.1.5.3.3.32 | N | N | Planned | DB - Preparation - perform DB upgrade on Secondary - GW | 1.5 | 2021-01-23 22:15 | 2021-01-23 23:45 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96847 |  |  | * |  | 2021-01-23 22:15 | 2021-01-23 23:45 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96845 | WBS.2.1.1.5.3.3.31 | N | N | Planned | DB - Preparation - Start HANA Replication(HSR) - GW | 6 | 2021-01-23 23:45 | 2021-01-24 05:45 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96846 |  |  | * |  | 2021-01-23 23:45 | 2021-01-24 05:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96844 | WBS.2.1.1.5.3.3.30 | N | N | Planned | DB - Downtime - failover DB to secondary - GW | 0.25 | 2021-01-24 06:00 | 2021-01-24 06:15 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96845,96849,96848 |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:00 | 2021-01-24 06:15 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96843 | WBS.2.1.1.5.3.3.29 | N | N | Planned | DB - Uptime - Stop HANA Replication(HSR) - GW | 0.25 | 2021-01-24 06:15 | 2021-01-24 06:30 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96844 |  |  | * |  | 2021-01-24 06:15 | 2021-01-24 06:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96842 | WBS.2.1.1.5.3.3.28 | N | N | Planned | DB - Uptime - perform DB upgrade on Primary - GW | 1.5 | 2021-01-24 06:30 | 2021-01-24 08:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96843 |  |  | * |  | 2021-01-24 06:30 | 2021-01-24 08:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96841 | WBS.2.1.1.5.3.3.27 | N | N | Planned | DB - Uptime - Start HANA Replication(HSR) - GW | 6 | 2021-01-24 08:00 | 2021-01-24 14:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96842 |  |  | * |  | 2021-01-24 08:00 | 2021-01-24 14:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96840 | WBS.2.1.1.5.3.3.26 | N | N | Planned | DB - Uptime - Start Stonebranch Jobs - GW | 0.25 | 2021-01-24 06:15 | 2021-01-24 06:30 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96844 |  |  | * |  | 2021-01-24 06:15 | 2021-01-24 06:30 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96839 | WBS.2.1.1.5.3.3.25 | N | N | Planned | DB - Preparation - Backup of PO | 1 | 2021-01-24 04:00 | 2021-01-24 05:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96871,97346 |  |  | * |  | 2021-01-24 04:00 | 2021-01-24 05:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96838 | WBS.2.1.1.5.3.3.24 | N | N | Planned | DB - Preparation - Stop Stonebranch Jobs - PO | 1 | 2021-01-24 05:00 | 2021-01-24 06:00 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96839 |  |  |  | 2021-01-24 05:00 | 2021-01-24 05:00 | 2021-01-24 06:00 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96837 | WBS.2.1.1.5.3.3.23 | N | N | Planned | DB - Preparation - Stop HANA Replication(HSR) - PO | 0.25 | 2021-01-23 22:00 | 2021-01-23 22:15 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-23 22:00 | 2021-01-23 22:00 | 2021-01-23 22:15 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96836 | WBS.2.1.1.5.3.3.22 | N | N | Planned | DB - Preparation - perform DB upgrade on Secondary - PO | 1.5 | 2021-01-23 22:15 | 2021-01-23 23:45 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96837 |  |  | * |  | 2021-01-23 22:15 | 2021-01-23 23:45 | DEV - INFRA | ALL | 2021-01-23 | 2021-01-23 | 1 | Ramp Down
96835 | WBS.2.1.1.5.3.3.21 | N | N | Planned | DB - Preparation - Start HANA Replication(HSR) - PO | 6 | 2021-01-23 23:45 | 2021-01-24 05:45 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96836 |  |  | * |  | 2021-01-23 23:45 | 2021-01-24 05:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96834 | WBS.2.1.1.5.3.3.20 | N | N | Planned | DB - Downtime - failover DB to secondary - PO | 0.75 | 2021-01-24 06:00 | 2021-01-24 06:45 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96835,96838,96839 |  |  |  | 2021-01-24 06:00 | 2021-01-24 06:00 | 2021-01-24 06:45 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96833 | WBS.2.1.1.5.3.3.19 | N | N | Planned | DB - Uptime - Stop HANA Replication(HSR) - PO | 0.25 | 2021-01-24 06:45 | 2021-01-24 07:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96834 |  |  | * |  | 2021-01-24 06:45 | 2021-01-24 07:00 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96832 | WBS.2.1.1.5.3.3.18 | N | N | Planned | DB - Uptime - perform DB upgrade on Primary - PO | 1.5 | 2021-01-24 07:00 | 2021-01-24 08:30 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96833 |  |  | * |  | 2021-01-24 07:00 | 2021-01-24 08:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96831 | WBS.2.1.1.5.3.3.17 | N | N | Planned | DB - Uptime - Start HANA Replication(HSR) - PO | 6 | 2021-01-24 08:30 | 2021-01-24 14:30 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96832 |  |  | * |  | 2021-01-24 08:30 | 2021-01-24 14:30 | DEV - INFRA | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96830 | WBS.2.1.1.5.3.3.16 | N | N | Planned | DB - Uptime - Start Stonebranch Jobs - PO | 0.25 | 2021-01-24 06:45 | 2021-01-24 07:00 | NNEKA MBA | NEMBA@GAPAC.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96834 |  |  | * |  | 2021-01-24 06:45 | 2021-01-24 07:00 | BATCH | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
96821 | WBS.2.1.1.5.3.3.7 | N | N | Planned | DB - Uptime - Stop HANA Replication(HSR) | 0.25 | 2021-01-24 04:00 | 2021-01-24 04:15 | SRINIVAS KAKUTURU | SKAKUTURU@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 93067,97346 |  |  | * |  | 2021-01-24 04:00 | 2021-01-24 04:15 | DEV | ALL | 2021-01-24 | 2021-01-24 | 2 | Ramp Down
97235 | WBS.2.1.1.5.3.3.68 | N | N | Planned | Preparation - Backup before start Sum tool - S4 | 3 | 2021-01-28 16:00 | 2021-01-28 19:00 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-28 16:00 | 2021-01-28 16:00 | 2021-01-28 19:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97234 | WBS.2.1.1.5.3.3.67 | N | N | Planned | Preparation - Import Pre Upgrade TRs S4 | 1 | 2021-01-28 19:00 | 2021-01-28 20:00 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97235 |  |  | * |  | 2021-01-28 19:00 | 2021-01-28 20:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97696 | WBS.2.1.1.5.3.3.198 | N | N | Planned | Pass along password for VIZI_READ user in S2H (S42 database) | 0.5 | 2021-01-28 20:00 | 2021-01-28 20:30 | CARLOS ROBELO TEJADA | CROBELOTEJADA@DELOITTE.COM | SEC TEAM;SAI TEAM | MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 97234 |  |  | * |  | 2021-01-28 20:00 | 2021-01-28 20:30 | SECURITY | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97233 | WBS.2.1.1.5.3.3.66 | N | N | Planned | Preparation - Execute Programs to avoid Deletion of Ariba/MRS/IDT | 0.5 | 2021-01-28 20:00 | 2021-01-28 20:30 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97234 |  |  | * |  | 2021-01-28 20:00 | 2021-01-28 20:30 | DEV | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97232 | WBS.2.1.1.5.3.3.65 | N | N | Planned | Preparation - Validate Pre Upgrade TRs S4 | 1 | 2021-01-28 20:00 | 2021-01-28 21:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97234 |  |  | * |  | 2021-01-28 20:00 | 2021-01-28 21:00 | DEV | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97231 | WBS.2.1.1.5.3.3.64 | N | N | Planned | Preparation - ARIBA - Import certificates and RFCs for CIG, add HTTP Destinations for SCPI trailer | 1 | 2021-01-28 20:30 | 2021-01-28 21:30 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97233 |  |  | * |  | 2021-01-28 20:30 | 2021-01-28 21:30 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97230 | WBS.2.1.1.5.3.3.63 | N | N | Planned | Preparation - Extract SUM tool and kick start Application Upgrade - S4 | 3 | 2021-01-28 21:00 | 2021-01-29 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97232 |  |  | * |  | 2021-01-28 21:00 | 2021-01-29 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97240 | WBS.2.1.1.5.3.3.73 | N | N | Planned | Pre-Processing - Start Preprocessing stage and monitor for import of SPDD TR - S4 | 8 | 2021-01-29 | 2021-01-29 08:00 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97230 |  |  | * |  | 2021-01-29 | 2021-01-29 08:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97239 | WBS.2.1.1.5.3.3.72 | N | N | Planned | Pre-Processing - Validate SPDD TR and SPDD transaction - S4 | 2 | 2021-01-29 08:00 | 2021-01-29 10:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97240 |  |  | * |  | 2021-01-29 08:00 | 2021-01-29 10:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97238 | WBS.2.1.1.5.3.3.71 | N | N | Planned | Pre-Processing - Continue Pre-Processing Stage S4 | 25 | 2021-01-29 10:00 | 2021-01-30 11:00 | FAROOQ SYED | SYFAROOQ@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97239 |  |  | * |  | 2021-01-29 10:00 | 2021-01-30 11:00 | DEV - INFRA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97306 | WBS.2.1.1.5.3.3.138 | N | N | Planned | Preparation - Backup before start Sum tool - MDG | 3 | 2021-01-28 18:00 | 2021-01-28 21:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-28 18:00 | 2021-01-28 18:00 | 2021-01-28 21:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97305 | WBS.2.1.1.5.3.3.137 | N | N | Planned | Preparation - Pre Upgrade TRs MDG | 1 | 2021-01-28 21:00 | 2021-01-28 22:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97306 |  |  | * |  | 2021-01-28 21:00 | 2021-01-28 22:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97304 | WBS.2.1.1.5.3.3.136 | N | N | Planned | Preparation - Validate Pre Upgrade TRs MDG | 1 | 2021-01-28 22:00 | 2021-01-28 23:00 | CHIRAG GUPTA | CHIRGUPTA@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97305 |  |  | * |  | 2021-01-28 22:00 | 2021-01-28 23:00 | DEV | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97744 | WBS.2.1.1.5.3.3.199 | N | N | Planned | Preparation - Uninstall CIDEON Add on's in MDG | 1 | 2021-01-28 23:00 | 2021-01-29 | CHIRAG GUPTA | CHIRGUPTA@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97304 |  |  | * |  | 2021-01-28 23:00 | 2021-01-29 | DEV | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97303 | WBS.2.1.1.5.3.3.135 | N | N | Planned | Preparation - Extract SUM tool and kick start Application Upgrade - MDG | 3 | 2021-01-29 | 2021-01-29 03:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97304,97744 |  |  | * |  | 2021-01-29 | 2021-01-29 03:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97302 | WBS.2.1.1.5.3.3.134 | N | N | Planned | Pre-Processing - Start Preprocessing stage and monitor for import of SPDD TR - MDG | 8 | 2021-01-29 03:00 | 2021-01-29 11:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97303 |  |  | * |  | 2021-01-29 03:00 | 2021-01-29 11:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97301 | WBS.2.1.1.5.3.3.133 | N | N | Planned | Pre-Processing - Validate SPDD TR and SPDD transaction - MDG | 2 | 2021-01-29 11:00 | 2021-01-29 13:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97302 |  |  | * |  | 2021-01-29 11:00 | 2021-01-29 13:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97300 | WBS.2.1.1.5.3.3.132 | N | N | Planned | Pre-Processing - Continue Pre-Processing Stage MDG | 25 | 2021-01-29 13:00 | 2021-01-30 14:00 | SHARATH RENIKUNTA | SRENIKUNTA@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97301 |  |  | * |  | 2021-01-29 13:00 | 2021-01-30 14:00 | DEV - INFRA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97299 | WBS.2.1.1.5.3.3.131 | N | N | Planned | Preparation - Backup before start Sum tool - GW | 3 | 2021-01-28 18:00 | 2021-01-28 21:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-28 18:00 | 2021-01-28 18:00 | 2021-01-28 21:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97298 | WBS.2.1.1.5.3.3.130 | N | N | Planned | Preparation - Pre Upgrade TRs GW | 1 | 2021-01-28 21:00 | 2021-01-28 22:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97299 |  |  | * |  | 2021-01-28 21:00 | 2021-01-28 22:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97297 | WBS.2.1.1.5.3.3.129 | N | N | Planned | Preparation - Validate Pre Upgrade TRs GW | 1 | 2021-01-28 22:00 | 2021-01-28 23:00 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97298 |  |  | * |  | 2021-01-28 22:00 | 2021-01-28 23:00 | DEV | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97296 | WBS.2.1.1.5.3.3.128 | N | N | Planned | Preparation - Extract SUM tool and kick start Application Upgrade - GW | 1 | 2021-01-28 23:00 | 2021-01-29 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97297 |  |  | * |  | 2021-01-28 23:00 | 2021-01-29 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97295 | WBS.2.1.1.5.3.3.127 | N | N | Planned | Pre-Processing - Start Preprocessing stage and monitor for import of SPDD TR - GW | 8 | 2021-01-29 | 2021-01-29 08:00 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97296 |  |  | * |  | 2021-01-29 | 2021-01-29 08:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97294 | WBS.2.1.1.5.3.3.126 | N | N | Planned | Pre-Processing - Validate SPDD TR and SPDD transaction - GW | 2 | 2021-01-29 08:00 | 2021-01-29 10:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97295 |  |  | * |  | 2021-01-29 08:00 | 2021-01-29 10:00 | DEV - INFRA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97293 | WBS.2.1.1.5.3.3.125 | N | N | Planned | Pre-Processing - Continue Pre-Processing Stage GW | 25 | 2021-01-29 10:00 | 2021-01-30 11:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 97294 |  |  | * |  | 2021-01-29 10:00 | 2021-01-30 11:00 | DEV - INFRA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97292 | WBS.2.1.1.5.3.3.124 | N | N | Planned | Preparation - Backup before start Sum tool - PO | 3 | 2021-01-28 18:00 | 2021-01-28 21:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV |  |  |  |  | 2021-01-28 18:00 | 2021-01-28 18:00 | 2021-01-28 21:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97291 | WBS.2.1.1.5.3.3.123 | N | N | Planned | Preparation - Extract SUM tool and kick start Application Upgrade- PO | 1 | 2021-01-28 21:00 | 2021-01-28 22:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97292 |  |  | * |  | 2021-01-28 21:00 | 2021-01-28 22:00 | DEV - INFRA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97290 | WBS.2.1.1.5.3.3.122 | N | N | Planned | Pre-Processing - Start Preprocessing stage PO | 33 | 2021-01-28 22:00 | 2021-01-30 07:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97291 |  |  | * |  | 2021-01-28 22:00 | 2021-01-30 07:00 | DEV - INFRA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90177 | WBS.2.1.2 | N | N |  | Ramp Down ¦ Security and Controls | 174.5 | 2021-01-17 22:15 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-30 18:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90952 | WBS.2.1.2.1 | N | N |  | Ramp Down ¦ Security and Controls - Configuration | 174.5 | 2021-01-17 22:15 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-30 18:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91341 | WBS.2.1.2.1.1 | N | N |  | Ramp Down ¦ Security and Controls - Configuration - SAP Systems | 174.5 | 2021-01-17 22:15 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-30 18:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90947 | WBS.2.1.2.1.1.1 | N | N |  | Ramp Down ¦ Security and Controls Configuration - SAP GRC | 8.25 | 2021-01-18 06:15 | 2021-01-18 14:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 14:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4422 | WBS.2.1.2.1.1.1.1 | N | N | Planned | Open QA Clients (GRC) For User Provisioning | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4492 | WBS.2.1.2.1.1.1.2 | N | N | Planned | Confirm Mitigating Controls Are Available In GRC AC | 8 | 2021-01-18 06:15 | 2021-01-18 14:15 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;JEFF GRICE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JEFFREY.GRICE@GAPAC.COM | SECURITY | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 14:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4501 | WBS.2.1.2.1.1.1.3 | N | N | Planned | Create Test IDs (Via Script For MC) | 8 | 2021-01-18 06:30 | 2021-01-18 14:30 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4500 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 14:30 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90948 | WBS.2.1.2.1.1.2 | N | N |  | Ramp Down ¦ Security and Controls Configuration - SAP PO | 2 | 2021-01-17 22:15 | 2021-01-18 06:15 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-18 06:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7869 | WBS.2.1.2.1.1.2.1 | N | N | Planned | Setup Access To Process Orchestration | 1 | 2021-01-17 22:15 | 2021-01-17 23:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 8813 |  |  | * |  | 2021-01-17 22:15 | 2021-01-17 23:15 | SECURITY | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
8811 | WBS.2.1.2.1.1.2.2 | N | N | Planned | Create 3rd-Party Application Users In SAP PO And Pass It On To Middleware Team | 1 | 2021-01-17 23:15 | 2021-01-18 06:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 8812 |  |  | * |  | 2021-01-17 23:15 | 2021-01-18 06:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90950 | WBS.2.1.2.1.1.4 | N | N |  | Ramp Down ¦ Security and Controls Configuration - S/4 HANA | 174.5 | 2021-01-17 22:15 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-17 22:15 | 2021-01-30 18:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
4500 | WBS.2.1.2.1.1.4.1 | N | N | Planned | Provide Go-Live User Assignments To Security Team | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JENNIFER EPSTEIN | jennifer.epstein@gapac.com | MELISSA COLLIER;MOHAMMED ABDULLAHI;SAI TEAM;OCM TEAM | MELISSA.COLLIER@GAPAC.COM;MABDULLAHI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jennifer.epstein@gapac.com | OCM | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | OCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93398 | WBS.2.1.2.1.1.4.2 | N | N | Planned | Prod Task - Provide list of Role Approvers for New roles | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | GREG CAPPS | GREG.CAPPS@GAPAC.COM | SOUMYA PANDA;SAI TEAM;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93399 | WBS.2.1.2.1.1.4.3 | N | N | Planned | Prod Task - Setup new Managers in GRC that do not exist | 3 | 2021-01-18 06:30 | 2021-01-18 09:30 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 4500 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 09:30 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93400 | WBS.2.1.2.1.1.4.4 | N | N | Planned | Create users from OCM Role Mapping file that do not currently exist in the system | 8 | 2021-01-18 06:30 | 2021-01-18 14:30 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 4500 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 14:30 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4423 | WBS.2.1.2.1.1.4.5 | N | N | Planned | Obtain Cutover Access Cutover Listing From SAI Team | 0.5 | 2021-01-17 22:15 | 2021-01-17 22:45 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 8813,93067 |  |  | * |  | 2021-01-17 22:15 | 2021-01-17 22:45 | SECURITY | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
4424 | WBS.2.1.2.1.1.4.6 | N | N | Planned | Provide Cutover Access To Cutover Task Owners | 8 | 2021-01-17 22:15 | 2021-01-18 06:15 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SAI TEAM;GREG CAPPS;SOUMYA PANDA;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 8813,93067 |  |  | * |  | 2021-01-17 22:15 | 2021-01-18 06:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7867 | WBS.2.1.2.1.1.4.7 | N | N | Planned | Provide Access To Basis, Dev, UI/UX Team | 2 | 2021-01-17 22:15 | 2021-01-18 00:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;MOHAMMED ABDULLAHI | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;MABDULLAHI@DELOITTE.COM | SECURITY | 8813,93067 |  |  | * |  | 2021-01-17 22:15 | 2021-01-18 00:15 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8817 | WBS.2.1.2.1.1.4.8 | N | N | Planned | Provision RFC Users And System Users As Received By Basis Team | 2 | 2021-01-18 07:45 | 2021-01-18 09:45 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4086,8812 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 09:45 | SECURITY | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92750 | WBS.2.1.2.1.1.4.9 | N | N | Planned | Cutover team to provide list of users needing Hypercare Access | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | SAI | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
7874 | WBS.2.1.2.1.1.4.10 | N | N | Planned | Setup Project Team Members for Hypercare With Approved User Listing Provided By SAI Team | 8.5 | 2021-01-28 07:15 | 2021-01-28 15:45 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;GREG CAPPS;SAI TEAM;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 92750,10853 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 15:45 | SECURITY | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
9993 | WBS.2.1.2.1.1.4.11 | N | N | Planned | Identify users that will perform golden transactions and provide to security team | 2 | 2021-01-28 15:45 | 2021-01-28 17:45 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 7874 |  |  | * |  | 2021-01-28 15:45 | 2021-01-28 17:45 | SAI | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
9992 | WBS.2.1.2.1.1.4.12 | N | N | Planned | Create users for Golden Transactions | 4 | 2021-01-28 17:45 | 2021-01-28 21:45 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SAI TEAM;GREG CAPPS;SOUMYA PANDA;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 9993 |  |  | * |  | 2021-01-28 17:45 | 2021-01-28 21:45 | SECURITY | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92452 | WBS.2.1.2.1.1.4.13 | N | N | Planned | Cutover team to provide list of users needing access to validate transports and other functions | 0.25 | 2021-01-30 18:15 | 2021-01-30 18:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:30 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92676 | WBS.2.1.2.1.1.4.14 | N | N | Planned | Provide User List for Users not to be Locked DURING Transport move | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | SAI | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97121 | WBS.2.1.2.1.1.4.15 | N | N | Planned | MC Task - Replicate AC MRS BP users that exist in S4P table IHPA-OBJNR = IF* into Quality | 2 | 2021-01-18 14:30 | 2021-01-18 16:30 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | CHAD FLAGG;SAI TEAM;SEC TEAM | CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 16:30 | SECURITY | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3949 | WBS.2.1.3 | N | N |  | Ramp Down ¦ Conversion Prep Activities | 85.75 | 2021-01-17 21:45 | 2021-01-25 09:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-25 09:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91342 | WBS.2.1.3.1 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions and Staging | 85.75 | 2021-01-17 21:45 | 2021-01-25 09:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-25 09:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90162 | WBS.2.1.3.1.1 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions | 85.75 | 2021-01-17 21:45 | 2021-01-25 09:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-25 09:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91343 | WBS.2.1.3.1.1.1 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions - AS8 Extracts | 6 | 2021-01-18 01:00 | 2021-01-18 07:00 | [8 empty] | * |  | 2021-01-18 01:00 | 2021-01-18 07:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3967 | WBS.2.1.3.1.1.1.1 | N | N | Planned | Execute Extracts from Maintelligence for master data and non open item transaction data conversions | 2 | 2021-01-18 01:00 | 2021-01-18 03:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-18 01:00 | 2021-01-18 03:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3968 | WBS.2.1.3.1.1.1.2 | N | N | Planned | Execute Extracts from AS8 (PTM) for master data and non open item transaction data conversions | 4 | 2021-01-18 01:00 | 2021-01-18 05:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-18 01:00 | 2021-01-18 05:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3966 | WBS.2.1.3.1.1.1.3 | N | N | Planned | Execute Extracts from AS8 for master data and non open item transaction data conversions | 6 | 2021-01-18 01:00 | 2021-01-18 07:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-18 01:00 | 2021-01-18 07:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94410 | WBS.2.1.3.1.1.2 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions - MP2 Extracts | 6 | 2021-01-17 21:45 | 2021-01-18 07:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 07:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94411 | WBS.2.1.3.1.1.2.1 | N | N | Planned | Execute Extracts from MP2 for master data and non open item transaction data conversions | 6 | 2021-01-17 21:45 | 2021-01-18 07:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;AMY EL-BASSIONI;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-18 07:00 | DATA | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91346 | WBS.2.1.3.1.1.3 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions - ECC Extracts | 5 | 2021-01-18 01:00 | 2021-01-18 06:00 | [8 empty] | * |  | 2021-01-18 01:00 | 2021-01-18 06:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3964 | WBS.2.1.3.1.1.3.1 | N | N | Planned | Execute Extracts from ECC for master data - confirm completed | 5 | 2021-01-18 01:00 | 2021-01-18 06:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-18 01:00 | 2021-01-18 06:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91345 | WBS.2.1.3.1.1.4 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions - AC | 82.5 | 2021-01-18 07:00 | 2021-01-25 09:30 | [8 empty] | * |  | 2021-01-18 07:00 | 2021-01-25 09:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94539 | WBS.2.1.3.1.1.4.1 | N | N | Planned | Receive Measuring Point Creation File from Facilities | 1 | 2021-01-25 06:30 | 2021-01-25 07:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | AC TEAM;SAI TEAM;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067,10845,92566 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 07:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94540 | WBS.2.1.3.1.1.4.2 | N | N | Planned | Validate/Parse measuring point creation file and enter into load sheet | 1 | 2021-01-25 07:30 | 2021-01-25 08:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | AC TEAM;SAI TEAM;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 94539,10845 |  |  | * |  | 2021-01-25 07:30 | 2021-01-25 08:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94541 | WBS.2.1.3.1.1.4.3 | N | N | Planned | Load measuring point creation file | 1 | 2021-01-25 08:30 | 2021-01-25 09:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | AC TEAM;SAI TEAM;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 94540,5451,92777,10845 |  |  | * |  | 2021-01-25 08:30 | 2021-01-25 09:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90491 | WBS.2.1.3.1.1.4.4 | N | N | Planned | Populate “GPD_OLE_LOCATION” table prior to data extracts | 12 | 2021-01-18 07:00 | 2021-01-18 19:00 | BRENNEN FRISQUE | BRENNEN.FRISQUE@GAPAC.COM | KELLY STRASSBURGER;JASON RAMSEY;SAI TEAM;AC TEAM | KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 3966,94411 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 19:00 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3950 | WBS.2.1.3.1.1.5 | N | N |  | Ramp Down ¦ Conversion Prep Activities - Data Extractions and Staging - EWM | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3953 | WBS.2.1.3.1.1.5.1 | N | N | Planned | PTH - Extract and Prepare Production Supply Area (PSA) upload file | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94424 | WBS.2.1.3.1.1.5.3 | N | N | Planned | HBG - Extract and Prepare Production Supply Area (PSA) upload file | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96557 | WBS.2.1.3.1.1.5.11 | N | N | Planned | BG - Extract and Prepare Production Supply Area (PSA) upload file | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;SAI TEAM;LYNN MCMURDO;DEAN PIPER;EWM TEAM | JORDAN.BUNDY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3954 | WBS.2.1.3.1.1.5.5 | N | N | Planned | PTH - Validate and business sign off for Production Supply Area (PSA) upload file- SCM MDM | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 3953 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94429 | WBS.2.1.3.1.1.5.7 | N | N | Planned | HBG - Validate and business sign off for Production Supply Area (PSA) upload file- SCM MDM | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94424 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96558 | WBS.2.1.3.1.1.5.12 | N | N | Planned | BG - Validate and business sign off for Production Supply Area (PSA) upload file- SCM MDM | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;SAI TEAM;LYNN MCMURDO;DEAN PIPER;EWM TEAM | JORDAN.BUNDY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96557 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3971 | WBS.2.1.3.1.1.6 | N | N |  | Ramp Down ¦ Data Extractions and Staging - Manual Data Prep | 3 | 2021-01-21 15:00 | 2021-01-21 18:00 | [8 empty] | * |  | 2021-01-21 15:00 | 2021-01-21 18:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92630 | WBS.2.1.3.1.1.6.1 | N | N | Planned | Add Overhead groups to finished goods for deployment live sites & confirm Val class & material type updates for BOMs | 3 | 2021-01-21 15:00 | 2021-01-21 18:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | DONNA COOPER;DENISE ROBINSON;SHANKAR RAMNARAYANAN;SAI TEAM;LINDSAY SAVAGE;KRISTEN DERINGER;LINDA GIBSON;NOEL CLARK;DATA ETL TEAM | DCOOPER@GAPAC.COM;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;KLDERING@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;NOEL.CLARK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 4424,92651 |  |  | * |  | 2021-01-21 15:00 | 2021-01-21 18:00 | DATA | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
4057 | WBS.2.1.3.1.1.7 | N | N |  | Ramp Down ¦ Data Extractions and Staging - Provide Finalized X-Ref Values | 6 | 2021-01-17 21:45 | 2021-01-18 09:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 09:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4063 | WBS.2.1.3.1.1.7.1 | N | N | Planned | Update delta values and upload X-ref file(s) to SharePoint for data conversions - AS8/MP2 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;JASON RAMSEY;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
80788 | WBS.2.1.3.1.1.7.2 | N | N | Planned | Update delta values and upload X-ref file(s) to SharePoint for data conversions- PTP | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;DOROTHY RUSSELL;PTP TEAM;CASEY HERMANSEN;BRUCE KIRKLEWSKI;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89679 | WBS.2.1.3.1.1.7.3 | N | N | Planned | Provide Vendor cross reference | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | DA JIANG | DA.JIANG@GAPAC.COM | JON LUKE DAVILA;SHANKAR RAMNARAYANAN;SAI TEAM;JON PINYON;DATA ETL TEAM;DAVID MILLER;DENISE ROBINSON | JONLUKE.DAVILA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DAVID.MILLER@GAPAC.COM;DOROBINS@GAPAC.COM | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9125 | WBS.2.1.3.1.1.7.4 | N | N | Planned | MDG_C0098 - Update any delta values and upload X-ref file(s) to SharePoint for Procured materials conversion | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89674 | WBS.2.1.3.1.1.7.5 | N | N | Planned | Update Material cross reference and In-Scope tables | 1 | 2021-01-18 08:45 | 2021-01-18 09:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 36501,9125 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4512 | WBS.2.1.4 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration | 180.25 | 2021-01-17 21:45 | 2021-01-31 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-31 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
4526 | WBS.2.1.4.1 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems | 180.25 | 2021-01-17 21:45 | 2021-01-31 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-31 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
91348 | WBS.2.1.4.1.1 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - S/4HANA | 173 | 2021-01-18 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
4641 | WBS.2.1.4.1.1.1 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - S/4HANA - AC | 22 | 2021-01-18 07:00 | 2021-01-19 13:00 | [8 empty] | * |  | 2021-01-18 07:00 | 2021-01-19 13:00 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
4648 | WBS.2.1.4.1.1.1.1 | N | N | Planned | Custom Table Population - ZITR_UNOADPNT | 2 | 2021-01-18 07:00 | 2021-01-18 09:00 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | KELLY STRASSBURGER;SAI TEAM;JASON RAMSEY;AC TEAM | KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 09:00 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9389 | WBS.2.1.4.1.1.1.2 | N | N | Planned | Custom Table Population - ZTITR_PLANTS_FAC | 0.25 | 2021-01-18 07:00 | 2021-01-18 07:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JEY MURUGESH;SAI TEAM;JASON RAMSEY;AC TEAM | ERIC.REINDL@GAPAC.COM;JMURUGESH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:15 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9391 | WBS.2.1.4.1.1.1.3 | N | N | Planned | Custom Table Population - ZTITR_E0120_SHFT | 1 | 2021-01-18 09:30 | 2021-01-18 10:30 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | KELLY STRASSBURGER;SAI TEAM;JASON RAMSEY;AC TEAM | KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084,5783 |  |  | * |  | 2021-01-18 09:30 | 2021-01-18 10:30 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9390 | WBS.2.1.4.1.1.1.4 | N | N | Planned | Custom Table Population - ZTITR_CSTAPRV_WO | 2.5 | 2021-01-18 07:00 | 2021-01-18 09:30 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | KELLY STRASSBURGER;SAI TEAM;JASON RAMSEY;AC TEAM | KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 09:30 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4649 | WBS.2.1.4.1.1.1.5 | N | N | Planned | Validate BRF+ Entries For D4 Facilities | 0.75 | 2021-01-18 07:00 | 2021-01-18 07:45 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;ERIC REINDL;JASON RAMSEY;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:45 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92091 | WBS.2.1.4.1.1.1.6 | N | N | Planned | Custom Table Population - ZITR_BUDGTOL & ZITR_E0371_COST | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | KELLY STRASSBURGER;SAI TEAM;JASON RAMSEY;AC TEAM | KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92240 | WBS.2.1.4.1.1.1.7 | N | N | Planned | Review / update document types ZMAINTAIN_DOCTYPES | 1 | 2021-01-19 12:00 | 2021-01-19 13:00 | PRASANNA KANNAN | PK@DELOITTE.COM | AC TEAM;JASON RAMSEY;SAI TEAM | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5408 |  |  | * |  | 2021-01-19 12:00 | 2021-01-19 13:00 | AC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92239 | WBS.2.1.4.1.1.1.8 | N | N | Planned | Review / update standard text templates for notification based on notif type t code SO10 | 1 | 2021-01-19 12:00 | 2021-01-19 13:00 | PRASANNA KANNAN | PK@DELOITTE.COM | AC TEAM;JASON RAMSEY;SAI TEAM | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5408 |  |  | * |  | 2021-01-19 12:00 | 2021-01-19 13:00 | AC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92242 | WBS.2.1.4.1.1.1.9 | N | N | Planned | Review / update storage locations ZMO_SLOC | 1 | 2021-01-18 18:15 | 2021-01-18 19:15 | PRASANNA KANNAN | PK@DELOITTE.COM | AC TEAM;JASON RAMSEY;SAI TEAM | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 4573,5218 |  |  | * |  | 2021-01-18 18:15 | 2021-01-18 19:15 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4527 | WBS.2.1.4.1.1.2 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - S/4HANA - EWM | 173 | 2021-01-18 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
4667 | WBS.2.1.4.1.1.2.1 | N | N | Planned | PTH - Create Production Supply Areas in S/4HANA | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 3954 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94432 | WBS.2.1.4.1.1.2.3 | N | N | Planned | HBG - Create Production Supply Areas in S/4HANA | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94429 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96559 | WBS.2.1.4.1.1.2.36 | N | N | Planned | BG - Create Production Supply Areas in S/4HANA | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96558 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8878 | WBS.2.1.4.1.1.2.5 | N | N | Planned | PTH - Replicate PSA from S/4HANA to EWM | 0.25 | 2021-01-18 09:00 | 2021-01-18 09:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4667 |  |  | * |  | 2021-01-18 09:00 | 2021-01-18 09:17 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94435 | WBS.2.1.4.1.1.2.7 | N | N | Planned | HBG - replicate PSA from S/4HANA to EWM | 0.25 | 2021-01-18 09:00 | 2021-01-18 09:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94432 |  |  | * |  | 2021-01-18 09:00 | 2021-01-18 09:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96560 | WBS.2.1.4.1.1.2.37 | N | N | Planned | BG - Replicate PSA from S/4HANA to EWM | 0.25 | 2021-01-18 09:00 | 2021-01-18 09:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96559 |  |  | * |  | 2021-01-18 09:00 | 2021-01-18 09:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93156 | WBS.2.1.4.1.1.2.9 | N | N | Planned | PTH - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93155 | WBS.2.1.4.1.1.2.10 | N | N | Planned | PTH - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 93400,4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95595 | WBS.2.1.4.1.1.2.11 | N | N | Planned | PTH - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) - MRO | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;AVINASH TALREJA;LEM LANCASTER;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AVTALREJA@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97192 | WBS.2.1.4.1.1.2.42 | N | N | Planned | PTH - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) - for MRO | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97193 | WBS.2.1.4.1.1.2.43 | N | N | Planned | BG - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) - MRO | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | BEAU EARLS;SAI TEAM;DEAN PIPER;LYNN MCMURDO;EWM TEAM;DOUG CARANGELLO;Mark Bernard | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;*;MARK.BERNARD@GAPAC.COM | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95594 | WBS.2.1.4.1.1.2.12 | N | N | Planned | PTH - Manual Config Steps (Maintain Users) - MRO | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | CHARLES DUPRE | charles.dupre@gapac.com | SAI TEAM;EWM TEAM;AVINASH TALREJA;LEM LANCASTER;NAWIETA HAMILTON-MATHIS;PAUL CARTER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AVTALREJA@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 93400,4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93154 | WBS.2.1.4.1.1.2.13 | N | N | Planned | PTH - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4573 | WBS.2.1.4.1.1.2.14 | N | N | Planned | Manual Config Steps (Open Client Configurations: Define Business System; Map WHS numbers - ERP to EWM; Map Storage Locations - ERP to EWM; Maintain Business System Group/Supply Chain Unit; Assign Logical System and Queue Type | 1.5 | 2021-01-18 07:00 | 2021-01-18 08:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95320 | WBS.2.1.4.1.1.2.15 | N | N | Planned | Run Program /scmb/check_scu to verify inconsistencies and make corrections for sites being deployed | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4573 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 09:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4579 | WBS.2.1.4.1.1.2.16 | N | N | Planned | Manual Config Steps (Activate Application Log For EWM applications) - EWM | 0.5 | 2021-01-18 07:00 | 2021-01-18 07:30 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4575 | WBS.2.1.4.1.1.2.18 | N | N | Planned | Manual Config Steps (Maintain Access Sequence For Staging Areas and Door Determination) - EWM | 1.5 | 2021-01-18 07:00 | 2021-01-18 08:30 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4560 | WBS.2.1.4.1.1.2.17 | N | N | Planned | Maintain Number Ranges (Warehouse Orders, Warehouse Tasks, Waves, Physical Inventory, Labor, TU, Vehicle, S&R activities) - EWM | 0.25 | 2021-01-18 07:00 | 2021-01-18 07:15 | AVINASH TALREJA | AVTALREJA@DELOITTE.COM | VINOD MADHANU;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;EWM TEAM | VMADHANU@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4572 | WBS.2.1.4.1.1.2.19 | N | N | Planned | PTH - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 95542,95536 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95228 | WBS.2.1.4.1.1.2.20 | N | N | Planned | Confirm delivery interim IDOCs in S4 are current – none in error status | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | EWM TEAM;SAI TEAM | ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95587 | WBS.2.1.4.1.1.2.21 | N | N | Planned | Update Default Shipment Type to ZLNG for Load and Go Shipments | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4572,36501 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | EWM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95586 | WBS.2.1.4.1.1.2.22 | N | N | Planned | Maintain Condition Records to Print BOL and Shipping Manifest for ZLNG | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4572,36501 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | EWM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95230 | WBS.2.1.4.1.1.2.23 | N | N | Planned | Confirm mirror shipments deleted in S4 | 2 | 2021-01-30 16:45 | 2021-01-30 18:45 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 90694,90693 |  |  | * |  | 2021-01-30 16:45 | 2021-01-30 18:45 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95231 | WBS.2.1.4.1.1.2.24 | N | N | Planned | Confirm mirror deliveries deleted in S4 | 1 | 2021-01-30 06:15 | 2021-01-30 07:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 90697 |  |  | * |  | 2021-01-29 20:15 | 2021-01-29 21:15 | EWM | CROSS | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95232 | WBS.2.1.4.1.1.2.25 | N | N | Planned | Confirm mirror shipments deleted in S4 - 2nd round | 0.25 | 2021-01-30 17:00 | 2021-01-30 17:15 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 92322 |  |  | * |  | 2021-01-30 17:00 | 2021-01-30 17:15 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95233 | WBS.2.1.4.1.1.2.26 | N | N | Planned | Confirm mirror deliveries deleted in S4 - 2nd round | 0.25 | 2021-01-30 19:00 | 2021-01-30 19:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 92317 |  |  | * |  | 2021-01-30 19:00 | 2021-01-30 19:15 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95542 | WBS.2.1.4.1.1.2.27 | N | N | Planned | PTH - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | CJ KAUTH | christopher.kauth@gapac.com | ROBBIE GARNER;JAMES COWELL;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Robbie.Garner2@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96561 | WBS.2.1.4.1.1.2.38 | N | N | Planned | BG - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | KELLY LEWIS | kelly.lewis@gapac.com | SAMUEL CHAMBERS;CRAIG HURST;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;EWM TEAM;DEAN PIPER;LYNN MCMURDO | SAMUEL.CHAMBERS@GAPAC.COM;CRAIG.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95539 | WBS.2.1.4.1.1.2.30 | N | N | Planned | HBG - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95538 | WBS.2.1.4.1.1.2.31 | N | N | Planned | SCH - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96697 | WBS.2.1.4.1.1.2.40 | N | N | Planned | RNC - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;LOCKLIN HINTON;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;LOCKLIN.HINTON@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96698 | WBS.2.1.4.1.1.2.41 | N | N | Planned | RVG - Maintain printers for Packing slips/HU Habel/Load plan/Forms( BOL, Manifest, Pick list, FEDEX/UPS Label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | SAI TEAM;EWM TEAM;JULI LEWIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JULI.LEWIS@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95536 | WBS.2.1.4.1.1.2.32 | N | N | Planned | PTH - Default printer for MRO labels ( Material label/pick HU label/serial number label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95534 | WBS.2.1.4.1.1.2.34 | N | N | Planned | HBG - Default printer for MRO labels ( Material label/pick HU label/serial number label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96562 | WBS.2.1.4.1.1.2.39 | N | N | Planned | BG - Default printer for MRO labels ( Material label/pick HU label/serial number label) | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | GERONIMO ROMERO | GERONIMO.ROMERO@GAPAC.COM | Jeron Wall;BRANDY MEREDITH;SAI TEAM | Jeron.wall@gapac.com;Brandy.Meredith@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 10531 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4635 | WBS.2.1.4.1.1.3 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - S/4HANA - PTP | 8.25 | 2021-01-18 06:45 | 2021-01-18 15:00 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-18 15:00 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92509 | WBS.2.1.4.1.1.3.1 | N | N | Planned | PTH MRO - Manual Config Steps (Maintain Resources; Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94439 | WBS.2.1.4.1.1.3.3 | N | N | Planned | HBG - MRO - Manual Config Steps (Maintain Resources; Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96563 | WBS.2.1.4.1.1.3.8 | N | N | Planned | BG - MRO - Manual Config Steps (Maintain Resources; Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | ROBBIE ISBELL;SAI TEAM;DEAN PIPER;LYNN MCMURDO;EWM TEAM;DOUG CARANGELLO;Mark Bernard | Daniel.Isbell@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;*;MARK.BERNARD@GAPAC.COM | EWM | 4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9919 | WBS.2.1.4.1.1.3.5 | N | N | Planned | Validate Supervisor Data for PR and PO Approvals | 2 | 2021-01-18 06:45 | 2021-01-18 08:45 | MASON DRAKE | MASON.DRAKE@GAPAC.COM | SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 08:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9920 | WBS.2.1.4.1.1.3.6 | N | N | Planned | Populate PR Approvals Table | 1 | 2021-01-18 08:45 | 2021-01-18 09:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | DOROTHY RUSSELL;NITIN GUPTA;CASEY HERMANSEN;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | DOROTHY.RUSSELL@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 9919,4084 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:45 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9921 | WBS.2.1.4.1.1.3.7 | N | N | Planned | Populate PO Approvals Table | 1 | 2021-01-18 08:45 | 2021-01-18 09:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | DOROTHY RUSSELL;NITIN GUPTA;CASEY HERMANSEN;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | DOROTHY.RUSSELL@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 9919,4084 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:45 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4595 | WBS.2.1.4.1.1.4 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - S/4HANA - RTR | 4.5 | 2021-01-18 06:15 | 2021-01-18 10:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 10:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95648 | WBS.2.1.4.1.1.4.1 | N | N | Planned | Stop batch jobs for mark, release and MF30 (costs rolls) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | NNEKA MBA | NEMBA@GAPAC.COM | SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | BATCH | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95649 | WBS.2.1.4.1.1.4.2 | N | N | Planned | Confirm, Create new variant for mark and release (for sites) | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95650 | WBS.2.1.4.1.1.4.3 | N | N | Planned | Validate the new variant for mark and release | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95649 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | RTR - PC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4624 | WBS.2.1.4.1.1.4.4 | N | N | Planned | Open CO Period (OKP1) | 0.25 | 2021-01-18 07:00 | 2021-01-18 07:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4628 | WBS.2.1.4.1.1.4.5 | N | N | Planned | Identify list of Batch Jobs along with variants that need to updated/included for D4 | 0.5 | 2021-01-18 10:15 | 2021-01-18 10:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90775 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 10:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9865 | WBS.2.1.4.1.1.4.6 | N | N | Planned | Verify BRF+ Entries - RTR - PC | 2 | 2021-01-18 07:00 | 2021-01-18 09:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7823 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 09:00 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4634 | WBS.2.1.4.1.1.4.7 | N | N | Planned | Update sets used in PC Substitutions to reflect D4 changes | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4625 | WBS.2.1.4.1.1.4.8 | N | N | Planned | Open FI Posting Periods (OB52) | 0.25 | 2021-01-18 07:15 | 2021-01-18 07:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4624 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:30 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4629 | WBS.2.1.4.1.1.4.9 | N | N | Planned | Confirm Variants Related To Batch Jobs Are Correct | 0.25 | 2021-01-18 07:00 | 2021-01-18 07:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
68330 | WBS.2.1.4.1.1.4.10 | N | N | Planned | Product Costing Job variant setup - Plants -1034, 1376, 1459 ( Std cost setup for PC & Group) | 2 | 2021-01-18 08:00 | 2021-01-18 10:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4634 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 10:00 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9866 | WBS.2.1.4.1.1.4.11 | N | N | Planned | Verify BRF+ Entries - RTR - GL | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90915 | WBS.2.1.4.1.2 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - MDG | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90180 | WBS.2.1.4.1.2.1 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - MDG - Data | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
9401 | WBS.2.1.4.1.2.1.1 | N | N | Planned | Update / Create New SAP Requirement Profile | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | GAURAV BHATIA;SAI TEAM;DENISE ROBINSON;AMY EL-BASSIONI;AC TEAM | GBHATIA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | AC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90992 | WBS.2.1.4.1.3 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - IBP | 23 | 2021-01-18 06:15 | 2021-01-19 13:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-19 13:15 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90993 | WBS.2.1.4.1.3.1 | N | N |  | Ramp Down ¦ Pre-Conversion Configuration - SAP Systems - IBP - SCM | 23 | 2021-01-18 06:15 | 2021-01-19 13:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-19 13:15 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92099 | WBS.2.1.4.1.3.1.2 | N | N | Planned | Create New Class for Work Center Classification for Dual Stream Line (Alt Resource) for All Sites | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91824 | WBS.2.1.4.1.3.1.3 | N | N | Planned | Replace current standard value key on Workcenters from the routing file (which are already in the system) with ZGP0 in plants 1101, 1357, 1462, 1503 | 1 | 2021-01-18 08:15 | 2021-01-18 09:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92099 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 09:15 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92097 | WBS.2.1.4.1.3.1.4 | N | N | Planned | Replace Current Standard Value Key on Dual Stream Rewinder with SAP4 for all Sites, Change Capacity Planner to RWH, Replace Work Center Processing Formula with SAPC00 | 1 | 2021-01-19 12:15 | 2021-01-19 13:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92099,5177 |  |  | * |  | 2021-01-19 12:15 | 2021-01-19 13:15 | SCM | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82987 | WBS.2.1.4.1.4 | N | N |  | Ramp Down ¦ SCM S/4 HANA Prep for Master Data | 177.75 | 2021-01-18 06:15 | 2021-01-31 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
90182 | WBS.2.1.4.1.4.1 | N | N |  | Ramp Down ¦ SCM S/4 HANA Prep for Master Data Tasks | 177.75 | 2021-01-18 06:15 | 2021-01-31 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
90866 | WBS.2.1.4.1.4.1.1 | N | N | Planned | Download the enhancement framework table contents from QA/PROD S4 | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | SRINIVAS KATA | SKATA@DELOITTE.COM | ARUN GANGADHARAN;SANDEEP THARWANI;RAKESH MAKKAPATI;SUVENDU KUMAR;SAI TEAM;DEV TEAM | ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | DEV | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82958 | WBS.2.1.4.1.4.1.2 | N | N | Planned | Take Back-up for GPPRD in Production- IBP DP | 4 | 2021-01-26 06:15 | 2021-01-26 10:15 | SANJAY JELAJI | SANJAY.JELAJI1@GAPAC.COM | JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;JEFFREY GILLIAM;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;JFGILLIA@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5246,5251,10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 10:15 | SCM | CROSS | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
97766 | WBS.2.1.4.1.4.1.3 | N | N | Planned | Provide Green light for completion of all IBP-HCI jobs | 0.25 | 2021-01-30 23:45 | 2021-01-31 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SCM TEAM;RTR TEAM;BRAD WYMAN;KIM LADZINSKE;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE;SAI TEAM | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SCM | 95633 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
90027 | WBS.2.1.5 | N | N |  | Ramp Down ¦ Multi Team Activities | 183 | 2021-01-17 21:45 | 2021-01-31 02:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-31 02:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95743 | WBS.2.1.5.1 | N | N |  | Ramp Down ¦ Multi Team Activities | 183 | 2021-01-17 21:45 | 2021-01-31 02:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-31 02:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
90242 | WBS.2.1.5.1.1 | N | N |  | Ramp Down ¦ Data Activities | 2 | 2021-01-17 21:45 | 2021-01-17 23:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 23:45 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
91714 | WBS.2.1.5.1.1.1 | N | N |  | Ramp Down ¦ Data Activities | 2 | 2021-01-17 21:45 | 2021-01-17 23:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-17 23:45 |  |  | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90024 | WBS.2.1.5.1.1.1.1 | N | N | Planned | MC Task ¦ Adjust The Address Numbers of Contact Persons of Employee BP's | 2 | 2021-01-17 21:45 | 2021-01-17 23:45 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | PRERNA BODKHE;DATA ETL TEAM;SAI TEAM;AMY EL-BASSIONI;DENISE ROBINSON | PRERNA.BODKHE@KOCHTC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;DOROBINS@GAPAC.COM | DATA | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 23:45 | DATA | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
95203 | WBS.2.1.5.1.2 | N | N |  | Ramp Down ¦ PTP Activities | 175 | 2021-01-18 06:15 | 2021-01-30 21:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 21:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95202 | WBS.2.1.5.1.2.1 | N | N |  | Ramp Down ¦ PTP Activities | 175 | 2021-01-18 06:15 | 2021-01-30 21:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 21:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95201 | WBS.2.1.5.1.2.1.1 | N | N | Planned | Provide list of Ariba P2O - Catalog users (email & name) to Ariba team | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MASON DRAKE | MASON.DRAKE@GAPAC.COM | PTP TEAM;MARK BURGIN;ABBY DREVIK;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MARK.BURGIN@GAPAC.COM;abigail.drevik@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5575 | WBS.2.1.5.1.2.1.2 | N | N | Planned | Load User Consolidated file for Ariba P2O - Catalog | 2 | 2021-01-18 07:15 | 2021-01-18 09:15 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;CHARLES BLUMREICH;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;ABBY DREVIK | MARK.BURGIN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com | PTP | 95201 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 09:15 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97142 | WBS.2.1.5.1.2.1.6 | N | N | Planned | Prod Only - Email Sandy Belk to update S4 facility list on supplier website | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MASON DRAKE | MASON.DRAKE@GAPAC.COM | PTP TEAM;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95382 | WBS.2.1.5.1.2.1.3 | N | N | Planned | Identify known GR/IR imbalances and provide to RTR | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MONICA CUEVAS;PTP TEAM;SAI TEAM;SANDEEP A | MONICA.CUEVAS@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95383 | WBS.2.1.5.1.2.1.4 | N | N | Planned | Communicate intercompany EDI functionality Pos / ASNs / Invoices | 3 | 2021-01-18 10:15 | 2021-01-18 13:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MONICA CUEVAS;PTP TEAM;SRUTHI SRINIVASAN;SAI TEAM;SANDEEP A | MONICA.CUEVAS@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 10846,95382 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 13:15 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95384 | WBS.2.1.5.1.2.1.5 | N | N | Planned | Verify ERS suppliers and send to data team if updates are required | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97450 | WBS.2.1.5.1.2.1.8 | N | N | Planned | Run report of all remaining invoices on hold, not approved, or credits | 1 | 2021-01-30 20:15 | 2021-01-30 21:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | ERIC BARSTOW;PTP TEAM;ALYSSA BAIRD;ANNA FLANAGAN;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ALYSSA.BAIRD@KBSLP.COM;ANNA.FLANAGAN@KBSLP.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 90005 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 21:15 | PTP | PTH,HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97452 | WBS.2.1.5.1.2.1.10 | N | N | Planned | Check the cross reference in the Vendor Master Files for intercompany vendors | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97453 | WBS.2.1.5.1.2.1.11 | N | N | Planned | Provide a list of ASN vendors (Ariba + File based) to EWM team to exclude from IBD batch job | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | MARK BURGIN | MARK.BURGIN@GAPAC.COM | BRIAN STARKE;PTP TEAM;ERIC BARSTOW;JACOB OWENS;YUDI MITRA;SAI TEAM | brian.starke@gapac.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;JACOB.OWENS@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97454 | WBS.2.1.5.1.2.1.12 | N | N | Planned | Provide a report of PO requisitioners and pgroups to facility buyers and EIM team | 2 | 2021-01-27 06:15 | 2021-01-27 08:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | PTP TEAM;MONICA CUEVAS;SRUTHI SRINIVASAN;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 08:15 | PTP | PTH,HBG,BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93896 | WBS.2.1.5.1.2.1.17 | N | N | Planned | HBG - Mill buyers to confirm requisitioner is populated and validate accuracy of P.Group for Service POs | 0.5 | 2021-01-27 08:15 | 2021-01-27 08:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 97454 |  |  | * |  | 2021-01-27 08:15 | 2021-01-27 08:45 | PTP | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
96373 | WBS.2.1.5.1.2.1.18 | N | N | Planned | BG - Mill buyers to confirm requisitioner is populated and validate accuracy of P.Group for Service POs | 0.5 | 2021-01-27 08:15 | 2021-01-27 08:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;Mark Bernard;DOUG CARANGELO;DOUG CARANGELLO | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM;douglas.carangelo@gapac.com;* | Business | 97454 |  |  | * |  | 2021-01-27 08:15 | 2021-01-27 08:45 | PTP | BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97455 | WBS.2.1.5.1.2.1.13 | N | N | Planned | Validate the Pgroup email address and the requisitioner user ID in Ariba from the report provided by | 2 | 2021-01-27 08:15 | 2021-01-27 10:15 | PAM NIX | PSNIX@GAPAC.COM | PTP TEAM;VIRGINIA SILICKIENE;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;VSILICK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 97454 |  |  | * |  | 2021-01-27 08:15 | 2021-01-27 10:15 | EIM | PTH,HBG,BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95624 | WBS.2.1.5.1.3 | N | N |  | Ramp Down ¦ SCM Activities | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | [8 empty] | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95623 | WBS.2.1.5.1.3.1 | N | N |  | Ramp Down ¦ SCM Activities | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | [8 empty] | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95625 | WBS.2.1.5.1.3.1.1 | N | N | Planned | MC Task Only ¦ Reset the number range for production orders | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | SCM TEAM;SAI TEAM;BRAD WYMAN;ANUPAM SHRIVASTAVA | DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 90775 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 | SCM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95634 | WBS.2.1.5.1.4 | N | N |  | Ramp Down ¦ EDI Activities | 3 | 2021-01-30 23:45 | 2021-01-31 02:45 | [8 empty] | * |  | 2021-01-30 23:45 | 2021-01-31 02:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95635 | WBS.2.1.5.1.4.1 | N | N |  | Ramp Down ¦ EDI Activities | 3 | 2021-01-30 23:45 | 2021-01-31 02:45 | [8 empty] | * |  | 2021-01-30 23:45 | 2021-01-31 02:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
83019 | WBS.2.1.5.1.4.1.1 | N | N | Planned | EDI - Raise S4 HANA Down flag after ensuring no active BPs | 1 | 2021-01-30 23:45 | 2021-01-31 00:45 | NAVEEN BODDU | NAVEEN.BODDU@KOCHTC.COM | SAI TEAM;DEV EDI TEAM;GRP_CPBSEDIDEVELOPERS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PATRICK.HERRING@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;IZKHAN@DELOITTE.COM;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM;CYNDI.HOTTENSTINE@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM;NAVEEN.BODDU@KOCHTC.COM;ABRADLEY@GAPAC.COM;GRP_CPBSEDIDEVELOPERS@GAPAC.COM | EDI | 95633 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 00:45 | EDI | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
4355 | WBS.2.1.5.1.4.1.2 | N | N | Planned | EDI - Maintain/Validate Code List for Vendor ASNs | 2 | 2021-01-31 00:45 | 2021-01-31 02:45 | NAVEEN BODDU | NAVEEN.BODDU@KOCHTC.COM | SAI TEAM;DEV EDI TEAM;GRP_CPBSEDIDEVELOPERS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PATRICK.HERRING@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;IZKHAN@DELOITTE.COM;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM;CYNDI.HOTTENSTINE@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM;NAVEEN.BODDU@KOCHTC.COM;ABRADLEY@GAPAC.COM;GRP_CPBSEDIDEVELOPERS@GAPAC.COM | EDI | 83019 |  |  | * |  | 2021-01-31 00:45 | 2021-01-31 02:45 | EDI | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
96991 | WBS.2.1.5.1.8 | N | N |  | Ramp Down ¦ RTR Activities | 172.25 | 2021-01-18 07:00 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 07:00 | 2021-01-30 19:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96990 | WBS.2.1.5.1.8.3 | N | N |  | Ramp Down ¦ RTR Activities | 172.25 | 2021-01-18 07:00 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 07:00 | 2021-01-30 19:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97005 | WBS.2.1.5.1.8.3.1 | N | N | Planned | Confirm all materials are costed and have valid settlement rules, FA, cost center, profit center | 2 | 2021-01-29 16:45 | 2021-01-29 18:45 | TONY SMITH | AJSMITH@GAPAC.COM | KRISHNA RAVI;KRISHNA SINGAREDDY;MANOJ ANNAJI;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;MANOJ.ANNAJI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8868,95612 |  |  | * |  | 2021-01-29 16:45 | 2021-01-29 18:45 | RTR - PC | CROSS | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97004 | WBS.2.1.5.1.8.3.2 | N | N | Planned | Manually update cost collectors that don’t use a routing | 1 | 2021-01-22 19:00 | 2021-01-22 20:00 | TONY SMITH | AJSMITH@GAPAC.COM | JACOB DENNIS;KRISHNA RAVI;KRISHNA SINGAREDDY;MANOJ ANNAJI;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;MANOJ.ANNAJI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 89807 |  |  | * |  | 2021-01-22 19:00 | 2021-01-22 20:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
93862 | WBS.2.1.5.1.8.3.16 | N | N | Planned | HBG - Run Inventory Reports for all materials - Bi report | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | CHRIS ZUMWALT;SAI TEAM;GLEN RICHARDSON;HOLLY KREUER | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GLEN.RICHARDSON@GAPAC.COM;HOLLY.KREUER@GAPAC.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | RTR - PC | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97002 | WBS.2.1.5.1.8.3.4 | N | N | Planned | PTH - Validate the mapping between work centers to cost centers; make sure work centers have the right cost centers | 2 | 2021-01-19 15:15 | 2021-01-19 17:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | TONY SMITH;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92189 |  |  | * |  | 2021-01-19 15:15 | 2021-01-19 17:15 | RTR - PC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97000 | WBS.2.1.5.1.8.3.6 | N | N | Planned | BG - Validate the mapping between work centers to cost centers; make sure work centers have the right cost centers | 2 | 2021-01-19 15:15 | 2021-01-19 17:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | TONY SMITH;RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92189 |  |  | * |  | 2021-01-19 15:15 | 2021-01-19 17:15 | RTR - PC | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96999 | WBS.2.1.5.1.8.3.7 | N | N | Planned | HBG - Validate the mapping between work centers to cost centers; make sure work centers have the right cost centers | 2 | 2021-01-19 15:15 | 2021-01-19 17:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92189 |  |  | * |  | 2021-01-19 15:15 | 2021-01-19 17:15 | RTR - PC | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96997 | WBS.2.1.5.1.8.3.9 | N | N | Planned | PTH - Make sure ZRTR_E0200 table have the right mapping from work center to variance cost center | 2 | 2021-01-21 19:15 | 2021-01-21 21:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | TONY SMITH;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8930 |  |  | * |  | 2021-01-21 19:15 | 2021-01-21 21:15 | RTR - PC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96995 | WBS.2.1.5.1.8.3.11 | N | N | Planned | BG - Make sure ZRTR_E0200 table have the right mapping from work center to variance cost center | 2 | 2021-01-21 19:15 | 2021-01-21 21:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | TONY SMITH;RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8930 |  |  | * |  | 2021-01-21 19:15 | 2021-01-21 21:15 | RTR - PC | BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96994 | WBS.2.1.5.1.8.3.12 | N | N | Planned | HBG - Make sure ZRTR_E0200 table have the right mapping from work center to variance cost center | 2 | 2021-01-21 19:15 | 2021-01-21 21:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8930 |  |  | * |  | 2021-01-21 19:15 | 2021-01-21 21:15 | RTR - PC | HBG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96993 | WBS.2.1.5.1.8.3.13 | N | N | Planned | Validate the overhead group on the material masters | 1 | 2021-01-21 18:00 | 2021-01-21 19:00 | TONY SMITH | AJSMITH@GAPAC.COM | KRISHNA RAVI;KRISHNA SINGAREDDY;MANOJ ANNAJI;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;MANOJ.ANNAJI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92630 |  |  | * |  | 2021-01-21 18:00 | 2021-01-21 19:00 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
97624 | WBS.2.1.5.1.8.3.17 | N | N | Planned | BG - Provide Transfer Prices for Printed Board | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 07:15 | RTR - PC | BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97439 | WBS.2.1.5.1.8.3.15 | N | N | Planned | Load transfer prices for printed board | 0.25 | 2021-01-27 07:15 | 2021-01-27 07:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | FRANK CONSIGLIO;MANOJ KUMAR;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | FRANK.CONSIGLIO@GAPAC.COM;manoj.annaji@gapac.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 10853,97624 |  |  | * |  | 2021-01-27 07:15 | 2021-01-27 07:30 | RTR | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97698 | WBS.2.1.5.1.8.3.21 | N | N | Planned | Confirm Variants Related To Batch Jobs Are Correct - for new Central Storeroon company code | 20.1 | 2021-01-18 07:00 | 2021-01-19 11:06 | LAWRENCE BOATENG | LAWRENCE.BOATENG@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;RICARDO OLIVEIRA;WENDY VOLLENWEIDER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;RICARDO.OLIVEIRA@GAPAC.COM;WENDY.VOLLENWEIDER@GAPAC.COM | RTR | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-19 11:06 | RTR - GL | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97711 | WBS.2.1.5.1.8.3.23 | N | N | Planned | ECC legacy batch job variants update prior to FCW | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | WENTAO TANG | WTANG@GAPAC.COM | AGNES DEBO;RICARDO OLIVEIRA;RANJAI JOHN;RTR TEAM;SAI TEAM | ADEBO@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 4084 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97699 | WBS.2.1.5.1.8.3.22 | N | N | Planned | Validate OneSource tax system set-up for Central Storeroom Company Code | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | RTR-TAX | ATL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97680 | WBS.2.1.5.1.9 |  |  |  | Ramp Down ¦ CMM Activities | 0.25 | 2021-01-30 22:45 | 2021-01-30 23:00 | [8 empty] | * |  | 2021-01-30 22:45 | 2021-01-30 23:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97679 | WBS.2.1.5.1.9.2 |  |  |  | Ramp Down ¦ CMM Activities | 0.25 | 2021-01-30 22:45 | 2021-01-30 23:00 | [8 empty] | * |  | 2021-01-30 22:45 | 2021-01-30 23:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97678 | WBS.2.1.5.1.9.2.4 | N | N | Planned | Turn off order replication jobs in Hybris | 0.25 | 2021-01-30 22:45 | 2021-01-30 23:00 | LEANNE EVANS | LEREVANS@gapac.com | JUDY LIGHTFOOT;SAI TEAM | JMLIGHTF@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | CMM | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-30 23:00 | CMM | ATL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91712 | WBS.2.1.6 | N | N |  | Ramp Down ¦ Conversions | 139 | 2021-01-17 21:45 | 2021-01-28 14:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-28 14:45 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
9257 | WBS.2.1.6.1 | N | N |  | Ramp Down ¦ Conversions - Big 3 | 139 | 2021-01-17 21:45 | 2021-01-28 14:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-28 14:45 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
9258 | WBS.2.1.6.1.1 | N | N |  | Ramp Down ¦ Conversions - Big 3 Conversions | 89.75 | 2021-01-17 21:45 | 2021-01-25 13:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-25 13:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5083 | WBS.2.1.6.1.1.1 | N | N |  | Ramp Down ¦ MDG_C0098 Material Master conversion to MDG | 89.75 | 2021-01-17 21:45 | 2021-01-25 13:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-25 13:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
82731 | WBS.2.1.6.1.1.1.1 | N | N | Planned | Inbound Delivery Type for Copack/MKLE transfer’ table via tcode: ZINBDELVTYP | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3976 | WBS.2.1.6.1.1.1.2 | N | N | Planned | Provide Load File For SPECS Materials plants 1034, 1376, 1459 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | NOEL CLARK;SAI TEAM;DENISE ROBINSON;CHIRAG PARIKH;JENNIFER LI;RTR TEAM;DONNA COOPER;RANJAI JOHN;BOATENG LAWRENCE;KRISHNA SINGAREDDY | NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;DCOOPER@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;ksingareddy@deloitte.com | RTR | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | RTR - PC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90886 | WBS.2.1.6.1.1.1.3 | N | N | Planned | Provide Load File For ZUNB Materials | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90887 | WBS.2.1.6.1.1.1.4 | N | N | Planned | Validate The Load File Provided For ZUNB Materials | 2 | 2021-01-18 07:15 | 2021-01-18 09:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;SAI TEAM;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90886 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 09:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10137 | WBS.2.1.6.1.1.1.5 | N | N | Planned | MDG_C0098 - Execute DQ job to identify in-scope AS8 Procured materials | 4 | 2021-01-18 06:45 | 2021-01-18 10:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 4229,36501 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 10:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5084 | WBS.2.1.6.1.1.1.6 | N | N | Planned | MDG_C0098 - Execute Transform program for AS8 Procured materials | 4 | 2021-01-18 08:45 | 2021-01-18 12:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 4229,9125 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 12:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94865 | WBS.2.1.6.1.1.1.7 | N | N | Planned | Validate Material Origin group in SPECS Load File | 1 | 2021-01-17 22:15 | 2021-01-17 23:15 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE;KRISHNA SINGAREDDY | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;ksingareddy@deloitte.com | RTR | 3976 |  |  | * |  | 2021-01-17 22:15 | 2021-01-17 23:15 | RTR - PLC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90768 | WBS.2.1.6.1.1.1.8 | N | N | Planned | MDG_C0098 Provide load file for SPECS extension of materials | 0.5 | 2021-01-17 22:15 | 2021-01-17 22:45 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | NOEL CLARK;DONNA COOPER;SAI TEAM;DENISE ROBINSON;CHIRAG PARIKH;JENNIFER LI;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;KRISHNA SINGAREDDY | NOEL.CLARK@GAPAC.COM;DCOOPER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;ksingareddy@deloitte.com | RTR | 3976 |  |  | * |  | 2021-01-17 22:15 | 2021-01-17 22:45 | RTR - PC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
90888 | WBS.2.1.6.1.1.1.9 | N | N | Planned | MDG_C0098 - Execute Preload for ZUNB materials manual load file | 2 | 2021-01-18 09:15 | 2021-01-18 11:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;VINOD MADHANU;CRAIG HURST;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;VMADHANU@DELOITTE.COM;CRAIG.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90886,90887,3976,4229 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 11:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9852 | WBS.2.1.6.1.1.1.10 | N | N | Planned | MDG_C0098 Validate the load file for SPECS materials (RTR) and SPECS extension file | 8 | 2021-01-17 22:45 | 2021-01-18 12:45 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | MARCOS MIRANDA;DENISE ROBINSON;DONNA COOPER;NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;KRISHNA SINGAREDDY | MARCOS.MIRANDA@GAPAC.COM;DOROBINS@GAPAC.COM;DCOOPER@GAPAC.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;ksingareddy@deloitte.com | RTR | 90768 |  |  | * |  | 2021-01-17 22:45 | 2021-01-18 12:45 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9851 | WBS.2.1.6.1.1.1.11 | N | N | Planned | MDG_C0098 Validate the load file for SPECS materials (Data) and SPECS extension file | 2 | 2021-01-17 22:45 | 2021-01-18 06:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 3976,90768 |  |  | * |  | 2021-01-17 22:45 | 2021-01-18 06:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90889 | WBS.2.1.6.1.1.1.12 | N | N | Planned | MDG_C0098 - Validate Preload for ZUNB materials | 2 | 2021-01-18 11:15 | 2021-01-18 13:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 90888 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 13:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92114 | WBS.2.1.6.1.1.1.13 | N | N | Planned | Check if AS8 materials in preload are in MDG workflows | 1 | 2021-01-18 12:45 | 2021-01-18 13:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;JON LUKE DAVILA;DAVID MILLER;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DAVID.MILLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5084,10846 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 13:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10492 | WBS.2.1.6.1.1.1.14 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Basic View | 1 | 2021-01-18 12:45 | 2021-01-18 13:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5084 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 13:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10138 | WBS.2.1.6.1.1.1.15 | N | N | Planned | MDG_C0098 - Compare DQ and ETL filtered in-scope AS8 Procured Materials and analyze/report differences | 3 | 2021-01-18 12:45 | 2021-01-18 15:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10137,5084 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 15:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10493 | WBS.2.1.6.1.1.1.16 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Purchasing/MRP View | 1 | 2021-01-18 13:45 | 2021-01-18 14:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10492 |  |  | * |  | 2021-01-18 13:45 | 2021-01-18 14:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5085 | WBS.2.1.6.1.1.1.17 | N | N | Planned | MDG_C0098 - Validate Preload Transform for AS8 Procured materials - Basic View | 1.5 | 2021-01-18 13:45 | 2021-01-18 15:15 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;DATA ETL TEAM;DEAN WILSON | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DEAN.WILSON@GAPAC.COM | DATA | 5084,10492 |  |  | * |  | 2021-01-18 13:45 | 2021-01-18 15:15 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90067 | WBS.2.1.6.1.1.1.18 | N | N | Planned | Provide load file for ZSOURCE characteristic for SPECS and ZUNB materials | 0.5 | 2021-01-18 07:15 | 2021-01-18 07:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9851,90886 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10494 | WBS.2.1.6.1.1.1.19 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Accounting view | 1 | 2021-01-18 14:45 | 2021-01-18 15:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10493 |  |  | * |  | 2021-01-18 14:45 | 2021-01-18 15:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9134 | WBS.2.1.6.1.1.1.20 | N | N | Planned | MDG_C0098 - Validate Preload Transform for AS8 Procured materials - Plant, MRP, Purchasing & Quality (MRO) | 4 | 2021-01-18 14:45 | 2021-01-18 18:45 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | ERIC BARSTOW;DENISE ROBINSON;SAI TEAM;DAVID COOK;NITIN GUPTA;DOROTHY RUSSELL;PTP TEAM;JON PINYON | ERIC.BARSTOW@GAPAC.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.COOK@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JWPINYON@GAPAC.COM | PTP | 5084,10493 |  |  | * |  | 2021-01-18 14:45 | 2021-01-18 18:45 | PTP | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92115 | WBS.2.1.6.1.1.1.21 | N | N | Planned | Turn OFF the interface (PO channel) from MDM before AS8 material load | 1 | 2021-01-18 15:15 | 2021-01-18 16:15 | ARUN SHARMA | ARUN.SHARMA@GAPAC.COM | DAVID MILLER;JON LUKE DAVILA;DENISE ROBINSON;AMY EL-BASSIONI;SAI TEAM | DAVID.MILLER@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 5085 |  |  | * |  | 2021-01-18 15:15 | 2021-01-18 16:15 | LSA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10425 | WBS.2.1.6.1.1.1.22 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload Transform for AS8 Procured materials - Basic View | 0.25 | 2021-01-18 15:15 | 2021-01-18 15:30 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JON PINYON | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JWPINYON@GAPAC.COM | DATA | 5085,10492 |  |  | * |  | 2021-01-18 15:15 | 2021-01-18 15:30 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10495 | WBS.2.1.6.1.1.1.23 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Storage view | 1 | 2021-01-18 15:45 | 2021-01-18 16:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10494 |  |  | * |  | 2021-01-18 15:45 | 2021-01-18 16:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9135 | WBS.2.1.6.1.1.1.24 | N | N | Planned | MDG_C0098 - Validate Preload Transform for AS8 Procured materials - Accounting /Costing Views | 1.5 | 2021-01-18 15:45 | 2021-01-18 17:15 | DENISE MARSH | DENISE.MARSH@GAPAC.COM | LINDA GIBSON;DONNA COOPER;DENISE ROBINSON;LINDSAY SAVAGE;SAI TEAM;TONY SMITH;RTR TEAM;NOEL CLARK;RANJAI JOHN;BOATENG LAWRENCE | LINDA.GIBSON@GAPAC.COM;DCOOPER@GAPAC.COM;DOROBINS@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5084,10494 |  |  | * |  | 2021-01-18 15:45 | 2021-01-18 17:15 | RTR - PC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94867 | WBS.2.1.6.1.1.1.25 | N | N | Planned | Load Custom Tables in S/4 HANA system (STOCK, LENGHTS OF RUN, RATE, etc) | 1 | 2021-01-19 16:15 | 2021-01-19 17:15 | CARTER BRISCOE | CARTER.BRISCOE@GAPAC.COM | SAI TEAM;RTR TEAM;TODD ROSNOW;PAUL WILLENBRING;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;TAROSNOW@GAPAC.COM;PAUL.WILLENBRING2@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94865,10120 |  |  | * |  | 2021-01-19 16:15 | 2021-01-19 17:15 | RTR - PLC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94868 | WBS.2.1.6.1.1.1.26 | N | N | Planned | Validate Custom Tables in S/4 HANA system | 1 | 2021-01-19 17:15 | 2021-01-19 18:15 | CARTER BRISCOE | CARTER.BRISCOE@GAPAC.COM | SAI TEAM;RTR TEAM;TODD ROSNOW;PAUL WILLENBRING;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;TAROSNOW@GAPAC.COM;PAUL.WILLENBRING2@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94867 |  |  | * |  | 2021-01-19 17:15 | 2021-01-19 18:15 | RTR - PLC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10496 | WBS.2.1.6.1.1.1.27 | N | N | Planned | MDG_C0098 - Generate Preload validation report - AS8 Procured materials - Sales View | 1 | 2021-01-18 16:45 | 2021-01-18 17:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10495 |  |  | * |  | 2021-01-18 16:45 | 2021-01-18 17:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9136 | WBS.2.1.6.1.1.1.28 | N | N | Planned | MDG_C0098 - Validate Preload Transform for AS8 Procured materials - Storage View | 1 | 2021-01-18 16:45 | 2021-01-18 17:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;DOUG STANISLAWSKI;SAI TEAM;JIM KIJEK;LEM LANCASTER;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEKIJEK@GAPAC.COM;LEM.LANCASTER@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5084,10495,5085 |  |  | * |  | 2021-01-18 16:45 | 2021-01-18 17:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10412 | WBS.2.1.6.1.1.1.29 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload Transform for AS8 Procured materials - Accounting /Costing Views | 0.5 | 2021-01-18 17:15 | 2021-01-18 17:45 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9135,10494 |  |  | * |  | 2021-01-18 17:15 | 2021-01-18 17:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9137 | WBS.2.1.6.1.1.1.30 | N | N | Planned | MDG_C0098 - Validate Preload Transform for AS8 Procured materials - Sales View | 2 | 2021-01-18 17:45 | 2021-01-18 19:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5084,10496,9136 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 19:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10306 | WBS.2.1.6.1.1.1.31 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload Transform for AS8 Procured materials - Storage View | 0.5 | 2021-01-18 17:45 | 2021-01-18 18:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9136,10495 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:15 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94866 | WBS.2.1.6.1.1.1.32 | N | N | Planned | Run the 'Fill Ratio' table transaction in S/4HANA System (PLCFILLRATIO) | 3 | 2021-01-21 09:00 | 2021-01-21 12:00 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94871 |  |  | * |  | 2021-01-21 09:00 | 2021-01-21 12:00 | RTR - PLC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10418 | WBS.2.1.6.1.1.1.33 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload Transform for AS8 Procured materials - Plant, MRP, Purchasing & Quality (MRO) | 0.25 | 2021-01-18 18:45 | 2021-01-18 19:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9134,10493 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:00 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10431 | WBS.2.1.6.1.1.1.34 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload Transform for AS8 Procured materials - Sales View | 0.25 | 2021-01-18 19:45 | 2021-01-18 20:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9137,10496 |  |  | * |  | 2021-01-18 19:45 | 2021-01-18 20:00 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9174 | WBS.2.1.6.1.1.1.35 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS semi-finished materials manual load file | 3 | 2021-01-18 12:45 | 2021-01-18 15:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 3976,9851,9852,4229 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 15:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
83323 | WBS.2.1.6.1.1.1.36 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - SPECS semi finished material load file (all views) | 2 | 2021-01-18 15:45 | 2021-01-18 17:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;NOEL CLARK;DONNA COOPER;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;DCOOPER@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9174 |  |  | * |  | 2021-01-18 15:45 | 2021-01-18 17:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9178 | WBS.2.1.6.1.1.1.37 | N | N | Planned | MDG_C0098 - Validate Preload for SPECS semi-finished material load file | 1 | 2021-01-18 17:45 | 2021-01-18 18:45 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | DONNA COOPER;VISHNU CHIRALA;AMY EL-BASSIONI;SAI TEAM;TONY SMITH;JON PINYON;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;DEAN WILSON;RANJAI JOHN;BOATENG LAWRENCE | DCOOPER@GAPAC.COM;VICHIRALA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;JWPINYON@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;DEAN.WILSON@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9174,83323 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:45 | RTR - PC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10371 | WBS.2.1.6.1.1.1.38 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload for SPECS semi-finished material load file | 0.5 | 2021-01-18 18:45 | 2021-01-18 19:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9178 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90082 | WBS.2.1.6.1.1.1.39 | N | N | Planned | Open client in MDG for turning ON change pointers for materials before load | 0.25 | 2021-01-18 19:15 | 2021-01-18 19:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 10371 |  |  | * |  | 2021-01-18 19:15 | 2021-01-18 19:30 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90054 | WBS.2.1.6.1.1.1.40 | N | N | Planned | Turn OFF job in S4 for MDG – S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL | 0.25 | 2021-01-18 19:15 | 2021-01-18 19:30 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;LSA TEAM;KESAVA BATTINA;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;KESAVAMANI.BATTINA@KOCHTC.COM;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 10371 |  |  | * |  | 2021-01-18 19:15 | 2021-01-18 19:30 | BATCH | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90055 | WBS.2.1.6.1.1.1.41 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.5 | 2021-01-18 19:30 | 2021-01-18 20:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DATA | 90082 |  |  | * |  | 2021-01-18 19:30 | 2021-01-18 20:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92829 | WBS.2.1.6.1.1.1.42 | N | N | Planned | Validate that the job in S4 for MDG – S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL has been turned OFF | 0.25 | 2021-01-18 19:30 | 2021-01-18 19:45 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | PHANI GHANTASALA;DENISE ROBINSON;DATA ETL TEAM;SAI TEAM;KAREN HUNNICUTT;AMY EL-BASSIONI | PGHANTASALA@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRHUNNIC@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 90054 |  |  | * |  | 2021-01-18 19:30 | 2021-01-18 19:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90890 | WBS.2.1.6.1.1.1.43 | N | N | Planned | MDG_C0098 - Execute load for ZUNB materials (Including ZSOURCE characteristic) | 2 | 2021-01-18 20:00 | 2021-01-18 22:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;VINOD MADHANU;CRAIG HURST;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;VMADHANU@DELOITTE.COM;CRAIG.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90889,90055,90054,90067,10371,92829 |  |  | * |  | 2021-01-18 20:00 | 2021-01-18 22:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
83325 | WBS.2.1.6.1.1.1.44 | N | N | Planned | Execute load for SPECS semi-finished materials manual load file (Including ZSOURCE characteristic) | 2.5 | 2021-01-18 20:00 | 2021-01-19 06:30 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 90055,90054,90067,10371,92829 |  |  | * |  | 2021-01-18 20:00 | 2021-01-19 06:30 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5090 | WBS.2.1.6.1.1.1.45 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Basic View | 2 | 2021-01-18 20:00 | 2021-01-18 22:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90055,90054,10425,92114,92115,92829 |  |  | * |  | 2021-01-18 20:00 | 2021-01-18 22:00 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90891 | WBS.2.1.6.1.1.1.46 | N | N | Planned | MDG_C0098 - Validate load in MDG for ZUNB materials manual load file | 2 | 2021-01-19 06:00 | 2021-01-19 08:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 90890 |  |  | * |  | 2021-01-19 06:00 | 2021-01-19 08:00 | EWM | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10498 | WBS.2.1.6.1.1.1.47 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Basic View | 2 | 2021-01-19 06:00 | 2021-01-19 08:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5090 |  |  | * |  | 2021-01-19 06:00 | 2021-01-19 08:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5096 | WBS.2.1.6.1.1.1.48 | N | N | Planned | MDG_C0098 - Execute Transform program for Materials - Classifications View | 3 | 2021-01-19 06:00 | 2021-01-19 09:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5090 |  |  | * |  | 2021-01-19 06:00 | 2021-01-19 09:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9148 | WBS.2.1.6.1.1.1.49 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Plant, MRP, Purchasing & Quality (MRO) | 4 | 2021-01-19 06:00 | 2021-01-19 10:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5090,10418 |  |  | * |  | 2021-01-19 06:00 | 2021-01-19 10:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
83324 | WBS.2.1.6.1.1.1.50 | N | N | Planned | Generate Post Load Validation report - SPECS semi-finished materials load file | 4 | 2021-01-19 06:30 | 2021-01-19 10:30 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | ANJALI SINHA;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM | ANJASINHA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 83325 |  |  | * |  | 2021-01-19 06:30 | 2021-01-19 10:30 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9149 | WBS.2.1.6.1.1.1.51 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Accounting/Costing Views | 4 | 2021-01-19 10:00 | 2021-01-19 14:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9148,10412 |  |  | * |  | 2021-01-19 10:00 | 2021-01-19 14:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9150 | WBS.2.1.6.1.1.1.52 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Storage View | 4 | 2021-01-19 14:00 | 2021-01-19 18:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9149,10306 |  |  | * |  | 2021-01-19 14:00 | 2021-01-19 18:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10499 | WBS.2.1.6.1.1.1.53 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Plant/Purchasing & Accounting/Costing Views | 3 | 2021-01-19 14:00 | 2021-01-19 17:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9148,9149 |  |  | * |  | 2021-01-19 14:00 | 2021-01-19 17:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5091 | WBS.2.1.6.1.1.1.54 | N | N | Planned | MDG_C0098 - Validate AS8 Procured Materials Load in MDG - Basic View | 2 | 2021-01-19 08:00 | 2021-01-19 10:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5090,10498 |  |  | * |  | 2021-01-19 08:00 | 2021-01-19 10:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10526 | WBS.2.1.6.1.1.1.55 | N | N | Planned | MDG_C0098 - Generate Preload Validation report - Procured materials - Classification view | 1 | 2021-01-19 09:00 | 2021-01-19 10:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5096 |  |  | * |  | 2021-01-19 09:00 | 2021-01-19 10:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10501 | WBS.2.1.6.1.1.1.56 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Storage View | 2 | 2021-01-19 18:00 | 2021-01-19 20:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;DENISE ROBINSON;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9150 |  |  | * |  | 2021-01-19 18:00 | 2021-01-19 20:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10424 | WBS.2.1.6.1.1.1.57 | N | N | Planned | MDG_C0098 - Business Sign-Off AS8 Procured Materials Load in MDG - Basic View | 0.25 | 2021-01-19 10:00 | 2021-01-19 10:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5091,10498 |  |  | * |  | 2021-01-19 10:00 | 2021-01-19 10:15 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5097 | WBS.2.1.6.1.1.1.58 | N | N | Planned | MDG_C0098 - Validate Preload transform for Procured Materials - Classification View | 2 | 2021-01-19 10:00 | 2021-01-19 12:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5096,10526,9137 |  |  | * |  | 2021-01-19 10:00 | 2021-01-19 12:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9151 | WBS.2.1.6.1.1.1.59 | N | N | Planned | MDG_C0098 - Execute Load in MDG - AS8 Procured Materials - Sales View | 3 | 2021-01-19 18:00 | 2021-01-19 21:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9150,10431 |  |  | * |  | 2021-01-19 18:00 | 2021-01-19 21:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9153 | WBS.2.1.6.1.1.1.60 | N | N | Planned | MDG_C0098 - Validate AS8 Procured Materials Load in MDG - Accounting/Costing View | 1.5 | 2021-01-19 17:00 | 2021-01-19 18:30 | DENISE MARSH | DENISE.MARSH@GAPAC.COM | NOEL CLARK;LINDA GIBSON;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9149,10499 |  |  | * |  | 2021-01-19 17:00 | 2021-01-19 18:30 | RTR - PC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9152 | WBS.2.1.6.1.1.1.61 | N | N | Planned | MDG_C0098 - Validate AS8 Procured Materials Load in MDG - Plant, MRP, Purchasing & Quality (MRO) | 3 | 2021-01-19 17:00 | 2021-01-19 20:00 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | ERIC BARSTOW;DENISE ROBINSON;SAI TEAM;DAVID COOK;NITIN GUPTA;JON PINYON;DOROTHY RUSSELL;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.COOK@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;JWPINYON@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 9148,10499 |  |  | * |  | 2021-01-19 17:00 | 2021-01-19 20:00 | PTP | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9186 | WBS.2.1.6.1.1.1.62 | N | N | Planned | MDG_C0098 - Validate load in MDG for SPECS SFG materials load file and provide list of updates (EKALR) to data team | 1 | 2021-01-19 10:30 | 2021-01-19 11:30 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | DONNA COOPER;VISHNU CHIRALA;AMY EL-BASSIONI;SAI TEAM;TONY SMITH;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | DCOOPER@GAPAC.COM;VICHIRALA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 83324 |  |  | * |  | 2021-01-19 10:30 | 2021-01-19 11:30 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92691 | WBS.2.1.6.1.1.1.63 | N | N | Planned | Update SPECS SFG materials (EKALR) with list provided by RTR | 1 | 2021-01-19 11:30 | 2021-01-19 12:30 | JIM KIJEK | JEKIJEK@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;SAI TEAM;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9186 |  |  | * |  | 2021-01-19 11:30 | 2021-01-19 12:30 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90767 | WBS.2.1.6.1.1.1.64 | N | N | Planned | MDG_C0098 - Execute Preload for SPECS extension semi-finished materials and generate report | 2.5 | 2021-01-19 11:30 | 2021-01-19 14:00 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9186,90768 |  |  | * |  | 2021-01-19 11:30 | 2021-01-19 14:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10414 | WBS.2.1.6.1.1.1.65 | N | N | Planned | MDG_C0098 - Business Sign-Off AS8 Procured Materials Load in MDG - Accounting/Costing View | 0.5 | 2021-01-19 18:30 | 2021-01-19 19:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9153,10499 |  |  | * |  | 2021-01-19 18:30 | 2021-01-19 19:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9154 | WBS.2.1.6.1.1.1.66 | N | N | Planned | MDG_C0098 - Validate AS8 Procured Materials Load in MDG - Storage View | 2.5 | 2021-01-19 20:00 | 2021-01-20 06:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | JIM KIJEK;SHANKAR RAMNARAYANAN;SAI TEAM;JENNIFER LI;LEM LANCASTER;DENISE ROBINSON;DATA ETL TEAM | JEKIJEK@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JQLI@GAPAC.COM;LEM.LANCASTER@GAPAC.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9150,10501,5091 |  |  | * |  | 2021-01-19 20:00 | 2021-01-20 06:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9928 | WBS.2.1.6.1.1.1.67 | N | N | Planned | MDG_C0098 - Generate In-Scope list and AS8 / S/4HANA material Xref and upload to SharePoint | 1 | 2021-01-19 21:00 | 2021-01-19 22:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9151 |  |  | * |  | 2021-01-19 21:00 | 2021-01-19 22:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10502 | WBS.2.1.6.1.1.1.68 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - AS8 Procured materials - Sales View | 2 | 2021-01-19 21:00 | 2021-01-20 07:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;DENISE ROBINSON;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9151 |  |  | * |  | 2021-01-19 21:00 | 2021-01-20 07:00 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5100 | WBS.2.1.6.1.1.1.69 | N | N | Planned | MDG_C0098 - Execute Load in MDG - Materials - Classification View (ECC & AS8) | 4.5 | 2021-01-19 21:00 | 2021-01-20 09:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10423,9151 |  |  | * |  | 2021-01-19 21:00 | 2021-01-20 09:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
92168 | WBS.2.1.6.1.1.1.70 | N | N | Planned | Send list of Quality Inspection material to EWM | 1 | 2021-01-19 20:00 | 2021-01-19 21:00 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | CASEY HERMANSEN;SAI TEAM;PTP TEAM | CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 9152 |  |  | * |  | 2021-01-19 20:00 | 2021-01-19 21:00 | PTP | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97516 | WBS.2.1.6.1.1.1.112 | N | N | Planned | Send list of Consignment Vendors by Plant to EWM | 1 | 2021-01-19 21:00 | 2021-01-19 22:00 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | CASEY HERMANSEN;PTP TEAM;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 92168 |  |  | * |  | 2021-01-19 21:00 | 2021-01-19 22:00 | PTP | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10413 | WBS.2.1.6.1.1.1.71 | N | N | Planned | MDG_C0098 - Business Sign-Off AS8 Procured Materials Load in MDG - Plant, MRP, Purchasing & Quality (MRO) | 0.5 | 2021-01-19 20:00 | 2021-01-19 20:30 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9152,10499 |  |  | * |  | 2021-01-19 20:00 | 2021-01-19 20:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10423 | WBS.2.1.6.1.1.1.72 | N | N | Planned | MDG_C0098 - Business Sign-Off Preload transform for Procured Materials - Classification View | 0.25 | 2021-01-19 12:00 | 2021-01-19 12:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5097,10526 |  |  | * |  | 2021-01-19 12:00 | 2021-01-19 12:15 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90766 | WBS.2.1.6.1.1.1.73 | N | N | Planned | MDG_C0098 - Validate Preload for SPECS extension semi-finished material load file | 1 | 2021-01-19 14:00 | 2021-01-19 15:00 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | DONNA COOPER;VISHNU CHIRALA;AMY EL-BASSIONI;SAI TEAM;TONY SMITH;JON PINYON;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | DCOOPER@GAPAC.COM;VICHIRALA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;JWPINYON@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90767 |  |  | * |  | 2021-01-19 14:00 | 2021-01-19 15:00 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10307 | WBS.2.1.6.1.1.1.74 | N | N | Planned | MDG_C0098 - Business Sign-Off AS8 Procured Materials Load in MDG - Storage View | 0.75 | 2021-01-20 06:30 | 2021-01-20 07:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9154,10501 |  |  | * |  | 2021-01-20 06:30 | 2021-01-20 07:15 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9155 | WBS.2.1.6.1.1.1.75 | N | N | Planned | MDG_C0098 - Validate AS8 Procured Materials Load in MDG - Sales View | 1 | 2021-01-20 07:00 | 2021-01-20 08:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9151,10502,9154 |  |  | * |  | 2021-01-20 07:00 | 2021-01-20 08:00 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90765 | WBS.2.1.6.1.1.1.76 | N | N | Planned | Execute load for SPECS extension semi-finished materials manual load file (Including ZSOURCE characteristic) MDG_C0098 | 3 | 2021-01-19 15:00 | 2021-01-19 18:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90766 |  |  | * |  | 2021-01-19 15:00 | 2021-01-19 18:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10430 | WBS.2.1.6.1.1.1.77 | N | N | Planned | MDG_C0098 - Business Sign-Off AS8 Procured Materials Load in MDG - Sales View | 0.5 | 2021-01-20 08:00 | 2021-01-20 08:30 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9155,10502 |  |  | * |  | 2021-01-20 08:00 | 2021-01-20 08:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10528 | WBS.2.1.6.1.1.1.78 | N | N | Planned | MDG_C0098 - Generate Post Load Validation report - Procured materials - Classification View | 1 | 2021-01-20 09:30 | 2021-01-20 10:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;JON PINYON;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5100 |  |  | * |  | 2021-01-20 09:30 | 2021-01-20 10:30 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90764 | WBS.2.1.6.1.1.1.79 | N | N | Planned | MDG_C0098 - Validate load in MDG for SPECS extension semi-finished materials manual load file | 0.5 | 2021-01-19 18:00 | 2021-01-19 18:30 | LINDA GIBSON | LINDA.GIBSON@GAPAC.COM | DONNA COOPER;VISHNU CHIRALA;AMY EL-BASSIONI;SAI TEAM;TONY SMITH;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | DCOOPER@GAPAC.COM;VICHIRALA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90765 |  |  | * |  | 2021-01-19 18:00 | 2021-01-19 18:30 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5101 | WBS.2.1.6.1.1.1.80 | N | N | Planned | MDG_C0098 - Validate Load in MDG - Procured Materials - Classification View | 1 | 2021-01-20 10:30 | 2021-01-20 11:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5100,10528,9155 |  |  | * |  | 2021-01-20 10:30 | 2021-01-20 11:30 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10372 | WBS.2.1.6.1.1.1.81 | N | N | Planned | MDG_C0098 - Business Sign-Off load in MDG for SPECS semi-finished materials manual load file | 0.5 | 2021-01-19 18:30 | 2021-01-19 19:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 9186,90764,92691 |  |  | * |  | 2021-01-19 18:30 | 2021-01-19 19:00 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92582 | WBS.2.1.6.1.1.1.82 | N | N | Planned | Turn OFF job in S4 to trigger MATMAS Idocs downstream: S4_DATA_ZMM_SEND_MAT_S4ECC_BOTH | 0.5 | 2021-01-19 19:00 | 2021-01-19 19:30 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 10372,90891 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:30 | BATCH | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92830 | WBS.2.1.6.1.1.1.83 | N | N | Planned | Validate that the job in S4 to trigger MATMAS Idocs downstream: S4_DATA_ZMM_SEND_MAT_S4ECC_BOTH has been turned OFF | 0.25 | 2021-01-19 19:30 | 2021-01-19 19:45 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | PHANI GHANTASALA;DENISE ROBINSON;DATA ETL TEAM;SAI TEAM;KAREN HUNNICUTT;AMY EL-BASSIONI | PGHANTASALA@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRHUNNIC@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 92582 |  |  | * |  | 2021-01-19 19:30 | 2021-01-19 19:45 | DATA | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10429 | WBS.2.1.6.1.1.1.84 | N | N | Planned | MDG_C0098 - Business Sign-Off Load in MDG - Procured Materials - Classification View | 0.25 | 2021-01-20 11:30 | 2021-01-20 11:45 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5101,10528 |  |  | * |  | 2021-01-20 11:30 | 2021-01-20 11:45 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95207 | WBS.2.1.6.1.1.1.85 | N | N | Planned | Provide Procurement MDM file of material remote keys for AS8 facilities being deployed | 2 | 2021-01-18 07:00 | 2021-01-18 09:00 | BRIAN MILLER | JBMILLER@GAPAC.COM | DAVID MILLER;DENISE ROBINSON;MARCOS MIRANDA;SAI TEAM;DATA ETL TEAM | DAVID.MILLER@GAPAC.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 3966,36501 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 09:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36931 | WBS.2.1.6.1.1.1.86 | N | N | Planned | Create the file to load the Procurement MDM system with the new MDG Procured Material number (remote keys) | 3.5 | 2021-01-21 08:00 | 2021-01-21 11:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JON PINYON;JON LUKE DAVILA;DAVID MILLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JWPINYON@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DAVID.MILLER@GAPAC.COM | DATA | 10428,89766,95207 |  |  | * |  | 2021-01-21 08:00 | 2021-01-21 11:30 | DATA | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
36932 | WBS.2.1.6.1.1.1.87 | N | N | Planned | Update Procurement MDM with the new MDG Procured Material number (remote keys) | 4 | 2021-01-21 11:30 | 2021-01-21 15:30 | BRIAN MILLER | JBMILLER@GAPAC.COM | DAVID MILLER;ARUN SHARMA;SAI TEAM;LSA TEAM | DAVID.MILLER@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36931 |  |  | * |  | 2021-01-21 11:30 | 2021-01-21 15:30 | LSA | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90079 | WBS.2.1.6.1.1.1.88 | N | N | Planned | Open client in MDG for turning OFF change pointers for materials after load | 0.25 | 2021-01-22 08:45 | 2021-01-22 09:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 10428,89709,10427 |  |  | * |  | 2021-01-22 08:45 | 2021-01-22 09:00 | DEV - INFRA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95189 | WBS.2.1.6.1.1.1.89 | N | N | Planned | Configure SAML SSO in S/4 HANA system | 2 | 2021-01-22 09:00 | 2021-01-22 11:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90079 |  |  | * |  | 2021-01-22 09:00 | 2021-01-22 11:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95188 | WBS.2.1.6.1.1.1.90 | N | N | Planned | Configure SAML SSO in CRM system | 2 | 2021-01-22 11:00 | 2021-01-22 13:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95189 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 13:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95187 | WBS.2.1.6.1.1.1.91 | N | N | Planned | Configure SAML SSO in MDG system | 2 | 2021-01-22 13:00 | 2021-01-22 15:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95188 |  |  | * |  | 2021-01-22 13:00 | 2021-01-22 15:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95186 | WBS.2.1.6.1.1.1.92 | N | N | Planned | Configure SAML SSO in GRC system | 2 | 2021-01-22 15:00 | 2021-01-22 17:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95187 |  |  | * |  | 2021-01-22 15:00 | 2021-01-22 17:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95185 | WBS.2.1.6.1.1.1.93 | N | N | Planned | Configure SAML SSO in BW system | 2 | 2021-01-22 17:00 | 2021-01-22 19:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95186 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 19:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95184 | WBS.2.1.6.1.1.1.94 | N | N | Planned | Disable SSO configured in earlier step | 2 | 2021-01-22 19:00 | 2021-01-22 21:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95185 |  |  | * |  | 2021-01-22 19:00 | 2021-01-22 21:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95183 | WBS.2.1.6.1.1.1.95 | N | N | Planned | Upload *.gpfiori.com certificate to GP-SAP-PROD VPC in ACM | 1 | 2021-01-22 21:00 | 2021-01-22 22:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95184 |  |  | * |  | 2021-01-22 21:00 | 2021-01-22 22:00 | DEV - INFRA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95182 | WBS.2.1.6.1.1.1.96 | N | N | Planned | Build and roll-out SCCM SAP Launchpad package with new business client link (duplicate entry) | 3 | 2021-01-25 06:00 | 2021-01-25 09:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95183 |  |  | * |  | 2021-01-25 06:00 | 2021-01-25 09:00 | DEV - INFRA | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90052 | WBS.2.1.6.1.1.1.98 | N | N | Planned | Turn ON DRFOUT, Turn OFF Change Pointers for CLFMAS, MATMAS, MATQM in MDG | 0.25 | 2021-01-22 09:00 | 2021-01-22 09:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DATA | 10428,89709,10427,90079 |  |  | * |  | 2021-01-22 09:00 | 2021-01-22 09:15 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
21140 | WBS.2.1.6.1.1.1.99 | N | N | Planned | Create Inspection Rule for quality managed materials in EWM | 0.5 | 2021-01-25 13:00 | 2021-01-25 13:30 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;PRAJWAL K S | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;prajks@deloitte.com | EWM | 8862,92168,5230,94302,94323,96567,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 13:30 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97353 | WBS.2.1.6.1.1.1.110 | N | N | Planned | Extract all active bins from AS8 | 2 | 2021-01-18 17:45 | 2021-01-18 19:45 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | DAVID COOK;PTP TEAM;SAI TEAM | DAVID.COOK@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 9136 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 19:45 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97354 | WBS.2.1.6.1.1.1.111 | N | N | Planned | Extact all active bins from ECC | 2 | 2021-01-18 17:45 | 2021-01-18 19:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CHARLES BLUMREICH;DAVID COOK;PTP TEAM;SAI TEAM;SANDEEP A | CHARLES.BLUMREICH@GAPAC.COM;DAVID.COOK@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 9136 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 19:45 | PTP | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9259 | WBS.2.1.6.1.2 | N | N |  | Ramp Down ¦ Conversions - Big 3 Conversions - Distribute Big 3 To S/4HANA | 77.5 | 2021-01-18 18:45 | 2021-01-25 16:15 | [8 empty] | * |  | 2021-01-18 18:45 | 2021-01-25 16:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5119 | WBS.2.1.6.1.2.1 | N | N |  | Ramp Down ¦ Conversions - Big 3 Conversions - Distribute Big 3 To S/4HANA - Sync Material Master to S/4HANA | 77.5 | 2021-01-18 18:45 | 2021-01-25 16:15 | [8 empty] | * |  | 2021-01-18 18:45 | 2021-01-25 16:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
81648 | WBS.2.1.6.1.2.1.1 | N | N | Planned | PTH - Provide file for 1034 - SFG materials price | 0.5 | 2021-01-18 18:45 | 2021-01-18 19:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9178 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:15 | RTR - PC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95602 | WBS.2.1.6.1.2.1.2 | N | N | Planned | Provide update file to Data team for materials with Val Class 3690-3695 that need the EP SLOC updated from 3000 to 4500 | 1 | 2021-01-19 17:00 | 2021-01-19 18:00 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MARCOS MIRANDA;PTP TEAM;SAI TEAM | MARCOS.MIRANDA@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 9148,10499 |  |  | * |  | 2021-01-19 17:00 | 2021-01-19 18:00 | PTP | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
68525 | WBS.2.1.6.1.2.1.3 | N | N | Planned | Mass updates on AS8 Procured materials | 2 | 2021-01-20 08:30 | 2021-01-20 10:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 10307,10414,10413,10424,10430,95602 |  |  | * |  | 2021-01-20 08:30 | 2021-01-20 10:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5121 | WBS.2.1.6.1.2.1.4 | N | N | Planned | Replicate Asset Suite Procured Materials from MDG to S/4HANA using t-code BD10 | 9 | 2021-01-20 10:30 | 2021-01-20 19:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 10307,10414,10413,10424,10430,68525,92582,92830 |  |  | * |  | 2021-01-20 10:30 | 2021-01-20 19:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
89712 | WBS.2.1.6.1.2.1.5 | N | N | Planned | Replicate SPECS and ZUNB materials from MDG to S4 using t-code BD10 | 3 | 2021-01-19 19:45 | 2021-01-20 06:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DENISE ROBINSON;SHANKAR RAMNARAYANAN;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 10372,90891,92582,92830 |  |  | * |  | 2021-01-19 19:45 | 2021-01-20 06:45 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
89711 | WBS.2.1.6.1.2.1.6 | N | N | Planned | Generate Replication Validation reports - SPECS and ZUNB materials | 2 | 2021-01-20 06:45 | 2021-01-20 08:45 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SHANKAR RAMNARAYANAN;BUS DATA VAL;JON PINYON;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 89712 |  |  | * |  | 2021-01-20 06:45 | 2021-01-20 08:45 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
89710 | WBS.2.1.6.1.2.1.7 | N | N | Planned | Validate SPECS & ZUNB materials in S4 | 1 | 2021-01-20 08:45 | 2021-01-20 09:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;MARCOS MIRANDA;SAI TEAM;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 89711 |  |  | * |  | 2021-01-20 08:45 | 2021-01-20 09:45 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
89709 | WBS.2.1.6.1.2.1.8 | N | N | Planned | Business Sign-off ZUNB and SPECS materials in S4 | 0.25 | 2021-01-20 09:45 | 2021-01-20 10:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM;DATA ETL TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 89710 |  |  | * |  | 2021-01-20 09:45 | 2021-01-20 10:00 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5122 | WBS.2.1.6.1.2.1.9 | N | N | Planned | Replicate Materials Quality View from MDG to S/4HANA | 0.5 | 2021-01-20 19:30 | 2021-01-20 20:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5121,10413 |  |  | * |  | 2021-01-20 19:30 | 2021-01-20 20:00 | DATA | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10503 | WBS.2.1.6.1.2.1.10 | N | N | Planned | Generate Replication Validation reports - AS8 Procured materials (Basic, Plant, Storage Location, Sales views) | 2 | 2021-01-20 19:30 | 2021-01-20 21:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5121 |  |  | * |  | 2021-01-20 19:30 | 2021-01-20 21:30 | DATA | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9188 | WBS.2.1.6.1.2.1.11 | N | N | Planned | Validate Asset Suite Procured materials in S/4HANA | 1 | 2021-01-20 21:30 | 2021-01-21 06:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5121,10503 |  |  | * |  | 2021-01-20 21:30 | 2021-01-21 06:30 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10428 | WBS.2.1.6.1.2.1.12 | N | N | Planned | Business Sign-Off Asset Suite Procured materials in S/4HANA | 0.5 | 2021-01-21 06:30 | 2021-01-21 07:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JON PINYON | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JWPINYON@GAPAC.COM | DATA | 9188,10503 |  |  | * |  | 2021-01-21 06:30 | 2021-01-21 07:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92116 | WBS.2.1.6.1.2.1.13 | N | N | Planned | Turn ON the interface (PO channel) from MDM after AS8 material load sign-off | 1 | 2021-01-21 07:00 | 2021-01-21 08:00 | ARUN SHARMA | ARUN.SHARMA@GAPAC.COM | DAVID MILLER;DENISE ROBINSON;AMY EL-BASSIONI;SAI TEAM | DAVID.MILLER@GAPAC.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 08:00 | LSA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
89766 | WBS.2.1.6.1.2.1.14 | N | N | Planned | Provide MARA and MARC extracts after materials sign-off to help prepare file for Procurement MDM | 1 | 2021-01-21 07:00 | 2021-01-21 08:00 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | MARCOS MIRANDA;SHANKAR RAMNARAYANAN;DATA ETL TEAM;DENISE ROBINSON;DON ABBOTT;SAI TEAM | MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 08:00 | DATA | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
80859 | WBS.2.1.6.1.2.1.15 | N | N | Planned | Replicate AS8 Procured Materials Classifiation View from MDG to S/4HANA using change pointers | 14 | 2021-01-21 07:00 | 2021-01-21 21:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 10429,10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 21:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
80860 | WBS.2.1.6.1.2.1.16 | N | N | Planned | Generate Replication Validation reports - AS8 Procured Materials Classification view | 2 | 2021-01-21 21:00 | 2021-01-22 07:00 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 80859 |  |  | * |  | 2021-01-21 21:00 | 2021-01-22 07:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
9191 | WBS.2.1.6.1.2.1.17 | N | N | Planned | Validate Procured Materials Classification view in S/4HANA | 1.5 | 2021-01-22 07:00 | 2021-01-22 08:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 80859,80860 |  |  | * |  | 2021-01-22 07:00 | 2021-01-22 08:30 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
10427 | WBS.2.1.6.1.2.1.18 | N | N | Planned | Business Sign-Off Procured Materials Classification view in S/4HANA | 0.25 | 2021-01-22 08:30 | 2021-01-22 08:45 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JON PINYON | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JWPINYON@GAPAC.COM | DATA | 9191 |  |  | * |  | 2021-01-22 08:30 | 2021-01-22 08:45 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92591 | WBS.2.1.6.1.2.1.19 | N | N | Planned | Turn ON job in S4 to trigger MATMAS iDOCS downstream: S4_DATA_ZMM_SEND_MAT_S4ECC_BOTH | 0.5 | 2021-01-22 08:45 | 2021-01-22 09:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 10428,89709,10427 |  |  | * |  | 2021-01-22 08:45 | 2021-01-22 09:15 | BATCH | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90051 | WBS.2.1.6.1.2.1.20 | N | N | Planned | Turn ON job in S4 for MDG -S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL | 0.5 | 2021-01-22 08:45 | 2021-01-22 09:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 10428,89709,10427 |  |  | * |  | 2021-01-22 08:45 | 2021-01-22 09:15 | BATCH | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95037 | WBS.2.1.6.1.2.1.21 | N | N | Planned | Provide Delta MRO Material Master Updates for ECC Facilities | 6 | 2021-01-25 06:15 | 2021-01-25 12:15 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | PTP TEAM;SAI TEAM;DENISE ROBINSON;ARUN SHARMA;JON LUKE DAVILA;LINDSAY SAVAGE | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM | PTP | 90051,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 12:15 | PTP | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95038 | WBS.2.1.6.1.2.1.22 | N | N | Planned | Update Material Master for ECC Facilities as Provided by PTP Team | 4 | 2021-01-25 12:15 | 2021-01-25 16:15 | SHANKAR RAMNARAYANAN | SRAMNARAYANAN@DELOITTE.COM | CASEY HERMANSEN;DENISE ROBINSON;MARCOS MIRANDA;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 95037 |  |  | * |  | 2021-01-25 12:15 | 2021-01-25 16:15 | PTP | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
9669 | WBS.2.1.6.1.2.1.23 | N | N | Planned | Run Interface to Push Material Master Data from S/4HANA ERP to ICPAQS,Markemimaje | 4 | 2021-01-22 08:45 | 2021-01-22 12:45 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SANDEEP THARWANI;SAI TEAM;PAYEL GHOSH;SUVENDU KUMAR;DEV TEAM;RAMYA IYER;BRIAN DOBASH | STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM;BJDOBASH@GAPAC.COM | DEV | 10428,10427 |  |  | * |  | 2021-01-22 08:45 | 2021-01-22 12:45 | INT | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90959 | WBS.2.1.6.1.2.1.24 | N | N | Planned | Identify changes in material master in MDG not made by conversion | 3 | 2021-01-22 09:15 | 2021-01-22 12:15 | SHANKAR RAMNARAYANAN | SRAMNARAYANAN@DELOITTE.COM | DATA ETL TEAM;LINDSAY SAVAGE;JOAN SEIDL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;LINDSAY.SAVAGE@GAPAC.COM;JOAN.SEIDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90052 |  |  | * |  | 2021-01-22 09:15 | 2021-01-22 12:15 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90960 | WBS.2.1.6.1.2.1.25 | N | N | Planned | Replicate changes in material master not made by conversion from MDG to S4 | 2 | 2021-01-22 12:15 | 2021-01-22 14:15 | SHANKAR RAMNARAYANAN | SRAMNARAYANAN@DELOITTE.COM | PHANI GHANTASALA;DENISE ROBINSON;DATA ETL TEAM;SAI TEAM;COURTNEY ANDERSON | PGHANTASALA@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;COURTNEY.ANDERSON@GAPAC.COM | DATA | 90959 |  |  | * |  | 2021-01-22 12:15 | 2021-01-22 14:15 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90831 | WBS.2.1.6.1.2.1.26 | N | N | Planned | Run Interface to Push Bill Of Materials from S/4HANA to ICPAQS | 0.5 | 2021-01-22 12:45 | 2021-01-22 13:15 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SANDEEP THARWANI;SAI TEAM;DEV TEAM;RAMYA IYER;BRIAN DOBASH | STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM;BJDOBASH@GAPAC.COM | DEV | 9669,9802,5186 |  |  | * |  | 2021-01-22 12:45 | 2021-01-22 13:15 | INT | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
9671 | WBS.2.1.6.1.2.1.27 | N | N | Planned | Run Interface to Push Customer Master from S/4HANA ERP to ICPAQS | 2 | 2021-01-22 12:45 | 2021-01-22 14:45 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SANDEEP THARWANI;SAI TEAM;PAYEL GHOSH;SUVENDU KUMAR;DEV TEAM;RAMYA IYER;BRIAN DOBASH | STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM;BJDOBASH@GAPAC.COM | DEV | 9669 |  |  | * |  | 2021-01-22 12:45 | 2021-01-22 14:45 | INT | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
82769 | WBS.2.1.6.1.3 | N | N |  | Ramp Down ¦ Conversions - Big 3 Conversions - Delta Loads | 56.5 | 2021-01-25 06:15 | 2021-01-28 14:45 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-28 14:45 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91713 | WBS.2.1.6.1.3.1 | N | N |  | Ramp Down ¦ Conversions - Big 3 Conversions - Delta Loads - AS8 Procured Materials | 56.5 | 2021-01-25 06:15 | 2021-01-28 14:45 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-28 14:45 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
82771 | WBS.2.1.6.1.3.1.1 | N | N | Planned | MDG_C0098 - Execute Extracts from AS8 for Delta load of AS8 Procured materials | 6 | 2021-01-26 06:30 | 2021-01-26 12:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM | DATA | 10428,10854,89967,5254 |  |  | * |  | 2021-01-26 06:30 | 2021-01-26 12:30 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82772 | WBS.2.1.6.1.3.1.2 | N | N | Planned | Execute Transform program for DELTA Asset Suite Procured materials | 4 | 2021-01-26 12:30 | 2021-01-26 16:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82771 |  |  | * |  | 2021-01-26 12:30 | 2021-01-26 16:30 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92124 | WBS.2.1.6.1.3.1.3 | N | N | Planned | Check if AS8 materials in Delta pre-load are in MDG workflows | 1 | 2021-01-26 16:30 | 2021-01-26 17:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;JON LUKE DAVILA;DAVID MILLER;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DAVID.MILLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 82772 |  |  | * |  | 2021-01-26 16:30 | 2021-01-26 17:30 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82773 | WBS.2.1.6.1.3.1.4 | N | N | Planned | Generate Preload validation reports - DELTA AS8 Procured materials - All Views | 4 | 2021-01-26 16:30 | 2021-01-26 20:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82772 |  |  | * |  | 2021-01-26 16:30 | 2021-01-26 20:30 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82775 | WBS.2.1.6.1.3.1.5 | N | N | Planned | Validate Preload Transform for DELTA Asset Suite Procured materials - Plant, MRP, Purchasing & Quality (MRO) | 2 | 2021-01-26 20:30 | 2021-01-27 06:30 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | ERIC BARSTOW;SAI TEAM;DAVID COOK;NITIN GUPTA;DENISE ROBINSON;DOROTHY RUSSELL;PTP TEAM;JON PINYON | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.COOK@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;DOROBINS@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JWPINYON@GAPAC.COM | PTP | 82773 |  |  | * |  | 2021-01-26 20:30 | 2021-01-27 06:30 | PTP | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82774 | WBS.2.1.6.1.3.1.6 | N | N | Planned | Validate Preload Transform for DELTA Asset Suite Procured materials - Basic, Sales, Storage Views | 2.5 | 2021-01-26 20:30 | 2021-01-27 07:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | JIM KIJEK;SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;DATA ETL TEAM;ALICIA BERNAL;DEAN WILSON | JEKIJEK@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Alicia.Bernal@gapac.com;DEAN.WILSON@GAPAC.COM | DATA | 82773 |  |  | * |  | 2021-01-26 20:30 | 2021-01-27 07:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82776 | WBS.2.1.6.1.3.1.7 | N | N | Planned | Validate Preload Transform for DELTA Asset Suite Procured materials - Accounting /Costing Views | 4 | 2021-01-26 20:30 | 2021-01-27 08:30 | DENISE MARSH | DENISE.MARSH@GAPAC.COM | NOEL CLARK;LINDA GIBSON;DONNA COOPER;DENISE ROBINSON;LINDSAY SAVAGE;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;DCOOPER@GAPAC.COM;DOROBINS@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82773 |  |  | * |  | 2021-01-26 20:30 | 2021-01-27 08:30 | RTR - PC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92471 | WBS.2.1.6.1.3.1.8 | N | N | Planned | Open client in MDG for turning ON change pointers for materials before delta load | 1 | 2021-01-27 08:30 | 2021-01-27 09:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 82774,82775,82776 |  |  | * |  | 2021-01-27 08:30 | 2021-01-27 09:30 | DEV - INFRA | CROSS | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92628 | WBS.2.1.6.1.3.1.9 | N | N | Planned | Turn OFF job in S4 for MDG – S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL before DELTA material load | 0.25 | 2021-01-27 09:30 | 2021-01-27 09:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 92471 |  |  | * |  | 2021-01-27 09:30 | 2021-01-27 09:45 | BATCH | CROSS | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82777 | WBS.2.1.6.1.3.1.10 | N | N | Planned | Turn OFF DRFOUT, Turn ON Change pointers for CLFMAS, MATMAS, MATQM in MDG for DELTA Procured Materials load | 0.5 | 2021-01-27 09:30 | 2021-01-27 10:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DON ABBOTT;SAI TEAM;DATA ETL TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;TED.ZEIDLER@GAPAC.COM | DATA | 92471 |  |  | * |  | 2021-01-27 09:30 | 2021-01-27 10:00 | DATA | CROSS | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92472 | WBS.2.1.6.1.3.1.11 | N | N | Planned | Close client in MDG for turning Off change pointers for materials | 1 | 2021-01-27 10:00 | 2021-01-27 11:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 82777,92628 |  |  | * |  | 2021-01-27 10:00 | 2021-01-27 11:00 | DEV - INFRA | CROSS | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82778 | WBS.2.1.6.1.3.1.12 | N | N | Planned | Execute Load in MDG - DELTA AS8 Procured Materials - All Views | 4 | 2021-01-27 10:00 | 2021-01-27 14:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | VENKATESH GANESHAN;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | VGANESHAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 82774,82775,82776,82777,92124,92628 |  |  | * |  | 2021-01-27 10:00 | 2021-01-27 14:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90681 | WBS.2.1.6.1.3.1.13 | N | N | Planned | MDG_C0098 - Execute Transform for DELTA AS8 Materials - Classifications View and generate validation report | 2 | 2021-01-27 14:00 | 2021-01-27 16:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;MARCOS MIRANDA | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM | DATA | 82778 |  |  | * |  | 2021-01-27 14:00 | 2021-01-27 16:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82779 | WBS.2.1.6.1.3.1.14 | N | N | Planned | Generate Post Load Validation report - DELTA AS8 Procured materials - All Views | 3 | 2021-01-27 14:00 | 2021-01-27 17:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;MARCOS MIRANDA;SHANKAR RAMNARAYANAN;BUS DATA VAL;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;MARCOS.MIRANDA@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;LINDSAY.SAVAGE@GAPAC.COM;JWPINYON@GAPAC.COM;CODY.BOWMAN2@GAPAC.COM;JAMES.SYKES@GAPAC.COM;ROB.LINDMARK@GAPAC.COM;SATHYA.CHAKRAVARTHY@GAPAC.COM;STEVEN.JACOBS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82778 |  |  | * |  | 2021-01-27 14:00 | 2021-01-27 17:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90680 | WBS.2.1.6.1.3.1.15 | N | N | Planned | MDG_C0098 - Validate Preload transform for AS8 Procured Materials - Classification View | 1 | 2021-01-27 16:00 | 2021-01-27 17:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SAI TEAM;DENISE ROBINSON;SHANKAR RAMNARAYANAN;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90681 |  |  | * |  | 2021-01-27 16:00 | 2021-01-27 17:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92125 | WBS.2.1.6.1.3.1.16 | N | N | Planned | Turn OFF the interface (PO channel) from MDM before delta AS8 material load | 1 | 2021-01-27 17:00 | 2021-01-27 18:00 | ARUN SHARMA | ARUN.SHARMA@GAPAC.COM | DAVID MILLER;JON LUKE DAVILA;DENISE ROBINSON;AMY EL-BASSIONI;SAI TEAM | DAVID.MILLER@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 90680 |  |  | * |  | 2021-01-27 17:00 | 2021-01-27 18:00 | LSA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90679 | WBS.2.1.6.1.3.1.17 | N | N | Planned | MDG_C0098 - Execute Load in MDG - DELTA AS8 Materials - Classification View and generate validation report | 1 | 2021-01-27 17:00 | 2021-01-27 18:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;MARCOS MIRANDA | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM | DATA | 90680 |  |  | * |  | 2021-01-27 17:00 | 2021-01-27 18:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82781 | WBS.2.1.6.1.3.1.18 | N | N | Planned | Validate DELTA AS8 Procured Materials Load in MDG - Plant, MRP, Purchasing & Quality (MRO) | 2 | 2021-01-27 17:00 | 2021-01-27 19:00 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | ERIC BARSTOW;SAI TEAM;DAVID COOK;NITIN GUPTA;JON PINYON;DENISE ROBINSON;DOROTHY RUSSELL;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.COOK@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;JWPINYON@GAPAC.COM;DOROBINS@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 82779 |  |  | * |  | 2021-01-27 17:00 | 2021-01-27 19:00 | PTP | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82782 | WBS.2.1.6.1.3.1.19 | N | N | Planned | Validate DELTA AS8 Procured Materials Load in MDG - Accounting/Costing View | 0.25 | 2021-01-27 17:00 | 2021-01-27 17:15 | DENISE MARSH | DENISE.MARSH@GAPAC.COM | NOEL CLARK;LINDA GIBSON;DONNA COOPER;DENISE ROBINSON;LINDSAY SAVAGE;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;DCOOPER@GAPAC.COM;DOROBINS@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82779 |  |  | * |  | 2021-01-27 17:00 | 2021-01-27 17:15 | RTR - PC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82780 | WBS.2.1.6.1.3.1.20 | N | N | Planned | Validate DELTA AS8 Procured Materials Load in MDG - Basic, Sales, Storage Views | 1.5 | 2021-01-27 17:00 | 2021-01-27 18:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;SAI TEAM;DENISE ROBINSON;JON PINYON;JIM KIJEK;JENNIFER LI;LEM LANCASTER;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JWPINYON@GAPAC.COM;JEKIJEK@GAPAC.COM;JQLI@GAPAC.COM;LEM.LANCASTER@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 82779 |  |  | * |  | 2021-01-27 17:00 | 2021-01-27 18:30 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90678 | WBS.2.1.6.1.3.1.21 | N | N | Planned | MDG_C0098 - Validate Load in MDG - DELTA AS8 Procured Materials - Classification View | 0.5 | 2021-01-27 18:00 | 2021-01-27 18:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SAI TEAM;DENISE ROBINSON;SHANKAR RAMNARAYANAN;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90679 |  |  | * |  | 2021-01-27 18:00 | 2021-01-27 18:30 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92627 | WBS.2.1.6.1.3.1.22 | N | N | Planned | Turn OFF job in S4 to trigger MATMAS Idocs downstream:S4_DATA_ZMM_SEND_MAT_S4ECC_BOTH before DELTA material replication | 0.25 | 2021-01-27 19:00 | 2021-01-27 19:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 82780,82781,82782 |  |  | * |  | 2021-01-27 19:00 | 2021-01-27 19:15 | BATCH | CROSS | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82798 | WBS.2.1.6.1.3.1.23 | N | N | Planned | Replicate DELTA AS8 Procured materials from MDG to S/4HANA | 1.5 | 2021-01-27 19:15 | 2021-01-27 20:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 82780,82781,82782,92627 |  |  | * |  | 2021-01-27 19:15 | 2021-01-27 20:45 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90677 | WBS.2.1.6.1.3.1.24 | N | N | Planned | Replicate DELTA AS8 Procured material classifications from MDG to S4 and generate report | 2 | 2021-01-27 19:15 | 2021-01-27 21:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DENISE ROBINSON;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90678,92627 |  |  | * |  | 2021-01-27 19:15 | 2021-01-27 21:15 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82799 | WBS.2.1.6.1.3.1.25 | N | N | Planned | Generate Replication validation report for DELTA AS8 Procured materials - All Views | 2 | 2021-01-27 20:45 | 2021-01-28 06:45 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;DON ABBOTT;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82798 |  |  | * |  | 2021-01-27 20:45 | 2021-01-28 06:45 | DATA | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90676 | WBS.2.1.6.1.3.1.26 | N | N | Planned | Validate DELTA AS8 Procured material classifications in S4 | 0.5 | 2021-01-27 21:15 | 2021-01-27 21:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;SHANKAR RAMNARAYANAN;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90677 |  |  | * |  | 2021-01-27 21:15 | 2021-01-27 21:45 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82800 | WBS.2.1.6.1.3.1.27 | N | N | Planned | Validate Delta AS8 Procured materials in S/4HANA | 2 | 2021-01-28 06:45 | 2021-01-28 08:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 82799 |  |  | * |  | 2021-01-28 06:45 | 2021-01-28 08:45 | DATA | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92473 | WBS.2.1.6.1.3.1.28 | N | N | Planned | Open client in MDG for turning OFF change pointers for materials after delta load | 1 | 2021-01-28 08:45 | 2021-01-28 09:45 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:45 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92126 | WBS.2.1.6.1.3.1.29 | N | N | Planned | Turn ON the interface (PO channel) from MDM after delta AS8 material load sign-off | 1 | 2021-01-28 08:45 | 2021-01-28 09:45 | ARUN SHARMA | ARUN.SHARMA@GAPAC.COM | DAVID MILLER;JON LUKE DAVILA;DENISE ROBINSON;AMY EL-BASSIONI;SAI TEAM | DAVID.MILLER@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 82800 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:45 | LSA | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95208 | WBS.2.1.6.1.3.1.31 | N | N | Planned | Provide Procurement MDM file of delta material remote keys for AS8 facilities being deployed | 2 | 2021-01-26 16:30 | 2021-01-26 18:30 | BRIAN MILLER | JBMILLER@GAPAC.COM | DAVID MILLER;DENISE ROBINSON;MARCOS MIRANDA;SAI TEAM;DATA ETL TEAM | DAVID.MILLER@GAPAC.COM;DOROBINS@GAPAC.COM;MARCOS.MIRANDA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 82772 |  |  | * |  | 2021-01-26 16:30 | 2021-01-26 18:30 | DATA | CROSS | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90970 | WBS.2.1.6.1.3.1.32 | N | N | Planned | Create file to load Procurement MDM with new MDG material numbers (remote keys) AFTER DELTA material load | 2 | 2021-01-28 08:45 | 2021-01-28 10:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SAI TEAM;JON LUKE DAVILA;DAVID MILLER;ARUN SHARMA;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JONLUKE.DAVILA@GAPAC.COM;DAVID.MILLER@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 95208,82800 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 10:45 | DATA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90971 | WBS.2.1.6.1.3.1.33 | N | N | Planned | Update Procurement MDM with the delta MDG Procured Material number (remote keys) | 4 | 2021-01-28 10:45 | 2021-01-28 14:45 | BRIAN MILLER | JBMILLER@GAPAC.COM | DAVID MILLER;ARUN SHARMA;SAI TEAM;DENISE ROBINSON;DATA ETL TEAM | DAVID.MILLER@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90970 |  |  | * |  | 2021-01-28 10:45 | 2021-01-28 14:45 | PTP | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
82804 | WBS.2.1.6.1.3.1.34 | N | N | Planned | Turn-ON DRFOUT, Turn OFF Change pointers for CLFMAS, MATMAS, MATQM in MDG after DELTA AS8 material signoff | 0.5 | 2021-01-28 09:45 | 2021-01-28 10:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DON ABBOTT;SAI TEAM;DATA ETL TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;TED.ZEIDLER@GAPAC.COM | DATA | 92473 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 10:15 | DATA | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92474 | WBS.2.1.6.1.3.1.35 | N | N | Planned | Close client in MDG for turning ON change pointers for materials | 1 | 2021-01-28 10:15 | 2021-01-28 11:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 82804 |  |  | * |  | 2021-01-28 10:15 | 2021-01-28 11:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92626 | WBS.2.1.6.1.3.1.36 | N | N | Planned | Turn ON job in S4 for MDG – S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL after DELTA material load | 0.25 | 2021-01-28 09:45 | 2021-01-28 10:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 92473 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 10:00 | BATCH | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95112 | WBS.2.1.6.1.3.1.37 | N | N | Planned | Update and confirm Procured Mat Outlook DLs for Product Master Extensions for new locations | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | KRISTINA KAUTH;COURTNEY ANDERSON;AMY EL-BASSIONI;SAI TEAM | KRISTINA.KAUTH@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | PTP | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95111 | WBS.2.1.6.1.3.1.38 | N | N | Planned | Update and confirm Finished Mat Outlook DLs for Product Master Extensions for new locations | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | COURTNEY MORTON | COURTNEY.MORTON@GAPAC.COM | MIKE BRUNNER;DOUG STANISLAWSKI;COURTNEY ANDERSON;AMY EL-BASSIONI;SAI TEAM;EWM TEAM | MIKE.BRUNNER@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92625 | WBS.2.1.6.1.3.1.39 | N | N | Planned | Turn ON job in S4 to trigger MATMAS Idocs downstream: S4_DATA_ZMM_SEND_MAT_S4ECC_BOTH after DELTA material load | 0.25 | 2021-01-28 09:45 | 2021-01-28 10:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUVENDU KUMAR;BRIAN DOBASH;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;SUNIL KORI;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 92473 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 10:00 | BATCH | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95110 | WBS.2.1.6.1.3.1.40 | N | N | Planned | Set up new DLs for Product Master Extensions for new locations | 1 | 2021-01-28 10:00 | 2021-01-28 11:00 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | AMY EL-BASSIONI;DENISE ROBINSON;SAI TEAM;KAREN HUNNICUTT;SHANKAR RAMNARAYANAN;DATA ETL TEAM | AMY.EL-BASSIONI@GAPAC.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRHUNNIC@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 95112,95111,92625 |  |  | * |  | 2021-01-28 10:00 | 2021-01-28 11:00 | DATA | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91029 | WBS.2.1.7 | N | N |  | Ramp Down ¦ Tech Activities - Post Conversions (Big 3) | 42.75 | 2021-01-28 08:45 | 2021-01-30 19:30 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-30 19:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91349 | WBS.2.1.7.1 | N | N |  | Ramp Down ¦ Tech Activities - Post Conversions (Big 3) - System Back-Ups | 42.75 | 2021-01-28 08:45 | 2021-01-30 19:30 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-30 19:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91071 | WBS.2.1.7.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Post Conversions (Big 3) - System Back-Ups | 42.75 | 2021-01-28 08:45 | 2021-01-30 19:30 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-30 19:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91116 | WBS.2.1.7.1.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - BW | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92441 | WBS.2.1.7.1.1.1.1 | N | N | Planned | Backup BW System - Post Data Conversions | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91115 | WBS.2.1.7.1.1.2 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - S/4HANA | 23.5 | 2021-01-28 08:45 | 2021-01-29 16:15 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-29 16:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92440 | WBS.2.1.7.1.1.2.1 | N | N | Planned | Backup S/4HANA System - Post Data Conversions | 3 | 2021-01-28 08:45 | 2021-01-28 11:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 11:45 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92329 | WBS.2.1.7.1.1.2.2 | N | N | Planned | Extract the Import History and Build the Import buffer for All system TRs | 4 | 2021-01-29 12:15 | 2021-01-29 16:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SUVENDU KUMAR;SAI TEAM;DEV TEAM | SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 16:15 | DEV - INFRA | CROSS | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91114 | WBS.2.1.7.1.1.3 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - MDG | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92445 | WBS.2.1.7.1.1.3.1 | N | N | Planned | Backup MDG System - Post Data Conversions | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91113 | WBS.2.1.7.1.1.4 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - PO | 0.25 | 2021-01-28 08:45 | 2021-01-28 09:00 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-28 09:00 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92446 | WBS.2.1.7.1.1.4.1 | N | N | Planned | Backup PO System - Post Data Conversions | 0.25 | 2021-01-28 08:45 | 2021-01-28 09:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:00 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91112 | WBS.2.1.7.1.1.5 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - GW | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92444 | WBS.2.1.7.1.1.5.1 | N | N | Planned | Backup GW System - Post Data Conversions | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91111 | WBS.2.1.7.1.1.6 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - CRM | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92442 | WBS.2.1.7.1.1.6.1 | N | N | Planned | Backup CRM System - Post Data Conversions | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91110 | WBS.2.1.7.1.1.7 | N | N |  | Ramp Down ¦ Tech Activities - Post Data Conversions – Big 3 – System Back-Ups - GRC | 42.75 | 2021-01-28 08:45 | 2021-01-30 19:30 | [8 empty] | * |  | 2021-01-28 08:45 | 2021-01-30 19:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92443 | WBS.2.1.7.1.1.7.1 | N | N | Planned | Backup GRC System - Post Data Conversions | 0.5 | 2021-01-28 08:45 | 2021-01-28 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10413,5763,82800,90676 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 09:15 | DEV - INFRA | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95226 | WBS.2.1.7.1.1.7.2 | N | N | Planned | Provide initial list of deliveries to be held in TOPS | 0.25 | 2021-01-29 17:00 | 2021-01-29 17:15 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KETAN PRADHAN;SAI TEAM;OTC TEAM;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 95221,97805 |  |  | * |  | 2021-01-29 15:00 | 2021-01-29 15:15 | OTC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95227 | WBS.2.1.7.1.1.7.3 | N | N | Planned | Validate delivery deletions updated the delivery xref table in ECC & S4 | 0.5 | 2021-01-30 19:00 | 2021-01-30 19:30 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | OTC TEAM;SAI TEAM;TRISHUL BUDDHA;KYNDAL CODY;ONI BORCHERS | PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TBUDDHA@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 92317,90697 |  |  | * |  | 2021-01-30 19:00 | 2021-01-30 19:30 | OTC | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
9264 | WBS.2.1.8 | N | N |  | Ramp Down ¦ Conversions - Dependent On Big 3 | 174.5 | 2021-01-17 21:45 | 2021-01-30 18:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-30 17:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91351 | WBS.2.1.8.1 | N | N |  | Ramp Down ¦ Conversions - Dependent On Big 3 - Conversion Objects | 174.5 | 2021-01-17 21:45 | 2021-01-30 18:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-30 17:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
5394 | WBS.2.1.8.1.1 | N | N |  | Ramp Down ¦ ITR_C0018 - Convert Equipment – AS8 | 63.25 | 2021-01-17 21:45 | 2021-01-21 19:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-21 19:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90283 | WBS.2.1.8.1.1.1 | N | N |  | Ramp Down ¦ ITR_C0018 - Convert Equipment – AS8 | 63.25 | 2021-01-17 21:45 | 2021-01-21 19:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-21 19:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
82989 | WBS.2.1.8.1.1.1.1 | N | N | Planned | ITR_C0018 - Provide load file for Convert equipment – AS8 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;KELLY STRASSBURGER;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | PTH | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5395 | WBS.2.1.8.1.1.1.2 | N | N | Planned | ITR_C0018 - Execute Preload - Convert equipment – AS8 | 4 | 2021-01-21 07:00 | 2021-01-21 11:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5393,82989,10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 11:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5396 | WBS.2.1.8.1.1.1.3 | N | N | Planned | ITR_C0018 - Validate Preload - Convert equipment – AS8 | 1 | 2021-01-21 11:00 | 2021-01-21 12:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;KELLY STRASSBURGER;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5395 |  |  | * |  | 2021-01-21 11:00 | 2021-01-21 12:00 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5397 | WBS.2.1.8.1.1.1.4 | N | N | Planned | ITR_C0018 - Execute Load program - Convert equipment – AS8 | 5 | 2021-01-21 12:00 | 2021-01-21 17:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5396 |  |  | * |  | 2021-01-21 12:00 | 2021-01-21 17:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5398 | WBS.2.1.8.1.1.1.5 | N | N | Planned | ITR_C0018 - Validate Load - Convert equipment – AS8 | 1 | 2021-01-21 17:00 | 2021-01-21 18:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;BOB BROWN;DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;GARY BENOIT | ERIC.REINDL@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 5397 |  |  | * |  | 2021-01-21 17:00 | 2021-01-21 18:00 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
81655 | WBS.2.1.8.1.1.1.6 | N | N | Planned | PTH - ITR_C0018 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert equipment – AS8) | 1 | 2021-01-21 18:00 | 2021-01-21 19:00 | TOMMY WOMACK | tommy.womack@gapac.com | DARRELL WATSON;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM | Darrell.watson@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | AC | 5398 |  |  | * |  | 2021-01-21 18:00 | 2021-01-21 19:00 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5414 | WBS.2.1.8.1.2 | N | N |  | Ramp Down ¦ ITR_C0020 Convert BOM – Functional Location Conversion – AS8 | 20.25 | 2021-01-21 07:00 | 2021-01-22 11:15 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 11:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90267 | WBS.2.1.8.1.2.1 | N | N |  | Ramp Down ¦ ITR_C0020 Convert BOM – Functional Location Conversion – AS8 | 20.25 | 2021-01-21 07:00 | 2021-01-22 11:15 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 11:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5415 | WBS.2.1.8.1.2.1.1 | N | N | Planned | IT ITR_C0020 - Execute Transform Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2021-01-21 07:00 | 2021-01-21 11:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5393,5408,10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 11:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5416 | WBS.2.1.8.1.2.1.2 | N | N | Planned | ITR_C0020 - Validate Preload Transform - Convert BOM – Functional Location Conversion – AS8 | 1 | 2021-01-21 15:45 | 2021-01-21 16:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5415,5471 |  |  | * |  | 2021-01-21 15:45 | 2021-01-21 16:45 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5417 | WBS.2.1.8.1.2.1.3 | N | N | Planned | ITR_C0020 - Execute Load Program - Convert BOM – Functional Location Conversion – AS8 | 4 | 2021-01-21 16:45 | 2021-01-21 20:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5416 |  |  | * |  | 2021-01-21 16:45 | 2021-01-21 20:45 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5418 | WBS.2.1.8.1.2.1.4 | N | N | Planned | ITR_C0020 - Validate Load - Convert BOM – Functional Location Conversion – AS8 | 2.5 | 2021-01-21 20:45 | 2021-01-22 07:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5417 |  |  | * |  | 2021-01-21 20:45 | 2021-01-22 07:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
81654 | WBS.2.1.8.1.2.1.5 | N | N | Planned | PTH - ITR_C0020 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert BOM – Functional Location Conversion – AS8) | 4 | 2021-01-22 07:15 | 2021-01-22 11:15 | DANIEL HENDERSON | daniel.henderson@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5418 |  |  | * |  | 2021-01-22 07:15 | 2021-01-22 11:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5399 | WBS.2.1.8.1.3 | N | N |  | Ramp Down ¦ ITR_C0024 - Convert BOM - Material / Assemblies Conversion – AS8 | 10 | 2021-01-22 07:15 | 2021-01-22 17:15 | [8 empty] | * |  | 2021-01-22 07:15 | 2021-01-22 17:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90265 | WBS.2.1.8.1.3.1 | N | N |  | Ramp Down ¦ ITR_C0024 - Convert BOM - Material / Assemblies Conversion – AS8 | 10 | 2021-01-22 07:15 | 2021-01-22 17:15 | [8 empty] | * |  | 2021-01-22 07:15 | 2021-01-22 17:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5400 | WBS.2.1.8.1.3.1.1 | N | N | Planned | ITR_C0024 - Execute Transform Program - Convert BOM - Material / Assemblies Conversion – AS8 | 2 | 2021-01-22 07:15 | 2021-01-22 09:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5408,10428,5418 |  |  | * |  | 2021-01-22 07:15 | 2021-01-22 09:15 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5401 | WBS.2.1.8.1.3.1.2 | N | N | Planned | ITR_C0024 - Validate Preload Transform - Convert BOM - Material / Assemblies Conversion – AS8 | 1 | 2021-01-22 09:15 | 2021-01-22 10:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5400,10428,5418 |  |  | * |  | 2021-01-22 09:15 | 2021-01-22 10:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5402 | WBS.2.1.8.1.3.1.3 | N | N | Planned | ITR_C0024 - Execute Load Program - Convert BOM - Material / Assemblies Conversion – AS8 | 5 | 2021-01-22 10:15 | 2021-01-22 15:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5401 |  |  | * |  | 2021-01-22 10:15 | 2021-01-22 15:15 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5403 | WBS.2.1.8.1.3.1.4 | N | N | Planned | ITR_C0024 - Validate Load - Convert BOM - Material / Assemblies Conversion – AS8 | 1 | 2021-01-22 15:15 | 2021-01-22 16:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5402 |  |  | * |  | 2021-01-22 15:15 | 2021-01-22 16:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
81599 | WBS.2.1.8.1.3.1.6 | N | N | Planned | PTH - ITR_C0024 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert BOM - Material / Assemblies Conversion – AS8) | 1 | 2021-01-22 16:15 | 2021-01-22 17:15 | DANIEL HENDERSON | daniel.henderson@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5403 |  |  | * |  | 2021-01-22 16:15 | 2021-01-22 17:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5447 | WBS.2.1.8.1.4 | N | N |  | Ramp Down ¦ ITR_C0038.1 - Convert Task Lists – Functional Location – AS8 | 16 | 2021-01-21 07:00 | 2021-01-22 07:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 07:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90271 | WBS.2.1.8.1.4.1 | N | N |  | Ramp Down ¦ ITR_C0038.1 - Convert Task Lists – Functional Location – AS8 | 16 | 2021-01-21 07:00 | 2021-01-22 07:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 07:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5448 | WBS.2.1.8.1.4.1.1 | N | N | Planned | ITR_C0038.1 - Execute Transform program - Convert Task Lists – Functional Location – AS8 | 2 | 2021-01-21 07:00 | 2021-01-21 09:00 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5393,5408,10428,5456,82900 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 09:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5449 | WBS.2.1.8.1.4.1.2 | N | N | Planned | ITR_C0038.1 - Validate Preload Transform - Convert Task Lists – Functional Location – AS8 | 1 | 2021-01-21 09:00 | 2021-01-21 10:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5448 |  |  | * |  | 2021-01-21 09:00 | 2021-01-21 10:00 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5450 | WBS.2.1.8.1.4.1.3 | N | N | Planned | ITR_C0038.1 - Execute Load program - Convert Task Lists – Functional Location – AS8 | 5 | 2021-01-21 10:00 | 2021-01-21 15:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | VENKATESH GANESHAN;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | VGANESHAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5449 |  |  | * |  | 2021-01-21 10:00 | 2021-01-21 15:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5451 | WBS.2.1.8.1.4.1.4 | N | N | Planned | ITR_C0038.1 - Validate Load - Convert Task Lists – Functional Location – AS8 | 4 | 2021-01-21 15:00 | 2021-01-21 19:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5450 |  |  | * |  | 2021-01-21 15:00 | 2021-01-21 19:00 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
81657 | WBS.2.1.8.1.4.1.6 | N | N | Planned | PTH - ITR_C0038.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data | 4 | 2021-01-21 19:00 | 2021-01-22 07:00 | DARRELL WATSON | Darrell.watson@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5451 |  |  | * |  | 2021-01-21 19:00 | 2021-01-22 07:00 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5467 | WBS.2.1.8.1.5 | N | N |  | Ramp Down ¦ ITR_C0038.6 - Convert Task Lists - General Conversion – AS8 | 11.25 | 2021-01-21 07:00 | 2021-01-21 18:15 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-21 18:15 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90272 | WBS.2.1.8.1.5.1 | N | N |  | Ramp Down ¦ ITR_C0038.6 - Convert Task Lists - General Conversion – AS8 | 11.25 | 2021-01-21 07:00 | 2021-01-21 18:15 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-21 18:15 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5468 | WBS.2.1.8.1.5.1.1 | N | N | Planned | ITR_C0038.6 - Execute Transform program - Convert Task Lists - General Conversion – AS8 | 2 | 2021-01-21 07:00 | 2021-01-21 09:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5408,10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 09:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5469 | WBS.2.1.8.1.5.1.2 | N | N | Planned | ITR_C0038.6 - Validate Preload Transform - Convert Task Lists - General Conversion – AS8 | 0.75 | 2021-01-21 10:00 | 2021-01-21 10:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5468,5449 |  |  | * |  | 2021-01-21 10:00 | 2021-01-21 10:45 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5470 | WBS.2.1.8.1.5.1.3 | N | N | Planned | ITR_C0038.6 - Execute Load program - Convert Task Lists - General Conversion – AS8 | 1 | 2021-01-21 10:45 | 2021-01-21 11:45 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | VENKATESH GANESHAN;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | VGANESHAN@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5469 |  |  | * |  | 2021-01-21 10:45 | 2021-01-21 11:45 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5471 | WBS.2.1.8.1.5.1.4 | N | N | Planned | ITR_C0038.6 - Validate Load - Convert Task Lists - General Conversion – AS8 | 4 | 2021-01-21 11:45 | 2021-01-21 15:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5470 |  |  | * |  | 2021-01-21 11:45 | 2021-01-21 15:45 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
81659 | WBS.2.1.8.1.5.1.5 | N | N | Planned | PTH - ITR_C0038.6 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data For Converted Task Lists - AS8 | 2.5 | 2021-01-21 15:45 | 2021-01-21 18:15 | DARRELL WATSON | Darrell.watson@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5471 |  |  | * |  | 2021-01-21 15:45 | 2021-01-21 18:15 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5472 | WBS.2.1.8.1.6 | N | N |  | Ramp Down ¦ ITR_C0050 - Convert Maintenance Plans Conversion – AS8 | 10.5 | 2021-01-21 19:00 | 2021-01-22 13:30 | [8 empty] | * |  | 2021-01-21 19:00 | 2021-01-22 13:30 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90266 | WBS.2.1.8.1.6.1 | N | N |  | Ramp Down ¦ ITR_C0050 - Convert Maintenance Plans Conversion – AS8 | 10.5 | 2021-01-21 19:00 | 2021-01-22 13:30 | [8 empty] | * |  | 2021-01-21 19:00 | 2021-01-22 13:30 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5473 | WBS.2.1.8.1.6.1.1 | N | N | Planned | ITR_C0050 - Execute Transform Program - Convert Maintenance Plans Conversion – AS8 | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | ANKIT AGARWAL;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | ANKITAGARWAL87@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5451,5471 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 22:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5474 | WBS.2.1.8.1.6.1.2 | N | N | Planned | ITR_C0050 - Validate Preload Transform - Convert Maintenance Plans Conversion – AS8 | 0.5 | 2021-01-22 06:00 | 2021-01-22 06:30 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5473 |  |  | * |  | 2021-01-22 06:00 | 2021-01-22 06:30 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5475 | WBS.2.1.8.1.6.1.3 | N | N | Planned | ITR_C0050 - Execute Load Program - Convert Maintenance Plans Conversion – AS8 | 2 | 2021-01-22 08:00 | 2021-01-22 10:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5474,95484 |  |  | * |  | 2021-01-22 08:00 | 2021-01-22 10:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5476 | WBS.2.1.8.1.6.1.4 | N | N | Planned | ITR_C0050 - Validate Load - Convert Maintenance Plans Conversion – AS8 | 1 | 2021-01-22 11:00 | 2021-01-22 12:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5475,95482 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 12:00 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
81661 | WBS.2.1.8.1.6.1.6 | N | N | Planned | PTH - ITR_C0050 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert Maintenance Plans Conversion – AS8) | 1.5 | 2021-01-22 12:00 | 2021-01-22 13:30 | TOMMY WOMACK | tommy.womack@gapac.com | DARRELL WATSON;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Darrell.watson@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5476 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 13:30 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95482 | WBS.2.1.8.1.6.1.11 | N | N | Planned | Update release indicator - IP18 | 1 | 2021-01-22 10:00 | 2021-01-22 11:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | KELLY STRASSBURGER;SAI TEAM | KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5475 |  |  | * |  | 2021-01-22 10:00 | 2021-01-22 11:00 | AC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95484 | WBS.2.1.8.1.6.1.12 | N | N | Planned | Update the strategy and package for hour based plans on 38.1 | 2 | 2021-01-22 06:00 | 2021-01-22 08:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | GAURAV BHATIA;KELLY STRASSBURGER;AC TEAM;SAI TEAM | GBHATIA@DELOITTE.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5473 |  |  | * |  | 2021-01-22 06:00 | 2021-01-22 08:00 | AC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5182 | WBS.2.1.8.1.7 | N | N |  | Ramp Down ¦ PTM_C0080 - Convert Bill of Materials | 56.75 | 2021-01-18 06:15 | 2021-01-21 15:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-21 15:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90275 | WBS.2.1.8.1.7.1 | N | N |  | Ramp Down ¦ PTM_C0080 - Convert Bill of Materials | 56.75 | 2021-01-18 06:15 | 2021-01-21 15:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-21 15:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
4037 | WBS.2.1.8.1.7.1.1 | N | N | Planned | PTM_C0080 - Prepare M-BOM upload file | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | BEN LEWIS;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | BENJAMIN.LEWIS@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | SCM | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94799 | WBS.2.1.8.1.7.1.2 | N | N | Planned | PTM_C0080 - Reconcile/Validate MBOM, Routing and Prod Version files (before RTR enrichment) | 10 | 2021-01-18 10:15 | 2021-01-18 20:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;CHIRAG PARIKH;SAI TEAM;SCM TEAM;DENISE ROBINSON;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;DOROBINS@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 4037,4047,4049 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 20:15 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9797 | WBS.2.1.8.1.7.1.3 | N | N | Planned | PTM_C0080 - Prepare BOM upload for Repetitive Manufacturing plants 1503, 1101, 1462, 1357 | 4 | 2021-01-18 08:00 | 2021-01-18 12:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4634 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 12:00 | RTR - PC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82286 | WBS.2.1.8.1.7.1.4 | N | N | Planned | PTM_C0080 - RTR Enrich SCM BOMs - PPDS | 4 | 2021-01-18 20:15 | 2021-01-19 08:15 | TONY SMITH | AJSMITH@GAPAC.COM | JACOB DENNIS;BEN LEWIS;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4037,94799 |  |  | * |  | 2021-01-18 20:15 | 2021-01-19 08:15 | RTR - PC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
80758 | WBS.2.1.8.1.7.1.5 | N | N | Planned | PTM_C0080 - Validate MBOM, Routing and Prod Version files after RTR enrichment and upload to sharepoint | 8 | 2021-01-19 08:15 | 2021-01-19 16:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | BEN LEWIS;CHANDRA BALASUBRAMANIAN;CHIRAG PARIKH;SAI TEAM;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | BENJAMIN.LEWIS@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 82956,82287,82286 |  |  | * |  | 2021-01-19 08:15 | 2021-01-19 16:15 | SCM | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94769 | WBS.2.1.8.1.7.1.6 | N | N | Planned | Update Unit of Issue for BOM components and also certain master data fields for Printed boards for BOMs | 2 | 2021-01-19 16:15 | 2021-01-19 18:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | TONY SMITH;LINDSAY SAVAGE;SHANKAR RAMNARAYANAN;DENISE ROBINSON;SAI TEAM;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO | AJSMITH@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 80758 |  |  | * |  | 2021-01-19 16:15 | 2021-01-19 18:15 | DATA | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94770 | WBS.2.1.8.1.7.1.7 | N | N | Planned | Replicate changes for Unit of Issue and Printed boards master data updates needed for BOMs | 1 | 2021-01-19 18:15 | 2021-01-19 19:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SHANKAR RAMNARAYANAN;JIM KIJEK;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM;JEKIJEK@GAPAC.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 94769 |  |  | * |  | 2021-01-19 18:15 | 2021-01-19 19:15 | DATA | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9798 | WBS.2.1.8.1.7.1.8 | N | N | Planned | PTM_C0080 - Execute Transform - Upload for Repetitive Manufacturing | 5 | 2021-01-19 19:15 | 2021-01-20 08:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9797,10372,94770 |  |  | * |  | 2021-01-19 19:15 | 2021-01-20 08:15 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10110 | WBS.2.1.8.1.7.1.9 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Bill of Materials (MBOMS) | 8 | 2021-01-19 19:15 | 2021-01-20 11:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JIM KIJEK;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JEKIJEK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10372,80758,94770,94724 |  |  | * |  | 2021-01-19 19:15 | 2021-01-20 11:15 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9799 | WBS.2.1.8.1.7.1.10 | N | N | Planned | PTM_C0080 - Analyze and Resolve errors for PTM_C0080 upload for Repetitive Manufacturing (Simulation) | 1 | 2021-01-20 08:15 | 2021-01-20 09:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;VISHNU CHIRALA;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9798 |  |  | * |  | 2021-01-20 08:15 | 2021-01-20 09:15 | RTR - PC | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10111 | WBS.2.1.8.1.7.1.11 | N | N | Planned | PTM_C0080 - Preload Validation - Convert Bill of Materials (MBOMS) | 1 | 2021-01-20 11:15 | 2021-01-20 12:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;NOEL CLARK;BEN LEWIS;TONY SMITH;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;NOEL.CLARK@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;AJSMITH@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 10110 |  |  | * |  | 2021-01-20 11:15 | 2021-01-20 12:15 | SCM | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
94724 | WBS.2.1.8.1.7.1.12 | N | N | Planned | PTM_C0080 - Preload Validation of file - Convert Bill of Materials (MBOMS) - RTR | 1 | 2021-01-19 16:15 | 2021-01-19 17:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;VISHNU CHIRALA;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 80758 |  |  | * |  | 2021-01-19 16:15 | 2021-01-19 17:15 | RTR - PC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90084 | WBS.2.1.8.1.7.1.13 | N | N | Planned | Turn off the workflow MD_CTM_Daily10min_Transfer which has the job MD_CTM_ZCTM_I0183_Z_D_CTM_BOM | 0.5 | 2021-01-20 12:15 | 2021-01-20 12:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;US GP BASIS;LSA TEAM;LINDSAY SAVAGE;MICHELLE AUSTIN-WILLARD;BRIAN WHITE;BEN LEWIS;TED ZEIDLER;JOHN J SMITH;DEAN PIPER;LYNN MCMURDO;KELLY HINSON;SURESH P;KESAVA BATTINA;PREETAM ROUT;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;USGPBASIS@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;KSHINSON@GAPAC.COM;suresh.p@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;preetam.rout@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 9799,10111 |  |  | * |  | 2021-01-20 12:15 | 2021-01-20 12:45 | BATCH | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90050 | WBS.2.1.8.1.7.1.14 | N | N | Planned | Change BOM partner profile to collect mode in MDG | 0.25 | 2021-01-20 12:15 | 2021-01-20 12:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER;ARLENE WALL;SARAVANA GNANAMOHAN;DEAN PIPER;LYNN MCMURDO | STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;AKWALL@GAPAC.COM;SARAVANAKUMAR.GNANAMOHAN@KOCHTC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9799,10111 |  |  | * |  | 2021-01-20 12:15 | 2021-01-20 12:30 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9800 | WBS.2.1.8.1.7.1.15 | N | N | Planned | PTM_C0080 - Execute Load in MDG - upload for Repetitive Manufacturing | 3 | 2021-01-20 12:45 | 2021-01-20 15:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 90050,9799,90084 |  |  | * |  | 2021-01-20 12:45 | 2021-01-20 15:45 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5183 | WBS.2.1.8.1.7.1.16 | N | N | Planned | PTM_C0080 - Execute Load in MDG - Convert Bill of Materials (MBOMS) | 8 | 2021-01-20 12:45 | 2021-01-20 20:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JIM KIJEK;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JEKIJEK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 90050,10111,90084,94724 |  |  | * |  | 2021-01-20 12:45 | 2021-01-20 20:45 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9801 | WBS.2.1.8.1.7.1.17 | N | N | Planned | PTM_C0080 - Validate Load in MDG - upload for Repetitive Manufacturing | 1 | 2021-01-20 15:45 | 2021-01-20 16:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;VISHNU CHIRALA;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9800 |  |  | * |  | 2021-01-20 15:45 | 2021-01-20 16:45 | RTR - PC | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5185 | WBS.2.1.8.1.7.1.18 | N | N | Planned | PTM_C0080 - Validate Load in MDG - Convert Bill of Materials (MBOMS) | 3 | 2021-01-20 20:45 | 2021-01-21 07:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;JON PINYON;NOEL CLARK;BRIAN WHITE;BEN LEWIS;TONY SMITH;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JWPINYON@GAPAC.COM;NOEL.CLARK@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;AJSMITH@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5183 |  |  | * |  | 2021-01-20 20:45 | 2021-01-21 07:45 | SCM | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90083 | WBS.2.1.8.1.7.1.19 | N | N | Planned | Turn ON the workflow MD_CTM_Daily10min_Transfer which has the job MD_CTM_ZCTM_I0183_Z_D_CTM_BOM | 0.5 | 2021-01-21 07:45 | 2021-01-21 08:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;US GP BASIS;LSA TEAM;LINDSAY SAVAGE;MICHELLE AUSTIN-WILLARD;BRIAN WHITE;BEN LEWIS;TED ZEIDLER;JOHN J SMITH;DEAN PIPER;LYNN MCMURDO;KELLY HINSON;SURESH P;KESAVA BATTINA;PREETAM ROUT;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;USGPBASIS@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;KSHINSON@GAPAC.COM;suresh.p@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;preetam.rout@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 9801,5185 |  |  | * |  | 2021-01-21 07:45 | 2021-01-21 08:15 | BATCH | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10334 | WBS.2.1.8.1.7.1.20 | N | N | Planned | PTM_C0080 - Business Sign-Off Load in MDG - Convert Bill of Materials (MBOMS) | 0.25 | 2021-01-21 07:45 | 2021-01-21 08:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JIM KIJEK;JON PINYON;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JEKIJEK@GAPAC.COM;JWPINYON@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5185 |  |  | * |  | 2021-01-21 07:45 | 2021-01-21 08:00 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5186 | WBS.2.1.8.1.7.1.21 | N | N | Planned | Replicate MBOMs (including Repetitive MFG BOMs from RTR) from MDG to S/4HANA | 4 | 2021-01-21 08:00 | 2021-01-21 12:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DENISE ROBINSON;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10334,9801 |  |  | * |  | 2021-01-21 08:00 | 2021-01-21 12:00 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
9802 | WBS.2.1.8.1.7.1.23 | N | N | Planned | Validate Repetitive Manufacturing MBOMS in S/4HANA after replication | 0.5 | 2021-01-21 12:00 | 2021-01-21 12:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;VISHNU CHIRALA;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5186 |  |  | * |  | 2021-01-21 12:00 | 2021-01-21 12:30 | RTR - PC | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5187 | WBS.2.1.8.1.7.1.24 | N | N | Planned | Validate SCM MBOMS in S/4HANA after replication - PPDS | 2 | 2021-01-21 12:00 | 2021-01-21 14:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | BEN LEWIS;CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | BENJAMIN.LEWIS@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5186 |  |  | * |  | 2021-01-21 12:00 | 2021-01-21 14:00 | SCM | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
90049 | WBS.2.1.8.1.7.1.25 | N | N | Planned | Change BOM partner profile to pass immediately in MDG | 0.25 | 2021-01-21 12:30 | 2021-01-21 12:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER;ARLENE WALL;SARAVANA GNANAMOHAN;DEAN PIPER;LYNN MCMURDO | STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;AKWALL@GAPAC.COM;SARAVANAKUMAR.GNANAMOHAN@KOCHTC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9801,10334,9802 |  |  | * |  | 2021-01-21 12:30 | 2021-01-21 12:45 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92651 | WBS.2.1.8.1.7.1.26 | N | N | Planned | Provide file for Overhead Group Updates to the Data | 1 | 2021-01-21 14:00 | 2021-01-21 15:00 | TONY SMITH | AJSMITH@GAPAC.COM | RTR TEAM;DONNA COOPER;AMY EL-BASSIONI;SAI TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;DCOOPER@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9797,5187 |  |  | * |  | 2021-01-21 14:00 | 2021-01-21 15:00 | RTR - PC | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5192 | WBS.2.1.8.1.8 | N | N |  | Ramp Down ¦ PTM_C0082 - Convert Routing Required For Planning & Execution From ECC Systems To S/4HANA | 101 | 2021-01-18 06:15 | 2021-01-26 11:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 11:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90274 | WBS.2.1.8.1.8.1 | N | N |  | Ramp Down ¦ PTM_C0082 - Convert Routing Required For Planning & Execution From ECC Systems To S/4HANA | 101 | 2021-01-18 06:15 | 2021-01-26 11:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 11:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
4047 | WBS.2.1.8.1.8.1.1 | N | N | Planned | PTM_C0082 - Prepare Routing upload file - SCM | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | SCM TEAM;BEN LEWIS;CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BENJAMIN.LEWIS@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | SCM | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9803 | WBS.2.1.8.1.8.1.2 | N | N | Planned | PTM_C0082 - Prepare Routing upload for Repetitive Manufacturing plants 1034, 1376, 1459 | 3 | 2021-01-19 14:15 | 2021-01-19 17:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4634,89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 17:15 | RTR - PC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82287 | WBS.2.1.8.1.8.1.3 | N | N | Planned | PTM_C0082 - RTR Enrich SCM Routings - PPDS | 4 | 2021-01-18 20:15 | 2021-01-19 08:15 | TONY SMITH | AJSMITH@GAPAC.COM | JACOB DENNIS;BRIAN WHITE;CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;MICHELLE AUSTIN-WILLARD;JIM KIJEK;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;MICHELLE.AUSTIN@GAPAC.COM;JEKIJEK@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4047,94799 |  |  | * |  | 2021-01-18 20:15 | 2021-01-19 08:15 | RTR - PC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10023 | WBS.2.1.8.1.8.1.4 | N | N | Planned | PTM_C0082 - Execute Preload for Convert Routing (simulation mode) | 2 | 2021-01-20 10:00 | 2021-01-20 12:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89709,80758,89619 |  |  | * |  | 2021-01-20 10:00 | 2021-01-20 12:00 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10024 | WBS.2.1.8.1.8.1.5 | N | N | Planned | PTM_C0082 - Validate Preload simulation results for Convert Routings | 1 | 2021-01-20 12:00 | 2021-01-20 13:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;BRIAN WHITE;BEN LEWIS;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 10023 |  |  | * |  | 2021-01-20 12:00 | 2021-01-20 13:00 | SCM | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5193 | WBS.2.1.8.1.8.1.6 | N | N | Planned | PTM_C0082 - Execute Actual Load - Convert Routings | 4 | 2021-01-20 13:00 | 2021-01-20 17:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JIM KIJEK;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JEKIJEK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10024 |  |  | * |  | 2021-01-20 13:00 | 2021-01-20 17:00 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
97456 | WBS.2.1.8.1.8.1.21 | N | N | Planned | Component prod storage locations updated & Provide Green light to start Routing component allocation run | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;BRIAN WHITE;BEN LEWIS;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | DATA | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | DATA | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95613 | WBS.2.1.8.1.8.1.7 | N | N | Planned | Run routing component allocation logic after BOM replication to S4 | 2 | 2021-01-26 07:15 | 2021-01-26 09:15 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;CHANDRA BALASUBRAMANIAN;ANUPAM SHRIVASTAVA;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5187,5193,10854,97456 |  |  | * |  | 2021-01-26 07:15 | 2021-01-26 09:15 | DATA | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95614 | WBS.2.1.8.1.8.1.8 | N | N | Planned | Verify component allocation | 2 | 2021-01-26 09:15 | 2021-01-26 11:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | ANUPAM SHRIVASTAVA;JIM KIJEK;SCM TEAM;SAI TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B | ANUPSHRIVASTAVA@DELOITTE.COM;JEKIJEK@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM | SCM | 95613,97456 |  |  | * |  | 2021-01-26 09:15 | 2021-01-26 11:15 | SCM | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5194 | WBS.2.1.8.1.8.1.9 | N | N | Planned | PTM_C0082 - Technical validation of Routing data load | 1 | 2021-01-20 17:00 | 2021-01-20 18:00 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5193 |  |  | * |  | 2021-01-20 17:00 | 2021-01-20 18:00 | SCM | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5195 | WBS.2.1.8.1.8.1.10 | N | N | Planned | PTM_C0082 - Validate Load - Convert Routings | 1 | 2021-01-20 18:00 | 2021-01-20 19:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;BRIAN WHITE;BEN LEWIS;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5194 |  |  | * |  | 2021-01-20 18:00 | 2021-01-20 19:00 | SCM | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9804 | WBS.2.1.8.1.8.1.11 | N | N | Planned | PTM_C0082 - Execute Preload - upload routes for Repetitive Manufacturing (Simulation Mode) | 3 | 2021-01-20 10:00 | 2021-01-20 13:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | VISHNU CHIRALA;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9803,10120,89709,89619 |  |  | * |  | 2021-01-20 10:00 | 2021-01-20 13:00 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82855 | WBS.2.1.8.1.8.1.12 | N | N | Planned | PTM_C0082 - Analyze and Resolve errors for upload for Repetitive Manufacturing (Simulation) | 1 | 2021-01-20 13:00 | 2021-01-20 14:00 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9804 |  |  | * |  | 2021-01-20 13:00 | 2021-01-20 14:00 | RTR - PC | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82854 | WBS.2.1.8.1.8.1.13 | N | N | Planned | PTM_C0082 - Execute Load in S/4 - upload routings for Repetitive Manufacturing | 1 | 2021-01-20 14:00 | 2021-01-20 15:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 82855,92189 |  |  | * |  | 2021-01-20 14:00 | 2021-01-20 15:00 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9807 | WBS.2.1.8.1.8.1.14 | N | N | Planned | PTM_C0082 - Validate Load - upload for Repetitive Manufacturing Routings | 2 | 2021-01-20 15:00 | 2021-01-20 17:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82854 |  |  | * |  | 2021-01-20 15:00 | 2021-01-20 17:00 | RTR - PC | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95363 | WBS.2.1.8.1.8.1.15 | N | N | Planned | PTM_C0082 - Business Sign-Off Load - Convert Routing | 0.5 | 2021-01-20 19:00 | 2021-01-20 19:30 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JIM KIJEK;JON PINYON;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JEKIJEK@GAPAC.COM;JWPINYON@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5195 |  |  | * |  | 2021-01-20 19:00 | 2021-01-20 19:30 | DATA | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95487 | WBS.2.1.8.1.8.1.16 | N | N | Planned | Validate that 'START DATE' on ROUTING Ops is on or after Validity DT of Work Center | 2 | 2021-01-20 19:00 | 2021-01-20 21:00 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;ROBERT WAGNER;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ROBERT.WAGNER1@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5195 |  |  | * |  | 2021-01-20 19:00 | 2021-01-20 21:00 | RTR - PLC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
8796 | WBS.2.1.8.1.9 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Costing Production Versions Required For Planning & Execution From ECC To S/4HANA | 140.75 | 2021-01-18 06:15 | 2021-01-28 19:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 19:00 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90273 | WBS.2.1.8.1.9.1 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Costing Production Versions Required For Planning & Execution From ECC To S/4HANA | 140.75 | 2021-01-18 06:15 | 2021-01-28 19:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 19:00 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
4049 | WBS.2.1.8.1.9.1.1 | N | N | Planned | PTM_C0085 - Prepare ProdVersion Upload File - SCM | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | BEN LEWIS;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | BENJAMIN.LEWIS@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | SCM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96564 | WBS.2.1.8.1.9.1.20 | N | N | Planned | HBG - Provide file for 1459 - SFG materials price | 0.5 | 2021-01-18 18:45 | 2021-01-18 19:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 9178 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:15 | RTR - PC | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94869 | WBS.2.1.8.1.9.1.10 | N | N | Planned | RTR_E0349 - Provide Routing Classifications Load File | 2 | 2021-01-20 19:00 | 2021-01-20 21:00 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;ROBERT WAGNER;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ROBERT.WAGNER1@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5195,9807 |  |  | * |  | 2021-01-20 19:00 | 2021-01-20 21:00 | RTR - PLC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
94870 | WBS.2.1.8.1.9.1.11 | N | N | Planned | RTR_E0349 - Execute Load For Routing Classifications | 2 | 2021-01-20 21:00 | 2021-01-21 07:00 | PAUL WILLENBRING | PAUL.WILLENBRING2@GAPAC.COM | CARTER BRISCOE;TODD ROSNOW;SAI TEAM;RTR TEAM;ROBERT WAGNER;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | CARTER.BRISCOE@GAPAC.COM;TAROSNOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ROBERT.WAGNER1@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95487,94869 |  |  | * |  | 2021-01-20 21:00 | 2021-01-21 07:00 | RTR - PLC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
95707 | WBS.2.1.8.1.9.1.12 | N | N | Planned | Provide master data changes for transfer rolls between live sites and update pricing or not live sites | 0.5 | 2021-01-20 10:00 | 2021-01-20 10:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 89709 |  |  | * |  | 2021-01-20 10:00 | 2021-01-20 10:30 | RTR - PLC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95708 | WBS.2.1.8.1.9.1.13 | N | N | Planned | Make transfer roll master data changes | 1 | 2021-01-20 10:30 | 2021-01-20 11:30 | JIM KIJEK | JEKIJEK@GAPAC.COM | DENISE ROBINSON;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | DOROBINS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95707 |  |  | * |  | 2021-01-20 10:30 | 2021-01-20 11:30 | RTR - PLC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
94871 | WBS.2.1.8.1.9.1.14 | N | N | Planned | RTR_E0349 - Validate Load For Routing Classifications | 2 | 2021-01-21 07:00 | 2021-01-21 09:00 | TODD ROSNOW | TAROSNOW@GAPAC.COM | PAUL WILLENBRING;SAI TEAM;RTR TEAM;ROBERT WAGNER;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | PAUL.WILLENBRING2@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ROBERT.WAGNER1@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94870,95707,95708 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 09:00 | RTR - PLC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5551 | WBS.2.1.8.1.9.1.15 | N | N | Planned | Cost rolls GP00 for 1034, 1376, 1459 Plant - Calculation of Std cost using CK40N ( pre mark and release, resolve errors) | 6 | 2021-01-25 06:00 | 2021-01-25 12:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;NOEL CLARK;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7906,97466,97467 |  |  | * |  | 2021-01-25 06:00 | 2021-01-25 12:00 | RTR - PC | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
68440 | WBS.2.1.8.1.9.1.16 | N | N | Planned | Validate Costing Results In S/4HANA Against Specs Using Comparison Tool And Sign-Off On Results | 48 | 2021-01-25 12:00 | 2021-01-28 12:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;VISHNU CHIRALA;SAI TEAM;DONNA SMITH;NOEL CLARK;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5551 |  |  | * |  | 2021-01-25 12:00 | 2021-01-28 12:00 | RTR - PC | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
7917 | WBS.2.1.8.1.9.1.17 | N | N | Planned | Cost rolls GPGR 1034, 1376, 1459 Plant - Calculation of Std cost using CK40N ( pre mark and release, resolve errors) | 3 | 2021-01-28 12:00 | 2021-01-28 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 68440 |  |  | * |  | 2021-01-28 12:00 | 2021-01-28 15:00 | RTR - PC | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
7918 | WBS.2.1.8.1.9.1.18 | N | N | Planned | Cost rolls GPPC for 1034, 1376, 1459 Plant - Calculation of Std cost using CK40N ( pre mark and release, resolve errors) | 3 | 2021-01-28 15:00 | 2021-01-28 18:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7917 |  |  | * |  | 2021-01-28 15:00 | 2021-01-28 18:00 | RTR - PC | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
89797 | WBS.2.1.8.1.9.1.19 | N | N | Planned | Validate Plants - 1034, 1376, 1459 release GP00=GPGR=GPPC | 1 | 2021-01-28 18:00 | 2021-01-28 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | TONY SMITH;SAI TEAM;DONNA SMITH;NOEL CLARK;SANDRA RICHARDS;RTR TEAM;PMO TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7918 |  |  | * |  | 2021-01-28 18:00 | 2021-01-28 19:00 | RTR - PC | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
5200 | WBS.2.1.8.1.10 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Production Versions Required For Planning & Execution From ECC To S/4HANA | 129.25 | 2021-01-18 20:15 | 2021-01-28 21:30 | [8 empty] | * |  | 2021-01-18 20:15 | 2021-01-28 21:30 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90282 | WBS.2.1.8.1.10.1 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Production Versions required for Planning & Execution from ECC To S/4HANA | 129.25 | 2021-01-18 20:15 | 2021-01-28 21:30 | [8 empty] | * |  | 2021-01-18 20:15 | 2021-01-28 21:30 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
9939 | WBS.2.1.8.1.10.1.1 | N | N | Planned | Creation of Control Cycles in S/4HANA (transaction LPK1) | 0.25 | 2021-01-19 14:15 | 2021-01-19 14:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | ANUPAM SHRIVASTAVA;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO | ANUPSHRIVASTAVA@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | SCM | 4667,94432,96559,89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 14:30 | SCM | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82956 | WBS.2.1.8.1.10.1.2 | N | N | Planned | PTM_C0085 Enrich Production Version load file (Costing) | 3 | 2021-01-18 20:15 | 2021-01-19 07:15 | TONY SMITH | AJSMITH@GAPAC.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;NOEL CLARK;BRIAN WHITE;BEN LEWIS;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;NOEL.CLARK@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94799 |  |  | * |  | 2021-01-18 20:15 | 2021-01-19 07:15 | RTR - PC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10022 | WBS.2.1.8.1.10.1.3 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions | 2 | 2021-01-21 14:00 | 2021-01-21 16:00 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;JIM KIJEK;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEKIJEK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5195,10334,5187,80758 |  |  | * |  | 2021-01-21 14:00 | 2021-01-21 16:00 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10021 | WBS.2.1.8.1.10.1.4 | N | N | Planned | PTM_C0085 Validate Preload Transform - Convert Production Versions | 2 | 2021-01-21 16:00 | 2021-01-21 18:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | SAI TEAM;CHANDRA BALASUBRAMANIAN;CHIRAG PARIKH;JENNIFER LI;BRIAN WHITE;BEN LEWIS;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 10022 |  |  | * |  | 2021-01-21 16:00 | 2021-01-21 18:00 | SCM | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5201 | WBS.2.1.8.1.10.1.5 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production versions | 1.5 | 2021-01-21 18:00 | 2021-01-21 19:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;JIM KIJEK;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEKIJEK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10021 |  |  | * |  | 2021-01-21 18:00 | 2021-01-21 19:30 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5202 | WBS.2.1.8.1.10.1.6 | N | N | Planned | PTM_C0085 Technical validation of ProdVersion data load | 5 | 2021-01-21 19:30 | 2021-01-22 08:30 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5201 |  |  | * |  | 2021-01-21 19:30 | 2021-01-22 08:30 | SCM | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95619 | WBS.2.1.8.1.10.1.7 | N | N | Planned | Execute ZIBPFAM table update program & Extract the new Setup Grp & Work center combinations that misses IBP Family assignment | 0.5 | 2021-01-28 12:45 | 2021-01-28 13:15 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 5202,95018,95021 |  |  | * |  | 2021-01-28 12:45 | 2021-01-28 13:15 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95618 | WBS.2.1.8.1.10.1.8 | N | N | Planned | Provide the missing IBP Family values to be maintained | 4 | 2021-01-28 13:15 | 2021-01-28 17:15 | BRIDGET T LEE | BTLEE@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;JEFFREY GILLIAM;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;JFGILLIA@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95619 |  |  | * |  | 2021-01-28 13:15 | 2021-01-28 17:15 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95617 | WBS.2.1.8.1.10.1.9 | N | N | Planned | Update the IBP Family values in the ZIBPFAM table | 2 | 2021-01-28 17:15 | 2021-01-28 19:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95618 |  |  | * |  | 2021-01-28 17:15 | 2021-01-28 19:15 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91863 | WBS.2.1.8.1.10.1.10 | N | N | Planned | IBP Confirms Daily Batch Job is complete & Turn off the Daily cycle | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | SCM | PTH,HBG,BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95616 | WBS.2.1.8.1.10.1.11 | N | N | Planned | Deployment Planning - Communication; save copy of deployment recs | 2 | 2021-01-28 06:45 | 2021-01-28 08:45 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO | KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | Business | 91863 |  |  | * |  | 2021-01-28 06:45 | 2021-01-28 08:45 | SCM | PTH,HBG,BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
5203 | WBS.2.1.8.1.10.1.12 | N | N | Planned | PTM_C0085 - Validate Load - Convert Production versions | 1.5 | 2021-01-22 08:30 | 2021-01-22 10:00 | JIM KIJEK | JEKIJEK@GAPAC.COM | CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;CHIRAG PARIKH;SAI TEAM;JENNIFER LI;BRIAN WHITE;BEN LEWIS;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JQLI@GAPAC.COM;BRIAN.WHITE@GAPAC.COM;BENJAMIN.LEWIS@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5202 |  |  | * |  | 2021-01-22 08:30 | 2021-01-22 10:00 | SCM | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
11032 | WBS.2.1.8.1.10.1.13 | N | N | Planned | PTM_C0085 - Business Sign-Off Load - Convert Production versions | 0.25 | 2021-01-22 10:00 | 2021-01-22 10:15 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JIM KIJEK;JON PINYON;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JEKIJEK@GAPAC.COM;JWPINYON@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5203 |  |  | * |  | 2021-01-22 10:00 | 2021-01-22 10:15 | DATA | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
91781 | WBS.2.1.8.1.10.1.14 | N | N | Planned | Assignment of apportionment structure to production version in plants 1503, 1101, 1462, 1357 | 1 | 2021-01-22 10:00 | 2021-01-22 11:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5203 |  |  | * |  | 2021-01-22 10:00 | 2021-01-22 11:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95218 | WBS.2.1.8.1.10.1.15 | N | N | Planned | Create Shifts, Shift Sequences, Capacity Variants and Connect Resources to Capacity Variants for D4 Sites | 4 | 2021-01-19 14:15 | 2021-01-19 18:15 | JOHN J SMITH | JOHNJ.SMITH@GAPAC.COM | MELISSA OLSEN;LISA SZCZUREK;FALKO KOEHLER;SCM TEAM;SAI TEAM | MELISSA.OLSEN@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;FKOEHLER@SCMO2.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 5783,89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 18:15 | SCM - TTN | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92236 | WBS.2.1.8.1.10.1.18 | N | N | Planned | HBG - Create Planned orders for HBG (Finished Goods) | 8 | 2021-01-28 11:15 | 2021-01-28 19:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM;LISA SZCZUREK;JOHN J SMITH;CHANDRA BALASUBRAMANIAN | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LISA.SZCZUREK@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM | Business | 95018,95218,90831,9669,95315 |  |  | * |  | 2021-01-28 11:15 | 2021-01-28 19:15 | SCM - TTN | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96566 | WBS.2.1.8.1.10.1.24 | N | N | Planned | BG - Create Planned orders for BG (Finished Goods) | 4 | 2021-01-28 11:15 | 2021-01-28 15:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;SAI TEAM;LYNN MCMURDO;DEAN PIPER;CHANDRA BALASUBRAMANIAN;JOHN J SMITH;LISA SZCZUREK | JORDAN.BUNDY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;CBALASUBRAMANIAN@DELOITTE.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM | Business | 95018,95218,90831,9669,95315 |  |  | * |  | 2021-01-28 11:15 | 2021-01-28 15:15 | SCM - TTN | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95125 | WBS.2.1.8.1.10.1.21 | N | N | Planned | PTH - Create Planned orders for PTH (Tissue Finished Goods) | 8 | 2021-01-28 11:15 | 2021-01-28 19:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM;CHANDRA BALASUBRAMANIAN | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM | Business | 95018,95218,90831,9669,95315 |  |  | * |  | 2021-01-28 11:15 | 2021-01-28 19:15 | SCM - TTN | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97552 | WBS.2.1.8.1.10.1.26 | N | N | Planned | PTH - Create Planned orders for PTH (Towel Finished Goods) Janet | 8 | 2021-01-28 11:15 | 2021-01-28 19:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM;CHANDRA BALASUBRAMANIAN | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM | Business | 95018,95218,90831,9669,95315 |  |  | * |  | 2021-01-28 11:15 | 2021-01-28 19:15 | SCM - TTN | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95124 | WBS.2.1.8.1.10.1.22 | N | N | Planned | Verify the Finished Goods planned orders and Date-fix - PTH/BG/HBG | 2 | 2021-01-28 19:15 | 2021-01-28 21:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | JOHN CASABURRI;SAI TEAM;SCM TEAM;BRAD WYMAN;JOHN J SMITH;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92236,95125,96566 |  |  | * |  | 2021-01-28 19:15 | 2021-01-28 21:15 | SCM | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97743 | WBS.2.1.8.1.10.1.27 | N | N | Planned | Green light to notify Production orders are created & to start IBP daily batch job | 0.25 | 2021-01-28 21:15 | 2021-01-28 21:30 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 95124 |  |  | * |  | 2021-01-28 21:15 | 2021-01-28 21:30 | SCM | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
91780 | WBS.2.1.8.1.10.1.23 | N | N | Planned | Validate Assignment of apportionment structure to production version in plants 1503, 1101, 1462, 1357 | 1 | 2021-01-22 11:00 | 2021-01-22 12:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 91781 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 12:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5214 | WBS.2.1.8.1.11 | N | N |  | Ramp Down ¦ PTM_C0092 - Convert Product Cost Collectors | 63.75 | 2021-01-18 21:15 | 2021-01-22 21:00 | [8 empty] | * |  | 2021-01-18 21:15 | 2021-01-22 21:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90260 | WBS.2.1.8.1.11.1 | N | N |  | Ramp Down ¦ PTM_C0092 - Convert Product Cost Collectors | 63.75 | 2021-01-18 21:15 | 2021-01-22 21:00 | [8 empty] | * |  | 2021-01-18 21:15 | 2021-01-22 21:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
89804 | WBS.2.1.8.1.11.1.1 | N | N | Planned | Add LSMW For Misc. Prod Versions | 2 | 2021-01-22 10:00 | 2021-01-22 12:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5203,9811 |  |  | * |  | 2021-01-22 10:00 | 2021-01-22 12:00 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95248 | WBS.2.1.8.1.11.1.2 | N | N | Planned | Confirm & Update REM Profile for all Rep Mfg Prod Versions | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 89804 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | RTR - PC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5549 | WBS.2.1.8.1.11.1.3 | N | N | Planned | PTM_C0092 - Load Activity rates (costing/legal) for all the Production/Work order cost centers only for go-live plants (PTH, HBG, LHV) | 2 | 2021-01-18 21:15 | 2021-01-19 07:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7888,36996 |  |  | * |  | 2021-01-18 21:15 | 2021-01-19 07:15 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
7913 | WBS.2.1.8.1.11.1.4 | N | N | Planned | RTR_E0114 - Validate Load Activity rates | 1 | 2021-01-19 07:15 | 2021-01-19 08:15 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5549 |  |  | * |  | 2021-01-19 07:15 | 2021-01-19 08:15 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
4055 | WBS.2.1.8.1.11.1.5 | N | N | Planned | PTM_C0092 - Prepare load file for Convert Product Cost Collectors -PE | 0.25 | 2021-01-22 12:00 | 2021-01-22 12:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;NOEL CLARK;SAI TEAM;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8932,89804 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 12:15 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
4056 | WBS.2.1.8.1.11.1.6 | N | N | Planned | PTM_C0092 - Validate, Business Sign Off, provide file for Convert Product Cost Collectors -PE | 1 | 2021-01-22 16:00 | 2021-01-22 17:00 | TONY SMITH | AJSMITH@GAPAC.COM | SANDRA RICHARDS;SAI TEAM;DONNA SMITH;NOEL CLARK;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4055,89804,95248 |  |  | * |  | 2021-01-22 16:00 | 2021-01-22 17:00 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5215 | WBS.2.1.8.1.11.1.7 | N | N | Planned | PTM_C0092 - Execute Load Program - Convert Product Cost Collectors - PE | 1 | 2021-01-22 17:00 | 2021-01-22 18:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 4056,11032 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 18:00 | DATA | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5216 | WBS.2.1.8.1.11.1.8 | N | N | Planned | PTM_C0092 - Post-Load Validation - Convert Product Cost Collectors | 0.5 | 2021-01-22 18:00 | 2021-01-22 18:30 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5215 |  |  | * |  | 2021-01-22 18:00 | 2021-01-22 18:30 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
89807 | WBS.2.1.8.1.11.1.9 | N | N | Planned | Run LSMW To Populate The Functional Areas In Cost Collectors | 0.5 | 2021-01-22 18:30 | 2021-01-22 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5216 |  |  | * |  | 2021-01-22 18:30 | 2021-01-22 19:00 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
89806 | WBS.2.1.8.1.11.1.10 | N | N | Planned | Validate The Functional Areas Are Updated On Cost Collectors | 1 | 2021-01-22 20:00 | 2021-01-22 21:00 | TONY SMITH | AJSMITH@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 97004 |  |  | * |  | 2021-01-22 20:00 | 2021-01-22 21:00 | RTR - PC | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5228 | WBS.2.1.8.1.12 | N | N |  | Ramp Down ¦ PTM_C0205 - Convert Product Master | 38 | 2021-01-21 07:00 | 2021-01-25 13:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-25 13:00 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90269 | WBS.2.1.8.1.12.1 | N | N |  | Ramp Down ¦ PTM_C0205 - Convert Product Master | 38 | 2021-01-21 07:00 | 2021-01-25 13:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-25 13:00 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
3955 | WBS.2.1.8.1.12.1.1 | N | N | Planned | PTM_C0205 - Extract MARD Data From S/4HANA For Product Master Upload File Worksheets By Site (Including MRO) into 1 Consolidated File | 12 | 2021-01-21 07:00 | 2021-01-21 19:00 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;MICHAEL MATTHEWS;SAI TEAM;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS | DAVID.BASCHE@GAPAC.COM;MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM | EWM | 10428,10846 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 19:00 | EWM | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8862 | WBS.2.1.8.1.12.1.2 | N | N | Planned | PTH - PTM_C0205 - Manually Update, Validate & Business Sign-Off Fixed Bin MRO Data on Product Master File - SCM MDM | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 22:00 | EWM | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96567 | WBS.2.1.8.1.12.1.33 | N | N | Planned | BG - PTM_C0205 - Manually Update, Validate & Business Sign-Off Fixed Bin MRO Data on Product Master File - SCM MDM | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 22:00 | EWM | BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
94302 | WBS.2.1.8.1.12.1.5 | N | N | Planned | HBG - PTM_C0205 - Manually Update, Validate & Business Sign-Off Fixed Bin MRO Data on Product Master File - SCM MDM | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 22:00 | EWM | HBG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
3956 | WBS.2.1.8.1.12.1.6 | N | N | Planned | PTH - PTM_C0205 - Manually Update, Validate & Business Sign-Off Mill non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | JAMES COWELL | James.Cowell@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ANDY JONES;DARRYL JOHNSON;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96568 | WBS.2.1.8.1.12.1.34 | N | N | Planned | BG - PTM_C0205 - Manually Update, Validate & Business Sign-Off Mill non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
94305 | WBS.2.1.8.1.12.1.9 | N | N | Planned | HBG - PTM_C0205 - Manually Update, Validate & Business Sign-Off Mill non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | HBG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8861 | WBS.2.1.8.1.12.1.10 | N | N | Planned | SCH - PTM_C0205 - Manually Update, Validate & Business Sign-Off Distribution Center non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | SCH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96699 | WBS.2.1.8.1.12.1.39 | N | N | Planned | RNC - PTM_C0205 - Manually Update, Validate & Business Sign-Off Distribution Center non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;LOCKLIN HINTON;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;LOCKLIN.HINTON@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | RNC | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96700 | WBS.2.1.8.1.12.1.40 | N | N | Planned | RVG - PTM_C0205 - Manually Update, Validate & Business Sign-Off Distribution Center non MRO data on Product Master File - SCM MDM | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | EWM | RVG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10032 | WBS.2.1.8.1.12.1.11 | N | N | Planned | PTM_C0205 - Execute Transform Program - Convert Product Master | 5 | 2021-01-22 06:00 | 2021-01-22 11:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10428,3956,8861,8862,94302,94305,96567,96568,96699,96700 |  |  | * |  | 2021-01-22 06:00 | 2021-01-22 11:00 | DATA | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95361 | WBS.2.1.8.1.12.1.12 | N | N | Planned | Technical Review of Product Master Transform | 1 | 2021-01-22 11:00 | 2021-01-22 12:00 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;JEFFREY GOLDMUNTZ;LEM LANCASTER;SANTOSH KUPPILI;EWM TEAM;SAI TEAM | AVTALREJA@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;VKUPPILI@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 10032 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 12:00 | EWM | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
10033 | WBS.2.1.8.1.12.1.13 | N | N | Planned | PTH - PTM_C0205 - (MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
96569 | WBS.2.1.8.1.12.1.35 | N | N | Planned | BG - PTM_C0205 - (MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
94316 | WBS.2.1.8.1.12.1.16 | N | N | Planned | HBG - PTM_C0205 - (MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | HBG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
94315 | WBS.2.1.8.1.12.1.17 | N | N | Planned | PTH - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Dan Ehrich;AVINASH TALREJA;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.EHRICH@GAPAC.COM;AVTALREJA@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
96570 | WBS.2.1.8.1.12.1.36 | N | N | Planned | BG - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
94312 | WBS.2.1.8.1.12.1.20 | N | N | Planned | HBG - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | HBG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
94311 | WBS.2.1.8.1.12.1.21 | N | N | Planned | SCH - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | SCH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
96701 | WBS.2.1.8.1.12.1.41 | N | N | Planned | RNC - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;LOCKLIN HINTON;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;LOCKLIN.HINTON@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | RNC | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
96702 | WBS.2.1.8.1.12.1.42 | N | N | Planned | RVG - PTM_C0205 - (Non-MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | RVG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5229 | WBS.2.1.8.1.12.1.22 | N | N | Planned | PTM_C0205 - Execute Load Program - Convert Product Master | 10 | 2021-01-22 16:00 | 2021-01-25 10:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10033,94316,94315,94312,94311,96569,96570,96701,96702 |  |  | * |  | 2021-01-22 16:00 | 2021-01-25 10:00 | DATA | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5231 | WBS.2.1.8.1.12.1.23 | N | N | Planned | SCH - PTM_C0205 - Validate Load for Distribution Centers Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96703 | WBS.2.1.8.1.12.1.43 | N | N | Planned | RNC - PTM_C0205 - Validate Load for Distribution Centers Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;JUSTIN KAINZ;CASSIE VANATTA;JORDAN SCHILLING;JEREMY RAY;DAVID ALENCASTRO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JUSTIN.KAINZ1@GAPAC.COM;CASSANDRA.VANATTA@GAPAC.COM;JORDAN_A_SCHILLING@RYDER.COM;JEREMY.RAY@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96704 | WBS.2.1.8.1.12.1.44 | N | N | Planned | RVG - PTM_C0205 - Validate Load for Distribution Centers Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | RVG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
8864 | WBS.2.1.8.1.12.1.24 | N | N | Planned | PTH - PTM_C0205 - Validate Load For Mills Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Dan Ehrich;AVINASH TALREJA;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.EHRICH@GAPAC.COM;AVTALREJA@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96571 | WBS.2.1.8.1.12.1.37 | N | N | Planned | BG - PTM_C0205 - Validate Load For Mills Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94320 | WBS.2.1.8.1.12.1.27 | N | N | Planned | HBG - PTM_C0205 - Validate Load For Mills Non-MRO - Convert Product Master | 2 | 2021-01-25 10:00 | 2021-01-25 12:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 12:00 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5230 | WBS.2.1.8.1.12.1.28 | N | N | Planned | PTH - PTM_C0205 - Validate Load MRO - Convert Product Master | 3 | 2021-01-25 10:00 | 2021-01-25 13:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 13:00 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96572 | WBS.2.1.8.1.12.1.38 | N | N | Planned | BG - PTM_C0205 - Validate Load MRO - Convert Product Master | 3 | 2021-01-25 10:00 | 2021-01-25 13:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 13:00 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94323 | WBS.2.1.8.1.12.1.31 | N | N | Planned | HBG - PTM_C0205 - Validate Load MRO - Convert Product Master | 3 | 2021-01-25 10:00 | 2021-01-25 13:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 13:00 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91820 | WBS.2.1.8.1.12.1.32 | N | N | Planned | Update Stock determination - ST for Raw materials + Update Process Type Determination Indicator to PR for Parent Rolls (All Mills) | 3 | 2021-01-25 10:00 | 2021-01-25 13:00 | NIKHIL NEGI | nikhnegi@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 13:00 | EWM | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95003 | WBS.2.1.8.1.13 | N | N |  | Ramp Down ¦ MFLE/MKLE | 172 | 2021-01-18 06:15 | 2021-01-30 18:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 17:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95002 | WBS.2.1.8.1.13.1 | N | N |  | Ramp Down ¦ MFLE/MKLE | 172 | 2021-01-18 06:15 | 2021-01-30 18:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 17:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95149 | WBS.2.1.8.1.13.1.5 | N | N | Planned | MFLE/MKLE - Deactivate E0428 Enhancement - Standard Cost Validation for Production Orders | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SANDRA RICHARDS;RTR TEAM;SUVENDU KUMAR;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 11032,10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:30 | RTR - PC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95021 | WBS.2.1.8.1.13.1.11 | N | N | Planned | MFLE/MKLE - Send PDS from S4 to PPDS | 2 | 2021-01-28 10:45 | 2021-01-28 12:45 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | CHIRAG PARIKH;SATISH KUMAR B;ANUPAM SHRIVASTAVA;SAI TEAM;BRAD WYMAN | CPARIKH@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 95018 |  |  | * |  | 2021-01-28 10:45 | 2021-01-28 12:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95018 | WBS.2.1.8.1.13.1.14 | N | N | Planned | Activate FG PVs for D4 Sites only | 4 | 2021-01-28 06:45 | 2021-01-28 10:45 | ANUPAM SHRIVASTAVA | ANUPSHRIVASTAVA@DELOITTE.COM | CHIRAG PARIKH;SATISH KUMAR B;SAI TEAM;CHANDRA BALASUBRAMANIAN;BRAD WYMAN | CPARIKH@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 91863 |  |  | * |  | 2021-01-28 06:45 | 2021-01-28 10:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95012 | WBS.2.1.8.1.13.1.21 | N | N | Planned | Delete MF50 planned orders for D4 sites | 4 | 2021-01-30 12:15 | 2021-01-30 16:15 | MICHAEL HOLLY | Michael.Holly@gapac.com | CHANDRA BALASUBRAMANIAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA;SAI TEAM;RAGHAVA GARRE;BRAD WYMAN;KIM LADZINSKE | CBALASUBRAMANIAN@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RAGHAVA.GARRE@KOCHTC.COM;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM | SCM | 95018,12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 16:15 | SCM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97849 | WBS.2.1.8.1.13.1.45 | N | N | Planned | Update Legacy work center characteristics value in S4 work center | 2 | 2021-01-30 16:15 | 2021-01-30 18:15 | RAGHAVA GARRE | RAGHAVA.GARRE@KOCHTC.COM | ANUPAM SHRIVASTAVA;BRAD WYMAN;CHANDRA BALASUBRAMANIAN;KIM LADZINSKE;MICHAEL HOLLY;SAI TEAM;SATISH KUMAR B | ANUPSHRIVASTAVA@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;KDLADZIN@GAPAC.COM;Michael.Holly@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM | SCM | 95012 |  |  | * |  | 2021-01-30 16:15 | 2021-01-30 18:15 | SCM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97403 | WBS.2.1.8.1.13.1.42 | N | N | Planned | Check for any planned orders and Purchase requisitions in the past for ZPAK materials and delete them in S4P | 1 | 2021-01-30 16:15 | 2021-01-30 17:15 | RAGHAVA GARRE | RAGHAVA.GARRE@KOCHTC.COM | ANUPAM SHRIVASTAVA;BRAD WYMAN;CHANDRA BALASUBRAMANIAN;KIM LADZINSKE;MICHAEL HOLLY;SAI TEAM;SATISH KUMAR B | ANUPSHRIVASTAVA@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;KDLADZIN@GAPAC.COM;Michael.Holly@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM | SCM | 95012,12178 |  |  | * |  | 2021-01-30 16:15 | 2021-01-30 17:15 | SCM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95142 | WBS.2.1.8.1.13.1.33 | N | N | Planned | Dixie Team: Save copy of deployment recs, guideline through 2/12 shipping. | 3 | 2021-01-28 08:45 | 2021-01-28 11:45 | KAREN HERRING | KAREN.HERRING@GAPAC.COM | SARA LUX;SAI TEAM;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;BRAD WYMAN;MICHELLE SADLER | SARA.LUX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 91863,95616 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 11:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95143 | WBS.2.1.8.1.13.1.34 | N | N | Planned | Retail Towel/Napkin Team: Save copy of deployment recs, guideline through 2/12 shipping. | 3 | 2021-01-28 08:45 | 2021-01-28 11:45 | THEASUS PAUL | TTPAUL@GAPAC.COM | VALERIE TURNER;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN;MICHELLE SADLER | VALERIE.TURNER@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 91863,95616 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 11:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95145 | WBS.2.1.8.1.13.1.35 | N | N | Planned | Pro Team: Save copy of deployment recs, guideline through 2/12 shipping. | 3 | 2021-01-28 08:45 | 2021-01-28 11:45 | KATIE MARKS | KATIE.MARKS@GAPAC.COM | Mary Belschner;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN;MICHELLE SADLER | mary.belschner@gapac.com;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 91863,95616 |  |  | * |  | 2021-01-28 08:45 | 2021-01-28 11:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95146 | WBS.2.1.8.1.13.1.36 | N | N | Planned | Supply Planning - Communication Start; supply plan executed through 3/13 | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | SCM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95555 | WBS.2.1.8.1.13.1.37 | N | N | Planned | Supply Planning - Communication COMPLETE; supply plan executed through 3/13 | 3 | 2021-01-25 06:15 | 2021-01-25 09:15 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 95146,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 09:15 | SCM | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97834 | WBS.2.1.8.1.13.1.44 | N | N | Planned | Identify any deliveries not attached to an STO | 1 | 2021-01-25 09:15 | 2021-01-25 10:15 | JASON DANFORTH | jason.danforth@gapac.com | LISA BABIASH;MICHELLE SADLER;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN | lisa.babiash@gapac.com;BMSADLER@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 95555 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 10:15 | SCM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95147 | WBS.2.1.8.1.13.1.38 | N | N | Planned | Deployment Planning - Communication Deployment | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | SCM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95315 | WBS.2.1.8.1.13.1.39 | N | N | Planned | Smoke test production order conversion for D3 Sites (Finished Goods) | 0.5 | 2021-01-28 10:45 | 2021-01-28 11:15 | ANUPAM SHRIVASTAVA | ANUPSHRIVASTAVA@DELOITTE.COM | CHIRAG PARIKH;SATISH KUMAR B;SAI TEAM;CHANDRA BALASUBRAMANIAN;SCM TEAM;BRAD WYMAN | CPARIKH@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM | SCM | 95018 |  |  | * |  | 2021-01-28 10:45 | 2021-01-28 11:15 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95314 | WBS.2.1.8.1.13.1.40 | N | N | Planned | Smoke test production order conversion for D3 Sites (Semi Finished Goods) | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | ANUPAM SHRIVASTAVA | ANUPSHRIVASTAVA@DELOITTE.COM | CHIRAG PARIKH;SATISH KUMAR B;SAI TEAM;CHANDRA BALASUBRAMANIAN;SCM TEAM;BRAD WYMAN | CPARIKH@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM | SCM | 11032,95149,90831,9669,10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97573 | WBS.2.1.8.1.13.1.43 | N | N | Planned | <Mock only> Create production orders for all live sites for dark period | 0.25 | 2021-01-28 11:15 | 2021-01-28 11:30 | MELISSA OLSEN | MELISSA.OLSEN@GAPAC.COM | CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;SCM TEAM;KRISTIE DOIRON;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KRISTIE.DOIRON@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 90831,9669,95018,95218,95315 |  |  | * |  | 2021-01-28 11:15 | 2021-01-28 11:30 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95620 | WBS.2.1.8.1.13.1.41 | N | N | Planned | Update the obsolete indicator on the ZIBPFAM entries | 5 | 2021-01-28 19:15 | 2021-01-29 08:15 | BRIDGET T LEE | BTLEE@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;JEFFREY GILLIAM;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;JFGILLIA@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501,92236,96566,95125 |  |  | * |  | 2021-01-28 19:15 | 2021-01-29 08:15 | SCM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
5232 | WBS.2.1.8.1.14 | N | N |  | Ramp Down ¦ PTP_C0001 - Convert PTP Contracts - ECC | 9 | 2021-01-18 10:45 | 2021-01-18 19:45 | [8 empty] | * |  | 2021-01-18 10:45 | 2021-01-18 19:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90279 | WBS.2.1.8.1.14.1 | N | N |  | Ramp Down ¦ PTP_C0001 - Convert PTP Contracts - ECC | 9 | 2021-01-18 10:45 | 2021-01-18 19:45 | [8 empty] | * |  | 2021-01-18 10:45 | 2021-01-18 19:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5233 | WBS.2.1.8.1.14.1.1 | N | N | Planned | PTP_C0001 - Execute Transform program - Convert PTP contracts | 2 | 2021-01-18 10:45 | 2021-01-18 12:45 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89679,89675,3964,82570,97452 |  |  | * |  | 2021-01-18 10:45 | 2021-01-18 12:45 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5234 | WBS.2.1.8.1.14.1.2 | N | N | Planned | PTP_C0001 - Validate Preload Transform - Convert PTP contracts | 2 | 2021-01-18 12:45 | 2021-01-18 14:45 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | BRUCE KIRKLEWSKI;SAI TEAM;CASEY HERMANSEN;ERIC BARSTOW;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5233 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 14:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5235 | WBS.2.1.8.1.14.1.3 | N | N | Planned | PTP_C0001 - Execute Load program - Contracts (Before load, manually create one contract but do not save) | 3 | 2021-01-18 14:45 | 2021-01-18 17:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5234 |  |  | * |  | 2021-01-18 14:45 | 2021-01-18 17:45 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5236 | WBS.2.1.8.1.14.1.4 | N | N | Planned | PTP_C0001 - Validate Load - Convert PTP contracts | 2 | 2021-01-18 17:45 | 2021-01-18 19:45 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | BRUCE KIRKLEWSKI;SAI TEAM;CASEY HERMANSEN;ERIC BARSTOW;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5235 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 19:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5242 | WBS.2.1.8.1.15 | N | N |  | Ramp Down ¦ PTP_C0008 - Convert Purchase Info Record - ECC | 70.25 | 2021-01-18 10:45 | 2021-01-22 17:00 | [8 empty] | * |  | 2021-01-18 10:45 | 2021-01-22 17:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90278 | WBS.2.1.8.1.15.1 | N | N |  | Ramp Down ¦ PTP_C0008 - Convert Purchase Info Record - ECC | 70.25 | 2021-01-18 10:45 | 2021-01-22 17:00 | [8 empty] | * |  | 2021-01-18 10:45 | 2021-01-22 17:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5243 | WBS.2.1.8.1.15.1.1 | N | N | Planned | PTP_C0008 - Execute Transform program - Convert Purchase Info Record - ECC | 1 | 2021-01-18 10:45 | 2021-01-18 11:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89675,89679,3964,82570,97452 |  |  | * |  | 2021-01-18 10:45 | 2021-01-18 11:45 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5244 | WBS.2.1.8.1.15.1.2 | N | N | Planned | PTP_C0008 - Validate Preload Transform - Convert Purchase Info Record - ECC | 2 | 2021-01-18 11:45 | 2021-01-18 13:45 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5243 |  |  | * |  | 2021-01-18 11:45 | 2021-01-18 13:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95365 | WBS.2.1.8.1.15.1.3 | N | N | Planned | PTP_C0008 - Provide list of FG PIRs for deletion- Convert Purchase Info Record - ECC | 1 | 2021-01-18 11:45 | 2021-01-18 12:45 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 5243 |  |  | * |  | 2021-01-18 11:45 | 2021-01-18 12:45 | PTP | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95364 | WBS.2.1.8.1.15.1.4 | N | N | Planned | PTP_C0008 - To perform deletion of FG PIRs - Convert Purchase Info Record - ECC | 1 | 2021-01-18 12:45 | 2021-01-18 13:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 95365 |  |  | * |  | 2021-01-18 12:45 | 2021-01-18 13:45 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5245 | WBS.2.1.8.1.15.1.5 | N | N | Planned | PTP_C0008 - Execute Load program - Convert Purchase Info Record - ECC | 4 | 2021-01-22 11:00 | 2021-01-22 15:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5244,5251,95364 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 15:00 | DATA | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5246 | WBS.2.1.8.1.15.1.6 | N | N | Planned | PTP_C0008 - Validate Load - Convert Purchase Info Record - ECC | 2 | 2021-01-22 15:00 | 2021-01-22 17:00 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5245 |  |  | * |  | 2021-01-22 15:00 | 2021-01-22 17:00 | PTP | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5247 | WBS.2.1.8.1.16 | N | N |  | Ramp Down ¦ PTP_C0008.1 - Convert Purchase Info Record - AS8 | 23 | 2021-01-21 07:00 | 2021-01-22 14:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 14:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90270 | WBS.2.1.8.1.16.1 | N | N |  | Ramp Down ¦ PTP_C0008.1 - Convert Purchase Info Record - AS8 | 23 | 2021-01-21 07:00 | 2021-01-22 14:00 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-22 14:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5248 | WBS.2.1.8.1.16.1.1 | N | N | Planned | PTP_C0008.1 - Execute Transform program - Convert Purchase Info Record - AS8 | 3 | 2021-01-21 07:00 | 2021-01-21 10:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10428,89675,89679 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 10:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5249 | WBS.2.1.8.1.16.1.2 | N | N | Planned | PTP_C0008.1 - Validate Preload Transform - Convert Purchase Info Record - AS8 | 2 | 2021-01-21 10:00 | 2021-01-21 12:00 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 5248 |  |  | * |  | 2021-01-21 10:00 | 2021-01-21 12:00 | PTP | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5250 | WBS.2.1.8.1.16.1.3 | N | N | Planned | PTP_C0008.1 - Execute Load program - Convert Purchase Info Record - AS8 | 13 | 2021-01-21 12:00 | 2021-01-22 09:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5249 |  |  | * |  | 2021-01-21 12:00 | 2021-01-22 09:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5251 | WBS.2.1.8.1.16.1.4 | N | N | Planned | PTP_C0008.1 - Validate Load - Convert Purchase Info Record - AS8 | 2 | 2021-01-22 09:00 | 2021-01-22 11:00 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 5250 |  |  | * |  | 2021-01-22 09:00 | 2021-01-22 11:00 | PTP | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92117 | WBS.2.1.8.1.16.1.5 | N | N | Planned | Begin Dual Maintenance for Locally Managed AS8 PIR | 1 | 2021-01-22 11:00 | 2021-01-22 12:00 | MASON DRAKE | MASON.DRAKE@GAPAC.COM | CASEY HERMANSEN;DOROTHY RUSSELL;ERIC BARSTOW;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 5251 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 12:00 | PTP | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92176 | WBS.2.1.8.1.16.1.6 | N | N | Planned | Check and update 'Auto PO' field based on AS8 PIR load & Create Inspection Type ( QMAT ) entries for deployment live sites Materials | 3 | 2021-01-22 11:00 | 2021-01-22 14:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 5251 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 14:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5252 | WBS.2.1.8.1.17 | N | N |  | Ramp Down ¦ PTP_C0200 - Source List Conversion - AS8 | 8 | 2021-01-22 11:00 | 2021-01-22 19:00 | [8 empty] | * |  | 2021-01-22 11:00 | 2021-01-22 19:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90264 | WBS.2.1.8.1.17.1 | N | N |  | Ramp Down ¦ PTP_C0200 - Source List Conversion AS8 | 8 | 2021-01-22 11:00 | 2021-01-22 19:00 | [8 empty] | * |  | 2021-01-22 11:00 | 2021-01-22 19:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5253 | WBS.2.1.8.1.17.1.1 | N | N | Planned | PTP_C0200 - Execute Transform Program - Source List Conversion - AS8 | 2 | 2021-01-22 11:00 | 2021-01-22 13:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5251,10428 |  |  | * |  | 2021-01-22 11:00 | 2021-01-22 13:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5254 | WBS.2.1.8.1.17.1.2 | N | N | Planned | PTP_C0200 - Validate Preload Transform - Source List Conversion - AS8 | 1 | 2021-01-22 13:00 | 2021-01-22 14:00 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;CHARLES BLUMREICH;PTP TEAM;BRUCE KIRKLEWSKI | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM | PTP | 5253 |  |  | * |  | 2021-01-22 13:00 | 2021-01-22 14:00 | PTP | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5255 | WBS.2.1.8.1.17.1.3 | N | N | Planned | PTP_C0200 - Execute Load Program - Source List Conversion - AS8 | 3 | 2021-01-22 14:00 | 2021-01-22 17:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5254 |  |  | * |  | 2021-01-22 14:00 | 2021-01-22 17:00 | DATA | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5256 | WBS.2.1.8.1.17.1.4 | N | N | Planned | PTP_C0200 - Validate Load - Source List Conversion - AS8 | 1 | 2021-01-22 17:00 | 2021-01-22 18:00 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;CHARLES BLUMREICH;PTP TEAM;BRUCE KIRKLEWSKI | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM | PTP | 5255 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 18:00 | PTP | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
94293 | WBS.2.1.8.1.17.1.5 | N | N | Planned | Update Source Lists with Relevant for MRP Flag | 1 | 2021-01-22 18:00 | 2021-01-22 19:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5256 |  |  | * |  | 2021-01-22 18:00 | 2021-01-22 19:00 | PTP | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5257 | WBS.2.1.8.1.18 | N | N |  | Ramp Down ¦ PTP_C0200.1 - Convert Source List - ECC | 7 | 2021-01-22 17:00 | 2021-01-25 08:00 | [8 empty] | * |  | 2021-01-22 17:00 | 2021-01-25 08:00 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90262 | WBS.2.1.8.1.18.1 | N | N |  | Ramp Down ¦ PTP_C0200.1 - Convert Source List - ECC | 7 | 2021-01-22 17:00 | 2021-01-25 08:00 | [8 empty] | * |  | 2021-01-22 17:00 | 2021-01-25 08:00 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5258 | WBS.2.1.8.1.18.1.1 | N | N | Planned | PTP_C0200.1 - Execute Transform Program - Convert Source List - ECC | 2 | 2021-01-22 17:00 | 2021-01-22 19:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5236,5246 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 19:00 | DATA | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5259 | WBS.2.1.8.1.18.1.2 | N | N | Planned | PTP_C0200.1 - Validate Preload Transform - Convert Source List - ECC | 1 | 2021-01-22 19:00 | 2021-01-22 20:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5258 |  |  | * |  | 2021-01-22 19:00 | 2021-01-22 20:00 | PTP | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5260 | WBS.2.1.8.1.18.1.3 | N | N | Planned | PTP_C0200.1 - Execute Load Program - Convert Source List - ECC | 2 | 2021-01-22 20:00 | 2021-01-22 22:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5259 |  |  | * |  | 2021-01-22 20:00 | 2021-01-22 22:00 | DATA | PTH,HBG,BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5261 | WBS.2.1.8.1.18.1.4 | N | N | Planned | PTP_C0200.1 - Validate Load - Convert Source List - ECC | 1 | 2021-01-25 06:00 | 2021-01-25 07:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | SAI TEAM;ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5260 |  |  | * |  | 2021-01-25 06:00 | 2021-01-25 07:00 | PTP | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
82239 | WBS.2.1.8.1.18.1.5 | N | N | Planned | Update PIR And Contracts To Remove GR Based IV | 1 | 2021-01-25 07:00 | 2021-01-25 08:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | NITIN GUPTA;CASEY HERMANSEN;YUDHAJIT MITRA;SRUTHI SRINIVASAN;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5261 |  |  | * |  | 2021-01-25 07:00 | 2021-01-25 08:00 | PTP | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90878 | WBS.2.1.8.1.18.1.6 | N | N | Planned | MC Task ¦ Maintain number ranges for PO, GR, and Quotes | 1 | 2021-01-25 07:00 | 2021-01-25 08:00 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;DON ABBOTT;SAI TEAM;PTP TEAM;PMO TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 5261 |  |  | * |  | 2021-01-25 07:00 | 2021-01-25 08:00 | PTP | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91352 | WBS.2.1.8.2 | N | N |  | Ramp Down ¦ Conversions - Dependent On Big 3 - Enhancements and Manual Activities | 79.75 | 2021-01-18 06:15 | 2021-01-22 22:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-22 22:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7930 | WBS.2.1.8.2.1 | N | N |  | Ramp Down ¦ OTC Post Master Data Conversion Steps | 5.5 | 2021-01-18 06:15 | 2021-01-18 11:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 11:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90255 | WBS.2.1.8.2.1.1 | N | N |  | Ramp Down ¦ OTC Post Master Data Conversion Steps | 5.5 | 2021-01-18 06:15 | 2021-01-18 11:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 11:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4569 | WBS.2.1.8.2.1.1.1 | N | N | Planned | Maintain BRF+ tables for OTC | 3 | 2021-01-18 08:45 | 2021-01-18 11:45 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | MICHELLE SADLER;TRISHUL BUDDHA;SAI TEAM;OTC TEAM;KYNDAL CODY;ONI BORCHERS | BMSADLER@GAPAC.COM;TBUDDHA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 7826 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 11:45 | OTC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95410 | WBS.2.1.8.2.1.1.2 | N | N | Planned | Mock Cutover Only - Update logical system partner on ZORD order output from POP to POQ | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | TRISHUL BUDDHA;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | TBUDDHA@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | OTC | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5126 | WBS.2.1.8.2.2 | N | N |  | Ramp Down ¦ RTR_E0113 - Maintenance of Planned Price Versions | 19.5 | 2021-01-19 07:15 | 2021-01-20 10:45 | [8 empty] | * |  | 2021-01-19 07:15 | 2021-01-20 10:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90280 | WBS.2.1.8.2.2.1 | N | N |  | Ramp Down ¦ RTR_E0113 - Maintenance of Planned Price Versions | 19.5 | 2021-01-19 07:15 | 2021-01-20 10:45 | [8 empty] | * |  | 2021-01-19 07:15 | 2021-01-20 10:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
7887 | WBS.2.1.8.2.2.1.1 | N | N | Planned | RTR_E0113 - Preparation of load file for Planned prices plants 1503, 1101, 1462, 1357 | 4 | 2021-01-19 07:15 | 2021-01-19 11:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5549 |  |  | * |  | 2021-01-19 07:15 | 2021-01-19 11:15 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5127 | WBS.2.1.8.2.2.1.2 | N | N | Planned | RTR_E0113 - Upload planned prices run program - Maintenance of planned price versions for std price, prior year average price, and forward looking price | 0.25 | 2021-01-20 10:00 | 2021-01-20 10:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7887,89709 |  |  | * |  | 2021-01-20 10:00 | 2021-01-20 10:15 | RTR - PC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5128 | WBS.2.1.8.2.2.1.3 | N | N | Planned | RTR_E0113 - Validate Load - for planned price versions - Maintenance of planned price versions for std price, prior year average price, and forward looking price | 0.5 | 2021-01-20 10:15 | 2021-01-20 10:45 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5127 |  |  | * |  | 2021-01-20 10:15 | 2021-01-20 10:45 | RTR - PC | CROSS | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90986 | WBS.2.1.8.2.3 | N | N |  | Ramp Down ¦ RTR_E0276 - Automatic Update To Mixed Ratio Periodically By Production Version Based On Production Volume - Mill | 10 | 2021-01-22 12:00 | 2021-01-22 22:00 | [8 empty] | * |  | 2021-01-22 12:00 | 2021-01-22 22:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90987 | WBS.2.1.8.2.3.1 | N | N |  | Ramp Down ¦ RTR_E0276 - Automatic Update To Mixed Ratio Periodically By Production Version Based On Production Volume - Mill | 10 | 2021-01-22 12:00 | 2021-01-22 22:00 | [8 empty] | * |  | 2021-01-22 12:00 | 2021-01-22 22:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7891 | WBS.2.1.8.2.3.1.1 | N | N | Planned | RTR_E0276 - Provide load file - MFLE Plants -1034, 1376, 1459 - proc alternatives of GP01 and GPTO | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 89804 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7901 | WBS.2.1.8.2.3.1.2 | N | N | Planned | RTR_E0276 - Load proc alternatives for GP01 and GPTO for MFLE Plants - 1034, 1376, 1459 (E0276) | 1 | 2021-01-22 16:00 | 2021-01-22 17:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7891 |  |  | * |  | 2021-01-22 16:00 | 2021-01-22 17:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95751 | WBS.2.1.8.2.3.1.3 | N | N | Planned | Assign procrment alternatives for subcontracted materilals PIRs | 0.5 | 2021-01-22 17:00 | 2021-01-22 17:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7901 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 17:30 | RTR - PC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7902 | WBS.2.1.8.2.3.1.4 | N | N | Planned | RTR_E0276 - Valid proc alternatives for GP01 and GPTO - MFLE Plants -1034, 1376, 1459 (E0276) | 1 | 2021-01-22 17:00 | 2021-01-22 18:00 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7901 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 18:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7892 | WBS.2.1.8.2.3.1.5 | N | N | Planned | RTR_E0276 - Provide load file - mixed ratios of GP01 and GPTO - MFLE plants 1034, 1376, 1459 | 2 | 2021-01-22 18:00 | 2021-01-22 20:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7902 |  |  | * |  | 2021-01-22 18:00 | 2021-01-22 20:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7905 | WBS.2.1.8.2.3.1.6 | N | N | Planned | RTR_E0276 - Load mix ratio for GP01 & GPTO in MFLE Plants 1034, 1376, 1459 | 0.5 | 2021-01-22 20:00 | 2021-01-22 20:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7892 |  |  | * |  | 2021-01-22 20:00 | 2021-01-22 20:30 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7906 | WBS.2.1.8.2.3.1.7 | N | N | Planned | RTR_E0276 - Validate mixed costing for GP01 & GPTO in MFLE Plants -1034, 1376, 1459 | 0.5 | 2021-01-22 20:30 | 2021-01-22 21:00 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7905 |  |  | * |  | 2021-01-22 20:30 | 2021-01-22 21:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
97466 | WBS.2.1.8.2.3.1.8 | N | N | Planned | Provide cost center/Formulas for Template allocations | 1 | 2021-01-22 21:00 | 2021-01-22 22:00 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7906 |  |  | * |  | 2021-01-22 21:00 | 2021-01-22 22:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
97467 | WBS.2.1.8.2.3.1.9 | N | N | Planned | Update Template allocation with D4 Cost center/Formulas | 1 | 2021-01-22 21:00 | 2021-01-22 22:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;NOEL CLARK;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 7906 |  |  | * |  | 2021-01-22 21:00 | 2021-01-22 22:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
9243 | WBS.2.1.9 | N | N |  | Ramp Down ¦ Conversions - Not Dependent On Big 3 | 178.75 | 2021-01-17 21:45 | 2021-01-30 22:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-30 22:30 |  | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91356 | WBS.2.1.9.1 | N | N |  | Ramp Down ¦ Conversions - Not Dependent On Big 3 - Enhancements and Manual Activities | 152.01 | 2021-01-18 06:15 | 2021-01-29 14:16 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 14:16 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90170 | WBS.2.1.9.1.1 | N | N |  | Ramp Down ¦ Work Center Rates Activity | 79.75 | 2021-01-18 07:45 | 2021-01-25 07:30 | [8 empty] | * |  | 2021-01-18 07:45 | 2021-01-25 07:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90193 | WBS.2.1.9.1.1.1 | N | N |  | Ramp Down ¦ Work Center Rates Tasks | 79.75 | 2021-01-18 07:45 | 2021-01-25 07:30 | [8 empty] | * |  | 2021-01-18 07:45 | 2021-01-25 07:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92566 | WBS.2.1.9.1.1.1.1 | N | N | Planned | AC OE Gate | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | JASON RAMSEY;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 36501,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
68538 | WBS.2.1.9.1.1.1.2 | N | N | Planned | Create AC Work Center Rates | 0.5 | 2021-01-18 07:45 | 2021-01-18 08:15 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 4649 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 08:15 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5782 | WBS.2.1.9.1.1.1.3 | N | N | Planned | Load Manual Work Centers | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;JASON RAMSEY;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 68538 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5783 | WBS.2.1.9.1.1.1.4 | N | N | Planned | Validate Work Centers | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | SAI TEAM;JASON RAMSEY;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5782 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 09:30 | AC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10827 | WBS.2.1.9.1.1.1.5 | N | N | Planned | Load or validate platform data for facility 1009 | 1 | 2021-01-25 06:30 | 2021-01-25 07:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5783,92566,10845 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 07:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92189 | WBS.2.1.9.1.1.1.6 | N | N | Planned | Check Mark Reference Field in Work Center after Work center Creation | 1 | 2021-01-19 14:15 | 2021-01-19 15:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | VISHNU CHIRALA;TONY SMITH;SAI TEAM;KRISHNA SINGAREDDY;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ksingareddy@deloitte.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5783,89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 15:15 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97707 | WBS.2.1.9.1.1.1.8 | N | N | Planned | Send file to mill resources for Work Center / cost center mapping validation file | 0.25 | 2021-01-19 15:15 | 2021-01-19 15:30 | TONY SMITH | AJSMITH@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;KRISHNA SINGAREDDY;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;KRISHNA RAVI | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ksingareddy@deloitte.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM | RTR | 92189 |  |  | * |  | 2021-01-19 15:15 | 2021-01-19 15:30 | RTR - PC | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10828 | WBS.2.1.9.1.1.1.7 | N | N | Planned | Create Maintenance Strategies | 0.5 | 2021-01-18 09:30 | 2021-01-18 10:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | JASON RAMSEY;GAURAV BHATIA;SAI TEAM;AC TEAM | JCRAMSEY@GAPAC.COM;GBHATIA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5783 |  |  | * |  | 2021-01-18 09:30 | 2021-01-18 10:00 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5567 | WBS.2.1.9.1.2 | N | N |  | Ramp Down ¦ Ariba Data Load Activity | 5.13 | 2021-01-18 06:15 | 2021-01-18 11:23 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 11:23 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90958 | WBS.2.1.9.1.2.1 | N | N |  | Ramp Down ¦ Ariba Data Load Tasks | 5.13 | 2021-01-18 06:15 | 2021-01-18 11:23 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 11:23 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5574 | WBS.2.1.9.1.2.1.2 | N | N | Planned | Validate all the Master Data loaded by Master Data Interface (P2O) | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;CHARLES BLUMREICH;SAI TEAM;PTP TEAM;ABBY DREVIK | MARK.BURGIN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9119 | WBS.2.1.9.1.2.1.4 | N | N | Planned | MC Task ¦ Create/Validate Supplier Test AN Accounts for ITC as Needed for Commerce Automation | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;MIKE PUPILLO;MARTIN ZIGAROVICH;YUDHAJIT MITRA;RICHARD WORTMAN;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;ABBY DREVIK | MARK.BURGIN@GAPAC.COM;MAPUPILL@GAPAC.COM;MARTIN.ZIGAROVICH@SAP.COM;YMITRA@DELOITTE.COM;RWORTMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89504 | WBS.2.1.9.1.2.1.5 | N | N | Planned | For prod only - prepare user load file for business users to be loaded into Koch.sourcing.ariba.com | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89505 | WBS.2.1.9.1.2.1.8 | N | N | Planned | For prod only - request business users to be loaded into Koch.sourcing.ariba.com | 0.5 | 2021-01-18 06:45 | 2021-01-18 07:15 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 89504 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:15 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8830 | WBS.2.1.9.1.2.1.13 | N | N | Planned | Ariba Invoice Management - Validate Incoterm/Freight BRF+ entries in S/4HANA (ZDT_PTP_I0095_INCO) | 1.13 | 2021-01-18 10:15 | 2021-01-18 11:23 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;CASEY HERMANSEN;YUDHAJIT MITRA;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 90775 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 11:23 | ARIBA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90957 | WBS.2.1.9.1.2.2 | N | N |  | Ramp Down ¦ ARIBA Data Load - Open and Close Client | 0.25 | 2021-01-18 10:00 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 10:00 | 2021-01-18 10:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90775 | WBS.2.1.9.1.2.2.1 | N | N | Planned | Confirm S/4HANA Client Is Open - Task 1 | 0.25 | 2021-01-18 10:00 | 2021-01-18 10:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 36501,90605,91838,90310 |  |  | * |  | 2021-01-18 10:00 | 2021-01-18 10:15 | DEV - INFRA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90926 | WBS.2.1.9.1.3 | N | N |  | Ramp Down ¦ RTR - Conversion of Finance Master Data | 93.75 | 2021-01-18 06:45 | 2021-01-25 20:30 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-25 20:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4713 | WBS.2.1.9.1.3.1 | N | N |  | Ramp Down ¦ Finance Master Data Conversion - Profit Centers | 93.75 | 2021-01-18 06:45 | 2021-01-25 20:30 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-25 20:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
7985 | WBS.2.1.9.1.3.1.1 | N | N | Planned | Load & validate additional Activity Types for CATS | 2 | 2021-01-18 06:45 | 2021-01-18 08:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;RTR TEAM;ASHLEY SEWELL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 08:45 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7986 | WBS.2.1.9.1.3.1.2 | N | N | Planned | Load prices to Activity Types | 0.25 | 2021-01-18 08:45 | 2021-01-18 09:00 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;RTR TEAM;ASHLEY SEWELL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM | RTR | 7985,93067,91838 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 09:00 | RTR - PS | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
7987 | WBS.2.1.9.1.3.1.3 | N | N | Planned | Assign Activity type to Employee records | 2 | 2021-01-25 18:30 | 2021-01-25 20:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;RTR TEAM;ASHLEY SEWELL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM | RTR | 7986,81579,94751,94755,96555 |  |  | * |  | 2021-01-25 18:30 | 2021-01-25 20:30 | RTR - PS | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4744 | WBS.2.1.9.1.3.2 | N | N |  | Ramp Down ¦ Finance Master Data Conversion - Allocation Cycles | 17.5 | 2021-01-18 06:45 | 2021-01-19 08:15 | [8 empty] | * |  | 2021-01-18 06:45 | 2021-01-19 08:15 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
4745 | WBS.2.1.9.1.3.2.1 | N | N | Planned | Maintain/Transport Sets for Validation/Substitution rules | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93067,91838 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4746 | WBS.2.1.9.1.3.2.2 | N | N | Planned | Confirm Sets are complete and accurate for Validation, Substitution & Allocations | 0.75 | 2021-01-18 07:00 | 2021-01-18 07:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4745 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90868 | WBS.2.1.9.1.3.2.3 | N | N | Planned | Compare FI Validations &Substitutions between N (S4P-100) & N+1 (SD1-100) (Including Sets, Rules & User Exits) | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4745 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92244 | WBS.2.1.9.1.3.2.4 | N | N | Planned | Review cost center master data for updates based on Product Costing needs, review OKB9 table | 0.75 | 2021-01-18 07:00 | 2021-01-18 07:45 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | SAI TEAM;BRETT DETTMERING;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4745 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36989 | WBS.2.1.9.1.3.2.5 | N | N | Planned | Prepare load file for BS Allocation cycles related to MFG and NonMFG CoCodes | 1 | 2021-01-18 07:45 | 2021-01-18 08:45 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | BRETT DETTMERING;SAI TEAM;DONNA SMITH;DONETTA HODGES;VICKI IVEY;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | BRETT.DETTMERING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;DONETTA.HODGES@GAPAC.COM;VLIVEY@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4746 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 08:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36995 | WBS.2.1.9.1.3.2.6 | N | N | Planned | Prepare load file for P&L Allocation cycles related to MFG CoCodes | 3 | 2021-01-18 07:45 | 2021-01-18 10:45 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | BRETT DETTMERING;SAI TEAM;DONNA SMITH;VICKI IVEY;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | BRETT.DETTMERING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VLIVEY@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4746 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 10:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36991 | WBS.2.1.9.1.3.2.7 | N | N | Planned | Prepare load file for Fringe Benefit Allocation cycles related to MFG CoCodes | 1.5 | 2021-01-18 07:45 | 2021-01-18 09:15 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | BRETT DETTMERING;SAI TEAM;DONNA SMITH;DONETTA HODGES;VICKI IVEY;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | BRETT.DETTMERING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;DONETTA.HODGES@GAPAC.COM;VLIVEY@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4746 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 09:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36990 | WBS.2.1.9.1.3.2.8 | N | N | Planned | Maintain Account Grps, PC Grps, SKF masters for BS Allocations for MFG and NonMFG CoCodes | 5 | 2021-01-18 08:45 | 2021-01-18 13:45 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36989 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 13:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4748 | WBS.2.1.9.1.3.2.9 | N | N | Planned | Upload of BS Allocations for MFG and NonMFG CoCodes & Validate Results | 2 | 2021-01-18 13:45 | 2021-01-18 15:45 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36990 |  |  | * |  | 2021-01-18 13:45 | 2021-01-18 15:45 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36992 | WBS.2.1.9.1.3.2.10 | N | N | Planned | Maintain CE, CC, SKF masters for Fringe Benefit Allocations for MFG CoCodes & Validate Results | 0.5 | 2021-01-18 15:45 | 2021-01-18 16:15 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36991,4748 |  |  | * |  | 2021-01-18 15:45 | 2021-01-18 16:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4749 | WBS.2.1.9.1.3.2.11 | N | N | Planned | Upload of Fringe Benefit Allocations for MFG CoCodes & Validate Results | 1 | 2021-01-18 16:15 | 2021-01-18 17:15 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36992 |  |  | * |  | 2021-01-18 16:15 | 2021-01-18 17:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36994 | WBS.2.1.9.1.3.2.12 | N | N | Planned | Maintain CE, CC, SKF masters for P&L Allocations for NonMFG CoCodes & Validate Results | 1 | 2021-01-18 17:15 | 2021-01-18 18:15 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;ASHLEY SEWELL;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 4749,4746 |  |  | * |  | 2021-01-18 17:15 | 2021-01-18 18:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4750 | WBS.2.1.9.1.3.2.13 | N | N | Planned | Upload of P&L Allocations for NonMFG CoCodes & Validate Results | 1 | 2021-01-18 18:15 | 2021-01-18 19:15 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;ASHLEY SEWELL;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36994 |  |  | * |  | 2021-01-18 18:15 | 2021-01-18 19:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36996 | WBS.2.1.9.1.3.2.14 | N | N | Planned | Maintain CE, CC, SKF masters for P&L Allocations for MFG CoCodes & Validate Results | 2 | 2021-01-18 19:15 | 2021-01-18 21:15 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;JACKIE ADAMS;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;Jacqueline.Adams@GAPAC.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36995,4750 |  |  | * |  | 2021-01-18 19:15 | 2021-01-18 21:15 | RTR - GL | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4751 | WBS.2.1.9.1.3.2.15 | N | N | Planned | Upload of P&L Allocations for MFG CoCodes & Validate Results | 2 | 2021-01-18 21:15 | 2021-01-19 07:15 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | SANDRA RICHARDS;BRETT DETTMERING;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;RICARDO OLIVEIRA;JACKIE ADAMS;RTR TEAM;SAI TEAM | SARICHARDS@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;Jacqueline.Adams@GAPAC.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36996 |  |  | * |  | 2021-01-18 21:15 | 2021-01-19 07:15 | RTR - GL | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
29561 | WBS.2.1.9.1.3.2.16 | N | N | Planned | Execute report RK811XST to refresh the CE Grps for Allocation Cycles & Perform Formal Check | 1 | 2021-01-19 07:15 | 2021-01-19 08:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 4751 |  |  | * |  | 2021-01-19 07:15 | 2021-01-19 08:15 | RTR - GL | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95725 | WBS.2.1.9.1.4 | N | N |  | Ramp Down ¦ RTR Mark and Release Costs - Deployed Plants D1/D2/D3 | 8.01 | 2021-01-29 06:15 | 2021-01-29 14:16 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-29 14:16 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95724 | WBS.2.1.9.1.4.1 | N | N |  | Ramp Down ¦ RTR Mark and Release Costs - Deployed Plants D1/D2/D3 | 8.01 | 2021-01-29 06:15 | 2021-01-29 14:16 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-29 14:16 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97314 | WBS.2.1.9.1.4.1.16 | N | N | Planned | Manually mark GP00- Plattsburgh/ 1006 - n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | ERIK LANZER | ERIK.LANZER@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97313 | WBS.2.1.9.1.4.1.15 | N | N | Planned | Manually mark GP00- Mt Holly/1106- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | ROBERT HUNTER | robert.hunter@gapac.com | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97312 | WBS.2.1.9.1.4.1.14 | N | N | Planned | Manually mark GP00- Savannagh/1104- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | JAMES VICK | JAMES.VICK@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97311 | WBS.2.1.9.1.4.1.13 | N | N | Planned | Manually mark GP00- 1357-LVP- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | BRIAN YOST | BRIAN.YOST@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;DENISE HUGHES;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;DENISE.HUGHES@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | LVP | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97310 | WBS.2.1.9.1.4.1.12 | N | N | Planned | Manually mark GP00- 1503-GBD- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | KELLY DUNN | KELLY.DUNN@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;RICK GLOUDEMANS;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;RICK.GLOUDEMANS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97309 | WBS.2.1.9.1.4.1.11 | N | N | Planned | Manually mark GP00- 1462-GBP- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | KELLY DUNN | KELLY.DUNN@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;CHAD KRAUSE;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;CHAD.KRAUSE@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97308 | WBS.2.1.9.1.4.1.10 | N | N | Planned | Manually mark GP00- 1101-GBB- n/a for Mock cutovers | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | KELLY DUNN | KELLY.DUNN@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA RAVI;TONY SMITH;RICK GLOUDEMANS;RANJAI JOHN;BOATENG LAWRENCE;LAURA FRY;DENISE MARSH | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;AJSMITH@GAPAC.COM;RICK.GLOUDEMANS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | RTR | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95695 | WBS.2.1.9.1.4.1.1 | N | N | Planned | Confirm mark GP00 is complete for deployed plants (1006, 1104, 1106 1357, 1503, 1462, 1101) n/a for mock cutovers | 0.51 | 2021-01-29 08:15 | 2021-01-29 08:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 97314,97313,97312,97311,97310,97309,97308 |  |  | * |  | 2021-01-29 08:15 | 2021-01-29 08:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95726 | WBS.2.1.9.1.4.1.2 | N | N | Planned | Calculate cost rolls GPGR/GPPC for MFLE Deployed plants 1006, 1104, 1106 1357, 1503, 1462, 1101)-n/a for mock cutovers | 1 | 2021-01-29 08:46 | 2021-01-29 09:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95695 |  |  | * |  | 2021-01-29 08:46 | 2021-01-29 09:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95727 | WBS.2.1.9.1.4.1.3 | N | N | Planned | Validate GP00 = GPGR = GPPC for MFLE Deployed plants 1006, 1104, 1106, 1357, 1503, 1462, 1101-n/a for mock cutovers | 0.5 | 2021-01-29 09:46 | 2021-01-29 10:16 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95726 |  |  | * |  | 2021-01-29 09:46 | 2021-01-29 10:16 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95696 | WBS.2.1.9.1.4.1.4 | N | N | Planned | Mark GPGR/GPPC for MFLE Deployed Plants 1006, 1104, 1106, 1357, 1503, 1462, 1101-n/a for mock cutovers | 0.5 | 2021-01-29 10:16 | 2021-01-29 10:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95727 |  |  | * |  | 2021-01-29 10:16 | 2021-01-29 10:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95728 | WBS.2.1.9.1.4.1.5 | N | N | Planned | Calculate cost rolls GP00 for 5* series plants - Deployed Plants (D1/D2/D3)-n/a for mock cutovers | 1 | 2021-01-29 10:46 | 2021-01-29 11:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95696 |  |  | * |  | 2021-01-29 10:46 | 2021-01-29 11:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95729 | WBS.2.1.9.1.4.1.6 | N | N | Planned | Validate 5* series GP00 = GPGR = GPPC for 1* series Deployed plants (D1/D2/D3)-n/a for mock cutovers | 0.5 | 2021-01-29 11:46 | 2021-01-29 12:16 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95728 |  |  | * |  | 2021-01-29 11:46 | 2021-01-29 12:16 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95681 | WBS.2.1.9.1.4.1.7 | N | N | Planned | GP00 - Mark cost estimates for 5* Series Plants - Deployed Plants (D1/D2/D3)-n/a for mock cutovers | 0.5 | 2021-01-29 12:16 | 2021-01-29 12:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95729 |  |  | * |  | 2021-01-29 12:16 | 2021-01-29 12:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95730 | WBS.2.1.9.1.4.1.8 | N | N | Planned | Calculate cost rolls GPGR/GPPC for 5* series plants - Deployed plants (D1/D2/D3)-n/a for mock cutovers | 1 | 2021-01-29 12:46 | 2021-01-29 13:46 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95681 |  |  | * |  | 2021-01-29 12:46 | 2021-01-29 13:46 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95683 | WBS.2.1.9.1.4.1.9 | N | N | Planned | Mark GPGR/GPPC for 5* Series Plants - Deployed Plants (D1/D2/D3)-n/a for mock cutovers | 0.5 | 2021-01-29 13:46 | 2021-01-29 14:16 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95730 |  |  | * |  | 2021-01-29 13:46 | 2021-01-29 14:16 | RTR - PC | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95731 | WBS.2.1.9.1.5 | N | N |  | Ramp Down ¦ RTR Mark and Release Costs - Non-Deployed Plants | 4 | 2021-01-27 06:15 | 2021-01-27 10:15 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-27 10:15 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95732 | WBS.2.1.9.1.5.1 | N | N |  | Ramp Down ¦ RTR Mark and Release Costs - Non-Deployed Plants | 4 | 2021-01-27 06:15 | 2021-01-27 10:15 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-27 10:15 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95685 | WBS.2.1.9.1.5.1.1 | N | N | Planned | Upload GP00 standard costs for Non-Deployed sites 1* and 5* series for FGs (n/a for Mock cut over) | 2 | 2021-01-27 06:15 | 2021-01-27 08:15 | FRANK CONSIGLIO | FRANK.CONSIGLIO@GAPAC.COM | KRISHNA RAVI;PAUL WILLENBRING;TODD ROSNOW;NORMAN REYNOLDS;MANOJ ANNAJI;J NAGENDRABABU;SAI TEAM | KRISHNACHAITANYA.RAVI@GAPAC.COM;PAUL.WILLENBRING2@GAPAC.COM;TAROSNOW@GAPAC.COM;norman.reynolds@gapac.com;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 08:15 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95686 | WBS.2.1.9.1.5.1.2 | N | N | Planned | Upload GPGR standard costs for Non-Deployed sites 1* and 5* series for FGs (n/a for Mock cut over) | 2 | 2021-01-27 06:15 | 2021-01-27 08:15 | FRANK CONSIGLIO | FRANK.CONSIGLIO@GAPAC.COM | KRISHNA RAVI;PAUL WILLENBRING;TODD ROSNOW;NORMAN REYNOLDS;MANOJ ANNAJI;J NAGENDRABABU;SAI TEAM | KRISHNACHAITANYA.RAVI@GAPAC.COM;PAUL.WILLENBRING2@GAPAC.COM;TAROSNOW@GAPAC.COM;norman.reynolds@gapac.com;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 08:15 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95687 | WBS.2.1.9.1.5.1.3 | N | N | Planned | Upload GPPC standard costs for Non-Deployed sites 1* and 5* series for FGs (n/a for Mock cut over) | 2 | 2021-01-27 06:15 | 2021-01-27 08:15 | FRANK CONSIGLIO | FRANK.CONSIGLIO@GAPAC.COM | KRISHNA RAVI;PAUL WILLENBRING;TODD ROSNOW;NORMAN REYNOLDS;MANOJ ANNAJI;J NAGENDRABABU;SAI TEAM | KRISHNACHAITANYA.RAVI@GAPAC.COM;PAUL.WILLENBRING2@GAPAC.COM;TAROSNOW@GAPAC.COM;norman.reynolds@gapac.com;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 08:15 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95733 | WBS.2.1.9.1.5.1.4 | N | N | Planned | Validate GP00 = GPGR = GPPC for Non-deployed sites after Upload of standard costs (n/a for Mock cut over) | 1 | 2021-01-27 08:15 | 2021-01-27 09:15 | TONY SMITH | AJSMITH@GAPAC.COM | JACOB DENNIS;KRISHNA RAVI;KRISHNA SINGAREDDY;MANOJ ANNAJI;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;MANOJ.ANNAJI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95685,95686,95687 |  |  | * |  | 2021-01-27 08:15 | 2021-01-27 09:15 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95688 | WBS.2.1.9.1.5.1.5 | N | N | Planned | GP00 - Mark cost estimates for 5* Series and 1* Series Plants - Non-Deployed sites | 0.5 | 2021-01-27 09:15 | 2021-01-27 09:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95733 |  |  | * |  | 2021-01-27 09:15 | 2021-01-27 09:45 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95690 | WBS.2.1.9.1.5.1.6 | N | N | Planned | Mark GPGR/GPPC for 5* Series and 1* Series Plants - Non-Deployed Sites | 0.5 | 2021-01-27 09:45 | 2021-01-27 10:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95688 |  |  | * |  | 2021-01-27 09:45 | 2021-01-27 10:15 | RTR - PC | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
91355 | WBS.2.1.9.2 | N | N |  | Ramp Down ¦ Conversions - Not Dependent On Big 3 - Conversion Objects | 178.75 | 2021-01-17 21:45 | 2021-01-30 22:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-30 22:30 |  | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94744 | WBS.2.1.9.2.1 | N | N |  | Extractions for Conversion of Contractors | 4 | 2021-01-25 06:15 | 2021-01-25 10:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-25 10:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94743 | WBS.2.1.9.2.1.1 | N | N |  | Extractions for Conversion of Contractors | 4 | 2021-01-25 06:15 | 2021-01-25 10:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-25 10:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94756 | WBS.2.1.9.2.1.1.1 | N | N | Planned | PTH - Provide Initial List of Contractors To Be Created | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | RTR - PS | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94755 | WBS.2.1.9.2.1.1.2 | N | N | Planned | PTH - Provide List of Activity Type Assignments For EE's And Contractors | 2 | 2021-01-25 08:15 | 2021-01-25 10:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94756,10845 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 10:15 | RTR - PS | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94752 | WBS.2.1.9.2.1.1.5 | N | N | Planned | HBG - Provide Initial List of Contractors To Be Created | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;BRENDA STAGGS | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENDA.STAGGS@GAPAC.COM | Business | 10846,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | RTR - PS | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94751 | WBS.2.1.9.2.1.1.6 | N | N | Planned | HBG - Provide List of Activity Type Assignments For EE's And Contractors | 2 | 2021-01-25 08:15 | 2021-01-25 10:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94752 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 10:15 | RTR - PS | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
9246 | WBS.2.1.9.2.2 | N | N |  | Ramp Down ¦ DAT_C0234 - Conversion of Contractors & non-CPG employees | 12.25 | 2021-01-25 06:15 | 2021-01-25 18:30 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-25 18:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4970 | WBS.2.1.9.2.2.1 | N | N |  | Ramp Down ¦ DAT_C0234 - Conversion of Contractors & non-CPG employees | 12.25 | 2021-01-25 06:15 | 2021-01-25 18:30 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-25 18:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
68521 | WBS.2.1.9.2.2.1.1 | N | N | Planned | DAT_C0234 - Provide Load File For Conversion of Contractors & non-CPG employees – Labor Management | 3 | 2021-01-25 06:15 | 2021-01-25 09:15 | Vinay Tawani | vtawani@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 09:15 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
7984 | WBS.2.1.9.2.2.1.2 | N | N | Planned | DAT_C0234 - Provide Load File Conversion of Contractors & non-CPG Employees - Eng. Contractors | 0.25 | 2021-01-25 08:15 | 2021-01-25 08:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;ASHLEY SEWELL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM | RTR | 94756,94752,96554 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 08:30 | RTR - PS | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
9101 | WBS.2.1.9.2.2.1.3 | N | N | Planned | DAT_C0234 - Consolidate And Format Load File For Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2021-01-25 09:15 | 2021-01-25 11:15 | DONNA COOPER | DCOOPER@GAPAC.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 7984,68521,96554 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 11:15 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4971 | WBS.2.1.9.2.2.1.4 | N | N | Planned | DAT_C0234 - Execute Transform Program -Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2021-01-25 11:15 | 2021-01-25 13:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9101,93067,91838 |  |  | * |  | 2021-01-25 11:15 | 2021-01-25 13:15 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4972 | WBS.2.1.9.2.2.1.5 | N | N | Planned | DAT_C0234 - Validate Preload Transform - Conversion of Contractors & non-CPG employees - Eng. Contractors | 0.25 | 2021-01-25 13:15 | 2021-01-25 13:30 | DONNA COOPER | DCOOPER@GAPAC.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 4971 |  |  | * |  | 2021-01-25 13:15 | 2021-01-25 13:30 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4973 | WBS.2.1.9.2.2.1.6 | N | N | Planned | DAT_C0234 - Execute Load Program - Conversion of Contractors & non-CPG employees - Eng. Contractors | 2 | 2021-01-25 13:30 | 2021-01-25 15:30 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 4972 |  |  | * |  | 2021-01-25 13:30 | 2021-01-25 15:30 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4974 | WBS.2.1.9.2.2.1.7 | N | N | Planned | DAT_C0234 - Validate Load In S/4HANA - Conversion of Contractors & non-CPG employees - Eng. Contractors | 2.5 | 2021-01-25 15:30 | 2021-01-25 18:00 | DONNA COOPER | DCOOPER@GAPAC.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 4973 |  |  | * |  | 2021-01-25 15:30 | 2021-01-25 18:00 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
81579 | WBS.2.1.9.2.2.1.8 | N | N | Planned | DAT_C0234 - Give RTR a Listing of EE #s (PERNR) and EWM a Listing of BPIDs associated with contractor load | 0.5 | 2021-01-25 18:00 | 2021-01-25 18:30 | DONNA COOPER | DCOOPER@GAPAC.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 4974 |  |  | * |  | 2021-01-25 18:00 | 2021-01-25 18:30 | DATA | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5389 | WBS.2.1.9.2.3 | N | N |  | Ramp Down ¦ ITR_C0016 - Convert Functional Locations - AS8 | 15.75 | 2021-01-17 21:45 | 2021-01-18 19:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 19:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90194 | WBS.2.1.9.2.3.1 | N | N |  | Ramp Down ¦ ITR_C0016 - Convert Functional Locations - AS8 | 15.75 | 2021-01-17 21:45 | 2021-01-18 19:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 19:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82990 | WBS.2.1.9.2.3.1.1 | N | N | Planned | ITR_C0016 - Provide Load File For Convert Functional Locations – AS8 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | PTH | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5390 | WBS.2.1.9.2.3.1.2 | N | N | Planned | ITR_C0016 - Execute Preload - Convert Functional Locations - AS8 | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5782 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 09:30 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5391 | WBS.2.1.9.2.3.1.3 | N | N | Planned | ITR_C0016 - Validate Preload - Convert Functional Locations - AS8 | 1.5 | 2021-01-18 09:30 | 2021-01-18 11:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;DAVID MCGINNIS;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.MCGINNIS@GAPAC.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5390 |  |  | * |  | 2021-01-18 09:30 | 2021-01-18 11:00 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5392 | WBS.2.1.9.2.3.1.4 | N | N | Planned | ITR_C0016 - Execute Load program - Convert Functional Locations - AS8 | 5 | 2021-01-18 11:00 | 2021-01-18 16:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5391 |  |  | * |  | 2021-01-18 11:00 | 2021-01-18 16:00 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5393 | WBS.2.1.9.2.3.1.5 | N | N | Planned | ITR_C0016 - Validate Load - Convert Functional Locations - AS8 | 2.5 | 2021-01-18 16:00 | 2021-01-18 18:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;BOB BROWN;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;KELLY STRASSBURGER;AC TEAM;GARY BENOIT | ERIC.REINDL@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 5392 |  |  | * |  | 2021-01-18 16:00 | 2021-01-18 18:30 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
81604 | WBS.2.1.9.2.3.1.6 | N | N | Planned | PTH - ITR_C0016 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data For Converted Functional Locations - AS8 | 1 | 2021-01-18 18:30 | 2021-01-18 19:30 | DANIEL HENDERSON | daniel.henderson@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5393 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 19:30 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92776 | WBS.2.1.9.2.4 | N | N |  | Ramp Down ¦ ITR_C0016.1 - Convert Functional Locations - MP2 | 66.25 | 2021-01-17 21:45 | 2021-01-21 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-21 22:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92775 | WBS.2.1.9.2.4.1 | N | N |  | Ramp Down ¦ ITR_C0016.1 - Convert Functional Locations - MP2 | 66.25 | 2021-01-17 21:45 | 2021-01-21 22:00 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-21 22:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92781 | WBS.2.1.9.2.4.1.1 | N | N | Planned | Provide Preload file ITR_C0016.1 - Convert Functional Locations - MP2 | 1 | 2021-01-17 21:45 | 2021-01-17 22:45 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:45 | AC | HBG,BG | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92780 | WBS.2.1.9.2.4.1.2 | N | N | Planned | Execute Preload ITR_C0016.1 - Convert Functional Locations - MP2 | 1 | 2021-01-18 08:30 | 2021-01-18 09:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92781,5782 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 09:30 | DATA | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92779 | WBS.2.1.9.2.4.1.3 | N | N | Planned | Validate Preload ITR_C0016.1 - Convert Functional Locations - MP2 | 2 | 2021-01-18 09:30 | 2021-01-18 11:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92780 |  |  | * |  | 2021-01-18 09:30 | 2021-01-18 11:30 | AC | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92778 | WBS.2.1.9.2.4.1.4 | N | N | Planned | Execute Load ITR_C0016.1 - Convert Functional Locations - MP2 | 3 | 2021-01-18 11:30 | 2021-01-18 14:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92779 |  |  | * |  | 2021-01-18 11:30 | 2021-01-18 14:30 | DATA | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92777 | WBS.2.1.9.2.4.1.5 | N | N | Planned | Validate Load ITR_C0016.1 - Convert Functional Locations - MP2 | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92778 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | AC | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93708 | WBS.2.1.9.2.4.1.8 | N | N | Planned | HBG - ITR_C0016.1 - Spot-check SAP DATA reflects loaded data (Convert Functional Locations - MP2) | 1 | 2021-01-18 15:30 | 2021-01-18 16:30 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92777 |  |  | * |  | 2021-01-18 15:30 | 2021-01-18 16:30 | AC | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95715 | WBS.2.1.9.2.4.1.11 | N | N | Planned | Send file format to get meter reading (LAST PERFORMED) and highest meter reading | 1 | 2021-01-21 19:00 | 2021-01-21 20:00 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | JASON RAMSEY;JEY MURUGESH;AC TEAM;SAI TEAM | JCRAMSEY@GAPAC.COM;JMURUGESH@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 92877 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 20:00 | AC | ALL | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
95716 | WBS.2.1.9.2.4.1.12 | N | N | Planned | Update file to get meter reading (LAST PERFORMED) and highest reading | 2 | 2021-01-21 20:00 | 2021-01-21 22:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 95715 |  |  | * |  | 2021-01-21 20:00 | 2021-01-21 22:00 | AC | ALL | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96983 | WBS.2.1.9.2.4.1.26 | N | N | Planned | BG - ITR_C0016.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Functional Locations - MP2) | 2 | 2021-01-18 15:30 | 2021-01-18 17:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92777 |  |  | * |  | 2021-01-18 15:30 | 2021-01-18 19:30 | AC | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92782 | WBS.2.1.9.2.5 | N | N |  | Ramp Down ¦ ITR_C0018.1 - Convert equipment – MP2 | 18.75 | 2021-01-17 21:45 | 2021-01-19 06:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-19 06:30 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92783 | WBS.2.1.9.2.5.1 | N | N |  | Ramp Down ¦ ITR_C0018.1 - Convert equipment – MP2 | 18.75 | 2021-01-17 21:45 | 2021-01-19 06:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-19 06:30 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92784 | WBS.2.1.9.2.5.1.1 | N | N | Planned | Provide Preload file ITR_C0018.1 - Convert equipment – MP2 | 1 | 2021-01-17 21:45 | 2021-01-17 22:45 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:45 | AC | HBG,BG | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
92785 | WBS.2.1.9.2.5.1.2 | N | N | Planned | Execute Preload ITR_C0018.1 - Convert equipment – MP2 | 1 | 2021-01-18 15:30 | 2021-01-18 16:30 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92784,92777 |  |  | * |  | 2021-01-18 15:30 | 2021-01-18 16:30 | DATA | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92786 | WBS.2.1.9.2.5.1.3 | N | N | Planned | Validate Preload ITR_C0018.1 - Convert equipment – MP2 | 2 | 2021-01-18 16:30 | 2021-01-18 18:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92785 |  |  | * |  | 2021-01-18 16:30 | 2021-01-18 18:30 | AC | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92787 | WBS.2.1.9.2.5.1.4 | N | N | Planned | Execute Load ITR_C0018.1 - Convert equipment – MP2 | 1 | 2021-01-18 18:30 | 2021-01-18 19:30 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | SAI TEAM;ANURAG ANAND;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92786 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 19:30 | DATA | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92788 | WBS.2.1.9.2.5.1.5 | N | N | Planned | Validate Load ITR_C0018.1 - Convert equipment – MP2 | 2 | 2021-01-18 19:30 | 2021-01-18 21:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92787 |  |  | * |  | 2021-01-18 19:30 | 2021-01-18 21:30 | AC | HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96982 | WBS.2.1.9.2.5.1.25 | N | N | Planned | BG - ITR_C0018.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert equipment – MP2) | 1 | 2021-01-18 21:30 | 2021-01-19 06:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92788 |  |  | * |  | 2021-01-18 21:30 | 2021-01-19 06:30 | AC | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92893 | WBS.2.1.9.2.5.1.7 | N | N | Planned | HBG - ITR_C0018.1 - Spot-check SAP DATA reflects loaded data (Convert equipment – MP2) | 1 | 2021-01-18 21:30 | 2021-01-19 06:30 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92788 |  |  | * |  | 2021-01-18 21:30 | 2021-01-19 06:30 | AC | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92803 | WBS.2.1.9.2.6 | N | N |  | Ramp Down ¦ ITR_C0065 - Convert Documents (Document Management System) - MP2 | 6.25 | 2021-01-18 21:30 | 2021-01-19 11:45 | [8 empty] | * |  | 2021-01-18 21:30 | 2021-01-19 13:15 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92804 | WBS.2.1.9.2.6.1 | N | N |  | Ramp Down ¦ ITR_C0065 - Convert Documents (Document Management System) - MP2 | 6.25 | 2021-01-18 21:30 | 2021-01-19 11:45 | [8 empty] | * |  | 2021-01-18 21:30 | 2021-01-19 13:15 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92806 | WBS.2.1.9.2.6.1.1 | N | N | Planned | Execute Preload ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2021-01-18 21:30 | 2021-01-19 06:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94411,92777,92788 |  |  | * |  | 2021-01-18 21:30 | 2021-01-19 06:30 | DATA | HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92807 | WBS.2.1.9.2.6.1.2 | N | N | Planned | Validate Preload ITR_C0065 - Convert Documents (Document Management System) - MP2 | 0.75 | 2021-01-19 06:30 | 2021-01-19 07:15 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92806 |  |  | * |  | 2021-01-19 06:30 | 2021-01-19 07:15 | AC | HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92808 | WBS.2.1.9.2.6.1.3 | N | N | Planned | Execute Load ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2021-01-19 07:15 | 2021-01-19 08:15 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92807 |  |  | * |  | 2021-01-19 07:15 | 2021-01-19 08:15 | DATA | HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92809 | WBS.2.1.9.2.6.1.4 | N | N | Planned | Validate Load ITR_C0065 - Convert Documents (Document Management System) - MP2 | 1 | 2021-01-19 08:15 | 2021-01-19 09:15 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92808 |  |  | * |  | 2021-01-19 08:15 | 2021-01-19 09:15 | AC | HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96981 | WBS.2.1.9.2.6.1.24 | N | N | Planned | BG-ITR_C0065 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Documents- MP2) | 2.5 | 2021-01-19 09:15 | 2021-01-19 11:45 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | ROBBIE ISBELL;DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Daniel.Isbell@GAPAC.com;Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92809 |  |  | * |  | 2021-01-19 09:15 | 2021-01-19 13:15 | AC | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92879 | WBS.2.1.9.2.6.1.6 | N | N | Planned | HBG - ITR_C0065 - Spot-check SAP DATA reflects loaded data (Convert Documents- MP2) | 0.5 | 2021-01-19 09:15 | 2021-01-19 09:45 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92809 |  |  | * |  | 2021-01-19 09:15 | 2021-01-19 09:45 | AC | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92810 | WBS.2.1.9.2.7 | N | N |  | Ramp Down ¦ ITR_C0247 - NRX 3D Enterprise Document Conversion | 66 | 2021-01-21 18:00 | 2021-01-27 20:00 | [8 empty] | * |  | 2021-01-21 18:00 | 2021-01-27 20:00 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92811 | WBS.2.1.9.2.7.1 | N | N |  | Ramp Down ¦ ITR_C0247 - NRX 3D Enterprise Document Conversion | 66 | 2021-01-21 18:00 | 2021-01-27 20:00 | [8 empty] | * |  | 2021-01-21 18:00 | 2021-01-27 20:00 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97397 | WBS.2.1.9.2.7.1.7 | N | N | Planned | Extract NRX part book drawings and provide XREF | 5 | 2021-01-21 18:00 | 2021-01-22 07:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;JOHN SIKES | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JOHN.SIKES2@GAPAC.COM | AC | 92777,5393,5398,92788,10428 |  |  | * |  | 2021-01-21 18:00 | 2021-01-22 07:00 | AC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95749 | WBS.2.1.9.2.7.1.1 | N | N | Planned | Run the VEG conversion job and validate metadata | 36 | 2021-01-22 07:00 | 2021-01-26 11:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;JASON RAMSEY | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM | AC | 97397 |  |  | * |  | 2021-01-22 07:00 | 2021-01-26 11:00 | AC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95626 | WBS.2.1.9.2.7.1.2 | N | N | Planned | Generate documents from the VEG tool for ITR_C0247 - NRX 3D Enterprise Document Conversion | 5 | 2021-01-26 11:00 | 2021-01-26 16:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | KELLY STRASSBURGER;TAJINDER KOHLI;AC TEAM;SAI TEAM | KELLY.STRASSBURGER@GAPAC.COM;TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 95749 |  |  | * |  | 2021-01-26 11:00 | 2021-01-26 16:00 | AC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92813 | WBS.2.1.9.2.7.1.3 | N | N | Planned | Execute Preload ITR_C0247 - NRX 3D Enterprise Document Conversion | 4 | 2021-01-26 16:00 | 2021-01-26 20:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 92777,5393,5398,92788,10428,95626 |  |  | * |  | 2021-01-26 16:00 | 2021-01-26 20:00 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92814 | WBS.2.1.9.2.7.1.4 | N | N | Planned | Validate Preload ITR_C0247 - NRX 3D Enterprise Document Conversion | 3 | 2021-01-26 20:00 | 2021-01-27 07:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 92813 |  |  | * |  | 2021-01-26 20:00 | 2021-01-27 07:00 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92815 | WBS.2.1.9.2.7.1.5 | N | N | Planned | Execute Load ITR_C0247 - NRX 3D Enterprise Document Conversion | 8 | 2021-01-27 07:00 | 2021-01-27 15:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 92814 |  |  | * |  | 2021-01-27 07:00 | 2021-01-27 15:00 | DATA | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92816 | WBS.2.1.9.2.7.1.6 | N | N | Planned | Validate Load ITR_C0247 - NRX 3D Enterprise Document Conversion | 3 | 2021-01-27 15:00 | 2021-01-27 18:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 92815 |  |  | * |  | 2021-01-27 15:00 | 2021-01-27 18:00 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97398 | WBS.2.1.9.2.7.1.8 | N | N | Planned | PTH - ITR_C0247 - Verify NRX conversion for part book drawings | 2 | 2021-01-27 18:00 | 2021-01-27 20:00 | LONNIE MORRIS | Lonnie.Morris@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 92816 |  |  | * |  | 2021-01-27 18:00 | 2021-01-27 20:00 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90020 | WBS.2.1.9.2.8 | N | N |  | Ramp Down ¦ OE Database Steps | 14 | 2021-01-25 06:30 | 2021-01-25 20:30 | [8 empty] | * |  | 2021-01-25 06:30 | 2021-01-25 20:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90191 | WBS.2.1.9.2.8.1 | N | N |  | Ramp Down ¦ OE Database Steps Tasks | 14 | 2021-01-25 06:30 | 2021-01-25 20:30 | [8 empty] | * |  | 2021-01-25 06:30 | 2021-01-25 20:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90016 | WBS.2.1.9.2.8.1.1 | N | N | Planned | Validate OE characteristics data is loaded correctly | 0.25 | 2021-01-25 06:30 | 2021-01-25 06:45 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5382,92566,10845 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 06:45 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90019 | WBS.2.1.9.2.8.1.2 | N | N | Planned | Confirm SAP Asset Hierarchy is updated in OE database for existing and possible FLOCs | 4 | 2021-01-25 06:30 | 2021-01-25 10:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;TAJINDER KOHLI;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;TKOHLI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5393,92566,92777 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 10:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90018 | WBS.2.1.9.2.8.1.3 | N | N | Planned | Extract OE Variable data with Supp & State info in MPoint Load format | 2 | 2021-01-25 10:30 | 2021-01-25 12:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;TAJINDER KOHLI;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;TKOHLI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90019,92566 |  |  | * |  | 2021-01-25 10:30 | 2021-01-25 12:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90830 | WBS.2.1.9.2.8.1.4 | N | N | Planned | Prepare, load and validate OE measuring point | 3 | 2021-01-25 12:30 | 2021-01-25 15:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;SAI TEAM;AC TEAM;BOB BROWN;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90018,92566,10845 |  |  | * |  | 2021-01-25 12:30 | 2021-01-25 15:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90014 | WBS.2.1.9.2.8.1.5 | N | N | Planned | Provide Measuring Point XREF For OE Legacy Variable IDs (PID) | 0.5 | 2021-01-25 15:30 | 2021-01-25 16:00 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90830 |  |  | * |  | 2021-01-25 15:30 | 2021-01-25 16:00 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90013 | WBS.2.1.9.2.8.1.6 | N | N | Planned | Transition Existing OE Variables to new Measuring Points (update PID) | 2 | 2021-01-25 15:30 | 2021-01-25 17:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;TAJINDER KOHLI;DON ABBOTT;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;TKOHLI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90019,90830 |  |  | * |  | 2021-01-25 15:30 | 2021-01-25 17:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95499 | WBS.2.1.9.2.8.1.7 | N | N | Planned | Extract OE Limit Values with Updated PID for validation | 1.5 | 2021-01-25 17:30 | 2021-01-25 19:00 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;TAJINDER KOHLI;DON ABBOTT;SAI TEAM;AC TEAM | DAVID.MCGINNIS@GAPAC.COM;TKOHLI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 90013 |  |  | * |  | 2021-01-25 17:30 | 2021-01-25 19:00 | AC | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95496 | WBS.2.1.9.2.8.1.8 | N | N | Planned | Ensure interface is turned off to OE legacy to ensure data congruency | 2 | 2021-01-25 06:30 | 2021-01-25 08:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;AC TEAM;SAI TEAM | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 92566 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 08:30 | AC | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90012 | WBS.2.1.9.2.8.1.9 | N | N | Planned | Prepare and validate template for OE custom table | 1 | 2021-01-25 16:00 | 2021-01-25 17:00 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90014 |  |  | * |  | 2021-01-25 16:00 | 2021-01-25 17:00 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90011 | WBS.2.1.9.2.8.1.10 | N | N | Planned | Load data in OE custom table using custom program | 0.5 | 2021-01-25 17:00 | 2021-01-25 17:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90012,92566,5430,95496 |  |  | * |  | 2021-01-25 17:00 | 2021-01-25 17:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90010 | WBS.2.1.9.2.8.1.11 | N | N | Planned | Validate data loaded in SAP OE custom table as accurate | 0.75 | 2021-01-25 17:30 | 2021-01-25 18:15 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90011,92566 |  |  | * |  | 2021-01-25 17:30 | 2021-01-25 18:15 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90009 | WBS.2.1.9.2.8.1.12 | N | N | Planned | Confirm interface ITR_I0299 is triggered to send the xml to OE | 0.25 | 2021-01-25 18:15 | 2021-01-25 18:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | TAJINDER KOHLI;JASON RAMSEY;DON ABBOTT;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90010,92566 |  |  | * |  | 2021-01-25 18:15 | 2021-01-25 18:30 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95498 | WBS.2.1.9.2.8.1.13 | N | N | Planned | Turn on interface at OE side to allow changes and additions | 2 | 2021-01-25 18:30 | 2021-01-25 20:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;AC TEAM;SAI TEAM | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 90009 |  |  | * |  | 2021-01-25 18:30 | 2021-01-25 20:30 | AC | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5436 | WBS.2.1.9.2.9 | N | N |  | Ramp Down ¦ ITR_C0028 - Convert Equipment Classification Values – AS8 | 4.33 | 2021-01-21 18:00 | 2021-01-22 06:20 | [8 empty] | * |  | 2021-01-21 18:00 | 2021-01-22 06:20 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90221 | WBS.2.1.9.2.9.1 | N | N |  | Ramp Down ¦ ITR_C0028 - Convert Equipment Classification Values – AS8 | 4.33 | 2021-01-21 18:00 | 2021-01-22 06:20 | [8 empty] | * |  | 2021-01-21 18:00 | 2021-01-22 06:20 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
10112 | WBS.2.1.9.2.9.1.1 | N | N | Planned | ITR_C0028 - Execute Transform program - Convert Equipment Classification values - AS8 | 2 | 2021-01-21 18:00 | 2021-01-21 20:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5385,5398 |  |  | * |  | 2021-01-21 18:00 | 2021-01-21 20:00 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10113 | WBS.2.1.9.2.9.1.2 | N | N | Planned | ITR_C0028 - Preload Validation - Convert Equipment Classification values - AS8 | 0.33 | 2021-01-21 20:00 | 2021-01-21 20:20 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 10112 |  |  | * |  | 2021-01-21 20:00 | 2021-01-21 20:20 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5437 | WBS.2.1.9.2.9.1.3 | N | N | Planned | ITR_C0028 - Execute Load program - Convert Equipment Classification Values – AS8 | 1 | 2021-01-21 20:20 | 2021-01-21 21:20 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10113 |  |  | * |  | 2021-01-21 20:20 | 2021-01-21 21:20 | DATA | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
5438 | WBS.2.1.9.2.9.1.4 | N | N | Planned | ITR_C0028 - Validate Load - Convert Equipment Classification Values – AS8 | 0.5 | 2021-01-21 21:20 | 2021-01-21 21:50 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5437 |  |  | * |  | 2021-01-21 21:20 | 2021-01-21 21:50 | AC | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
81616 | WBS.2.1.9.2.9.1.5 | N | N | Planned | PTH - ITR_C0028 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Equipment Classification Values – AS8) | 0.5 | 2021-01-21 21:50 | 2021-01-22 06:20 | DANIEL HENDERSON | daniel.henderson@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5438 |  |  | * |  | 2021-01-21 21:50 | 2021-01-22 06:20 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92864 | WBS.2.1.9.2.10 | N | N |  | Ramp Down ¦ ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 8.5 | 2021-01-21 07:00 | 2021-01-21 15:30 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-21 17:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92865 | WBS.2.1.9.2.10.1 | N | N |  | Ramp Down ¦ ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 8.5 | 2021-01-21 07:00 | 2021-01-21 15:30 | [8 empty] | * |  | 2021-01-21 07:00 | 2021-01-21 17:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92867 | WBS.2.1.9.2.10.1.1 | N | N | Planned | Execute Preload ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2021-01-21 07:00 | 2021-01-21 08:00 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92777,92809,10428 |  |  | * |  | 2021-01-21 07:00 | 2021-01-21 08:00 | DATA | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92868 | WBS.2.1.9.2.10.1.2 | N | N | Planned | Validate Preload ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 2 | 2021-01-21 08:00 | 2021-01-21 10:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92867 |  |  | * |  | 2021-01-21 08:00 | 2021-01-21 10:00 | AC | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92869 | WBS.2.1.9.2.10.1.3 | N | N | Planned | Execute Load ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 1 | 2021-01-21 10:00 | 2021-01-21 11:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | SAI TEAM;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92868 |  |  | * |  | 2021-01-21 10:00 | 2021-01-21 11:00 | DATA | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92870 | WBS.2.1.9.2.10.1.4 | N | N | Planned | Validate Load ITR_C0038.7 - Convert Task Lists - General Conversion – MP2 | 2 | 2021-01-21 11:00 | 2021-01-21 13:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92869 |  |  | * |  | 2021-01-21 11:00 | 2021-01-21 13:00 | AC | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96980 | WBS.2.1.9.2.10.1.23 | N | N | Planned | BG - ITR_C0038.7 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Task Lists - General Conversion – MP2) | 2.5 | 2021-01-21 13:00 | 2021-01-21 15:30 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92870 |  |  | * |  | 2021-01-21 13:00 | 2021-01-21 17:00 | AC | BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92882 | WBS.2.1.9.2.10.1.5 | N | N | Planned | HBG - ITR_C0038.7 - Spot-check SAP DATA reflects loaded data (Convert Task Lists - General Conversion – MP2) | 0.5 | 2021-01-21 13:00 | 2021-01-21 13:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92870 |  |  | * |  | 2021-01-21 13:00 | 2021-01-21 13:30 | AC | HBG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92871 | WBS.2.1.9.2.11 | N | N |  | Ramp Down ¦ ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 15 | 2021-01-21 13:00 | 2021-01-22 12:00 | [8 empty] | * |  | 2021-01-21 13:00 | 2021-01-22 12:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92872 | WBS.2.1.9.2.11.1 | N | N |  | Ramp Down ¦ ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 15 | 2021-01-21 13:00 | 2021-01-22 12:00 | [8 empty] | * |  | 2021-01-21 13:00 | 2021-01-22 12:00 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92874 | WBS.2.1.9.2.11.1.1 | N | N | Planned | Execute Preload ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2021-01-21 13:00 | 2021-01-21 14:00 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92870 |  |  | * |  | 2021-01-21 13:00 | 2021-01-21 14:00 | DATA | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92875 | WBS.2.1.9.2.11.1.2 | N | N | Planned | Validate Preload ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 2 | 2021-01-21 14:00 | 2021-01-21 16:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92874 |  |  | * |  | 2021-01-21 14:00 | 2021-01-21 16:00 | AC | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92876 | WBS.2.1.9.2.11.1.3 | N | N | Planned | Execute Load ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 1 | 2021-01-21 16:00 | 2021-01-21 17:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92875 |  |  | * |  | 2021-01-21 16:00 | 2021-01-21 17:00 | DATA | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92877 | WBS.2.1.9.2.11.1.4 | N | N | Planned | Validate Load ITR_C0050.2 - Convert Maintenance Plans Conversion – MP2 | 2 | 2021-01-21 17:00 | 2021-01-21 19:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92876 |  |  | * |  | 2021-01-21 17:00 | 2021-01-21 19:00 | AC | HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
95748 | WBS.2.1.9.2.11.1.5 | N | N | Planned | Update call horizon in MP2 maintenance plans | 2 | 2021-01-21 19:00 | 2021-01-21 21:00 | BRENNEN FRISQUE | BRENNEN.FRISQUE@GAPAC.COM | TAJINDER KOHLI;AC TEAM;PAVAN KUMAR;SAI TEAM | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;PAVAN.KUMARCS@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 92877 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 21:00 | AC | ALL | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
96979 | WBS.2.1.9.2.11.1.22 | N | N | Planned | BG - ITR_C0050.2 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Maintenance Plans Conversion – MP2) | 2.5 | 2021-01-21 21:00 | 2021-01-22 07:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 95748 |  |  | * |  | 2021-01-21 21:00 | 2021-01-22 09:00 | AC | BG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
92885 | WBS.2.1.9.2.11.1.6 | N | N | Planned | HBG - ITR_C0050.2 - Spot-check SAP DATA reflects loaded data (Convert Job Plans – MP2) | 2 | 2021-01-21 21:00 | 2021-01-22 07:00 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 95748 |  |  | * |  | 2021-01-21 21:00 | 2021-01-22 07:00 | AC | HBG | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95554 | WBS.2.1.9.2.11.1.8 | N | N | Planned | Load Meter based maint. Plan for MP2 | 4 | 2021-01-22 06:00 | 2021-01-22 10:00 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | JEY MURUGESH;SAI TEAM;AC TEAM;JASON RAMSEY | JMURUGESH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM | AC | 95716 |  |  | * |  | 2021-01-22 06:00 | 2021-01-22 10:00 | AC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
95553 | WBS.2.1.9.2.11.1.9 | N | N | Planned | Validate meter based maint plan for MP2 | 2 | 2021-01-22 10:00 | 2021-01-22 12:00 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 95554 |  |  | * |  | 2021-01-22 10:00 | 2021-01-22 12:00 | AC | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
5439 | WBS.2.1.9.2.12 | N | N |  | Ramp Down ¦ ITR_C0030 - Convert Functional Location Classification Values – AS8 | 8.5 | 2021-01-18 18:30 | 2021-01-19 11:00 | [8 empty] | * |  | 2021-01-18 18:30 | 2021-01-19 11:00 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90203 | WBS.2.1.9.2.12.1 | N | N |  | Ramp Down ¦ ITR_C0030 - Convert Functional Location Classification Values – AS8 | 8.5 | 2021-01-18 18:30 | 2021-01-19 11:00 | [8 empty] | * |  | 2021-01-18 18:30 | 2021-01-19 11:00 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
8807 | WBS.2.1.9.2.12.1.1 | N | N | Planned | ITR_C0030 - Execute Transformation program - Convert Functional Location Classification Values – AS8 | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;BOB BROWN;JASON RAMSEY;GARY BENOIT | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;GARY.BENOIT@GAPAC.COM | DATA | 5385,5393,3966,82569 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 20:30 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
8808 | WBS.2.1.9.2.12.1.2 | N | N | Planned | ITR_C0030 - Validate Pre Load - Convert Functional Location Classification Values – AS8 | 0.5 | 2021-01-18 20:30 | 2021-01-18 21:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 8807 |  |  | * |  | 2021-01-18 20:30 | 2021-01-18 21:00 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5440 | WBS.2.1.9.2.12.1.3 | N | N | Planned | ITR_C0030 - Execute Load program - Convert Functional Location Classification Values – AS8 | 2 | 2021-01-18 21:00 | 2021-01-19 07:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;BOB BROWN;JASON RAMSEY;GARY BENOIT | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;GARY.BENOIT@GAPAC.COM | DATA | 8808 |  |  | * |  | 2021-01-18 21:00 | 2021-01-19 07:00 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5441 | WBS.2.1.9.2.12.1.4 | N | N | Planned | ITR_C0030 - Validate Load - Convert Functional Location Classification Values – AS8 | 4 | 2021-01-19 07:00 | 2021-01-19 11:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5440 |  |  | * |  | 2021-01-19 07:00 | 2021-01-19 11:00 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5759 | WBS.2.1.9.2.13 | N | N |  | Ramp Down ¦ ITR_C0032 - Convert Open Work Orders – AS8 | 12 | 2021-01-26 10:15 | 2021-01-27 06:15 | [8 empty] | * |  | 2021-01-26 10:15 | 2021-01-27 06:15 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
90905 | WBS.2.1.9.2.13.1 | N | N |  | Ramp Down ¦ ITR_C0032 - Convert Open Work Orders – AS8 | 12 | 2021-01-26 10:15 | 2021-01-27 06:15 | [8 empty] | * |  | 2021-01-26 10:15 | 2021-01-27 06:15 |  |  | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
5760 | WBS.2.1.9.2.13.1.1 | N | N | Planned | ITR_C0032 - Execute Transform program - Convert Open work orders – Asset Suite | 2 | 2021-01-26 10:15 | 2021-01-26 12:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10428,5398,5408,89967,89987,90973,94400 |  |  | * |  | 2021-01-26 10:15 | 2021-01-26 12:15 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5761 | WBS.2.1.9.2.13.1.2 | N | N | Planned | ITR_C0032 - Validate Preload Transform - Convert Open work orders – Asset Suite | 1 | 2021-01-26 12:15 | 2021-01-26 13:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5760 |  |  | * |  | 2021-01-26 12:15 | 2021-01-26 13:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5762 | WBS.2.1.9.2.13.1.3 | N | N | Planned | ITR_C0032 - Execute Load program - Convert Open work orders – Asset Suite | 4 | 2021-01-26 13:15 | 2021-01-26 17:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;ANKIT AGARWAL | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;ANKITAGARWAL87@DELOITTE.COM | DATA | 5761 |  |  | * |  | 2021-01-26 13:15 | 2021-01-26 17:15 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5763 | WBS.2.1.9.2.13.1.4 | N | N | Planned | ITR_C0032 - Validate Load - Convert Open work orders – Asset Suite | 1 | 2021-01-26 17:15 | 2021-01-26 18:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | CHAD FLAGG;JASON RAMSEY;SAI TEAM;TAJINDER KOHLI;BRENNEN FRISQUE;AC TEAM | CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5762 |  |  | * |  | 2021-01-26 17:15 | 2021-01-26 18:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
93221 | WBS.2.1.9.2.13.1.5 | N | N | Planned | PTH - ITR_C0032 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Open work orders – Asset Suite) | 1 | 2021-01-26 18:15 | 2021-01-26 19:15 | LONNIE MORRIS | Lonnie.Morris@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5763 |  |  | * |  | 2021-01-26 18:15 | 2021-01-26 19:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94646 | WBS.2.1.9.2.13.1.7 | N | N | Planned | PTH - Pre-Load: Verify the PM auto-generated WO and in flight planned and approved WO converted correctly | 2 | 2021-01-26 18:15 | 2021-01-26 20:15 | TOMMY WOMACK | tommy.womack@gapac.com | DARRELL WATSON;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Darrell.watson@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5763 |  |  | * |  | 2021-01-26 18:15 | 2021-01-26 20:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94647 | WBS.2.1.9.2.13.1.8 | N | N | Planned | PTH - Pre-load: Load and maintain Work Orders - ready for work (kitted), completed or in progress | 4 | 2021-01-26 18:15 | 2021-01-27 06:15 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5763 |  |  | * |  | 2021-01-26 18:15 | 2021-01-27 06:15 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82904 | WBS.2.1.9.2.14 | N | N |  | Ramp Down ¦ ITR_C0038 - Convert Task Lists – Functional Location Conversion - PTM | 11 | 2021-01-18 18:30 | 2021-01-19 13:30 | [8 empty] | * |  | 2021-01-18 18:30 | 2021-01-19 13:30 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90202 | WBS.2.1.9.2.14.1 | N | N |  | Ramp Down ¦ ITR_C0038 - Convert Task Lists – Functional Location Conversion - PTM Tasks | 11 | 2021-01-18 18:30 | 2021-01-19 13:30 | [8 empty] | * |  | 2021-01-18 18:30 | 2021-01-19 13:30 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82903 | WBS.2.1.9.2.14.1.6 | N | N | Planned | ITR_C0038 - Execute Transform program - Convert Task Lists – Functional Location Conversion - PTM | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5393,3968,82569 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 20:30 | DATA | PTH,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82902 | WBS.2.1.9.2.14.1.7 | N | N | Planned | ITR_C0038 - Validate Preload Transform - Convert Task Lists – Functional Location Conversion - PTM | 0.5 | 2021-01-18 20:30 | 2021-01-18 21:00 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 82903 |  |  | * |  | 2021-01-18 20:30 | 2021-01-18 21:00 | AC | PTH,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82901 | WBS.2.1.9.2.14.1.8 | N | N | Planned | ITR_C0038 - Execute Load program - Convert Task Lists – Functional Location Conversion - PTM | 1 | 2021-01-18 21:00 | 2021-01-18 22:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 82902 |  |  | * |  | 2021-01-18 21:00 | 2021-01-18 22:00 | DATA | PTH,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82900 | WBS.2.1.9.2.14.1.9 | N | N | Planned | ITR_C0038 - Validate Load - Convert Task Lists – Functional Location Conversion - PTM | 4 | 2021-01-19 06:30 | 2021-01-19 10:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | KELLY STRASSBURGER;DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | KELLY.STRASSBURGER@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 82901,5428 |  |  | * |  | 2021-01-19 06:30 | 2021-01-19 10:30 | AC | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95432 | WBS.2.1.9.2.14.1.10 | N | N | Planned | PTH - ITR_C0038 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data For Converted Task Lists - PTM | 3 | 2021-01-19 10:30 | 2021-01-19 13:30 | JT THOMAS | Jerry.Thomas2@gapac.com | CJ KAUTH;ROBBIE GARNER;DANIEL HENDERSON;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;daniel.henderson@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 82900 |  |  | * |  | 2021-01-19 10:30 | 2021-01-19 13:30 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5452 | WBS.2.1.9.2.15 | N | N |  | Ramp Down ¦ ITR_C0038.2 - Convert Task Lists – Functional Location Conversion - Maintelligence | 12.5 | 2021-01-19 10:30 | 2021-01-20 07:00 | [8 empty] | * |  | 2021-01-19 10:30 | 2021-01-20 07:00 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90201 | WBS.2.1.9.2.15.1 | N | N |  | Ramp Down ¦ ITR_C0038.2 - Convert Task Lists – Functional Location Conversion - Maintelligence Tasks | 12.5 | 2021-01-19 10:30 | 2021-01-20 07:00 | [8 empty] | * |  | 2021-01-19 10:30 | 2021-01-20 07:00 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5453 | WBS.2.1.9.2.15.1.1 | N | N | Planned | ITR_C0038.2 - Execute Transform program - Convert Task Lists – Functional Location Conversion - Maintelligence | 4 | 2021-01-19 10:30 | 2021-01-19 14:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5393,3967,82569,82900 |  |  | * |  | 2021-01-19 10:30 | 2021-01-19 14:30 | DATA | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5454 | WBS.2.1.9.2.15.1.2 | N | N | Planned | ITR_C0038.2 - Validate Preload Transform - Convert Task Lists – Functional Location Conversion - Maintelligence | 2 | 2021-01-19 14:30 | 2021-01-19 16:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5453,82902 |  |  | * |  | 2021-01-19 14:30 | 2021-01-19 16:30 | AC | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5455 | WBS.2.1.9.2.15.1.3 | N | N | Planned | ITR_C0038.2 - Execute Load program - Convert Task Lists – Functional Location Conversion - Maintelligence | 1 | 2021-01-19 16:30 | 2021-01-19 17:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5454 |  |  | * |  | 2021-01-19 16:30 | 2021-01-19 17:30 | DATA | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5456 | WBS.2.1.9.2.15.1.4 | N | N | Planned | ITR_C0038.2 - Validate Load - Convert Task Lists – Functional Location Conversion - Maintelligence | 2 | 2021-01-19 18:00 | 2021-01-19 20:00 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | KELLY STRASSBURGER;DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | KELLY.STRASSBURGER@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5455,82900,95483 |  |  | * |  | 2021-01-19 18:00 | 2021-01-19 20:00 | AC | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95433 | WBS.2.1.9.2.15.1.5 | N | N | Planned | PTH - ITR_C0038.2 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data For Converted Task Lists - Maintelligence | 3 | 2021-01-19 20:00 | 2021-01-20 07:00 | PORTER CRAIG | Porter.Craig@gapac.com | SEAN HERTZBURG;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | sean.hertzberg@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5456 |  |  | * |  | 2021-01-19 20:00 | 2021-01-20 07:00 | AC | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95483 | WBS.2.1.9.2.15.1.6 | N | N | Planned | Update PTM operation description | 0.5 | 2021-01-19 17:30 | 2021-01-19 18:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | BOB BROWN;AC TEAM;SAI TEAM | ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5455 |  |  | * |  | 2021-01-19 17:30 | 2021-01-19 18:00 | AC | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5477 | WBS.2.1.9.2.16 | N | N |  | Ramp Down ¦ ITR_C0050.1 - Convert Maintenance Plans Conversion - Maintelligence | 9.75 | 2021-01-19 20:00 | 2021-01-20 13:45 | [8 empty] | * |  | 2021-01-19 20:00 | 2021-01-20 13:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90207 | WBS.2.1.9.2.16.1 | N | N |  | Ramp Down ¦ ITR_C0050.1 - Convert Maintenance Plans Conversion - Maintelligence Tasks | 9.75 | 2021-01-19 20:00 | 2021-01-20 13:45 | [8 empty] | * |  | 2021-01-19 20:00 | 2021-01-20 13:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9400 | WBS.2.1.9.2.16.1.1 | N | N | Planned | Ensure Unique 40 Character ‘Route Name-Schedule Description’ Exist for Maint. Plans | 0.25 | 2021-01-19 20:00 | 2021-01-19 20:15 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;SAI TEAM;JASON RAMSEY;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5456 |  |  | * |  | 2021-01-19 20:00 | 2021-01-19 20:15 | AC | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5478 | WBS.2.1.9.2.16.1.2 | N | N | Planned | ITR_C0050.1 - Execute Transform program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2021-01-19 20:15 | 2021-01-20 06:15 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9400,5430 |  |  | * |  | 2021-01-19 20:15 | 2021-01-20 06:15 | DATA | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5479 | WBS.2.1.9.2.16.1.3 | N | N | Planned | ITR_C0050.1 - Validate Preload Transform - Convert Maintenance Plans Conversion - Maintelligence | 1.5 | 2021-01-20 06:15 | 2021-01-20 07:45 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5478 |  |  | * |  | 2021-01-20 06:15 | 2021-01-20 07:45 | AC | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5480 | WBS.2.1.9.2.16.1.4 | N | N | Planned | ITR_C0050.1 - Execute Load program - Convert Maintenance Plans Conversion - Maintelligence | 2 | 2021-01-20 07:45 | 2021-01-20 09:45 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5479 |  |  | * |  | 2021-01-20 07:45 | 2021-01-20 09:45 | DATA | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5481 | WBS.2.1.9.2.16.1.5 | N | N | Planned | ITR_C0050.1 - Validate Load - Convert Maintenance Plans Conversion - Maintelligence | 1 | 2021-01-20 09:45 | 2021-01-20 10:45 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;SAI TEAM;KELLY STRASSBURGER;DAVID MCGINNIS;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KELLY.STRASSBURGER@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5480 |  |  | * |  | 2021-01-20 09:45 | 2021-01-20 10:45 | AC | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95048 | WBS.2.1.9.2.16.1.6 | N | N | Planned | PTH - ITR_C0050.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Maintenance Plans Conversion - Maintelligence - Hoist and Crane Specific) | 1 | 2021-01-20 10:45 | 2021-01-20 11:45 | PORTER CRAIG | Porter.Craig@gapac.com | SEAN HERTZBURG;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;BOB BROWN | sean.hertzberg@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ROBERT.BROWN4@GAPAC.COM | AC | 5481 |  |  | * |  | 2021-01-20 10:45 | 2021-01-20 11:45 | AC | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
81620 | WBS.2.1.9.2.16.1.10 | N | N | Planned | PTH - ITR_C0050.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Maintenance Plans Conversion - Maintelligence) | 3 | 2021-01-20 10:45 | 2021-01-20 13:45 | PORTER CRAIG | Porter.Craig@gapac.com | SEAN HERTZBURG;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;BOB BROWN | sean.hertzberg@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ROBERT.BROWN4@GAPAC.COM | AC | 5481 |  |  | * |  | 2021-01-20 10:45 | 2021-01-20 13:45 | AC | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5426 | WBS.2.1.9.2.17 | N | N |  | Ramp Down ¦ ITR_C0055 - Convert Measuring Points (with catalogs) – Maintelligence | 41.75 | 2021-01-17 21:45 | 2021-01-20 13:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-20 13:30 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90205 | WBS.2.1.9.2.17.1 | N | N |  | Ramp Down ¦ ITR_C0055 - Convert Measuring Points (with catalogs) – Maintelligence Tasks | 41.75 | 2021-01-17 21:45 | 2021-01-20 13:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-20 13:30 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
3994 | WBS.2.1.9.2.17.1.1 | N | N | Planned | ITR_C0055 - Provide Load File For Convert Measuring Points (w/Catalogs) - AS8 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;KELLY STRASSBURGER;BOB BROWN;AC TEAM;GARY BENOIT | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KELLY.STRASSBURGER@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | PTH | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5427 | WBS.2.1.9.2.17.1.2 | N | N | Planned | ITR_C0055 - Execute Transform program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2021-01-18 18:30 | 2021-01-18 20:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5382,5388,5393,3967,82569 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 20:30 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5428 | WBS.2.1.9.2.17.1.3 | N | N | Planned | ITR_C0055 - Validate Preload Transform - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2021-01-18 20:30 | 2021-01-19 06:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 5427 |  |  | * |  | 2021-01-18 20:30 | 2021-01-19 06:30 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5429 | WBS.2.1.9.2.17.1.4 | N | N | Planned | ITR_C0055 - Execute Load program - Convert Measuring Points (with catalogs) – Maintelligence | 2 | 2021-01-19 06:30 | 2021-01-19 08:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5428 |  |  | * |  | 2021-01-19 06:30 | 2021-01-19 08:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10472 | WBS.2.1.9.2.17.1.5 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points Classification | 2 | 2021-01-19 08:30 | 2021-01-19 10:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 5429,82569 |  |  | * |  | 2021-01-19 08:30 | 2021-01-19 10:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10473 | WBS.2.1.9.2.17.1.6 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points Classification | 1 | 2021-01-19 10:30 | 2021-01-19 11:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10472 |  |  | * |  | 2021-01-19 10:30 | 2021-01-19 11:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
68443 | WBS.2.1.9.2.17.1.7 | N | N | Planned | ITR_C0055 - Execute Transform program - Measuring Points-Entry List | 1 | 2021-01-19 11:30 | 2021-01-19 12:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;US INDIA GP DATA | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM | DATA | 5382,5388,5393,10473 |  |  | * |  | 2021-01-19 11:30 | 2021-01-19 12:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
68444 | WBS.2.1.9.2.17.1.8 | N | N | Planned | ITR_C0055 - Execute Load - Measuring Points-Entry List | 1 | 2021-01-19 12:30 | 2021-01-19 13:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;US GP BASIS | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;USGPBASIS@DELOITTE.COM | DATA | 68443 |  |  | * |  | 2021-01-19 12:30 | 2021-01-19 13:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5430 | WBS.2.1.9.2.17.1.11 | N | N | Planned | ITR_C0055 - Validate Load - Convert Measuring Points(with catalogs) - Maintelligence and Entry List | 4 | 2021-01-19 13:30 | 2021-01-19 17:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | KELLY STRASSBURGER;DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT | KELLY.STRASSBURGER@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 5429,10473,68444 |  |  | * |  | 2021-01-19 13:30 | 2021-01-19 17:30 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
81613 | WBS.2.1.9.2.17.1.13 | N | N | Planned | PTH - ITR_C0055 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Measuring Points(with catalogs) - Maintelligence) | 1 | 2021-01-19 17:30 | 2021-01-19 18:30 | PORTER CRAIG | Porter.Craig@gapac.com | SEAN HERTZBURG;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | sean.hertzberg@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 68444,5430 |  |  | * |  | 2021-01-19 17:30 | 2021-01-19 18:30 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95489 | WBS.2.1.9.2.17.1.15 | N | N | Planned | ITR_C0055 - Execute Loads - Measuring Points & Entry Lists (From External Load File - PTH e-Plus Routes) | 8 | 2021-01-19 17:30 | 2021-01-20 09:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | BOB BROWN;KELLY STRASSBURGER;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;JEY MURUGESH | ROBERT.BROWN4@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;JMURUGESH@DELOITTE.COM | AC | 5430 |  |  | * |  | 2021-01-19 17:30 | 2021-01-20 09:30 | AC | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95488 | WBS.2.1.9.2.17.1.16 | N | N | Planned | ITR_C0055 - Execute Loads - Measuring Points & Entry Lists (From External Load File - PTH IR Scan Routes) | 4 | 2021-01-20 09:30 | 2021-01-20 13:30 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | BOB BROWN;KELLY STRASSBURGER;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;JEY MURUGESH | ROBERT.BROWN4@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;JMURUGESH@DELOITTE.COM | AC | 95489 |  |  | * |  | 2021-01-20 09:30 | 2021-01-20 13:30 | AC | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5377 | WBS.2.1.9.2.18 | N | N |  | Ramp Down ¦ ITR_C0061 - Convert Work Center - HR Assignments Conversion | 102.58 | 2021-01-17 21:45 | 2021-01-26 10:20 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-26 10:20 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90213 | WBS.2.1.9.2.18.1 | N | N |  | Ramp Down ¦ ITR_C0061 - Convert Work Center - HR Assignments Conversion Tasks | 102.58 | 2021-01-17 21:45 | 2021-01-26 10:20 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-26 10:20 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
3991 | WBS.2.1.9.2.18.1.1 | N | N | Planned | ITR_C0061 - Provide Load File For Convert Work Center - HR Assignments - AS8 and MP2 | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JEY MURUGESH;SAI TEAM;JASON RAMSEY;KELLY STRASSBURGER;BOB BROWN;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JMURUGESH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | AC | PTH,HBG,BG | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
10474 | WBS.2.1.9.2.18.1.2 | N | N | Planned | ITR_C0061 - Execute Preload - Convert Work Center - HR assignments | 1 | 2021-01-25 18:00 | 2021-01-25 19:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 4974 |  |  | * |  | 2021-01-25 18:00 | 2021-01-25 19:00 | DATA | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
10475 | WBS.2.1.9.2.18.1.3 | N | N | Planned | ITR_C0061 - Validate Preload - Convert Work Center - HR assignments | 0.33 | 2021-01-25 19:00 | 2021-01-25 19:20 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;HOWARD ZAHORIK;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 10474 |  |  | * |  | 2021-01-25 19:00 | 2021-01-25 19:20 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
5378 | WBS.2.1.9.2.18.1.4 | N | N | Planned | ITR_C0061 - Execute Load program - Convert Work Center - HR assignments | 4 | 2021-01-25 19:20 | 2021-01-26 07:20 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10475 |  |  | * |  | 2021-01-25 19:20 | 2021-01-26 07:20 | DATA | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5379 | WBS.2.1.9.2.18.1.5 | N | N | Planned | ITR_C0061 - Validate Load - Convert Work Center - HR assignments | 1 | 2021-01-26 07:20 | 2021-01-26 08:20 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;HOWARD ZAHORIK;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5378 |  |  | * |  | 2021-01-26 07:20 | 2021-01-26 08:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96976 | WBS.2.1.9.2.18.1.10 | N | N | Planned | BG - ITR_C0061 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Work Center - HR assignments) | 2 | 2021-01-26 08:20 | 2021-01-26 10:20 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | ROBBIE ISBELL;DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Daniel.Isbell@GAPAC.com;Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 5379 |  |  | * |  | 2021-01-26 08:20 | 2021-01-26 10:20 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
81602 | WBS.2.1.9.2.18.1.7 | N | N | Planned | PTH - ITR_C0061 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Work Center - HR assignments AS8 & MP2) | 0.75 | 2021-01-26 08:20 | 2021-01-26 09:05 | JT THOMAS | Jerry.Thomas2@gapac.com | CJ KAUTH;ROBBIE GARNER;DANIEL HENDERSON;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;daniel.henderson@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5379 |  |  | * |  | 2021-01-26 08:20 | 2021-01-26 09:05 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92908 | WBS.2.1.9.2.18.1.8 | N | N | Planned | HBG - ITR_C0061 - Spot-check SAP DATA reflects loaded data (Convert Work Center - HR roles) | 0.5 | 2021-01-26 08:20 | 2021-01-26 08:50 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 5379 |  |  | * |  | 2021-01-26 08:20 | 2021-01-26 08:50 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5386 | WBS.2.1.9.2.19 | N | N |  | Ramp Down ¦ ITR_C0064 - Convert Code and Code Groups | 11.5 | 2021-01-17 21:45 | 2021-01-18 15:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 15:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90195 | WBS.2.1.9.2.19.1 | N | N |  | Ramp Down ¦ ITR_C0064 - Convert Code and Code Groups | 11.5 | 2021-01-17 21:45 | 2021-01-18 15:15 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 15:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3995 | WBS.2.1.9.2.19.1.1 | N | N | Planned | ITR_C0064 - Provide Load File For Convert Code And Code Groups | 0.25 | 2021-01-17 21:45 | 2021-01-17 22:00 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;SAI TEAM;JASON RAMSEY;AC TEAM;GARY BENOIT | DAVID.MCGINNIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | AC | CROSS | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5387 | WBS.2.1.9.2.19.1.2 | N | N | Planned | ITR_C0064 - Execute Load program - Convert Code And Code Groups | 1 | 2021-01-18 10:00 | 2021-01-18 11:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | ANURAG ANAND;DATA ETL TEAM;SAI TEAM | ANANAND@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 4091,3995 |  |  | * |  | 2021-01-18 10:00 | 2021-01-18 11:00 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5388 | WBS.2.1.9.2.19.1.3 | N | N | Planned | ITR_C0064 - Validate Load - Convert Code And Code Groups | 0.25 | 2021-01-18 11:00 | 2021-01-18 11:15 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM | AC | 5387 |  |  | * |  | 2021-01-18 11:00 | 2021-01-18 11:15 | AC | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96975 | WBS.2.1.9.2.19.1.7 | N | N | Planned | BG - ITR_C0064 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert Code And Code Groups) | 2.5 | 2021-01-18 11:15 | 2021-01-18 13:45 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 5388 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 15:15 | AC | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
81581 | WBS.2.1.9.2.19.1.5 | N | N | Planned | PTH - ITR_C0064 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert Code And Code Groups) | 4 | 2021-01-18 11:15 | 2021-01-18 15:15 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5388 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 15:15 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96987 | WBS.2.1.9.2.19.1.8 | N | N | Planned | HBG - ITR_C0064 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert Code And Code Groups) | 4 | 2021-01-18 11:15 | 2021-01-18 15:15 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 5388 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 15:15 | AC | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5769 | WBS.2.1.9.2.20 | N | N |  | Ramp Down ¦ ITR_C0067 - Convert Scheduled Maintenance Plans – AS8 | 10.5 | 2021-01-26 10:15 | 2021-01-26 20:45 | [8 empty] | * |  | 2021-01-26 10:15 | 2021-01-26 20:45 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90904 | WBS.2.1.9.2.20.1 | N | N |  | Ramp Down ¦ ITR_C0067 - Convert Scheduled Maintenance Plans – AS8 | 10.5 | 2021-01-26 10:15 | 2021-01-26 20:45 | [8 empty] | * |  | 2021-01-26 10:15 | 2021-01-26 20:45 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89993 | WBS.2.1.9.2.20.1.1 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 2 | 2021-01-26 10:15 | 2021-01-26 12:15 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 89987,90973,94400,5476 |  |  | * |  | 2021-01-26 10:15 | 2021-01-26 12:15 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89996 | WBS.2.1.9.2.20.1.2 | N | N | Planned | ITR_C0067 - Validate Preload Transform - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 0.33 | 2021-01-26 12:15 | 2021-01-26 12:35 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 89993 |  |  | * |  | 2021-01-26 12:15 | 2021-01-26 12:35 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89994 | WBS.2.1.9.2.20.1.3 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 2 | 2021-01-26 12:35 | 2021-01-26 14:35 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 89996 |  |  | * |  | 2021-01-26 12:35 | 2021-01-26 14:35 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89997 | WBS.2.1.9.2.20.1.4 | N | N | Planned | ITR_C0067 - Validate Load - Convert Scheduled Maintenance Plans (T-4 Days) - AS8 | 0.5 | 2021-01-26 18:15 | 2021-01-26 18:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 89994,5763 |  |  | * |  | 2021-01-26 18:15 | 2021-01-26 18:45 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89998 | WBS.2.1.9.2.20.1.6 | N | N | Planned | PTH - ITR_C0067 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data For Scheduled Maintenance Plans (T-4 Days) - AS8 | 2 | 2021-01-26 18:45 | 2021-01-26 20:45 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 89997 |  |  | * |  | 2021-01-26 18:45 | 2021-01-26 20:45 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5383 | WBS.2.1.9.2.21 | N | N |  | Ramp Down ¦ ITR_C0069 - Convert Classes | 9 | 2021-01-17 21:45 | 2021-01-18 12:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 12:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90200 | WBS.2.1.9.2.21.1 | N | N |  | Ramp Down ¦ ITR_C0069 - Convert Classes Tasks | 9 | 2021-01-17 21:45 | 2021-01-18 12:45 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 12:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3993 | WBS.2.1.9.2.21.1.1 | N | N | Planned | ITR_C0069 - Provide Sorted Load File For Convert Classes - AS8 and MP2 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;KELLY STRASSBURGER;BOB BROWN;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KELLY.STRASSBURGER@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | PTH,HBG,BG | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5384 | WBS.2.1.9.2.21.1.2 | N | N | Planned | ITR_C0069 - Execute Load program - Convert Classes - AS8 and MP2 | 1 | 2021-01-18 11:30 | 2021-01-18 12:30 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 5382 |  |  | * |  | 2021-01-18 11:30 | 2021-01-18 12:30 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5385 | WBS.2.1.9.2.21.1.3 | N | N | Planned | ITR_C0069 - Validate Load - Convert Classes -AS8 and MP2 | 0.25 | 2021-01-18 12:30 | 2021-01-18 12:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5384 |  |  | * |  | 2021-01-18 12:30 | 2021-01-18 12:45 | AC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5380 | WBS.2.1.9.2.22 | N | N |  | Ramp Down ¦ ITR_C0070 - Convert Characteristics | 7.75 | 2021-01-17 21:45 | 2021-01-18 11:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 11:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90196 | WBS.2.1.9.2.22.1 | N | N |  | Ramp Down ¦ ITR_C0070 - Convert Characteristics | 7.75 | 2021-01-17 21:45 | 2021-01-18 11:30 | [8 empty] | * |  | 2021-01-17 21:45 | 2021-01-18 11:30 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
3992 | WBS.2.1.9.2.22.1.1 | N | N | Planned | ITR_C0070 - Provide Load File For Convert Characteristics - AS8 and MP2 | 0.5 | 2021-01-17 21:45 | 2021-01-17 22:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;JASON RAMSEY;SAI TEAM;KELLY STRASSBURGER;BOB BROWN;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KELLY.STRASSBURGER@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 93067 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:15 | AC | PTH,HBG,BG | 2021-01-17 | 2021-01-17 | 1 | Ramp Down
5381 | WBS.2.1.9.2.22.1.2 | N | N | Planned | ITR_C0070 - Execute Load program - Convert Characteristics - AS8 and MP2 | 1 | 2021-01-18 10:00 | 2021-01-18 11:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 3992,4091 |  |  | * |  | 2021-01-18 10:00 | 2021-01-18 11:00 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5382 | WBS.2.1.9.2.22.1.3 | N | N | Planned | ITR_C0070 - Validate Load - Convert Characteristics - AS8 and MP2 | 0.5 | 2021-01-18 11:00 | 2021-01-18 11:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | KELLY STRASSBURGER;ERIC REINDL;HOWARD ZAHORIK;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;DEAN PIPER;LYNN MCMURDO | KELLY.STRASSBURGER@GAPAC.COM;ERIC.REINDL@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5381 |  |  | * |  | 2021-01-18 11:00 | 2021-01-18 11:30 | AC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5404 | WBS.2.1.9.2.23 | N | N |  | Ramp Down ¦ ITR_C0071 - Convert Documents (Document Management System) | 9.33 | 2021-01-18 19:00 | 2021-01-19 12:20 | [8 empty] | * |  | 2021-01-18 19:00 | 2021-01-19 12:20 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90204 | WBS.2.1.9.2.23.1 | N | N |  | Ramp Down ¦ ITR_C0071 - Convert Documents (Document Management System) Tasks | 9.33 | 2021-01-18 19:00 | 2021-01-19 12:20 | [8 empty] | * |  | 2021-01-18 19:00 | 2021-01-19 12:20 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5405 | WBS.2.1.9.2.23.1.1 | N | N | Planned | ITR_C0071 - Execute Transform program - Convert Documents | 2 | 2021-01-18 19:00 | 2021-01-18 21:00 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5393,3966,82569,90491,94411 |  |  | * |  | 2021-01-18 19:00 | 2021-01-18 21:00 | DATA | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5406 | WBS.2.1.9.2.23.1.2 | N | N | Planned | ITR_C0071 - Validate Preload Transform - Convert Documents | 0.5 | 2021-01-18 21:00 | 2021-01-18 21:30 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5405,8808 |  |  | * |  | 2021-01-18 21:00 | 2021-01-18 21:30 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5407 | WBS.2.1.9.2.23.1.3 | N | N | Planned | ITR_C0071 - Execute Load program - Convert Documents | 2 | 2021-01-18 21:30 | 2021-01-19 07:30 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5406 |  |  | * |  | 2021-01-18 21:30 | 2021-01-19 07:30 | DATA | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5408 | WBS.2.1.9.2.23.1.4 | N | N | Planned | ITR_C0071 - Validate Load - Convert Documents | 1 | 2021-01-19 11:00 | 2021-01-19 12:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5407,5441 |  |  | * |  | 2021-01-19 11:00 | 2021-01-19 12:00 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
81606 | WBS.2.1.9.2.23.1.5 | N | N | Planned | PTH - ITR_C0071 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Documents) | 0.33 | 2021-01-19 12:00 | 2021-01-19 12:20 | TOMMY WOMACK | tommy.womack@gapac.com | DARRELL WATSON;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Darrell.watson@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5408 |  |  | * |  | 2021-01-19 12:00 | 2021-01-19 12:20 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82909 | WBS.2.1.9.2.24 | N | N |  | Ramp Down ¦ ITR_C0175 - Convert Documents for Measuring Points | 10 | 2021-01-19 17:30 | 2021-01-20 11:30 | [8 empty] | * |  | 2021-01-19 17:30 | 2021-01-20 11:30 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
90214 | WBS.2.1.9.2.24.1 | N | N |  | Ramp Down ¦ ITR_C0175 - Convert Documents for Measuring Points | 10 | 2021-01-19 17:30 | 2021-01-20 11:30 | [8 empty] | * |  | 2021-01-19 17:30 | 2021-01-20 11:30 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82908 | WBS.2.1.9.2.24.1.1 | N | N | Planned | ITR_C0175 - Execute Transform program - Convert Documents for measuring points | 1 | 2021-01-19 17:30 | 2021-01-19 18:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5430 |  |  | * |  | 2021-01-19 17:30 | 2021-01-19 18:30 | DATA | PTH,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
82907 | WBS.2.1.9.2.24.1.2 | N | N | Planned | ITR_C0175 - Validate Preload Transform - Convert Documents for measuring points | 0.25 | 2021-01-20 07:45 | 2021-01-20 08:00 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 82908,5479 |  |  | * |  | 2021-01-20 07:45 | 2021-01-20 08:00 | AC | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82906 | WBS.2.1.9.2.24.1.3 | N | N | Planned | ITR_C0175 - Execute Load program - Convert Documents for measuring points | 1 | 2021-01-20 08:00 | 2021-01-20 09:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | JASPREET SINGH;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | JASPSINGH@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 82907 |  |  | * |  | 2021-01-20 08:00 | 2021-01-20 09:00 | DATA | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82905 | WBS.2.1.9.2.24.1.4 | N | N | Planned | ITR_C0175 - Validate Load - Convert Documents for measuring points | 0.75 | 2021-01-20 10:45 | 2021-01-20 11:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | KELLY STRASSBURGER;DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | KELLY.STRASSBURGER@GAPAC.COM;DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 82906,5481 |  |  | * |  | 2021-01-20 10:45 | 2021-01-20 11:30 | AC | PTH,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
5176 | WBS.2.1.9.2.25 | N | N |  | Ramp Down ¦ PTM_C0079 - Convert Work Center Objects from ECC to S/4HANA Platform | 130 | 2021-01-18 06:15 | 2021-01-28 08:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 08:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90192 | WBS.2.1.9.2.25.1 | N | N |  | Ramp Down ¦ PTM_C0079 - Convert Work Center Objects from ECC to S/4HANA Platform Tasks | 130 | 2021-01-18 06:15 | 2021-01-28 08:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 08:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
89611 | WBS.2.1.9.2.25.1.1 | N | N | Planned | PTM_C0079 - Prepare Work center upload file -SCM-MDM | 3.5 | 2021-01-18 06:15 | 2021-01-18 09:45 | ANGELA COMO | ANGELA.COMO2@GAPAC.COM | FALKO KOEHLER;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;CHANDRA BALASUBRAMANIAN;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | FKOEHLER@SCMO2.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;CBALASUBRAMANIAN@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:45 | SCM | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92229 | WBS.2.1.9.2.25.1.2 | N | N | Planned | PTM_C0079 - Enrich PTM_C0079 Workcenter Load File | 2 | 2021-01-18 09:45 | 2021-01-18 11:45 | TONY SMITH | AJSMITH@GAPAC.COM | JACOB DENNIS;RTR TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 89611 |  |  | * |  | 2021-01-18 09:45 | 2021-01-18 11:45 | RTR - PC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89610 | WBS.2.1.9.2.25.1.3 | N | N | Planned | PTM_C0079 - Validate Work Center Load & Update Metrices | 0.25 | 2021-01-18 11:45 | 2021-01-18 12:00 | ANGELA COMO | ANGELA.COMO2@GAPAC.COM | CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;JIM KIJEK;SCM TEAM;MELISSA OLSEN;KRISTIE DOIRON;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JEKIJEK@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;MELISSA.OLSEN@GAPAC.COM;KRISTIE.DOIRON@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92229 |  |  | * |  | 2021-01-18 11:45 | 2021-01-18 12:00 | SCM | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95362 | WBS.2.1.9.2.25.1.4 | N | N | Planned | PTM_C0079 - Validate, business sign off, and provide Work center upload file - Business requirement | 1 | 2021-01-18 12:00 | 2021-01-18 13:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | SAI TEAM;DATA ETL TEAM;JON PINYON;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JWPINYON@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89610 |  |  | * |  | 2021-01-18 12:00 | 2021-01-18 13:00 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10116 | WBS.2.1.9.2.25.1.5 | N | N | Planned | PTM_C0079 - Execute transformation for Work Center Conversion | 1 | 2021-01-18 12:00 | 2021-01-18 13:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89610,92229,92244,93067,91838,4667,94432,96559 |  |  | * |  | 2021-01-18 12:00 | 2021-01-18 13:00 | DATA | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89613 | WBS.2.1.9.2.25.1.6 | N | N | Planned | PTM_C0079 – Validate transformation for Work Center Conversion | 1.5 | 2021-01-18 13:00 | 2021-01-18 14:30 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 10116 |  |  | * |  | 2021-01-18 13:00 | 2021-01-18 14:30 | SCM | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10118 | WBS.2.1.9.2.25.1.7 | N | N | Planned | PTM_C0079 - Execute Smoke test load for Work Center Conversion | 1 | 2021-01-19 08:15 | 2021-01-19 09:15 | ANURAG ANAND | ANANAND@DELOITTE.COM | DEEPA SAW;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | DEESAW@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89613,7913 |  |  | * |  | 2021-01-19 08:15 | 2021-01-19 09:15 | DATA | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
89612 | WBS.2.1.9.2.25.1.8 | N | N | Planned | PTM_C0079 – Validate Smoke test load for Work Center Conversion | 1 | 2021-01-19 09:15 | 2021-01-19 10:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 10118 |  |  | * |  | 2021-01-19 09:15 | 2021-01-19 10:15 | SCM | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5177 | WBS.2.1.9.2.25.1.9 | N | N | Planned | PTM_C0079 - Execute Load program - PPDS Convert Work Centers | 2 | 2021-01-19 10:15 | 2021-01-19 12:15 | ANURAG ANAND | ANANAND@DELOITTE.COM | MADAN ZOLLU;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | MZOLLU@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89612,36996,4667,94432,96559 |  |  | * |  | 2021-01-19 10:15 | 2021-01-19 12:15 | DATA | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
89619 | WBS.2.1.9.2.25.1.10 | N | N | Planned | PTM_C0079 -Technical Validation of Work Center Data Load - PPDS | 2 | 2021-01-19 12:15 | 2021-01-19 14:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SAI TEAM;CHIRAG PARIKH;JENNIFER LI;SCM TEAM;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5177 |  |  | * |  | 2021-01-19 12:15 | 2021-01-19 14:15 | SCM | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95590 | WBS.2.1.9.2.25.1.11 | N | N | Planned | Run IL02 for AA workcenter , main WC , manufacturer , model, mfg serial no. and cost center update | 6 | 2021-01-19 14:15 | 2021-01-19 20:15 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | ERIC REINDL;TAJINDER KOHLI;SAI TEAM | ERIC.REINDL@GAPAC.COM;TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 20:15 | AC | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10120 | WBS.2.1.9.2.25.1.12 | N | N | Planned | PTM_C0079 - Execute load for Work Center Hierarchy | 2 | 2021-01-19 14:15 | 2021-01-19 16:15 | ANURAG ANAND | ANANAND@DELOITTE.COM | MADAN ZOLLU;DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | MZOLLU@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 16:15 | DATA | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95512 | WBS.2.1.9.2.25.1.13 | N | N | Planned | Validate & update Supply area on Active work centers | 1.5 | 2021-01-19 14:15 | 2021-01-19 15:45 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 15:45 | SCM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95511 | WBS.2.1.9.2.25.1.14 | N | N | Planned | Update PPDS job variants & steps | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36501,10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 08:15 | SCM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95502 | WBS.2.1.9.2.26 | N | N |  | Ramp Down ¦ PTM_C0094 Convert Setup groups / Setup Matrix | 11.5 | 2021-01-19 14:15 | 2021-01-20 09:45 | [8 empty] | * |  | 2021-01-19 14:15 | 2021-01-20 09:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95501 | WBS.2.1.9.2.26.1 | N | N |  | Ramp Down ¦ PTM_C0094 Convert Setup groups / Setup Matrix | 11.5 | 2021-01-19 14:15 | 2021-01-20 09:45 | [8 empty] | * |  | 2021-01-19 14:15 | 2021-01-20 09:45 |  |  | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95510 | WBS.2.1.9.2.26.1.1 | N | N | Planned | Validate, business sign off, provide file for Setup Matrix upload file- SCM MDM PTM_C0094 | 0.25 | 2021-01-19 14:15 | 2021-01-19 14:30 | ANGELA COMO | ANGELA.COMO2@GAPAC.COM | CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;JIM KIJEK;SCM TEAM;MELISSA OLSEN;KRISTIE DOIRON;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JEKIJEK@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;MELISSA.OLSEN@GAPAC.COM;KRISTIE.DOIRON@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 14:30 | SCM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95509 | WBS.2.1.9.2.26.1.2 | N | N | Planned | Create & Activate Integration Model for Setup group- PPDS | 1.5 | 2021-01-19 14:15 | 2021-01-19 15:45 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 89619 |  |  | * |  | 2021-01-19 14:15 | 2021-01-19 15:45 | SCM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96762 | WBS.2.1.9.2.26.1.9 | N | N | Planned | Create production calendar based on shifts for D4 sites and assign to D4 locations (MFLE). | 0.5 | 2021-01-19 15:45 | 2021-01-19 16:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95509 |  |  | * |  | 2021-01-19 15:45 | 2021-01-19 16:15 | SCM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95508 | WBS.2.1.9.2.26.1.3 | N | N | Planned | Execute Transform program - PTM_C0094 Convert Setup groups / Setup Matrix | 4 | 2021-01-19 15:45 | 2021-01-19 19:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 95509,95510 |  |  | * |  | 2021-01-19 15:45 | 2021-01-19 19:45 | DATA | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95507 | WBS.2.1.9.2.26.1.4 | N | N | Planned | Validate Preload Transform - PTM_C0094 Convert Setup groups / Setup matrix | 1 | 2021-01-19 19:45 | 2021-01-19 20:45 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95508 |  |  | * |  | 2021-01-19 19:45 | 2021-01-19 20:45 | SCM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95506 | WBS.2.1.9.2.26.1.5 | N | N | Planned | Execute Load program - PTM_C0094 Convert Setup groups / Setup Matrix | 1 | 2021-01-19 20:45 | 2021-01-19 21:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 95507 |  |  | * |  | 2021-01-19 20:45 | 2021-01-19 21:45 | DATA | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95505 | WBS.2.1.9.2.26.1.6 | N | N | Planned | Technical validation of PTM_C0094 Setup Matrix data load - PPDS | 1 | 2021-01-19 21:45 | 2021-01-20 06:45 | ANGELA COMO | ANGELA.COMO2@GAPAC.COM | CHIRAG PARIKH;SAI TEAM;CHANDRA BALASUBRAMANIAN;FALKO KOEHLER;JIM KIJEK;SCM TEAM;MELISSA OLSEN;KRISTIE DOIRON;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;FKOEHLER@SCMO2.COM;JEKIJEK@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;MELISSA.OLSEN@GAPAC.COM;KRISTIE.DOIRON@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95506 |  |  | * |  | 2021-01-19 21:45 | 2021-01-20 06:45 | SCM | ALL | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95504 | WBS.2.1.9.2.26.1.7 | N | N | Planned | Business Sign-Off Load - PTM_C0094 Convert Setup groups / Setup Matrix | 0.25 | 2021-01-20 06:45 | 2021-01-20 07:00 | LINDSAY SAVAGE | LINDSAY.SAVAGE@GAPAC.COM | JON PINYON;SAI TEAM | JWPINYON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 95505 |  |  | * |  | 2021-01-20 06:45 | 2021-01-20 07:00 | DATA | ALL | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
95503 | WBS.2.1.9.2.26.1.8 | N | N | Planned | Assign set up matrix to Resource - PPDS | 3 | 2021-01-20 06:45 | 2021-01-20 09:45 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;SCM TEAM;KIM VANWYCHEN;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KIM.VANWYCHEN@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95505 |  |  | * |  | 2021-01-20 06:45 | 2021-01-20 09:45 | SCM | ALL | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
9812 | WBS.2.1.9.2.27 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Production Versions Required For Repetitive Manufacturing | 65.25 | 2021-01-18 06:15 | 2021-01-22 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-22 07:30 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90211 | WBS.2.1.9.2.27.1 | N | N |  | Ramp Down ¦ PTM_C0085 - Convert Production Versions Required For Repetitive Manufacturing Tasks | 65.25 | 2021-01-18 06:15 | 2021-01-22 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-22 07:30 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
7888 | WBS.2.1.9.2.27.1.1 | N | N | Planned | PTM_C0085 - Prepare Load File for Activity Rates (costing/legal) for Product Costing plants 1503, 1101, 1462, 1357 | 1.5 | 2021-01-18 06:15 | 2021-01-18 07:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:45 | RTR - PC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9809 | WBS.2.1.9.2.27.1.2 | N | N | Planned | PTM_C0085 - Prepare Production Version Upload For Repetitive Manufacturing | 0.25 | 2021-01-20 17:00 | 2021-01-20 17:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | TONY SMITH;NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9807,9801 |  |  | * |  | 2021-01-20 17:00 | 2021-01-20 17:15 | RTR - PC | PTH,HBG,BG | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
10114 | WBS.2.1.9.2.27.1.3 | N | N | Planned | PTM_C0085 - Execute Preload Transform - Convert Production Versions for Repetitive Manufacturing | 2 | 2021-01-21 12:30 | 2021-01-21 14:30 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | SAI TEAM;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 9809,9807,9802 |  |  | * |  | 2021-01-21 12:30 | 2021-01-21 14:30 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
10115 | WBS.2.1.9.2.27.1.4 | N | N | Planned | PTM_C0085 - Validate Preload Transform - Convert Production Versions for Repetitive Manufacturing | 0.25 | 2021-01-21 14:30 | 2021-01-21 14:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 10114 |  |  | * |  | 2021-01-21 14:30 | 2021-01-21 14:45 | RTR - PC | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
9810 | WBS.2.1.9.2.27.1.5 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Production Versions for Repetitive Manufacturing | 2 | 2021-01-21 14:45 | 2021-01-21 16:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | SAI TEAM;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10115 |  |  | * |  | 2021-01-21 14:45 | 2021-01-21 16:45 | DATA | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
9811 | WBS.2.1.9.2.27.1.6 | N | N | Planned | PTM_C0085 - Validate Load - Convert Production Versions for Repetitive Manufacturing | 1 | 2021-01-21 16:45 | 2021-01-21 17:45 | TONY SMITH | AJSMITH@GAPAC.COM | VISHNU CHIRALA;DATA ETL TEAM;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;NOEL CLARK;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;DEAN PIPER;LYNN MCMURDO;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9810 |  |  | * |  | 2021-01-21 16:45 | 2021-01-21 17:45 | RTR - PC | PTH,HBG,BG | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8929 | WBS.2.1.9.2.27.1.7 | N | N | Planned | RTR_E0200 - Prepare mapping file from work center to responsible cost center | 1 | 2021-01-21 17:45 | 2021-01-21 18:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9811 |  |  | * |  | 2021-01-21 17:45 | 2021-01-21 18:45 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8930 | WBS.2.1.9.2.27.1.8 | N | N | Planned | RTR_E0200 - Manual update of responsible cost center using transaction code ZTRTR_E0200_KOST | 0.5 | 2021-01-21 18:45 | 2021-01-21 19:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8929 |  |  | * |  | 2021-01-21 18:45 | 2021-01-21 19:15 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8932 | WBS.2.1.9.2.27.1.9 | N | N | Planned | RTR_E0200 - Validation of table entries in ZTRTR_E0200_KOST and sign off | 1 | 2021-01-21 19:15 | 2021-01-21 20:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;NOEL CLARK;VISHNU CHIRALA;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8930 |  |  | * |  | 2021-01-21 19:15 | 2021-01-21 20:15 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8933 | WBS.2.1.9.2.27.1.10 | N | N | Planned | RTR_E0201_Prepare mapping file for plant, profit center and receiver cost center | 1 | 2021-01-21 20:15 | 2021-01-21 21:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;NOEL CLARK;VISHNU CHIRALA;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8932 |  |  | * |  | 2021-01-21 20:15 | 2021-01-21 21:15 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8934 | WBS.2.1.9.2.27.1.11 | N | N | Planned | RTR_E0201_Manual update of receiver cost center using transaction code ZMAP_PC_CC | 0.25 | 2021-01-21 21:15 | 2021-01-21 21:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8933 |  |  | * |  | 2021-01-21 21:15 | 2021-01-21 21:30 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
8936 | WBS.2.1.9.2.27.1.13 | N | N | Planned | RTR_E0201_Validation of table entries by using transaction code ZMAP_PC_CC and sign off | 1 | 2021-01-21 21:30 | 2021-01-22 06:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;NOEL CLARK;VISHNU CHIRALA;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8934 |  |  | * |  | 2021-01-21 21:30 | 2021-01-22 06:30 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
81844 | WBS.2.1.9.2.27.1.14 | N | N | Planned | Validate Profit centers added for substitution in BRF+ in ZBRF_RTR_OKC9_SUBST application name | 0.5 | 2021-01-22 06:30 | 2021-01-22 07:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8936 |  |  | * |  | 2021-01-22 06:30 | 2021-01-22 07:00 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
81843 | WBS.2.1.9.2.27.1.15 | N | N | Planned | Validate sets to be maintained for OKC9 - FA substitution | 0.5 | 2021-01-22 07:00 | 2021-01-22 07:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 81844 |  |  | * |  | 2021-01-22 07:00 | 2021-01-22 07:30 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
91803 | WBS.2.1.9.2.27.1.16 | N | N | Planned | RTR_E0200 - Update - BRF+ (TTN/DIXIE/Other) for Plants 1034, 1376, 1459 | 1 | 2021-01-21 20:15 | 2021-01-21 21:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8932 |  |  | * |  | 2021-01-21 20:15 | 2021-01-21 21:15 | RTR - PC | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
91802 | WBS.2.1.9.2.27.1.17 | N | N | Planned | RTR_E0200 - Validate - BRF+ Entries for Plants 1503, 1101, 1462, 1357 | 1 | 2021-01-21 21:15 | 2021-01-22 06:15 | TONY SMITH | AJSMITH@GAPAC.COM | SANDRA RICHARDS;SAI TEAM;DONNA SMITH;NOEL CLARK;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 91803 |  |  | * |  | 2021-01-21 21:15 | 2021-01-22 06:15 | RTR - PC | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
91353 | WBS.2.1.9.2.28 | N | N |  | Ramp Down ¦ PTM_C0203 - Convert Warehouse/ Storage Bin Structure | 87.75 | 2021-01-18 06:15 | 2021-01-25 14:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 14:00 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91357 | WBS.2.1.9.2.28.1 | N | N |  | Ramp Down ¦ PTM_C0203 - Convert Warehouse/ Storage Bin Structure - All Sites | 87.75 | 2021-01-18 06:15 | 2021-01-25 14:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 14:00 |  | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94257 | WBS.2.1.9.2.28.1.1 | N | N | Planned | SCH - PTM_C0203 - Extract and Prepare Storage Bin upload file | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | RASHI KUCHYA | rkuchya@deloitte.com | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96705 | WBS.2.1.9.2.28.1.24 | N | N | Planned | RNC - PTM_C0203 - Extract and Prepare Storage Bin upload file | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | Shefali Kushwaha | shefkushwaha@deloitte.com | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96706 | WBS.2.1.9.2.28.1.25 | N | N | Planned | RVG - PTM_C0203 - Extract and Prepare Storage Bin upload file | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
9990 | WBS.2.1.9.2.28.1.2 | N | N | Planned | PTH - PTM_C0203 - Extract and Prepare Storage Bin upload file | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96573 | WBS.2.1.9.2.28.1.20 | N | N | Planned | BG - PTM_C0203 - Extract and Prepare Storage Bin upload file | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;DEAN PIPER;LYNN MCMURDO | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94258 | WBS.2.1.9.2.28.1.5 | N | N | Planned | HBG - PTM_C0203 - Extract and Prepare Storage Bin upload file | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | AJIT GOLE | ajgole@deloitte.com | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;CHRIS ZUMWALT | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94270 | WBS.2.1.9.2.28.1.6 | N | N | Planned | PTH - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 9990 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96574 | WBS.2.1.9.2.28.1.21 | N | N | Planned | BG - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96573 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94267 | WBS.2.1.9.2.28.1.8 | N | N | Planned | HBG - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94258 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97492 | WBS.2.1.9.2.28.1.110 | N | N | Planned | Provide Min/Max for HBG Bin replenishment from DC to Mill | 2 | 2021-01-18 10:15 | 2021-01-18 12:15 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94267 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 12:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97493 | WBS.2.1.9.2.28.1.111 | N | N | Planned | Update Min/Max for HBG Bin replenishment from DC to Mill | 2 | 2021-01-25 12:00 | 2021-01-25 14:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97492,94320 |  |  | * |  | 2021-01-25 12:00 | 2021-01-25 14:00 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94543 | WBS.2.1.9.2.28.1.10 | N | N | Planned | SCH - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | GIOVANY CARVAJAL;JEREMY RAY;ESSEX B;ANDY KEOYOTHY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;EWM TEAM | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94257 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96707 | WBS.2.1.9.2.28.1.26 | N | N | Planned | RNC - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;LOCKLIN HINTON;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;LOCKLIN.HINTON@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 96705 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96708 | WBS.2.1.9.2.28.1.27 | N | N | Planned | RVG - PTM_C0203 - Validate and business sign off for Storage Bin upload file | 1 | 2021-01-18 10:15 | 2021-01-18 11:15 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | JENNIFER MCLEOD;SAI TEAM;EWM TEAM | JENNIFER.MCLEOD@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96706 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 11:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94441 | WBS.2.1.9.2.28.1.11 | N | N | Planned | PTH - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 3 | 2021-01-19 15:45 | 2021-01-19 18:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 97215 |  |  | * |  | 2021-01-19 20:45 | 2021-01-20 07:45 | EWM | PTH | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
94274 | WBS.2.1.9.2.28.1.13 | N | N | Planned | HBG - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 3 | 2021-01-18 16:45 | 2021-01-18 19:45 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97219 |  |  | * |  | 2021-01-18 16:45 | 2021-01-18 19:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92977 | WBS.2.1.9.2.28.1.14 | N | N | Planned | SCH - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 0.5 | 2021-01-18 17:45 | 2021-01-18 18:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 97223 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96709 | WBS.2.1.9.2.28.1.28 | N | N | Planned | RNC - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 0.5 | 2021-01-18 19:45 | 2021-01-18 20:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;DAVID ALENCASTRO;EWM TEAM | JEREMY.RAY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97224 |  |  | * |  | 2021-01-18 19:45 | 2021-01-18 20:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96710 | WBS.2.1.9.2.28.1.29 | N | N | Planned | RVG - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 0.5 | 2021-01-18 17:45 | 2021-01-18 18:15 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36888 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96575 | WBS.2.1.9.2.28.1.22 | N | N | Planned | BG - PTM_C0203 - Validate Storage Bins Loaded Properly - EWM | 2 | 2021-01-18 16:45 | 2021-01-18 18:45 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97221 |  |  | * |  | 2021-01-18 16:45 | 2021-01-18 18:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95712 | WBS.2.1.9.2.28.1.17 | N | N | Planned | HBG-Maintain EWM Work Center storage bins and packaging material for SFG (transaction /SCWM/TWORKST) | 1 | 2021-01-18 19:45 | 2021-01-18 20:47 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94274 |  |  | * |  | 2021-01-18 19:45 | 2021-01-18 20:47 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95713 | WBS.2.1.9.2.28.1.18 | N | N | Planned | PTH-Maintain EWM Work Center storage bins and packaging material for SFG (transaction /SCWM/TWORKST) | 1 | 2021-01-19 18:45 | 2021-01-19 19:45 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94441 |  |  | * |  | 2021-01-20 07:45 | 2021-01-20 08:45 | EWM | PTH | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
96578 | WBS.2.1.9.2.28.1.23 | N | N | Planned | BG-Maintain EWM Work Center storage bins and packaging material for SFG (transaction /SCWM/TWORKST) | 1 | 2021-01-18 18:45 | 2021-01-18 19:45 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96575 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97209 | WBS.2.1.9.2.28.1.104 | N | N | Planned | PTH - PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 13:15 | 2021-01-18 15:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97200 |  |  | * |  | 2021-01-18 13:15 | 2021-01-18 15:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97211 | WBS.2.1.9.2.28.1.106 | N | N | Planned | BG - PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 13:15 | 2021-01-18 15:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 95374 |  |  | * |  | 2021-01-18 13:15 | 2021-01-18 15:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97212 | WBS.2.1.9.2.28.1.107 | N | N | Planned | HBG - PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 13:15 | 2021-01-18 15:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 95373 |  |  | * |  | 2021-01-18 13:15 | 2021-01-18 15:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97213 | WBS.2.1.9.2.28.1.108 | N | N | Planned | SCH - PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 14:15 | 2021-01-18 16:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 95375 |  |  | * |  | 2021-01-18 14:15 | 2021-01-18 16:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97214 | WBS.2.1.9.2.28.1.109 | N | N | Planned | RVG - PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 14:15 | 2021-01-18 16:15 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 9875 |  |  | * |  | 2021-01-18 14:15 | 2021-01-18 16:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91360 | WBS.2.1.9.2.28.2 | N | N |  | Ramp Down ¦ PTM_C0203 - Convert Warehouse/ Storage Bin Structure - MRO | 10.5 | 2021-01-18 19:45 | 2021-01-19 14:15 | [8 empty] | * |  | 2021-01-18 19:45 | 2021-01-19 19:18 |  |  | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
9991 | WBS.2.1.9.2.28.2.1 | N | N | Planned | PTH - PTM_C0203 - Extract and Prepare Storage Bin upload file (MRO) | 3 | 2021-01-18 19:45 | 2021-01-19 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | Wesley Dean;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI | wdean@deloitte.com;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM | EWM | 36501,97353 |  |  | * |  | 2021-01-18 19:45 | 2021-01-19 06:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94262 | WBS.2.1.9.2.28.2.3 | N | N | Planned | HBG - PTM_C0203 - Extract and Prepare Storage Bin upload file (MRO) | 3 | 2021-01-18 19:45 | 2021-01-19 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;Wesley Dean | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;wdean@deloitte.com | EWM | 36501,97354 |  |  | * |  | 2021-01-18 19:45 | 2021-01-19 06:45 | EWM | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96576 | WBS.2.1.9.2.28.2.13 | N | N | Planned | BG - PTM_C0203 - Extract and Prepare Storage Bin upload file (MRO) | 3 | 2021-01-18 19:45 | 2021-01-19 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI;Wesley Dean | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;wdean@deloitte.com | EWM | 36501,97354 |  |  | * |  | 2021-01-18 19:45 | 2021-01-19 06:45 | EWM | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
68514 | WBS.2.1.9.2.28.2.5 | N | N | Planned | PTH - PTM_C0203 - MRO - Identify, validate and business sign-off - Stock and Non-Stock Storage bins | 5 | 2021-01-19 06:45 | 2021-01-19 11:45 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 9991 |  |  | * |  | 2021-01-19 06:45 | 2021-01-19 11:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94272 | WBS.2.1.9.2.28.2.7 | N | N | Planned | HBG - PTM_C0203 - MRO - Identify, validate and business sign-off - Stock and Non-Stock Storage bins | 5 | 2021-01-19 06:45 | 2021-01-19 11:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94262 |  |  | * |  | 2021-01-19 06:45 | 2021-01-19 11:45 | EWM | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5219 | WBS.2.1.9.2.28.2.9 | N | N | Planned | PTH - PTM_C0203 - MRO - Validate Storage Bins Loaded Properly - EWM | 1 | 2021-01-19 13:15 | 2021-01-19 14:15 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 97216 |  |  | * |  | 2021-01-19 18:15 | 2021-01-19 19:15 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96577 | WBS.2.1.9.2.28.2.14 | N | N | Planned | BG - PTM_C0203 - MRO - Validate Storage Bins Loaded Properly - EWM | 1 | 2021-01-19 13:15 | 2021-01-19 14:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | ARNAB DEY;SAI TEAM;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;MIKE LACEY;EWM TEAM;MARY BERMAN;DEAN PIPER;LYNN MCMURDO;DOUG CARANGELLO;Mark Bernard | ADEY@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;MICHAEL.LACEY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MARY.BERMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 97222 |  |  | * |  | 2021-01-19 18:18 | 2021-01-19 19:18 | EWM | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94277 | WBS.2.1.9.2.28.2.12 | N | N | Planned | HBG - PTM_C0203 - MRO - Validate Storage Bins Loaded Properly - EWM | 1 | 2021-01-19 13:15 | 2021-01-19 14:15 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97220 |  |  | * |  | 2021-01-19 18:15 | 2021-01-19 19:15 | EWM | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5217 | WBS.2.1.9.2.29 | N | N |  | Ramp Down ¦ PTM_C0203 - Convert Warehouse/ Storage Bin Structure | 31.25 | 2021-01-18 06:30 | 2021-01-19 21:45 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-20 10:45 |  |  | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
90198 | WBS.2.1.9.2.29.1 | N | N |  | Ramp Down ¦ PTM_C0203 - Convert Warehouse/ Storage Bin Structure - Manual Conversion | 31.25 | 2021-01-18 06:30 | 2021-01-19 21:45 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-20 10:45 |  |  | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
4576 | WBS.2.1.9.2.29.1.1 | N | N | Planned | Manual Config Steps (Maintain Staging Areas and Door Determination for Outbound and Inbound) - EWM | 1 | 2021-01-18 17:45 | 2021-01-18 18:45 | Uday Athwal | uathwal@deloitte.com | DEEPIKA ARRABOLU;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;EWM TEAM | DREDDYARRABOLU@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501,36888,4100 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:45 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4574 | WBS.2.1.9.2.29.1.2 | N | N | Planned | Manual Config Steps (Maintain Start/End Storage Bins for Activity Area) - EWM | 1 | 2021-01-19 18:45 | 2021-01-19 19:45 | NIKHIL NEGI | nikhnegi@deloitte.com | SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501,36888,4100,94441,94274,92977,5219,94277,96575,96709,96710 |  |  | * |  | 2021-01-20 07:45 | 2021-01-20 08:45 | EWM | CROSS | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
10050 | WBS.2.1.9.2.29.1.4 | N | N | Planned | PTM_C0203 - Manual Interim Bin Upload (GI-ZONE, PACKBIN, GR-ZONE, GR_REVERSAL etc for Mills & DC's) | 0.5 | 2021-01-19 19:45 | 2021-01-19 20:15 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4574,4573,4100 |  |  | * |  | 2021-01-20 08:45 | 2021-01-20 09:15 | EWM | CROSS | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
9875 | WBS.2.1.9.2.29.1.5 | N | N | Planned | RVG - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 11:15 | 2021-01-18 14:15 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 4100,96708 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 14:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5218 | WBS.2.1.9.2.29.1.6 | N | N | Planned | PTM_C0203 - Manual conversion of Warehouse bins | 2 | 2021-01-18 16:15 | 2021-01-18 18:15 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97213 |  |  | * |  | 2021-01-18 16:15 | 2021-01-18 18:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
81126 | WBS.2.1.9.2.29.1.7 | N | N | Planned | Create Storage Bins for MRO Storage Types OSDD, SRC1, SRQ1, SRT1, SRD1, SRS1 in respective warehouses | 1 | 2021-01-18 18:15 | 2021-01-18 19:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5218 |  |  | * |  | 2021-01-18 18:15 | 2021-01-18 19:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97215 | WBS.2.1.9.2.29.1.36 | N | N | Planned | PTH - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-19 14:15 | 2021-01-19 15:45 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5219 |  |  | * |  | 2021-01-19 19:15 | 2021-01-19 20:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97216 | WBS.2.1.9.2.29.1.37 | N | N | Planned | PTH - PTM_C0203 - Prepare Bin Validation file - MRO | 1.5 | 2021-01-19 11:45 | 2021-01-19 13:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4100,68514 |  |  | * |  | 2021-01-19 16:45 | 2021-01-19 18:15 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97219 | WBS.2.1.9.2.29.1.40 | N | N | Planned | HBG - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-18 15:15 | 2021-01-18 16:45 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 97212 |  |  | * |  | 2021-01-18 15:15 | 2021-01-18 16:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97220 | WBS.2.1.9.2.29.1.41 | N | N | Planned | HBG - PTM_C0203 - Prepare Bin Validation file - MRO | 1.5 | 2021-01-19 11:45 | 2021-01-19 13:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 4100,94272 |  |  | * |  | 2021-01-19 16:45 | 2021-01-19 18:15 | EWM | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97221 | WBS.2.1.9.2.29.1.42 | N | N | Planned | BG - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-18 15:15 | 2021-01-18 16:45 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 97211 |  |  | * |  | 2021-01-18 15:15 | 2021-01-18 16:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97222 | WBS.2.1.9.2.29.1.43 | N | N | Planned | BG - PTM_C0203 - Prepare Bin Validation file - MRO | 1.5 | 2021-01-19 11:45 | 2021-01-19 13:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 4100,97191 |  |  | * |  | 2021-01-19 16:48 | 2021-01-19 18:18 | EWM | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97223 | WBS.2.1.9.2.29.1.44 | N | N | Planned | SCH - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-18 16:15 | 2021-01-18 17:45 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 97213 |  |  | * |  | 2021-01-18 16:15 | 2021-01-18 17:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97224 | WBS.2.1.9.2.29.1.45 | N | N | Planned | RNC - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-18 18:15 | 2021-01-18 19:45 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 5218 |  |  | * |  | 2021-01-18 18:15 | 2021-01-18 19:45 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36888 | WBS.2.1.9.2.29.1.8 | N | N | Planned | RVG - PTM_C0203 - Prepare Bin Validation file | 1.5 | 2021-01-18 16:15 | 2021-01-18 17:45 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97214 |  |  | * |  | 2021-01-18 16:15 | 2021-01-18 17:45 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95360 | WBS.2.1.9.2.29.1.9 | N | N | Planned | Set Up Goods Movement Bin GI_PACK | 0.5 | 2021-01-18 17:45 | 2021-01-18 18:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36888 |  |  | * |  | 2021-01-18 17:45 | 2021-01-18 18:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94851 | WBS.2.1.9.2.29.1.10 | N | N | Planned | Validate that storage bins in staging areas are created with storage section 0001 | 1 | 2021-01-19 15:45 | 2021-01-19 16:45 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36888,97215,97216,97219,97220,97221,97222,97223,97224 |  |  | * |  | 2021-01-19 20:45 | 2021-01-19 21:45 | EWM | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
5221 | WBS.2.1.9.2.29.1.12 | N | N | Planned | PTH - Manual Conversion of PSA (Prod Supply Area) settings (no load is dependent on this) | 2 | 2021-01-19 18:45 | 2021-01-19 20:45 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 8878,94441 |  |  | * |  | 2021-01-20 07:45 | 2021-01-20 09:45 | EWM | PTH | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
94445 | WBS.2.1.9.2.29.1.14 | N | N | Planned | HBG - Manual Conversion of PSA (Prod Supply Area) settings (no load is dependent on this) | 2 | 2021-01-18 18:45 | 2021-01-18 20:45 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94435,96575 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 20:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96579 | WBS.2.1.9.2.29.1.27 | N | N | Planned | BG - Manual Conversion of PSA (Prod Supply Area) settings (no load is dependent on this) | 2 | 2021-01-18 09:15 | 2021-01-18 11:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96560 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 11:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5222 | WBS.2.1.9.2.29.1.16 | N | N | Planned | PTH - Validate PSA Bins - EWM | 1 | 2021-01-19 20:45 | 2021-01-19 21:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 5221 |  |  | * |  | 2021-01-20 09:45 | 2021-01-20 10:45 | EWM | PTH | 2021-01-19 | 2021-01-20 | 1 | Ramp Down
94447 | WBS.2.1.9.2.29.1.18 | N | N | Planned | HBG - Validate PSA Bins - EWM | 1 | 2021-01-18 20:45 | 2021-01-18 21:45 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | BOBBY WHITE;SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | Bobby.White@gapac.com;VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94445 |  |  | * |  | 2021-01-18 20:45 | 2021-01-18 21:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95373 | WBS.2.1.9.2.29.1.20 | N | N | Planned | HBG - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 10:15 | 2021-01-18 13:15 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 4100,94267 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 13:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97200 | WBS.2.1.9.2.29.1.34 | N | N | Planned | PTH - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 10:15 | 2021-01-18 13:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4100,94270 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 13:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97201 | WBS.2.1.9.2.29.1.35 | N | N | Planned | RNC - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 11:15 | 2021-01-18 14:15 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 4100,96707 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 14:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95374 | WBS.2.1.9.2.29.1.21 | N | N | Planned | BG - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 10:15 | 2021-01-18 13:15 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 4100,96574 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 13:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95375 | WBS.2.1.9.2.29.1.22 | N | N | Planned | SCH - PTM_C0203 - Validate Storage bin file with EWM Configuration | 3 | 2021-01-18 11:15 | 2021-01-18 14:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 4100,94543 |  |  | * |  | 2021-01-18 11:15 | 2021-01-18 14:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97188 | WBS.2.1.9.2.29.1.28 | N | N | Planned | RNC - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | Shefali Kushwaha | shefkushwaha@deloitte.com | SAI TEAM;SANTOSH KUPPILI;AVINASH TALREJA;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96697 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97189 | WBS.2.1.9.2.29.1.29 | N | N | Planned | RVG - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 96698 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95378 | WBS.2.1.9.2.29.1.24 | N | N | Planned | HBG - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 95539,95534 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95379 | WBS.2.1.9.2.29.1.25 | N | N | Planned | BG - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;DEAN PIPER;LYNN MCMURDO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96561,96562 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95381 | WBS.2.1.9.2.29.1.26 | N | N | Planned | SCH - Condition Records For PPF (WO and Delivery) | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 95538,96697,96698 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89986 | WBS.2.1.9.2.30 | N | N |  | Ramp Down ¦ PTM_C0245 - TAPPI ID Conversion | 6.5 | 2021-01-18 06:15 | 2021-01-18 12:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 12:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90186 | WBS.2.1.9.2.30.1 | N | N |  | Ramp Down ¦ PTM_C0245 - TAPPI ID Conversion Tasks | 6.5 | 2021-01-18 06:15 | 2021-01-18 12:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 12:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89985 | WBS.2.1.9.2.30.1.1 | N | N | Planned | PTM_C0245 - Provide Load File for TAPPI ID conversion (IM Sites with PR Inventory) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | NIKHIL NEGI | nikhnegi@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89984 | WBS.2.1.9.2.30.1.2 | N | N | Planned | PTM_C0245 - Execute Preload - TAPPI ID conversion | 2 | 2021-01-18 07:15 | 2021-01-18 09:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 89985 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 09:15 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89983 | WBS.2.1.9.2.30.1.3 | N | N | Planned | PTM_C0245 - Validate Preload - TAPPI ID conversion (IM Sites wit Parent Roll Inventory) | 0.25 | 2021-01-18 09:15 | 2021-01-18 09:30 | Vinay Tawani | vtawani@deloitte.com | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM | EWM | 89984 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 09:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89982 | WBS.2.1.9.2.30.1.4 | N | N | Planned | PTM_C0245 - Execute Load program - TAPPI ID conversion | 3 | 2021-01-18 09:30 | 2021-01-18 12:30 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 89983 |  |  | * |  | 2021-01-18 09:30 | 2021-01-18 12:30 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
89981 | WBS.2.1.9.2.30.1.5 | N | N | Planned | PTM_C0245 - Validate Load - TAPPI ID conversion (IM Sites wit Parent Roll Inventory) | 0.25 | 2021-01-18 12:30 | 2021-01-18 12:45 | Vinay Tawani | vtawani@deloitte.com | ARNAB DEY;DON ABBOTT;DOUG STANISLAWSKI;SAI TEAM;EWM TEAM | ADEY@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 89982 |  |  | * |  | 2021-01-18 12:30 | 2021-01-18 12:45 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94361 | WBS.2.1.9.2.31 | N | N |  | Ramp Down ¦ ITR_C0067.1 - Convert Scheduled Maintenance Plans | 6.75 | 2021-01-26 09:45 | 2021-01-26 16:30 | [8 empty] | * |  | 2021-01-26 09:45 | 2021-01-26 16:30 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94360 | WBS.2.1.9.2.31.1 | N | N |  | Ramp Down ¦ ITR_C0067.1 - Convert Scheduled Maintenance Plans | 6.75 | 2021-01-26 09:45 | 2021-01-26 16:30 | [8 empty] | * |  | 2021-01-26 09:45 | 2021-01-26 16:30 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94357 | WBS.2.1.9.2.31.1.1 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2021-01-26 09:45 | 2021-01-26 10:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94359,94400,92877 |  |  | * |  | 2021-01-26 09:45 | 2021-01-26 10:45 | DATA | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94356 | WBS.2.1.9.2.31.1.2 | N | N | Planned | Validate Preload ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 2 | 2021-01-26 10:45 | 2021-01-26 12:45 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 94357 |  |  | * |  | 2021-01-26 10:45 | 2021-01-26 12:45 | AC | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94355 | WBS.2.1.9.2.31.1.3 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 1 | 2021-01-26 12:45 | 2021-01-26 13:45 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94356 |  |  | * |  | 2021-01-26 12:45 | 2021-01-26 13:45 | DATA | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94354 | WBS.2.1.9.2.31.1.4 | N | N | Planned | Validate Load ITR_C0067.1 Convert Scheduled Maintenance Plans (T-4 Days) - MP2 | 0.75 | 2021-01-26 13:45 | 2021-01-26 14:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 94355 |  |  | * |  | 2021-01-26 13:45 | 2021-01-26 14:30 | AC | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96974 | WBS.2.1.9.2.31.1.7 | N | N | Planned | BG - ITR_C0067.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Scheduled Maintenance Plans (T-4 Days) - MP2) | 2 | 2021-01-26 14:30 | 2021-01-26 16:30 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 94354 |  |  | * |  | 2021-01-26 14:30 | 2021-01-26 16:30 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94362 | WBS.2.1.9.2.31.1.6 | N | N | Planned | HBG - ITR_C0067.1 - Spot-check SAP DATA reflects loaded data (Convert Scheduled Maintenance Plans (T-4 Days) - MP2) | 1 | 2021-01-26 14:30 | 2021-01-26 15:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 94354 |  |  | * |  | 2021-01-26 14:30 | 2021-01-26 15:30 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92848 | WBS.2.1.9.2.32 | N | N |  | Ramp Down ¦ ITR_C0032.1 Convert Open work orders – MP2 | 7.5 | 2021-01-26 09:45 | 2021-01-26 17:15 | [8 empty] | * |  | 2021-01-26 09:45 | 2021-01-26 19:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94589 | WBS.2.1.9.2.32.1 | N | N |  | Ramp Down ¦ ITR_C0032.1 Convert Open work orders – MP2 | 7.5 | 2021-01-26 09:45 | 2021-01-26 17:15 | [8 empty] | * |  | 2021-01-26 09:45 | 2021-01-26 19:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92846 | WBS.2.1.9.2.32.1.1 | N | N | Planned | Execute Preload ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2021-01-26 09:45 | 2021-01-26 10:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94359,94400,92777,92788,92809 |  |  | * |  | 2021-01-26 09:45 | 2021-01-26 10:45 | DATA | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92845 | WBS.2.1.9.2.32.1.2 | N | N | Planned | Validate Preload ITR_C0032.1 Convert Open work orders – MP2 | 1.5 | 2021-01-26 10:45 | 2021-01-26 12:15 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92846 |  |  | * |  | 2021-01-26 10:45 | 2021-01-26 12:15 | AC | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92844 | WBS.2.1.9.2.32.1.3 | N | N | Planned | Execute Load ITR_C0032.1 Convert Open work orders – MP2 | 1 | 2021-01-26 12:15 | 2021-01-26 13:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92845 |  |  | * |  | 2021-01-26 12:15 | 2021-01-26 13:15 | DATA | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92843 | WBS.2.1.9.2.32.1.4 | N | N | Planned | Validate Load ITR_C0032.1 Convert Open work orders – MP2 | 2 | 2021-01-26 13:15 | 2021-01-26 15:15 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92844 |  |  | * |  | 2021-01-26 13:15 | 2021-01-26 15:15 | AC | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96973 | WBS.2.1.9.2.32.1.11 | N | N | Planned | BG - ITR_C0032.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Open work orders – MP2) | 2 | 2021-01-26 15:15 | 2021-01-26 17:15 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 19:15 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96972 | WBS.2.1.9.2.32.1.12 | N | N | Planned | BG - Pre-Load: Verify the PM auto-generated WO and in flight planned and approved WO converted correctly | 2 | 2021-01-26 15:15 | 2021-01-26 17:15 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 17:15 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
93797 | WBS.2.1.9.2.32.1.6 | N | N | Planned | HBG - ITR_C0032.1 - Spot-check SAP DATA reflects loaded data (Convert Open work orders – MP2) | 2 | 2021-01-26 15:15 | 2021-01-26 17:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 17:15 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94607 | WBS.2.1.9.2.33 | N | N |  | Ramp Down ¦ PTM_I0270 - Point New SAPCreateHU_S4.exe S4 instance | 2 | 2021-01-30 20:30 | 2021-01-30 22:30 | [8 empty] | * |  | 2021-01-30 20:30 | 2021-01-30 22:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94606 | WBS.2.1.9.2.33.1 | N | N |  | Ramp Down ¦ PTM_I0270 - Point New SAPCreateHU_S4.exe S4 instance | 2 | 2021-01-30 20:30 | 2021-01-30 22:30 | [8 empty] | * |  | 2021-01-30 20:30 | 2021-01-30 22:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96809 | WBS.2.1.9.2.33.1.2 | N | N | Planned | BG - DixieIT - Deploy S/4 Pending Transactions - PTM_I0271 to shop floor thin clients and PC's. - not time critical | 2 | 2021-01-30 20:30 | 2021-01-30 22:30 | DEREK SARGENT | Derek.Sargent@GAPAC.com | ROBERT THOMPSON;JOHN WHITE;LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RLTHOMPSO@GAPAC.com;JOHN.WHITE@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | LSA | 96591 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 22:30 | LSA | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
5634 | WBS.2.1.10 | N | N |  | Ramp Down ¦ Post Conversion Configuration | 110 | 2021-01-18 06:15 | 2021-01-26 20:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 20:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
91363 | WBS.2.1.10.1 | N | N |  | Ramp Down ¦ Post Conversion Configuration - SAP Systems | 110 | 2021-01-18 06:15 | 2021-01-26 20:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 20:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
91364 | WBS.2.1.10.1.1 | N | N |  | Ramp Down ¦ Post Conversion Configuration - SAP Systems - S/4HANA | 110 | 2021-01-18 06:15 | 2021-01-26 20:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 20:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90225 | WBS.2.1.10.1.1.1 | N | N |  | Ramp Down ¦ Post Conversion Configuration - SAP Systems - S/4HANA - AC | 101.75 | 2021-01-18 14:30 | 2021-01-26 20:15 | [8 empty] | * |  | 2021-01-18 14:30 | 2021-01-26 20:15 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
9402 | WBS.2.1.10.1.1.1.1 | N | N | Planned | Build Distribution Lists For Inbox | 3 | 2021-01-18 14:30 | 2021-01-18 17:30 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | JEY MURUGESH;SAI TEAM;JASON RAMSEY;AC TEAM;DEAN PIPER;LYNN MCMURDO | JMURUGESH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 17:30 | AC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92089 | WBS.2.1.10.1.1.1.2 | N | N | Planned | Prepare and Mass load Partners onto Functional Locations | 3 | 2021-01-25 06:15 | 2021-01-25 09:15 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | DAVID MCGINNIS;AC TEAM;SAI TEAM;JASON RAMSEY;TAJINDER KOHLI;ERIC REINDL;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;ERIC.REINDL@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5393,9402,10845,92777 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 09:15 | AC | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92092 | WBS.2.1.10.1.1.1.3 | N | N | Planned | Run load file for equipment groups to characteristics | 1 | 2021-01-18 18:30 | 2021-01-18 19:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;AC TEAM;SAI TEAM;JASON RAMSEY;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5393 |  |  | * |  | 2021-01-18 18:30 | 2021-01-18 19:30 | AC | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92088 | WBS.2.1.10.1.1.1.4 | N | N | Planned | Pull PERNR from IR02 (PA0105 and HRP1001), confirm same PERNR assigned in MRS nodes; If not add | 2 | 2021-01-26 10:20 | 2021-01-26 12:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 95770 |  |  | * |  | 2021-01-26 10:20 | 2021-01-26 12:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92087 | WBS.2.1.10.1.1.1.5 | N | N | Planned | Run LSMW to update PERNR with the new work schedule rule for MRS | 1 | 2021-01-26 12:20 | 2021-01-26 13:20 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | TAJINDER KOHLI;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92088 |  |  | * |  | 2021-01-26 12:20 | 2021-01-26 13:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92085 | WBS.2.1.10.1.1.1.6 | N | N | Planned | Manually run program ZMRS_TRANSFER_PERS - Tranfer personnel to MRS | 1 | 2021-01-26 13:20 | 2021-01-26 14:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92088,92087 |  |  | * |  | 2021-01-26 13:20 | 2021-01-26 14:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92084 | WBS.2.1.10.1.1.1.7 | N | N | Planned | Manually run program ZMRS_TRANSFER_WC - Transfer Work Center to MRS | 1 | 2021-01-26 14:20 | 2021-01-26 15:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92085 |  |  | * |  | 2021-01-26 14:20 | 2021-01-26 15:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92083 | WBS.2.1.10.1.1.1.8 | N | N | Planned | Manually run program ZMRS_TRANSFER_PN - Transfer planning node to MRS | 1 | 2021-01-26 15:20 | 2021-01-26 16:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92084 |  |  | * |  | 2021-01-26 15:20 | 2021-01-26 16:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92082 | WBS.2.1.10.1.1.1.9 | N | N | Planned | Run SMQ2 to confirm that there is no queue stuck for MRS | 1 | 2021-01-26 16:20 | 2021-01-26 17:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92083 |  |  | * |  | 2021-01-26 16:20 | 2021-01-26 17:20 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95771 | WBS.2.1.10.1.1.1.10 | N | N | Planned | Create MRS nodes for Work Center and assign Personnel No. in MRS | 1 | 2021-01-26 08:20 | 2021-01-26 09:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5379 |  |  | * |  | 2021-01-26 08:20 | 2021-01-26 09:20 | AC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95770 | WBS.2.1.10.1.1.1.11 | N | N | Planned | Update variants for MRS batch jobs | 1 | 2021-01-26 09:20 | 2021-01-26 10:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 95771 |  |  | * |  | 2021-01-26 09:20 | 2021-01-26 10:20 | AC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96582 | WBS.2.1.10.1.1.1.29 | N | N | Planned | BG - Pre-Load: Validate Work Center and resource loads are in alignment between SAP and MRS | 2 | 2021-01-26 15:20 | 2021-01-26 17:20 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | TAJINDER KOHLI;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92084 |  |  | * |  | 2021-01-26 15:20 | 2021-01-26 17:20 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94648 | WBS.2.1.10.1.1.1.13 | N | N | Planned | PTH - Pre-Load: Validate Work Center and resource loads are in alignment between SAP and MRS | 2 | 2021-01-26 15:20 | 2021-01-26 17:20 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | TAJINDER KOHLI;SAI TEAM;KIM VANWYCHEN | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | AC | 92084 |  |  | * |  | 2021-01-26 15:20 | 2021-01-26 17:20 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94651 | WBS.2.1.10.1.1.1.14 | N | N | Planned | HBG - Pre-Load: Validate Work Center and resource loads are in alignment between SAP and MRS | 2 | 2021-01-26 15:20 | 2021-01-26 17:20 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | TAJINDER KOHLI;SAI TEAM;MELISSA KOTAREK | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM | AC | 92084 |  |  | * |  | 2021-01-26 15:20 | 2021-01-26 17:20 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96580 | WBS.2.1.10.1.1.1.27 | N | N | Planned | BG - Initiate MRS week 1 schedule build | 3 | 2021-01-26 15:15 | 2021-01-26 18:15 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;STEPHEN GREENWOOD;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Stephen.Greenwood@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94354,92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 19:15 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94655 | WBS.2.1.10.1.1.1.17 | N | N | Planned | PTH - Initiate MRS week 1 schedule build | 1 | 2021-01-26 18:45 | 2021-01-26 19:45 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 5763,89997 |  |  | * |  | 2021-01-26 18:45 | 2021-01-26 19:45 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94650 | WBS.2.1.10.1.1.1.18 | N | N | Planned | HBG - Initiate MRS week 1 schedule build | 4 | 2021-01-26 15:15 | 2021-01-26 19:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 94354,92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 19:15 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96581 | WBS.2.1.10.1.1.1.28 | N | N | Planned | BG - Verify the MRS look ahead schedule in SAP | 0.5 | 2021-01-26 18:15 | 2021-01-26 18:45 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM | Business | 96580 |  |  | * |  | 2021-01-26 19:15 | 2021-01-26 19:45 | AC | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94654 | WBS.2.1.10.1.1.1.21 | N | N | Planned | PTH - Verify the MRS look ahead schedule in SAP | 0.5 | 2021-01-26 19:45 | 2021-01-26 20:15 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94655 |  |  | * |  | 2021-01-26 19:45 | 2021-01-26 20:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94649 | WBS.2.1.10.1.1.1.22 | N | N | Planned | HBG - Verify the MRS look ahead schedule in SAP | 0.5 | 2021-01-26 19:15 | 2021-01-26 19:45 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 94650 |  |  | * |  | 2021-01-26 19:15 | 2021-01-26 19:45 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5781 | WBS.2.1.10.1.1.1.24 | N | N | Planned | Validate Activity Types / Rates / Cost Elements Groups | 0.5 | 2021-01-19 07:15 | 2021-01-19 07:45 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5549 |  |  | * |  | 2021-01-19 07:15 | 2021-01-19 07:45 | AC | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
94652 | WBS.2.1.10.1.1.1.25 | N | N | Planned | HBG - Pre-Load: Verify the PM auto-generated WO and in flight planned and approved WO converted correctly | 2 | 2021-01-26 15:15 | 2021-01-26 17:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 17:15 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94653 | WBS.2.1.10.1.1.1.26 | N | N | Planned | HBG - Pre-load: Load and maintain Work Orders - ready for work (kitted), completed or in progress | 4 | 2021-01-26 15:15 | 2021-01-26 19:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 19:15 | AC | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
90223 | WBS.2.1.10.1.1.2 | N | N |  | Ramp Down ¦ Post Conversion Configuration - SAP Systems - S/4HANA - EWM | 95 | 2021-01-18 06:15 | 2021-01-25 21:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 21:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
4578 | WBS.2.1.10.1.1.2.1 | N | N | Planned | Manual Config Steps (Maintain Link between Packaging Material and Means of Transport) - EWM | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;Vinay Tawani | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;vtawani@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4577 | WBS.2.1.10.1.1.2.2 | N | N | Planned | Manual Config Steps (Maintain Pack spec for PICK-HUs) - EWM | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;Uday Athwal | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;uathwal@deloitte.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
4582 | WBS.2.1.10.1.1.2.3 | N | N | Planned | Manual Config Steps (Yard Management setting - Assign Door Storage Bin and Supply Chain Unit; Assign Warehouse Door to Yard Bin; Assign Checkpoint to Yard Bin and SCU - EWM | 1 | 2021-01-19 15:45 | 2021-01-19 16:45 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36501,36888,4100,97215,97216,97219,97220,97221,97222,97223,97224 |  |  | * |  | 2021-01-19 20:45 | 2021-01-19 21:45 | EWM | CROSS | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
90879 | WBS.2.1.10.1.1.2.4 | N | N | Planned | PTH - Load and Activate Site Specific Pack Spec File | 2 | 2021-01-25 13:00 | 2021-01-25 15:00 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 15:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97489 | WBS.2.1.10.1.1.2.13 | N | N | Planned | BG - Load and Activate Site Specific Pack Spec File | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97488 | WBS.2.1.10.1.1.2.12 | N | N | Planned | HBG - Load and Activate Site Specific Pack Spec File | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97487 | WBS.2.1.10.1.1.2.11 | N | N | Planned | RVG - Load and Activate Site Specific Pack Spec File | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97486 | WBS.2.1.10.1.1.2.10 | N | N | Planned | RNC - Load and Activate Site Specific Pack Spec File | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97485 | WBS.2.1.10.1.1.2.9 | N | N | Planned | SCH - Load and Activate Site Specific Pack Spec File | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90295 | WBS.2.1.10.1.1.2.5 | N | N | Planned | Prepare & Validate Site Specific Packaging Specification CSV file | 8 | 2021-01-25 13:00 | 2021-01-25 21:00 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4577,8864,94320,5230,94323,96572 |  |  | * |  | 2021-01-25 13:00 | 2021-01-25 21:00 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90294 | WBS.2.1.10.1.1.2.6 | N | N | Planned | Upload Site Specific Packaging Specifications records from CSV file (use /SCWM/IPU) | 0.25 | 2021-01-25 21:00 | 2021-01-25 21:15 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 90295 |  |  | * |  | 2021-01-25 21:00 | 2021-01-25 21:15 | EWM | CROSS | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
29586 | WBS.2.1.10.1.1.2.7 | N | N | Planned | Maintain variants for 'Inbound delivery creation' batch job, 'MRO Outbound delivery creation', and 'Dock Scheduling' batch job in S/4HANA | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | NIKHIL NEGI | nikhnegi@deloitte.com | JACOB OWENS;DEEPIKA ARRABOLU;AVINASH TALREJA;DOUG STANISLAWSKI;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM | JACOB.OWENS@GAPAC.COM;DREDDYARRABOLU@DELOITTE.COM;AVTALREJA@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 91838,36501,97453 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | EWM | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90224 | WBS.2.1.10.1.1.3 | N | N |  | Ramp Down ¦ Post Conversion Configuration - SAP Systems - S/4HANA - SCM | 4 | 2021-01-20 19:00 | 2021-01-21 07:00 | [8 empty] | * |  | 2021-01-20 19:00 | 2021-01-21 07:00 |  |  | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
92110 | WBS.2.1.10.1.1.3.1 | N | N | Planned | Routing Change for Dual Stream - Max Interval 1 sec, Assign Class to Pack Operation | 4 | 2021-01-20 19:00 | 2021-01-21 07:00 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;SAI TEAM;SCM TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5195 |  |  | * |  | 2021-01-20 19:00 | 2021-01-21 07:00 | SCM | CROSS | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
89960 | WBS.2.1.11 | N | N |  | Ramp Down ¦ System Cut-Off Activities | 185 | 2021-01-18 06:15 | 2021-01-31 07:15 | [8 empty] | * |  | 2021-01-17 21:30 | 2021-02-01 06:30 |  |  | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
90173 | WBS.2.1.11.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Digital Core Systems | 185 | 2021-01-18 06:15 | 2021-01-31 07:15 | [8 empty] | * |  | 2021-01-17 21:30 | 2021-02-01 06:30 |  |  | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
90251 | WBS.2.1.11.1.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Digital Core Systems - SAP Systems | 144.5 | 2021-01-18 08:45 | 2021-01-29 09:15 | [8 empty] | * |  | 2021-01-18 08:45 | 2021-01-29 09:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91365 | WBS.2.1.11.1.1.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Digital Core Systems - SAP Systems - S/4HANA | 144.5 | 2021-01-18 08:45 | 2021-01-29 09:15 | [8 empty] | * |  | 2021-01-18 08:45 | 2021-01-29 09:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
89675 | WBS.2.1.11.1.1.1.1 | N | N | Planned | Update Vendor cross reference and Vendor In-Scope | 2 | 2021-01-18 08:45 | 2021-01-18 10:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;BOB BROWN;JASON RAMSEY;GARY BENOIT | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;ROBERT.BROWN4@GAPAC.COM;JCRAMSEY@GAPAC.COM;GARY.BENOIT@GAPAC.COM | DATA | 89679 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 10:45 | DATA | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90973 | WBS.2.1.11.1.1.1.2 | N | N | Planned | ITR_C0067/ITR_C0032 - Provide Factory Start Date and GO live date | 0.5 | 2021-01-26 09:45 | 2021-01-26 10:15 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;JASON RAMSEY;AC TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | AC | 89987,94400 |  |  | * |  | 2021-01-26 09:45 | 2021-01-26 10:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82352 | WBS.2.1.11.1.1.1.3 | N | N | Planned | Load New S/4HANA Accounting Information into Costar Application (D4-D6 relevant) | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | ROMANI GUY | RCGUY@GAPAC.COM | BRUCE KIRKLEWSKI;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 08:15 | PTP | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
82351 | WBS.2.1.11.1.1.1.4 | N | N | Planned | Validate S/4HANA Accounting Information in Costar Real Estate Application (D4-D6 relevant) | 3 | 2021-01-29 06:15 | 2021-01-29 09:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | JANE BLOCK;BRETT DETTMERING;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | JANE.BLOCK@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 82352,10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 09:15 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91457 | WBS.2.1.11.1.2 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Digital Core Systems - Non-SAP Systems | 185 | 2021-01-18 06:15 | 2021-01-31 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-02-01 06:30 |  |  | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
91458 | WBS.2.1.11.1.2.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Digital Core Systems - Non-SAP Systems - ICPAQS | 185 | 2021-01-18 06:15 | 2021-01-31 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-02-01 06:30 |  |  | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
94365 | WBS.2.1.11.1.2.1.1 | N | N | Planned | BG - Task - Update AA Codes - (Coordination - ICPAQS / AA Teams) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM;HOWARD ZAHORIK;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;HOWARD.ZAHORIK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | ICPAQS | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94873 | WBS.2.1.11.1.2.1.3 | N | N | Planned | HBG - Task - Update AA Codes - (Coordination - ICPAQS / AA Teams) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;HOWARD ZAHORIK | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM | ICPAQS | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | ICPAQS | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
80974 | WBS.2.1.11.1.2.1.8 | N | N | Planned | PTH - Task - Update AA Codes - (Coordination - ICPAQS / AA Teams) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;HOWARD ZAHORIK | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM | ICPAQS | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | ICPAQS | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94898 | WBS.2.1.11.1.2.1.10 | N | N | Planned | HBG - Validation - S/4HANA and ICPAQS Integration End Points | 0.25 | 2021-01-19 19:00 | 2021-01-19 19:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 4250,10846 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:15 | ICPAQS | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
96586 | WBS.2.1.11.1.2.1.85 | N | N | Planned | BG - Validation - S/4HANA and ICPAQS Integration End Points | 0.25 | 2021-01-19 19:00 | 2021-01-19 19:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 4250,10846 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:15 | ICPAQS | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97019 | WBS.2.1.11.1.2.1.130 | N | N | Planned | Validate End Polints for finished goods (U2I, E80, Gateway) | 0.25 | 2021-01-19 19:00 | 2021-01-19 19:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 4250,10846 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:15 | ICPAQS | PTH,HBG,BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97180 | WBS.2.1.11.1.2.1.138 | N | N | Planned | BG - Task - Add S4 workcenters to ICPAQS Assets. Set Production Order QTY and Production Order Materials to Yes, Production Order BOM to True | 0.25 | 2021-01-19 19:15 | 2021-01-19 19:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96586 |  |  | * |  | 2021-01-19 19:15 | 2021-01-19 19:30 | ICPAQS | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97177 | WBS.2.1.11.1.2.1.135 | N | N | Planned | HBG - Task - Add S4 workcenters to ICPAQS Assets. Set Production Order QTY and Production Order Materials to Yes, Production Order BOM to True | 0.25 | 2021-01-19 19:15 | 2021-01-19 19:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94898 |  |  | * |  | 2021-01-19 19:15 | 2021-01-19 19:30 | ICPAQS | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95371 | WBS.2.1.11.1.2.1.13 | N | N | Planned | BG - Task - Update Bin Types References | 0.25 | 2021-01-19 19:30 | 2021-01-19 19:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 97180 |  |  | * |  | 2021-01-19 19:30 | 2021-01-19 19:45 | ICPAQS | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95369 | WBS.2.1.11.1.2.1.17 | N | N | Planned | HBG - Task - Update Bin Types References | 0.25 | 2021-01-19 19:30 | 2021-01-19 19:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97177 |  |  | * |  | 2021-01-19 19:30 | 2021-01-19 19:45 | ICPAQS | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92261 | WBS.2.1.11.1.2.1.19 | N | N | Planned | BG - Action - Turn on consumption allocation to distributed | 0.25 | 2021-01-30 20:00 | 2021-01-30 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;TODD DAKINS;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 97020 |  |  | * |  | 2021-01-30 20:00 | 2021-01-30 20:15 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94891 | WBS.2.1.11.1.2.1.21 | N | N | Planned | HBG - Action - Turn on consumption allocation to distributed | 0.25 | 2021-01-30 20:00 | 2021-01-30 20:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94878 |  |  | * |  | 2021-01-30 20:00 | 2021-01-30 20:15 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
80972 | WBS.2.1.11.1.2.1.22 | N | N | Planned | BG - Task - Update Defect Reason Codes | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 90852 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94881 | WBS.2.1.11.1.2.1.24 | N | N | Planned | HBG - Task - Update Defect Reason Codes | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94886 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94878 | WBS.2.1.11.1.2.1.28 | N | N | Planned | HBG - Task - Update Storage Bin and Backstands | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94886 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97020 | WBS.2.1.11.1.2.1.131 | N | N | Planned | BG - Task - Update Storage Bin and Backstands | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 90852 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90852 | WBS.2.1.11.1.2.1.30 | N | N | Planned | BG - Task - Update Asset Names and Descriptions, WMS codes, Set Estimate Finished Goods Flag to True on Palletizers | 0.25 | 2021-01-30 19:30 | 2021-01-30 19:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;TODD DAKINS;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 12178,95902 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 19:45 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94886 | WBS.2.1.11.1.2.1.32 | N | N | Planned | HBG - Task - Update Asset Names and Descriptions, WMS codes, Set Estimate Finished Goods Flag to True on Palletizers | 0.25 | 2021-01-30 19:30 | 2021-01-30 19:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94943,12178 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 19:45 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94367 | WBS.2.1.11.1.2.1.34 | N | N | Planned | HBG - Task - Copy Trim Patterns | 0.25 | 2021-01-19 19:45 | 2021-01-19 20:00 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 95369 |  |  | * |  | 2021-01-19 19:45 | 2021-01-19 20:00 | ICPAQS | HBG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
8868 | WBS.2.1.11.1.2.1.37 | N | N | Planned | Validate production order in ICPAQS from S/4HANA-Finished Goods | 0.25 | 2021-01-28 21:15 | 2021-01-28 21:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 95124 |  |  | * |  | 2021-01-28 21:15 | 2021-01-28 21:30 | ICPAQS | PTH,HBG,BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95612 | WBS.2.1.11.1.2.1.38 | N | N | Planned | Valdiate Production Orders for Paper Machine | 0.25 | 2021-01-29 16:30 | 2021-01-29 16:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 95122 |  |  | * |  | 2021-01-29 16:30 | 2021-01-29 16:45 | ICPAQS | PTH,HBG,BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96588 | WBS.2.1.11.1.2.1.87 | N | N | Planned | BG - Action - Turn off facility Legacy WM Integration (SAPWM) | 0.25 | 2021-01-30 18:15 | 2021-01-30 18:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:30 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94366 | WBS.2.1.11.1.2.1.43 | N | N | Planned | Disable ability to add new planning scenario - config | 0.25 | 2021-01-30 18:15 | 2021-01-30 18:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:30 | ICPAQS | HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96810 | WBS.2.1.11.1.2.1.112 | N | N | Planned | BG - DixieIT - Shutdown FG-LPN posting at D4 Sites. (1376 BG) - Stop SapCreateHU.exe, Watch.dog.exe, and leave DATA GATEWAY.exe running. | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | JOHN WHITE | JOHN.WHITE@GAPAC.COM | Jeron Wall;LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | Jeron.wall@gapac.com;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96591 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 20:45 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97852 | WBS.2.1.11.1.2.1.200 | N | N | Planned | BG - Action - Point LPN Uploader program to ICPAQS Prod - ICPAQS Finished Goods Integration (Change URL In LPN Uploader Program) | 0.25 | 2021-01-30 20:45 | 2021-01-30 21:00 | MINT VICKERY | MINT.VICKERY@GAPAC.COM | SUSAN RIELS;TODD DAKINS;DORESA WARD;SAI TEAM;JOHN WHITE | SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM;DVWARD@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.WHITE@GAPAC.COM | ICPAQS | 96810 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:00 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96591 | WBS.2.1.11.1.2.1.90 | N | N | Planned | BG - Stop current ECC Runs in ICPAQS | 0.25 | 2021-01-30 20:15 | 2021-01-30 20:30 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 95902,92261 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 20:30 | ICPAQS OPERATIONS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96644 | WBS.2.1.11.1.2.1.11 | N | N | Planned | BG - Run Inventory report for all items in Bowling Green | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;SAI TEAM;LYNN MCMURDO;DEAN PIPER;EWM TEAM | Jeana.Harrer@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96591 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | BG | 2021-01-30 | 2021-01-31 | 3 | Ramp Down
94893 | WBS.2.1.11.1.2.1.47 | N | N | Planned | PTH - Task - Dismount all materials on assets prior to shutown | 0.25 | 2021-01-30 19:30 | 2021-01-30 19:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94945 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 19:45 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96594 | WBS.2.1.11.1.2.1.93 | N | N | Planned | HBG - Action - Turn off Scheduled Task Interface | 0.25 | 2021-01-30 21:00 | 2021-01-30 21:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94548 |  |  | * |  | 2021-01-30 21:00 | 2021-01-30 21:15 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94390 | WBS.2.1.11.1.2.1.52 | N | N | Planned | PTH - Action - Disable ECC Integration - Turn off SAPME Interface | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;TODD DAKINS;MINT VICKERY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94893 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97022 | WBS.2.1.11.1.2.1.133 | N | N | Planned | PTH - Valdiate all transactions processed to ECC | 0.5 | 2021-01-30 20:00 | 2021-01-30 20:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94390 |  |  | * |  | 2021-01-30 20:00 | 2021-01-30 20:30 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94376 | WBS.2.1.11.1.2.1.60 | N | N | Planned | HBG - Task - Dismount all materials on assets prior to shutown | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 94728 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 20:45 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94548 | WBS.2.1.11.1.2.1.61 | N | N | Planned | HBG - Action - Update to EWM and Directed Work in Mill Configuration | 0.25 | 2021-01-30 20:45 | 2021-01-30 21:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 94376 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:00 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94735 | WBS.2.1.11.1.2.1.66 | N | N | Planned | HBG - Validation - All Converting S4 Production Orders are started | 0.25 | 2021-01-30 21:00 | 2021-01-30 21:18 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93865 |  |  | * |  | 2021-01-30 21:00 | 2021-01-30 21:18 | ICPAQS OPERATIONS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94728 | WBS.2.1.11.1.2.1.72 | N | N | Planned | HBG - Stop current ECC Runs in ICPAQS | 0.25 | 2021-01-30 20:15 | 2021-01-30 20:30 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 94943,94891 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 20:30 | ICPAQS OPERATIONS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96592 | WBS.2.1.11.1.2.1.91 | N | N | Planned | BG - Task - Dismount all materials on assets prior to shutown | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96591 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 20:45 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96593 | WBS.2.1.11.1.2.1.92 | N | N | Planned | BG - Action - Update to EWM and Directed Work in Mill Configuration | 0.5 | 2021-01-30 20:45 | 2021-01-30 21:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;LYNN MCMURDO;DEAN PIPER | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com | Business | 96592 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:15 | ICPAQS OPERATIONS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96597 | WBS.2.1.11.1.2.1.96 | N | N | Planned | BG - Action - Disable ECC Integration | 0.25 | 2021-01-30 21:15 | 2021-01-30 21:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96593 |  |  | * |  | 2021-01-30 21:15 | 2021-01-30 21:30 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95579 | WBS.2.1.11.1.2.1.84 | N | N | Planned | PLT - Fill staging lane with vitals needed for converting while S/4 EWM unavailable | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | CHRIS HARTIGAN | CHRISTOPHER.HARTIGAN@GAPAC.COM | LEONARD GIBSON;SAI TEAM;EWM TEAM | LEONARD.GIBSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | PLT | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96931 | WBS.2.1.11.1.2.1.118 | N | N | Planned | PTH - Task - Run Script to update Workflows | 0.25 | 2021-01-30 20:15 | 2021-01-30 20:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 97582 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 20:30 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96930 | WBS.2.1.11.1.2.1.117 | N | N | Planned | BG - Task - Run Script to update Workflows | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 90852 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96936 | WBS.2.1.11.1.2.1.123 | N | N | Planned | BG - Run Script to remove old ECC orders and manual orders | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96591 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 20:45 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96935 | WBS.2.1.11.1.2.1.122 | N | N | Planned | PTH - Run Script to remove old ECC orders and manual orders | 0.25 | 2021-01-30 19:30 | 2021-01-30 19:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 94945 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 19:45 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96933 | WBS.2.1.11.1.2.1.120 | N | N | Planned | HBG - Run Script to remove old ECC orders and manual orders | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 94728 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 20:45 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97183 | WBS.2.1.11.1.2.1.141 | N | N | Planned | HBG - Task - Delete old orders from ECC | 0.25 | 2021-01-30 20:45 | 2021-01-30 21:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 94376 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:00 | ICPAQS | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97181 | WBS.2.1.11.1.2.1.139 | N | N | Planned | BG - Task - - Delete old orders from ECC | 0.25 | 2021-01-30 20:45 | 2021-01-30 21:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 96592 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:00 | ICPAQS | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97574 | WBS.2.1.11.1.2.1.146 | N | N | Planned | PTH - Validation - S/4HANA and ICPAQS Integration End Points | 0.25 | 2021-01-19 19:00 | 2021-01-19 19:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 4250,10846 |  |  | * |  | 2021-01-19 19:00 | 2021-01-19 19:15 | ICPAQS | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97575 | WBS.2.1.11.1.2.1.147 | N | N | Planned | PTH - Task - Paper Machine - Disable Publish to SAP before we start receiving Production Orders from SAP | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;HOWARD ZAHORIK | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;HOWARD.ZAHORIK@GAPAC.COM | ICPAQS | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | ICPAQS | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97576 | WBS.2.1.11.1.2.1.148 | N | N | Planned | PTH - Task - Add S4 workcenters to ICPAQS Assets. Set Production Order QTY and Production Order Materials to Yes, Production Order BOM to True | 0.25 | 2021-01-19 19:15 | 2021-01-19 19:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 97574 |  |  | * |  | 2021-01-19 19:15 | 2021-01-19 19:30 | ICPAQS | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97577 | WBS.2.1.11.1.2.1.149 | N | N | Planned | PTH - Task - Update Bin Types References | 0.25 | 2021-01-19 19:30 | 2021-01-19 19:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;SAI TEAM;TODD DAKINS | MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97576 |  |  | * |  | 2021-01-19 19:30 | 2021-01-19 19:45 | ICPAQS | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97578 | WBS.2.1.11.1.2.1.150 | N | N | Planned | PTH - Task - Copy Trim Patterns | 0.25 | 2021-01-19 19:45 | 2021-01-19 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;PHIL RACINE;FRANZ JURVA | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;phil.racine@gapac.com;FRANZ.JURVA@GAPAC.COM | ICPAQS | 97577 |  |  | * |  | 2021-01-19 19:45 | 2021-01-19 20:00 | ICPAQS | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97579 | WBS.2.1.11.1.2.1.151 | N | N | Planned | PTH (Paper Machine sites) - Remove Recalc PM Est Start Date/Time Service | 0.25 | 2021-01-29 16:45 | 2021-01-29 17:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 95612 |  |  | * |  | 2021-01-29 16:45 | 2021-01-29 17:00 | ICPAQS | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97580 | WBS.2.1.11.1.2.1.152 | N | N | Planned | PTH - Task - Update Asset Names and Descriptions, WMS codes, Set Estimate Finished Goods Flag to True on Palletizers | 0.25 | 2021-01-30 19:30 | 2021-01-30 19:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94945,12178 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 19:45 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97581 | WBS.2.1.11.1.2.1.153 | N | N | Planned | PTH - Task - Update Defect Reason Codes | 0.25 | 2021-01-30 19:45 | 2021-01-30 20:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 97580 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:00 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97582 | WBS.2.1.11.1.2.1.154 | N | N | Planned | PTH - Task - Update Storage Bin and Backstands | 0.25 | 2021-01-30 20:00 | 2021-01-30 20:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 97581 |  |  | * |  | 2021-01-30 20:00 | 2021-01-30 20:15 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97583 | WBS.2.1.11.1.2.1.155 | N | N | Planned | PTH - Action - Turn on consumption allocation to distributed | 0.25 | 2021-01-30 20:15 | 2021-01-30 20:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 97582 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 20:30 | ICPAQS | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97616 | WBS.2.1.11.1.2.1.179 | N | N | Planned | MC TASK - EWM Team to provide HUs and quantities for all Sites (WMS Data) | 0.25 | 2021-01-28 11:30 | 2021-01-28 11:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DORESA WARD | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;DVWARD@GAPAC.COM | EWM | 97573 |  |  | * |  | 2021-01-28 11:30 | 2021-01-28 11:45 | EWM | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97670 | WBS.2.1.11.1.2.1.180 | N | N | Planned | GBD - Identify Staging area for dark period for each asset and begin emptying bins | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | GBD | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97671 | WBS.2.1.11.1.2.1.181 | N | N | Planned | GBD - Physcially stage parent rolls for dark period | 6 | 2021-01-28 06:15 | 2021-01-28 12:15 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 12:15 | EWM | GBD | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97672 | WBS.2.1.11.1.2.1.182 | N | N | Planned | GBD - Move HU's to staging lanes in EWM & ICPAQs | 1 | 2021-01-30 23:45 | 2021-01-31 00:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 95633 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 00:45 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97760 | WBS.2.1.11.1.2.1.199 | N | N | Planned | Send email 1 hr prior to FCW outage for Digital Core Sysems S4P, MDP, GWP, PO an HAP | 0.5 | 2021-01-30 23:45 | 2021-01-31 00:15 | KYNDAL CODY | KYNDAL.CODY@GAPAC.COM | DANI SIMMONS;MAMIE TREZVANT;TAMMY WILLIAMS;SAI TEAM | DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;TLWILLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 95633 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 06:30 | DEV | ALL | 2021-01-31 | 2021-02-01 | 3 | Ramp Down
97673 | WBS.2.1.11.1.2.1.183 | N | N | Planned | GBD - Communicate when to start manual EWM Processes for Converting and Paper Machines | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | EWM | GBD | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97674 | WBS.2.1.11.1.2.1.184 | N | N | Planned | GBD - Communicate when to start manual parts and work tracking process | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | AC | GBD | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97676 | WBS.2.1.11.1.2.1.185 | N | N | Planned | GBB - Communicate when to start manual parts and work tracking processes | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | CHRIS KANE | CHRIS.KANE@GAPAC.COM | RYAN VANCAMPENHOUT;KIM VANWYCHEN;SAI TEAM | RYAN.VANCAMPENHOUT2@GAPAC.COM;KIM.VANWYCHEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | AC | GBB | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97713 | WBS.2.1.11.1.2.1.187 | N | N | Planned | GBB - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | BRYAN PAVLIK | BRYAN.PAVLIK@GAPAC.COM | MIKE DEPREZ;KIM VANWYCHEN;JOHN CASABURRI;SAI TEAM | MICHAEL.DEPREZ@GAPAC.COM;KIM.VANWYCHEN@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | GBB | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97714 | WBS.2.1.11.1.2.1.188 | N | N | Planned | GBB - Mill communicates to all constituencies (mill and DC) to begin manual processes through system shutdown | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97715 | WBS.2.1.11.1.2.1.189 | N | N | Planned | GBB - Verify that LGVs are idle and no work is in the queue | 0.5 | 2021-01-31 06:45 | 2021-01-31 07:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 93271 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97716 | WBS.2.1.11.1.2.1.190 | N | N | Planned | GBB - Validate no more LGV Movements | 0.5 | 2021-01-30 19:30 | 2021-01-30 20:00 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 94945 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 20:00 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97717 | WBS.2.1.11.1.2.1.191 | N | N | Planned | GBB - Operations confirms all system activities to perform prior to cutover have been completed. | 2 | 2021-01-30 12:15 | 2021-01-30 14:15 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97718 | WBS.2.1.11.1.2.1.192 | N | N | Planned | GBB - Operations notifies cutover team that they are ready for the cutover work to begin. | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97719 | WBS.2.1.11.1.2.1.193 | N | N | Planned | GBB - All shipments are load end and none started. | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97720 | WBS.2.1.11.1.2.1.194 | N | N | Planned | GBB - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 4 | 2021-01-30 12:15 | 2021-01-30 16:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 16:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97721 | WBS.2.1.11.1.2.1.195 | N | N | Planned | GBB - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97722 | WBS.2.1.11.1.2.1.196 | N | N | Planned | GBB - At mills, operations confirms system activities to perform for mill production & converting prior to cutover have been completed | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 20:15 | EWM | GBB | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97735 | WBS.2.1.11.1.2.1.198 | N | N | Planned | GBP- Load up staging lanes at assets that are running - and keep full | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | GREGG GENTILE | GREGG.GENTILE@GAPAC.COM | JEREMY HEYDEN;MELISSA KOTAREK;SAI TEAM | JEREMY.HEYDEN@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 20:15 | EWM | GBP | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97734 | WBS.2.1.11.1.2.1.197 | N | N | Planned | GBP- Communicate to converting to start shut down- and DO NOT CLOSE ICPAQs ORDER | 1 | 2021-01-30 22:45 | 2021-01-30 23:45 | GREGG GENTILE | GREGG.GENTILE@GAPAC.COM | JEREMY HEYDEN;MELISSA KOTAREK;SAI TEAM | JEREMY.HEYDEN@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-30 23:45 | EWM | GBP | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91366 | WBS.2.1.11.1.3 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - Non-SAP Systems | 182.25 | 2021-01-18 06:30 | 2021-01-31 04:45 | [8 empty] | * |  | 2021-01-17 21:30 | 2021-01-31 04:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
94351 | WBS.2.1.11.1.3.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - Non-SAP Systems - MP2 | 3.5 | 2021-01-26 06:15 | 2021-01-26 09:45 | [8 empty] | * |  | 2021-01-26 06:15 | 2021-01-26 09:45 |  |  | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94359 | WBS.2.1.11.1.3.1.1 | N | N | Planned | AC MP2 T-4 GATE | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | AC | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
94400 | WBS.2.1.11.1.3.1.2 | N | N | Planned | Execute T-4 Extracts for MP2 | 2.5 | 2021-01-26 07:15 | 2021-01-26 09:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;AMY EL-BASSIONI;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94359 |  |  | * |  | 2021-01-26 07:15 | 2021-01-26 09:45 | DATA | HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
91367 | WBS.2.1.11.1.3.2 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - Non-SAP Systems - AS8 | 182.25 | 2021-01-18 06:30 | 2021-01-31 04:45 | [8 empty] | * |  | 2021-01-17 21:30 | 2021-01-31 04:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
92570 | WBS.2.1.11.1.3.2.1 | N | N | Planned | Create PTM Documents & update XREF | 1 | 2021-01-18 11:00 | 2021-01-18 12:00 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | TAJINDER KOHLI;SAI TEAM;US GP BASIS;AC TEAM | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 5391 |  |  | * |  | 2021-01-18 11:00 | 2021-01-18 12:00 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92571 | WBS.2.1.11.1.3.2.2 | N | N | Planned | Load PTM maintenance plan & update item description | 1 | 2021-01-19 10:30 | 2021-01-19 11:30 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | TAJINDER KOHLI;SAI TEAM;US GP BASIS;AC TEAM | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 82900 |  |  | * |  | 2021-01-19 10:30 | 2021-01-19 11:30 | AC | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
92572 | WBS.2.1.11.1.3.2.3 | N | N | Planned | Update job type PD,PM,FA on open WO | 0.5 | 2021-01-26 06:15 | 2021-01-26 06:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | TAJINDER KOHLI;JEY MURUGESH;SAI TEAM;US GP BASIS;BRENNEN FRISQUE;AC TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:45 | AC | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89967 | WBS.2.1.11.1.3.2.4 | N | N | Planned | AC AS8 T-4 GATE | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | SAI TEAM;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:30 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
89987 | WBS.2.1.11.1.3.2.5 | N | N | Planned | Execute T-4 Extracts for Asset Suite | 2.5 | 2021-01-26 06:30 | 2021-01-26 09:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 89967,5254 |  |  | * |  | 2021-01-26 06:30 | 2021-01-26 09:00 | DATA | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92569 | WBS.2.1.11.1.3.2.6 | N | N | Planned | Create revisions | 0.5 | 2021-01-26 09:00 | 2021-01-26 09:30 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | TAJINDER KOHLI;SAI TEAM;US GP BASIS;AC TEAM | TKOHLI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 89987 |  |  | * |  | 2021-01-26 09:00 | 2021-01-26 09:30 | AC | CROSS | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
5872 | WBS.2.1.11.1.3.2.7 | N | N | Planned | In-Flight wo manual conversion (WO have been approved in legacy) | 4 | 2021-01-26 18:45 | 2021-01-27 06:45 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | SAI TEAM;JASON RAMSEY;KELLY STRASSBURGER;AC TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 89997,89967,5763 |  |  | * |  | 2021-01-26 18:45 | 2021-01-27 06:45 | AC | PTH,HBG,BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95316 | WBS.2.1.11.1.3.2.8 | N | N | Planned | In-Flight wo manual conversion (WO have been approved in legacy) - MP2. | 4 | 2021-01-26 15:15 | 2021-01-26 19:17 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | SAI TEAM;JASON RAMSEY;KELLY STRASSBURGER;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 92843 |  |  | * |  | 2021-01-26 15:15 | 2021-01-26 19:17 | AC | ALL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82768 | WBS.2.1.11.1.3.2.9 | N | N | Planned | Remove approvers for Mill in Asset Suite security tool | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | MARK GLAESER;JASON RAMSEY;AC TEAM;SAI TEAM | MARK.GLAESER@GAPAC.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ASSET SUITE | 10531 |  |  | * |  | 2021-01-17 21:30 | 2021-01-17 21:45 | ASSET SUITE | PTH | 2021-01-18 | 2021-01-17 | 1 | Ramp Down
94636 | WBS.2.1.11.1.3.2.10 | N | N | Planned | Turn off auto-generation of Wos for converted facilities in MP2 and MOE | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | SCOTT BOZEMAN | JSBOZEMA@GAPAC.COM | JASON RAMSEY;AC TEAM;SAI TEAM;JIM FARRELL;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JIM.FARRELL@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ASSET SUITE | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | ASSET SUITE | HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94637 | WBS.2.1.11.1.3.2.11 | N | N | Planned | Remove converted MP2 facilities from Automator/ServiceNow | 0.5 | 2021-01-30 12:45 | 2021-01-30 13:15 | JIM FARRELL | JIM.FARRELL@GAPAC.COM | JASON RAMSEY;AC TEAM;SAI TEAM;SCOTT BOZEMAN;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JSBOZEMA@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ASSET SUITE | 94636 |  |  | * |  | 2021-01-30 12:45 | 2021-01-30 13:15 | ASSET SUITE | HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94638 | WBS.2.1.11.1.3.2.12 | N | N | Planned | Move MP2 & MOE all users to Read-only for converted facilities | 0.25 | 2021-01-30 13:15 | 2021-01-30 13:30 | SCOTT BOZEMAN | JSBOZEMA@GAPAC.COM | JASON RAMSEY;AC TEAM;SAI TEAM;JIM FARRELL;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JIM.FARRELL@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ASSET SUITE | 94637 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 13:30 | ASSET SUITE | HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94639 | WBS.2.1.11.1.3.2.13 | N | N | Planned | Turn off MOE for converted facilities | 0.25 | 2021-01-30 13:30 | 2021-01-30 13:45 | SCOTT BOZEMAN | JSBOZEMA@GAPAC.COM | JASON RAMSEY;AC TEAM;SAI TEAM;JIM FARRELL;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JIM.FARRELL@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ASSET SUITE | 94638 |  |  | * |  | 2021-01-30 13:30 | 2021-01-30 13:45 | ASSET SUITE | HBG,BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82192 | WBS.2.1.11.1.3.2.14 | N | N | Planned | Notify accruals are ready for processing | 0.25 | 2021-01-30 18:30 | 2021-01-30 18:45 | MARK GLAESER | MARK.GLAESER@GAPAC.COM | BRENNEN FRISQUE;SAI TEAM;JASON RAMSEY;AC TEAM | BRENNEN.FRISQUE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 94592 |  |  | * |  | 2021-01-30 18:30 | 2021-01-30 18:45 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82191 | WBS.2.1.11.1.3.2.15 | N | N | Planned | Add simple code | 0.25 | 2021-01-30 18:45 | 2021-01-30 19:00 | BRENNEN FRISQUE | BRENNEN.FRISQUE@GAPAC.COM | PATRICK BOOMER;SAI TEAM;JASON RAMSEY;AC TEAM | PATRICK.BOOMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82192 |  |  | * |  | 2021-01-30 18:45 | 2021-01-30 19:00 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82190 | WBS.2.1.11.1.3.2.16 | N | N | Planned | Verify PBKIN is clean | 0.25 | 2021-01-30 19:00 | 2021-01-30 19:15 | MARK GLAESER | MARK.GLAESER@GAPAC.COM | BRENNEN FRISQUE;SAI TEAM;JASON RAMSEY;AC TEAM | BRENNEN.FRISQUE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 93177,82191 |  |  | * |  | 2021-01-30 19:00 | 2021-01-30 19:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82189 | WBS.2.1.11.1.3.2.17 | N | N | Planned | Set all converted Asset Suite users to Read-only and bounce FA a second time | 0.25 | 2021-01-30 19:00 | 2021-01-30 19:15 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | BRENNEN FRISQUE;SAI TEAM;JASON RAMSEY;AC TEAM | BRENNEN.FRISQUE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82191 |  |  | * |  | 2021-01-30 19:00 | 2021-01-30 19:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82626 | WBS.2.1.11.1.3.2.18 | N | N | Planned | Identify units of purchase in AS8 PO's that are missing in material master and Create those Alt UOM's for AS8 materials | 1.5 | 2021-01-30 19:15 | 2021-01-30 20:45 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DATA ETL TEAM;SHANKAR RAMNARAYANAN;DENISE ROBINSON;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 20:45 | DATA | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82188 | WBS.2.1.11.1.3.2.19 | N | N | Planned | Run final Asset Suite accrual job | 2 | 2021-01-30 19:15 | 2021-01-30 21:15 | MARK GLAESER | MARK.GLAESER@GAPAC.COM | PATRICK BOOMER;SAI TEAM;JASON RAMSEY;AC TEAM | PATRICK.BOOMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82192,82191,82190,82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 21:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82187 | WBS.2.1.11.1.3.2.20 | N | N | Planned | Run final Asset Suite transactions job | 2 | 2021-01-30 19:15 | 2021-01-30 21:15 | MARK GLAESER | MARK.GLAESER@GAPAC.COM | PATRICK BOOMER;SAI TEAM;JASON RAMSEY;AC TEAM | PATRICK.BOOMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82192,82191,82190,82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 21:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97761 | WBS.2.1.11.1.3.2.142 | N | N | Planned | Dump check tables for PTM_C0201 | 1 | 2021-01-30 21:15 | 2021-01-30 22:15 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82187 |  |  | * |  | 2021-01-30 22:15 | 2021-01-30 23:15 | DATA | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82185 | WBS.2.1.11.1.3.2.21 | N | N | Planned | Remove facilities from PTM interface jobs | 1 | 2021-01-30 21:15 | 2021-01-30 22:15 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | ALEX MEDVEDEV;SAI TEAM;JASON RAMSEY;AC TEAM | ALEX.MEDVEDEV@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82187,82188 |  |  | * |  | 2021-01-30 21:15 | 2021-01-30 22:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
81155 | WBS.2.1.11.1.3.2.22 | N | N | Planned | Execute Extracts from AS8 for PTP_C0005.1, ITR_C0062 | 7.5 | 2021-01-30 21:15 | 2021-01-31 04:45 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 5251,3968,82187 |  |  | * |  | 2021-01-30 21:15 | 2021-01-31 04:45 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
92415 | WBS.2.1.11.1.3.2.23 | N | N | Planned | Move OE Master data security from OE to SAP S/4 | 1 | 2021-01-30 22:15 | 2021-01-30 23:15 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | ALEX MEDVEDEV;SAI TEAM;JASON RAMSEY;AC TEAM | ALEX.MEDVEDEV@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82185 |  |  | * |  | 2021-01-30 22:15 | 2021-01-30 23:15 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92414 | WBS.2.1.11.1.3.2.26 | N | N | Planned | Set all Maintelligence users for the converted sites to Read Only | 0.25 | 2021-01-30 22:15 | 2021-01-30 22:30 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | ALEX MEDVEDEV;SAI TEAM;JASON RAMSEY;AC TEAM | ALEX.MEDVEDEV@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82185 |  |  | * |  | 2021-01-30 22:15 | 2021-01-30 22:30 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82184 | WBS.2.1.11.1.3.2.27 | N | N | Planned | Remove facilities from EQ interface jobs | 0.25 | 2021-01-30 22:15 | 2021-01-30 22:30 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | ALEX MEDVEDEV;SAI TEAM;JASON RAMSEY;AC TEAM | ALEX.MEDVEDEV@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82185 |  |  | * |  | 2021-01-30 22:15 | 2021-01-30 22:30 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82183 | WBS.2.1.11.1.3.2.28 | N | N | Planned | Change user vars | 0.25 | 2021-01-30 22:30 | 2021-01-30 22:45 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | ALEX MEDVEDEV;SAI TEAM;JASON RAMSEY;AC TEAM | ALEX.MEDVEDEV@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82184 |  |  | * |  | 2021-01-30 22:30 | 2021-01-30 22:45 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95779 | WBS.2.1.11.1.3.2.29 | N | N | Planned | Turn off AAA email preferences | 0.25 | 2021-01-30 19:15 | 2021-01-30 19:30 | BRENNEN FRISQUE | BRENNEN.FRISQUE@GAPAC.COM | PATRICK BOOMER;SAI TEAM;JASON RAMSEY;AC TEAM | PATRICK.BOOMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:30 | ASSET SUITE | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95778 | WBS.2.1.11.1.3.2.30 | N | N | Planned | Send notification to Asset Suite CPG facility leads and IT of app bounce | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | PATRICK BOOMER | PATRICK.BOOMER@GAPAC.COM | BRENNEN FRISQUE;SAI TEAM;JASON RAMSEY;AC TEAM | BRENNEN.FRISQUE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 82768 |  |  | * |  | 2021-01-17 21:45 | 2021-01-17 22:00 | ASSET SUITE | PTH | 2021-01-18 | 2021-01-17 | 1 | Ramp Down
91371 | WBS.2.1.11.1.3.3 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - Non-SAP Systems - JDA | 25.5 | 2021-01-29 12:15 | 2021-01-30 21:45 | [8 empty] | * |  | 2021-01-29 12:15 | 2021-01-30 23:00 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
89596 | WBS.2.1.11.1.3.3.1 | N | N | Planned | Verify that there all JDA sites (legacy) disable their resyncs for day of outage | 1 | 2021-01-29 12:15 | 2021-01-29 13:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;SAI TEAM;LSA TEAM;JACOB OWENS | DAVID.BASCHE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JACOB.OWENS@GAPAC.COM | LSA | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 13:15 | LSA | CROSS | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
80968 | WBS.2.1.11.1.3.3.2 | N | N | Planned | Run script to lock out all non-essential users out of JDA WM for sites going live | 0.5 | 2021-01-30 19:00 | 2021-01-30 19:30 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | ARNAB DEY;AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;DOUG STANISLAWSKI | ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 93028,95844,95786 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 20:45 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
80967 | WBS.2.1.11.1.3.3.3 | N | N | Planned | JDA IT confirm all transactions have flowed to SAP | 1 | 2021-01-30 19:30 | 2021-01-30 20:30 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | ARNAB DEY;AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;DOUG STANISLAWSKI | ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 80968 |  |  | * |  | 2021-01-30 20:45 | 2021-01-30 21:45 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
89673 | WBS.2.1.11.1.3.3.4 | N | N | Planned | PTH - Disable jobs in JDA for PTH to prevent unwanted EMS events or transactions from going out of system | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JEFF DUCKETT;ARNAB DEY;AVINASH TALREJA;SAI TEAM;LSA TEAM | JEFFREY.DUCKETT@GAPAC.COM;ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 80967 |  |  | * |  | 2021-01-30 21:45 | 2021-01-30 22:15 | LSA | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
68450 | WBS.2.1.11.1.3.3.5 | N | N | Planned | Turn off Integrator Sender to start queueing up transactions going to SAP (P40) for all JDA sites | 0.25 | 2021-01-30 20:30 | 2021-01-30 20:45 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | ARNAB DEY;AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;DOUG STANISLAWSKI | ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 80967 |  |  | * |  | 2021-01-30 21:45 | 2021-01-30 22:00 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
5797 | WBS.2.1.11.1.3.3.6 | N | N | Planned | Verify Table Entries In ZTPTM_INTRM_VMAP | 1 | 2021-01-30 20:45 | 2021-01-30 21:45 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;PRAJWAL K S | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;prajks@deloitte.com | EWM | 68450,93067,91838 |  |  | * |  | 2021-01-30 22:00 | 2021-01-30 23:00 | EWM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94928 | WBS.2.1.11.2 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - ECC | 132.75 | 2021-01-20 08:00 | 2021-01-30 12:45 | [8 empty] | * |  | 2021-01-20 08:00 | 2021-01-30 12:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94929 | WBS.2.1.11.2.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - ECC | 132.75 | 2021-01-20 08:00 | 2021-01-30 12:45 | [8 empty] | * |  | 2021-01-20 08:00 | 2021-01-30 12:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94930 | WBS.2.1.11.2.1.1 | N | N |  | Ramp Down ¦ System Cut-Off Activities - Legacy - ECC | 132.75 | 2021-01-20 08:00 | 2021-01-30 12:45 | [8 empty] | * |  | 2021-01-20 08:00 | 2021-01-30 12:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92370 | WBS.2.1.11.2.1.1.1 | N | N | Planned | Send email on upcoming outage for Digital Core Systems S4P, MDP, GWP, PO and HAP | 0.5 | 2021-01-20 08:00 | 2021-01-20 08:30 | KYNDAL CODY | KYNDAL.CODY@GAPAC.COM | DANI SIMMONS;MAMIE TREZVANT;TAMMY WILLIAMS;SAI TEAM | DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;TLWILLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 10846 |  |  |  | 2021-01-20 08:00 | 2021-01-20 08:00 | 2021-01-20 08:30 | DEV | ALL | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
92368 | WBS.2.1.11.2.1.1.3 | N | N | Planned | Send 1st reminder email on upcoming outage for Digital Core Sysems S4P, MDP, GWP, PO, and HAP | 0.5 | 2021-01-27 06:15 | 2021-01-27 06:45 | KYNDAL CODY | KYNDAL.CODY@GAPAC.COM | DANI SIMMONS;MAMIE TREZVANT;TAMMY WILLIAMS;SAI TEAM | DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;TLWILLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:45 | DEV | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92366 | WBS.2.1.11.2.1.1.4 | N | N | Planned | Send 2nd reminder email on upcoming outage for Digital Core Sysems S4P, MDP, GWP, PO an HAP | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | KYNDAL CODY | KYNDAL.CODY@GAPAC.COM | DANI SIMMONS;MAMIE TREZVANT;TAMMY WILLIAMS;SAI TEAM | DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;TLWILLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | DEV | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82501 | WBS.2.1.11.2.1.1.2 | N | N | Planned | Make schedule/job changes and Execute Jobs prior to ECC Shut Down | 40 | 2021-01-25 06:15 | 2021-01-27 14:15 | WILL COLEMAN | WCOLEMA@GAPAC.COM | CYNDI HOTTENSTINE;DON ABBOTT;SAI TEAM;LSA TEAM | CYNDI.HOTTENSTINE@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-27 14:15 | LSA | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82671 | WBS.2.1.11.3 | N | N |  | Ramp Down ¦ Purchase Order Conversion Ramp Down Prep | 174.5 | 2021-01-18 06:15 | 2021-01-30 20:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 20:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90171 | WBS.2.1.11.3.1 | N | N |  | Ramp Down ¦ Purchase Order Conversion Ramp Down Prep Activity | 174.5 | 2021-01-18 06:15 | 2021-01-30 20:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 20:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91715 | WBS.2.1.11.3.1.1 | N | N |  | Ramp Down ¦ Purchase Order Conversion Ramp Down Prep Activity | 174.5 | 2021-01-18 06:15 | 2021-01-30 20:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 20:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82718 | WBS.2.1.11.3.1.1.1 | N | N | Planned | Provide list to RTR to clear aged credits and invalid sub-debits- Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | RANJAI JOHN | RANJAI.JOHN@KOCHTC.COM | RICARDO OLIVEIRA;JHANSI NAIDUVARI;SANDRA RICHARDS;DONNA SMITH;SAI TEAM;LAURA FRY;RTR TEAM;CHRIS GENTRY;DENISE MARSH;BOATENG LAWRENCE | RICARDO.OLIVEIRA@GAPAC.COM;JHANSI.NAIDUVARI@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;CHRIS.GENTRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82719 | WBS.2.1.11.3.1.1.2 | N | N | Planned | Provide list to RTR to clear aged credits and invalid sub-debits- Round 2 | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | RANJAI JOHN | RANJAI.JOHN@KOCHTC.COM | RICARDO OLIVEIRA;JHANSI NAIDUVARI;SANDRA RICHARDS;DONNA SMITH;SAI TEAM;LAURA FRY;RTR TEAM;CHRIS GENTRY;DENISE MARSH;BOATENG LAWRENCE | RICARDO.OLIVEIRA@GAPAC.COM;JHANSI.NAIDUVARI@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;CHRIS.GENTRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | RTR - GL | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
82720 | WBS.2.1.11.3.1.1.3 | N | N | Planned | Provide list to RTR to clear aged credits and invalid sub-debits- Round 3 | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | RANJAI JOHN | RANJAI.JOHN@KOCHTC.COM | RICARDO OLIVEIRA;JHANSI NAIDUVARI;SANDRA RICHARDS;DONNA SMITH;SAI TEAM;LAURA FRY;RTR TEAM;CHRIS GENTRY;DENISE MARSH;BOATENG LAWRENCE | RICARDO.OLIVEIRA@GAPAC.COM;JHANSI.NAIDUVARI@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;CHRIS.GENTRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | RTR - GL | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82683 | WBS.2.1.11.3.1.1.4 | N | N | Planned | Provide Open PO Report for WBS for AS8 - Round 1 | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;ERIC BARSTOW;SAI TEAM;DOROTHY RUSSELL;PTP TEAM | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | PTP | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82691 | WBS.2.1.11.3.1.1.5 | N | N | Planned | Provide Open PO Report for WBS for ECC - Round 1 | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;SHRISH MUDRI;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;SHRISH.MUDRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 80788 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82687 | WBS.2.1.11.3.1.1.6 | N | N | Planned | Add missing WBS Elements for AS8 to Project Xref - Round 1 | 1 | 2021-01-20 14:45 | 2021-01-20 15:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BRETT DETTMERING | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82683,94741 |  |  | * |  | 2021-01-20 14:45 | 2021-01-20 15:45 | RTR - PS | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82695 | WBS.2.1.11.3.1.1.7 | N | N | Planned | Add missing WBS Elements for ECC to Project Xref - Round 1 | 2 | 2021-01-20 15:45 | 2021-01-20 17:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;SAI TEAM;RTR TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82691,82687 |  |  | * |  | 2021-01-20 15:45 | 2021-01-20 17:45 | RTR - PS | PTH | 2021-01-20 | 2021-01-20 | 1 | Ramp Down
82692 | WBS.2.1.11.3.1.1.8 | N | N | Planned | Provide Open PO Report for WBS for ECC - Round 2 (Production Only) | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;SHRISH MUDRI;SAI TEAM;PTP TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;SHRISH.MUDRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | PTP | PTH,HBG,BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82684 | WBS.2.1.11.3.1.1.9 | N | N | Planned | Provide Open PO Report for WBS for AS8 - Round 2 (Production Only) | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;ERIC BARSTOW;SAI TEAM;PTP TEAM | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | PTP | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82688 | WBS.2.1.11.3.1.1.10 | N | N | Planned | Add missing WBS Elements for AS8 to Project Xref - Round 2 (Production Only) | 0.75 | 2021-01-26 07:15 | 2021-01-26 08:00 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BRETT DETTMERING | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82684 |  |  | * |  | 2021-01-26 07:15 | 2021-01-26 08:00 | RTR - PS | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82696 | WBS.2.1.11.3.1.1.11 | N | N | Planned | Add missing WBS Elements for ECC to Project Xref - Round 2 (Production Only) | 1 | 2021-01-26 08:00 | 2021-01-26 09:00 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;SAI TEAM;RTR TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82692,82688 |  |  | * |  | 2021-01-26 08:00 | 2021-01-26 09:00 | RTR - PS | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82693 | WBS.2.1.11.3.1.1.12 | N | N | Planned | Provide Open PO Report for WBS for ECC - Round 3 (Production Only) | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;SHRISH MUDRI;SAI TEAM;PTP TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;SHRISH.MUDRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | PTP | PTH,HBG,BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82685 | WBS.2.1.11.3.1.1.13 | N | N | Planned | Provide Open PO Report for WBS for AS8 - Round 3 (Production Only) | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;ERIC BARSTOW;SAI TEAM;PTP TEAM | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82689 | WBS.2.1.11.3.1.1.14 | N | N | Planned | Add missing WBS Elements for AS8 to Project Xref - Round 3 (Production Only) | 1 | 2021-01-29 07:15 | 2021-01-29 08:15 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BRETT DETTMERING | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82685 |  |  | * |  | 2021-01-29 07:15 | 2021-01-29 08:15 | RTR - PS | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82697 | WBS.2.1.11.3.1.1.15 | N | N | Planned | Add missing WBS Elements for ECC to Project Xref - Round 3 (Production Only) | 1 | 2021-01-29 08:15 | 2021-01-29 09:15 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;SAI TEAM;RTR TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82693,82689 |  |  | * |  | 2021-01-29 08:15 | 2021-01-29 09:15 | RTR - PS | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92649 | WBS.2.1.11.3.1.1.16 | N | N | Planned | Identify WBS Elements with TECO status that are required for PO Conversion and set status to REL | 1 | 2021-01-29 09:15 | 2021-01-29 10:15 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;SAI TEAM;RTR TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 82697 |  |  | * |  | 2021-01-29 09:15 | 2021-01-29 10:15 | RTR - PS | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82716 | WBS.2.1.11.3.1.1.17 | N | N | Planned | Run AS8 Open PO Dollar Amount report to be used for PO baseline data and upload to SharePoint | 0.5 | 2021-01-30 19:15 | 2021-01-30 19:45 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;DOROTHY RUSSELL;SRUTHI SRINIVASAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;ERIC BARSTOW;PTP TEAM;DAVID COOK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP | 5251,82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:45 | PTP | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82717 | WBS.2.1.11.3.1.1.18 | N | N | Planned | Run AS8 Open Service PO Dollar Amount report to be used for PO baseline data and upload to SharePoint | 0.5 | 2021-01-30 19:15 | 2021-01-30 19:45 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;DOROTHY RUSSELL;CASEY HERMANSEN;ERIC BARSTOW;PTP TEAM;DAVID COOK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP | 5251,82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:45 | PTP | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90005 | WBS.2.1.11.3.1.1.19 | N | N | Planned | Run UVL Report for AS8 facilities to be used for GR/IR baseline data and upload to SharePoint | 1 | 2021-01-30 19:15 | 2021-01-30 20:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | ERIC BARSTOW;CASEY HERMANSEN;DOROTHY RUSSELL;DON ABBOTT;SAI TEAM;PTP TEAM;DAVID COOK | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP | 82189 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 20:15 | PTP | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94292 | WBS.2.1.11.3.1.1.20 | N | N | Planned | Add UVL POs into the AS8 Baseline | 1 | 2021-01-30 19:45 | 2021-01-30 20:45 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | PTP TEAM;CHARLES BLUMREICH;ERIC BARSTOW;SAI TEAM;KRISTINA KAUTH | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;CHARLES.BLUMREICH@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTINA.KAUTH@GAPAC.COM | PTP | 82716,82717 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:45 | PTP | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
82290 | WBS.2.1.11.4 | N | N |  | Ramp Down ¦ Subcon-BoM Conversion Process for POs | 1.25 | 2021-01-22 17:00 | 2021-01-22 18:15 | [8 empty] | * |  | 2021-01-22 17:00 | 2021-01-22 18:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
90169 | WBS.2.1.11.4.1 | N | N |  | Ramp Down ¦ Subcon-BoM Conversion Process for POs Activity | 1.25 | 2021-01-22 17:00 | 2021-01-22 18:15 | [8 empty] | * |  | 2021-01-22 17:00 | 2021-01-22 18:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
91716 | WBS.2.1.11.4.1.1 | N | N |  | Ramp Down ¦ Subcon-BoM Conversion Process for POs Activity | 1.25 | 2021-01-22 17:00 | 2021-01-22 18:15 | [8 empty] | * |  | 2021-01-22 17:00 | 2021-01-22 18:15 |  |  | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
89840 | WBS.2.1.11.4.1.1.1 | N | N | Planned | PTM-WM Provide MDM list of subcontractor vendor ship-to for setting delivery priority 9 from PIR table EINE type 3 and D4 plants | 0.25 | 2021-01-22 17:00 | 2021-01-22 17:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | BRIAN LEMOND;SAI TEAM;ARNAB DEY;JEFFREY GOLDMUNTZ;EWM TEAM | BDLEMOND@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5246,5251 |  |  | * |  | 2021-01-22 17:00 | 2021-01-22 17:15 | EWM | ALL | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
89841 | WBS.2.1.11.4.1.1.2 | N | N | Planned | Change ship-to delivery priority to '9' for list provided by EWM | 1 | 2021-01-22 17:15 | 2021-01-22 18:15 | SUSAN MONTALVO | SUSAN.MONTALVO@GAPAC.COM | DENISE ROBINSON;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 89840 |  |  | * |  | 2021-01-22 17:15 | 2021-01-22 18:15 | DATA | CROSS | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
82087 | WBS.2.1.11.5 | N | N |  | Ramp Down ¦ STO Conversion Steps | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90166 | WBS.2.1.11.5.1 | N | N |  | Ramp Down ¦ STO Conversion Step Activity | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
91717 | WBS.2.1.11.5.1.1 | N | N |  | Ramp Down ¦ STO Conversion Step Activity | 2.5 | 2021-01-18 06:15 | 2021-01-18 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 08:45 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82090 | WBS.2.1.11.5.1.1.3 | N | N | Planned | Request production security access to SAP ECC P40 and CPG AS8 Production for Eric Barstow, Charles Blumreich and David Cook (Key transactions PO Change, Output change) | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;BRUCE KIRKLEWSKI;CASEY HERMANSEN;CHARLES BLUMREICH;YUDHAJIT MITRA;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | PTP | CROSS | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82089 | WBS.2.1.11.5.1.1.4 | N | N | Planned | Update delivery complete indicator for PO’s that are fully received or within a 5% tolerance. Identify non-FG/PR STOs - determine if they are to be closed before freeze (MRO, RM, etc.) | 1 | 2021-01-18 06:45 | 2021-01-18 07:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;BRUCE KIRKLEWSKI;CASEY HERMANSEN;CHARLES BLUMREICH;YUDHAJIT MITRA;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 82090 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:45 | PTP | PTH,HBG,BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95430 | WBS.2.1.11.5.1.1.5 | N | N | Planned | Execute catch up job for ERS processing (Program: RMMR1MRS) | 1 | 2021-01-18 07:45 | 2021-01-18 08:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 82089 |  |  | * |  | 2021-01-18 07:45 | 2021-01-18 08:45 | BATCH | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90163 | WBS.2.1.11.6 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports FCW | 6.75 | 2021-01-30 18:15 | 2021-01-31 01:00 | [8 empty] | * |  | 2021-01-30 18:15 | 2021-01-31 01:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
91053 | WBS.2.1.11.6.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups | 6.75 | 2021-01-30 18:15 | 2021-01-31 01:00 | [8 empty] | * |  | 2021-01-30 18:15 | 2021-01-31 01:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
91131 | WBS.2.1.11.6.1.1 | N | N |  | Ramp Down ¦ Tech Activities - Pre-Conversions - Pre-Transports – System Back-Ups | 6.75 | 2021-01-30 18:15 | 2021-01-31 01:00 | [8 empty] | * |  | 2021-01-30 18:15 | 2021-01-31 01:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
96913 | WBS.2.1.11.6.1.1.2 | N | N | Planned | Preparation - Backup before Downtime - S4 | 4 | 2021-01-30 18:15 | 2021-01-30 22:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 90821,97238 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 22:15 | DEV - INFRA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96895 | WBS.2.1.11.6.1.1.3 | N | N | Planned | Pre-Processing - Backup before Downtime - MDG | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;SHARATH RENIKUNTA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SRENIKUNTA@DELOITTE.COM | DEV | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
96889 | WBS.2.1.11.6.1.1.4 | N | N | Planned | Pre-Processing - Backup before Downtime - GW | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;PRASANNA KAPANIGOWDA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM | DEV | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
96882 | WBS.2.1.11.6.1.1.5 | N | N | Planned | Pre-Processing - Backup before Downtime - PO | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;Sujit Sandbhor | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;ssandbhor@deloitte.com | DEV | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
92148 | WBS.2.1.11.6.1.1.6 | N | N | Planned | Disable all triggers in Digital Core Production Environments | 0.25 | 2021-01-30 23:45 | 2021-01-31 | DON BIGALKE | DONALD.BIGALKE@KBSLP.COM | NNEKA MBA;SUNIL KORI;MAMIE TREZVANT;LSA TEAM;SAI TEAM;KELLY HINSON;SURESH P;KESAVA BATTINA;PREETAM ROUT | NEMBA@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;suresh.p@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;preetam.rout@kochtc.com | BATCH | 95633 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 | BATCH | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97420 | WBS.2.1.11.6.1.1.116 | N | N | Planned | Reprocess failed CI9 messages in POP Middleware - Round 2 | 1 | 2021-01-31 | 2021-01-31 01:00 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;ANKIT SONI;PAYEL GHOSH;RADHIKA RASTOGI;SUVENDU KUMAR;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANKISONI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92148 |  |  | * |  | 2021-01-31 | 2021-01-31 01:00 | DEV-INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97751 | WBS.2.1.11.6.1.1.117 | N | N | Planned | Validate if jobs are still running in S4. Also check SM66 for any RFC calls from GRC, GW, MDG | 0.5 | 2021-01-31 | 2021-01-31 00:30 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;VENKATESH GANESHAN;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92148 |  |  | * |  | 2021-01-31 | 2021-01-31 00:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97752 | WBS.2.1.11.6.1.1.118 | N | N | Planned | Stop replication in SLP | 0.25 | 2021-01-31 | 2021-01-31 00:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92148 |  |  | * |  | 2021-01-31 | 2021-01-31 00:15 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97753 | WBS.2.1.11.6.1.1.119 | N | N | Planned | Validate if any SM13 Failed update requests/messages are present in S4 before downtime starts | 0.25 | 2021-01-31 00:30 | 2021-01-31 00:45 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;VENKATESH GANESHAN;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 97751,97752 |  |  | * |  | 2021-01-31 00:30 | 2021-01-31 00:45 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
90927 | WBS.2.1.12 | N | N |  | Ramp Down ¦ Reporting Activities | 81 | 2021-01-18 06:15 | 2021-01-25 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
9548 | WBS.2.1.12.1 | N | N |  | Ramp Down ¦ Update EHANA Control Table | 81 | 2021-01-18 06:15 | 2021-01-25 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
90933 | WBS.2.1.12.1.1 | N | N |  | Ramp Down ¦ Update EHANA Control Table | 81 | 2021-01-18 06:15 | 2021-01-25 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91718 | WBS.2.1.12.1.1.1 | N | N |  | Ramp Down ¦ Update EHANA Control Table | 81 | 2021-01-18 06:15 | 2021-01-25 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94937 | WBS.2.1.12.1.1.1.1 | N | N | Planned | Clean up of Delivery xref table | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | TRISHUL BUDDHA;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | TBUDDHA@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | OTC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
82497 | WBS.2.1.12.1.1.1.2 | N | N | Planned | EHANA control table (rpt_cpg.reuse.md::PLANT_S4_DATES) to be updated | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | DWIGHT WORRELL | DLWORREL@GAPAC.COM | LISA HEROLD;ABHINAV SAXENA;SAI TEAM;RPT TEAM;PANKAJ SINGH;ATUL KUMAR AGNIHOTRI | LISA.HEROLD@GAPAC.COM;ABSAXENA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ABSAXENA@DELOITTE.COM;ATAGNIHOTRI@DELOITTE.COM;SSANJEEV@DELOITTE.COM;BRIAN.RIDENHOUR@GAPAC.COM;DAVID.MILLER3@GAPAC.COM;DLWORREL@GAPAC.COM;LISA.HEROLD@GAPAC.COM;MARK.GILSON@GAPAC.COM;PANKASINGH@DELOITTE.COM;PANKASINGH@DELOITTE.COM;ATAGNIHOTRI@DELOITTE.COM | RPT | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RPT | ATL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97571 | WBS.2.1.12.1.1.1.3 | N | N | Planned | Update RTR CPV extract to include the new live company codes (plants) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | LISA HEROLD | LISA.HEROLD@GAPAC.COM | ABHISHEK SINGH;SAI TEAM;RPT TEAM | abhishek.singh@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ABSAXENA@DELOITTE.COM;ATAGNIHOTRI@DELOITTE.COM;SSANJEEV@DELOITTE.COM;BRIAN.RIDENHOUR@GAPAC.COM;DAVID.MILLER3@GAPAC.COM;DLWORREL@GAPAC.COM;LISA.HEROLD@GAPAC.COM;MARK.GILSON@GAPAC.COM;PANKASINGH@DELOITTE.COM | RPT | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RPT | ATL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
10530 | WBS.2.1.13 | N | N |  | Ramp Down ¦ Business Activities | 186.5 | 2021-01-18 06:15 | 2021-01-31 08:45 | [8 empty] | * |  | 2021-01-18 06:00 | 2021-01-31 03:15 |  | ALL | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
91807 | WBS.2.1.13.1 | N | N |  | Ramp Down ¦ Business Activities - Atlanta | 173.5 | 2021-01-18 06:15 | 2021-01-30 19:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91811 | WBS.2.1.13.1.1 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Prep Activities | 157 | 2021-01-18 06:15 | 2021-01-29 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 17:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91818 | WBS.2.1.13.1.1.2 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Prep Activities - OTC | 154.75 | 2021-01-18 06:15 | 2021-01-29 17:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 17:00 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10743 | WBS.2.1.13.1.1.2.1 | N | N | Planned | ATL - Schedule appt's as far forward as possible according cutover routing schedule for D4 | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | HEATHER SWOKOWSK | HEATHER.SWOKOWSKI@KBXLOGISTICS.COM | TIFFANY HINZ;JOHN NATZKE;DON ABBOTT;JOHN CASABURRI;SAI TEAM;ANDREW HELMANN | TIFFANY.HINZ@KBXLOGISTICS.COM;JOHN.NATZKE@KBXLOGISTICS.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Andrew.Helmann@kbxlogistics.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | OTC - KBX | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97633 | WBS.2.1.13.1.1.2.9 | N | N | Planned | ATL - PREP - START - VMI reps manage customer inventory levels to prevent or minimize shipping from Deployment Facilities over the cut-over period - Retail | 3.25 | 2021-01-18 17:15 | 2021-01-18 20:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 94284 |  |  | * |  | 2021-01-18 17:15 | 2021-01-18 20:30 | OTC - OM | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10705 | WBS.2.1.13.1.1.2.3 | N | N | Planned | ATL - RETAIL/PRO - PREP - Goods issue all CPU and delivery loads - Deployment Facilities | 2 | 2021-01-26 06:15 | 2021-01-26 08:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 08:15 | OTC - OM | ATL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
10740 | WBS.2.1.13.1.1.2.5 | N | N | Planned | ATL - Start extra attention to assign D4 facility returns | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | ANNA LEISNER | ANNA.LEISNER@KBXLOGISTICS.COM | DON ABBOTT;JOHN CASABURRI;SAI TEAM;JOHN NATZKE;ANDREW HELMANN;KARI LADE | DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.NATZKE@KBXLOGISTICS.COM;Andrew.Helmann@kbxlogistics.com;kari.lade@kbxlogistics.com | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:30 | OTC - KBX | ATL | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
82303 | WBS.2.1.13.1.1.2.7 | N | N | Planned | ATL - Ensure Returns filters for D4 are clean | 0.25 | 2021-01-29 13:30 | 2021-01-29 13:45 | ANNA LEISNER | ANNA.LEISNER@KBXLOGISTICS.COM | DON ABBOTT;JOHN CASABURRI;SAI TEAM;JOHN NATZKE;ANDREW HELMANN;KARI LADE | DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.NATZKE@KBXLOGISTICS.COM;Andrew.Helmann@kbxlogistics.com;kari.lade@kbxlogistics.com | Business | 81826,92310 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 13:45 | OTC - KBX | ATL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90457 | WBS.2.1.13.1.1.2.8 | N | N | Planned | ATL - Communicate business continuity form for 3rd party sales order process until go-live | 0.5 | 2021-01-29 15:00 | 2021-01-29 15:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10623 |  |  | * |  | 2021-01-29 15:00 | 2021-01-29 15:30 | OTC - OM | ATL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97805 | WBS.2.1.13.1.1.2.10 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF - Run Open Order List (Deployment Facilities) | 1.5 | 2021-01-29 15:30 | 2021-01-29 17:00 | CHRIS FRENCH | CFRENCH@GAPAC.COM | JEFF WAGNER;OTC TEAM;SAI TEAM | JEFFREY.WAGNER@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90457 |  |  | * |  | 2021-01-29 15:30 | 2021-01-29 17:00 | OTC - OM | ATL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91819 | WBS.2.1.13.1.1.3 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Prep Activities - EWM | 31.75 | 2021-01-27 06:15 | 2021-01-29 00:15 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-29 00:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82207 | WBS.2.1.13.1.1.3.1 | N | N | Planned | Update all invoice payment due dates in CPG AS8 for Live facilities | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | ALYSSA BAIRD;SAI TEAM;ANNA FLANAGAN;ERIC BARSTOW;MASON DRAKE;PTP TEAM;DAVID COOK | ALYSSA.BAIRD@KBSLP.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANNA.FLANAGAN@KBSLP.COM;ERIC.BARSTOW@GAPAC.COM;MASON.DRAKE@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | PTP | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82206 | WBS.2.1.13.1.1.3.2 | N | N | Planned | Run report of all remaining invoices on hold, not approved, or credits (Round 1) | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;PTP TEAM;ALYSSA BAIRD;ANNA FLANAGAN;ERIC BARSTOW;MASON DRAKE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ALYSSA.BAIRD@KBSLP.COM;ANNA.FLANAGAN@KBSLP.COM;ERIC.BARSTOW@GAPAC.COM;MASON.DRAKE@GAPAC.COM | PTP | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | PTP | ATL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
82205 | WBS.2.1.13.1.1.3.3 | N | N | Planned | Place all remaining AS8 invoices to canceled | 0.25 | 2021-01-28 20:00 | 2021-01-28 20:15 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | PAM NIX;PTP TEAM;SAI TEAM | PSNIX@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 97551 |  |  | * |  | 2021-01-28 20:00 | 2021-01-28 20:15 | PTP | ATL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
82204 | WBS.2.1.13.1.1.3.4 | N | N | Planned | Pull report of all Credits for both ECC and AS8 by supplier by facility to determine if any invoices will not pay, send to AP Governance (Round 3+) | 0.25 | 2021-01-28 20:15 | 2021-01-28 20:30 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | ALYSSA BAIRD;SAI TEAM;ANNA FLANAGAN;ERIC BARSTOW;MASON DRAKE;PTP TEAM;DAVID COOK;ALYSHIA RASMUSSEN | ALYSSA.BAIRD@KBSLP.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANNA.FLANAGAN@KBSLP.COM;ERIC.BARSTOW@GAPAC.COM;MASON.DRAKE@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM | PTP | 82205 |  |  | * |  | 2021-01-28 20:15 | 2021-01-28 20:30 | PTP | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
82203 | WBS.2.1.13.1.1.3.5 | N | N | Planned | Run final invoice update of payment due dates for Dx facilities | 3 | 2021-01-28 20:15 | 2021-01-28 23:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;PTP TEAM;DAVID COOK;ALYSSA BAIRD;ANNA FLANAGAN;ERIC BARSTOW;MASON DRAKE;ALYSHIA RASMUSSEN | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM;ALYSSA.BAIRD@KBSLP.COM;ANNA.FLANAGAN@KBSLP.COM;ERIC.BARSTOW@GAPAC.COM;MASON.DRAKE@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM | PTP | 82205 |  |  | * |  | 2021-01-28 20:15 | 2021-01-28 23:15 | PTP | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97550 | WBS.2.1.13.1.1.3.6 | N | N | Planned | Run script to stop all invoices for Dx deployment into AS8 | 1 | 2021-01-28 23:15 | 2021-01-29 00:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;PTP TEAM;DAVID COOK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP | 82203 |  |  | * |  | 2021-01-28 23:15 | 2021-01-29 00:15 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97551 | WBS.2.1.13.1.1.3.7 | N | N | Planned | Pull report of all Credits for both ECC and AS8 by supplier by facility to determine if any invoices will not pay, send to AP Governance (Round 2) | 1 | 2021-01-28 19:00 | 2021-01-28 20:00 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | SAI TEAM;PTP TEAM;DAVID COOK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DAVID.COOK@GAPAC.COM | PTP |  |  |  |  | 2021-01-28 19:00 | 2021-01-28 19:00 | 2021-01-28 20:00 | PTP | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
90076 | WBS.2.1.13.1.1.4 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Prep Activities - DATA | 8 | 2021-01-18 06:15 | 2021-01-18 14:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 14:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
90074 | WBS.2.1.13.1.1.4.1 | N | N | Planned | Close out open material workflows and ramp down/initiate material freeze at deployment live plants | 8 | 2021-01-18 06:15 | 2021-01-18 14:15 | JOAN SEIDL | JOAN.SEIDL@GAPAC.COM | KRISTEN DERINGER;LINDSAY SAVAGE;AMY EL-BASSIONI;DENISE ROBINSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | KLDERING@GAPAC.COM;LINDSAY.SAVAGE@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 14:15 | MDM - FG Material | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
37000 | WBS.2.1.13.1.1.5 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Prep Activities - EIM | 157 | 2021-01-18 06:15 | 2021-01-29 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 17:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90413 | WBS.2.1.13.1.1.5.1 | N | N | Planned | Run reports for open invoices in ECC and AS8 Ariba realms and in AS8 for open Sig. Contract invoices, then notify users to resolve before cutover | 5 | 2021-01-18 07:30 | 2021-01-18 12:30 | BETH MYERS | BETH.MYERS@GAPAC.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 12:30 | EIM | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95288 | WBS.2.1.13.1.1.5.2 | N | N | Planned | Review the facility lists for ECC and AS8 on the EIM SharePoint and provide EIM (Teresa & Pam) which facilities should be moved to S/4 or inactivated | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EIM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97167 | WBS.2.1.13.1.1.5.10 | N | N | Planned | Send the list of facilities moving realms to the AP Gov Team and Datacap teams, Beth, Abby, and Mark Burgin | 0.25 | 2021-01-18 07:15 | 2021-01-18 07:30 | PAM NIX | PSNIX@GAPAC.COM | MYRA BATES;SAI TEAM;PTP TEAM | MYRA.BATES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10846,95288 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:30 | EIM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97166 | WBS.2.1.13.1.1.5.9 | N | N | Planned | Start the prep of notifying suppliers about the upcoming PO conversion and expectations | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;WILL STINSON;ABBY DREVIK;PAM NIX;SAI TEAM;PTP TEAM | MARK.BURGIN@GAPAC.COM;william.stinson@gapac.com ;abigail.drevik@gapac.com;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | EIM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97628 | WBS.2.1.13.1.1.5.15 | N | N | Planned | New Push Fails in AS8 & ECC for converted facilities need to be resolved | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | Carrol Steele-Smith | carrol.steele-smith@kbslp.com | PAM NIX;SANDEE LAUDRE;ANNA FLANAGAN;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;SANDRA.LAUNDRE@GAPAC.COM;ANNA.FLANAGAN@KBSLP.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EIM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
83210 | WBS.2.1.13.1.1.5.4 | N | N | Planned | Expire ECC And AS8 PWRs For Converting Facilities in Ariba | 1 | 2021-01-18 07:30 | 2021-01-18 08:30 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | ANNA FLANAGAN;PAM NIX;SAI TEAM;PTP TEAM | ANNA.FLANAGAN@KBSLP.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 08:30 | EIM | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
83211 | WBS.2.1.13.1.1.5.5 | N | N | Planned | Create S/4HANA PWRs For Converting Facilities in Ariba | 1 | 2021-01-18 07:30 | 2021-01-18 08:30 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | ANNA FLANAGAN;PAM NIX;SAI TEAM;PTP TEAM | ANNA.FLANAGAN@KBSLP.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 08:30 | EIM | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97514 | WBS.2.1.13.1.1.5.14 | N | N | Planned | Focus effort needed to clear Push Fails in AS8 & ECC for converted facilities | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | Carrol Steele-Smith | carrol.steele-smith@kbslp.com | PAM NIX;SANDEE LAUDRE;ANNA FLANAGAN;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;SANDRA.LAUNDRE@GAPAC.COM;ANNA.FLANAGAN@KBSLP.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | EIM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97513 | WBS.2.1.13.1.1.5.13 | N | N | Planned | AS8 Open Items have to be resovled prior to cutover | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | ANNA FLANAGAN;PAM NIX;SAI TEAM;PTP TEAM | ANNA.FLANAGAN@KBSLP.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97167 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | EIM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97512 | WBS.2.1.13.1.1.5.12 | N | N | Planned | AS8 Open Items have to be cancelled prior to cutover in advance of FCW | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | ANNA FLANAGAN;PAM NIX;SAI TEAM;PTP TEAM | ANNA.FLANAGAN@KBSLP.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EIM | ALL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97511 | WBS.2.1.13.1.1.5.11 | N | N | Planned | New AS8 Open Items have to be cancelled right before cutover | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | ALYSSA BAIRD | ALYSSA.BAIRD@KBSLP.COM | ANNA FLANAGAN;PAM NIX;SAI TEAM;PTP TEAM | ANNA.FLANAGAN@KBSLP.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EIM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10701 | WBS.2.1.13.1.1.5.16 | N | N | Planned | ATL - RETAIL/PRO - CLEAN UP-Check for Shipped but not Invoiced and process billing for all goods issued loads | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | OTC - OM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95224 | WBS.2.1.13.1.1.5.7 | N | N | Planned | ATL - Final run of carrier assignment of outbound and transfer loads from PTH,HBG,SCH,BG,RNC,RVG,SAT,REX according to cutover routing schedule | 1 | 2021-01-29 13:30 | 2021-01-29 14:30 | Rachelle Chikowski | rachelle.chikowski@kbxlogistics.com | OTC TEAM;SAI TEAM;JOHN NATZKE;ANDREW HELMANN;Brock McCain | PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.NATZKE@KBXLOGISTICS.COM;Andrew.Helmann@kbxlogistics.com;Brock.McCain@kbxlogistics.com | Business | 81826,92310,91227 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 14:30 | OTC - KBX | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95225 | WBS.2.1.13.1.1.5.8 | N | N | Planned | ATL - Within TOPS - Flag all D4 ECC DN's to wait for replacement DN (1st list provided by OTC-OM) | 2 | 2021-01-29 17:15 | 2021-01-29 19:15 | DAVE LEGOIS | DAVID.LEGOIS@KBXLOGISTICS.COM | TOM OLIVE;JOHN NATZKE;OTC TEAM;SAI TEAM;ANDREW HELMANN | THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.NATZKE@KBXLOGISTICS.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Andrew.Helmann@kbxlogistics.com | Business | 95226,97805 |  |  | * |  | 2021-01-29 15:15 | 2021-01-29 17:15 | OTC - KBX | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91810 | WBS.2.1.13.1.2 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Clean-Up Activities | 87.75 | 2021-01-18 06:30 | 2021-01-25 14:15 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-25 14:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91814 | WBS.2.1.13.1.2.1 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Clean-Up Activities - RTR | 80 | 2021-01-18 06:30 | 2021-01-25 06:30 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-25 06:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
36516 | WBS.2.1.13.1.2.1.1 | N | N | Planned | ATL - Ensure that tax accounts are reconciled prior to cutover | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | RTR - Tax | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36518 | WBS.2.1.13.1.2.1.2 | N | N | Planned | ATL - Validate and record tax GL balances from ECC | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | RTR - Tax | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36517 | WBS.2.1.13.1.2.1.3 | N | N | Planned | ATL - Ensure all ECC data required for quarterly and annual returns has been captured | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | RTR - Tax | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
36519 | WBS.2.1.13.1.2.1.4 | N | N | Planned | ATL - Review and close applicable ARO Internal orders | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DAVID HOFFMAN | DAVID.HOFFMAN2@GAPAC.COM | DANNY NGUYEN;BRETT DETTMERING;DON ABBOTT;JOHN CASABURRI;SAI TEAM | DANNY.NGUYEN@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | RTR - GL | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91816 | WBS.2.1.13.1.2.2 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Clean-Up Activities - OTC | 86 | 2021-01-18 08:15 | 2021-01-25 14:15 | [8 empty] | * |  | 2021-01-18 08:15 | 2021-01-25 14:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94281 | WBS.2.1.13.1.2.2.1 | N | N | Planned | ATL - Start Task - Ship Deployment Facility Orders early to avoid shipping during cutover period - PRO | 2 | 2021-01-18 08:15 | 2021-01-18 10:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10701 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 10:15 | OTC - OM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10724 | WBS.2.1.13.1.2.2.2 | N | N | Planned | ATL - RETAIL/PRO - CLEAN UP-Cancel or update all delivery relevant sales orders with delivery dates in the past (Deployment Facilities) | 2 | 2021-01-18 10:15 | 2021-01-18 12:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 94281 |  |  | * |  | 2021-01-18 10:15 | 2021-01-18 12:15 | OTC - OM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94285 | WBS.2.1.13.1.2.2.5 | N | N | Planned | ATL - RETAIL/PRO - PREP - Alternate Source Customer Shipments from Deployment Facilities | 2 | 2021-01-18 12:15 | 2021-01-18 14:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10724 |  |  | * |  | 2021-01-18 12:15 | 2021-01-18 14:15 | OTC - OM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94284 | WBS.2.1.13.1.2.2.6 | N | N | Planned | ATL - RETAIL/PRO - PREP - Convert all CPU Customers from Deployment Facilities to be Vendor shipped or Alt Sourced | 3 | 2021-01-18 14:15 | 2021-01-18 17:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 94285 |  |  | * |  | 2021-01-18 14:15 | 2021-01-18 17:15 | OTC - OM | ALL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
10716 | WBS.2.1.13.1.2.2.9 | N | N | Planned | ATL - RETAIL/PRO - CLEAN UP-Third Party order Clean-up (Deployment Facilities) | 8 | 2021-01-18 20:30 | 2021-01-19 12:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 97633 |  |  | * |  | 2021-01-18 20:30 | 2021-01-19 12:30 | OTC - OM | ALL | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
10719 | WBS.2.1.13.1.2.2.10 | N | N | Planned | ATL - RETAIL/PRO - CLEAN UP-Process, Cancel or PGI/Credit any open returns from Deployment Facilities | 8 | 2021-01-25 06:15 | 2021-01-25 14:15 | RACHEL COLWITZ | RACHEL.COLWITZ@GAPAC.COM | MELISSA FOLEY;JEFF WAGNER;DON ABBOTT;JOHN CASABURRI;SAI TEAM;CHRIS FRENCH | MELISSA.FOLEY@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CFRENCH@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 14:15 | OTC - OM | ALL | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
91809 | WBS.2.1.13.1.3 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Cut-Off Activities | 173.5 | 2021-01-18 06:15 | 2021-01-30 19:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91813 | WBS.2.1.13.1.3.1 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Cut-Off Activities - RTR | 173.5 | 2021-01-18 06:15 | 2021-01-30 19:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:45 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95584 | WBS.2.1.13.1.3.1.2 | N | N | Planned | ATL - Validate new material/material group mappings in OneSource | 1 | 2021-01-27 07:00 | 2021-01-27 08:00 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 9178,5085,82774 |  |  | * |  | 2021-01-27 07:00 | 2021-01-27 08:00 | RTR - Tax | ATL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
36515 | WBS.2.1.13.1.3.1.1 | N | N | Planned | ATL - Clean up any existing tax credits created in ECC | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | MATT BURROUGHS | MATT.BURROUGHS@KOCHIND.COM | JENNIFER PENNER;DEAN WILSON;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JENNIFER.PENNER@kochind.com;DEAN.WILSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | RTR - Tax | ATL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
68565 | WBS.2.1.13.1.3.1.19 | N | N | Planned | ATL - Perform any Vendor Bucket adjustments for deploying sites prior to cutoff | 1.5 | 2021-01-30 18:15 | 2021-01-30 19:45 | TASHA WINKLE-DALLAS | TASHA.WINKLE-DALLAS@GAPAC.COM | BRETT DETTMERING;DON ABBOTT;JOHN CASABURRI;SAI TEAM;SAV RTR TEAM;IRINA HARDER | BRETT.DETTMERING@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;JAMIE.LAWHON@GAPAC.COM;JAMES.VICK@GAPAC.COM;JENNIFER.RICORD@GAPAC.COM;JJHONHAR@GAPAC.COM;COURTNEY.ARNSDORFF@GAPAC.COM;ANDREW.MAXEY@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;IRINA.HARDER@GAPAC.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:45 | RTR - GL | ATL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95567 | WBS.2.1.13.1.3.1.3 | N | N | Planned | PTH - Clear Vendor Blocked Invoices (ZAP 32) - Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Malinda Spaeth;ALYSHIA RASMUSSEN;JAZMINE STEINFELDT;LAURA FRY;DENISE MARSH | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Malinda.Spaeth@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;JAZMINE.STEINFELDT@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97118 | WBS.2.1.13.1.3.1.13 | N | N | Planned | HBG - Clear Blocked Invoices (ZAP 32) - Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;BRUCE KIRKLEWSKI;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;JAZMINE STEINFELDT;NICOLE FARLEY;LAURA FRY;DENISE MARSH | Avie.Lindsey@gapac.com;BRUCE.KIRKLEWSKI@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAZMINE.STEINFELDT@GAPAC.COM;NICOLE.FARLEY@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95566 | WBS.2.1.13.1.3.1.4 | N | N | Planned | PTH - Clear Vendor Blocked Invoices (ZAP 32) - Round 2 | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JAZMINE STEINFELDT;Malinda Spaeth | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAZMINE.STEINFELDT@GAPAC.COM;Malinda.Spaeth@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - GL | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92030 | WBS.2.1.13.1.3.2 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Cut-Off Activities - PTP | 49 | 2021-01-25 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-28 07:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97116 | WBS.2.1.13.1.3.2.11 | N | N | Planned | HBG - Clear Blocked Invoices (ZAP 32) - Round 2 | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;BRUCE KIRKLEWSKI;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;JAZMINE STEINFELDT;NICOLE FARLEY | Avie.Lindsey@gapac.com;BRUCE.KIRKLEWSKI@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAZMINE.STEINFELDT@GAPAC.COM;NICOLE.FARLEY@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - GL | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97114 | WBS.2.1.13.1.3.2.9 | N | N | Planned | HBG - Clear Blocked Invoices (ZAP 32) - Round 3 | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;BRUCE KIRKLEWSKI;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;JAZMINE STEINFELDT;NICOLE FARLEY | Avie.Lindsey@gapac.com;BRUCE.KIRKLEWSKI@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAZMINE.STEINFELDT@GAPAC.COM;NICOLE.FARLEY@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | RTR - GL | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95565 | WBS.2.1.13.1.3.2.15 | N | N | Planned | PTH - Clear Vendor Blocked Invoices (ZAP 32) - Round 3 | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JAZMINE STEINFELDT;Malinda Spaeth | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAZMINE.STEINFELDT@GAPAC.COM;Malinda.Spaeth@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | RTR - GL | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
94297 | WBS.2.1.13.1.3.2.1 | N | N | Planned | PTH - Send 10 Critical AS8 POs to Dorothy Russell to use in PO Validation | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | PTP | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94296 | WBS.2.1.13.1.3.2.3 | N | N | Planned | PTH - Send 10 Critical ECC POs to Mike Pupillo to use in PO Validation | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | PTP | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96627 | WBS.2.1.13.1.3.2.8 | N | N | Planned | BG - Send 10 Critical ECC POs to Mike Pupillo to use in PO Validation | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | Mark Bernard;SAI TEAM;DOUG CARANGELLO | MARK.BERNARD@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;* | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | PTP | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94409 | WBS.2.1.13.1.3.2.6 | N | N | Planned | HBG - Send 10 Critical ECC POs to Mike Pupillo to use in PO Validation | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | PTP | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95644 | WBS.2.1.13.1.3.2.7 | N | N | Planned | Send reports to buyers for Open Pos w/ UoM Mismatch & Pos Relevant for Final Invoice Flag | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MASON DRAKE;PTP TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;SANDEEP A | MASON.DRAKE@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | PTP | PTH,HBG,BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92031 | WBS.2.1.13.1.3.3 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Cut-Off Activities - SCM | 169.25 | 2021-01-18 06:15 | 2021-01-30 15:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 15:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94697 | WBS.2.1.13.1.3.3.1 | N | N | Planned | Validate PGI for STO's completed for All Plants in Current Deployment | 2.75 | 2021-01-30 12:15 | 2021-01-30 15:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;KETAN PRADHAN;PUNEET KUMAR;DON ABBOTT;JOHN NATZKE;TOM OLIVE;JOHN CASABURRI;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JOHN.NATZKE@KBXLOGISTICS.COM;THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:00 | SCM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94698 | WBS.2.1.13.1.3.3.2 | N | N | Planned | ReRun open STO list for All Plants in Current Deployment | 0.5 | 2021-01-30 15:00 | 2021-01-30 15:30 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;PUNEET KUMAR;DON ABBOTT;JOHN NATZKE;TOM OLIVE;JOHN CASABURRI;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JOHN.NATZKE@KBXLOGISTICS.COM;THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 94697,92324 |  |  | * |  | 2021-01-30 15:00 | 2021-01-30 15:30 | SCM | CROSS | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95256 | WBS.2.1.13.1.3.3.3 | N | N | Planned | HBG - Create Planned orders for Semi finished goods HBG | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM;JOHN J SMITH;LISA SZCZUREK | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM | Business | 11032,95149,90831,9669,95314,95736,92236,97573,10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | SCM - TTN | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95123 | WBS.2.1.13.1.3.3.4 | N | N | Planned | Verify and convert production orders for Finished Goods & Semi finished goods - PTH/HBG/BG | 2 | 2021-01-29 14:15 | 2021-01-29 16:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | JOHN CASABURRI;SAI TEAM;SCM TEAM;BRAD WYMAN;JOHN J SMITH;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95256,95963 |  |  | * |  | 2021-01-29 14:15 | 2021-01-29 16:15 | SCM | CROSS | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97848 | WBS.2.1.13.1.3.3.21 | N | N | Planned | Remove Characteristics values from Obsolete work center | 2 | 2021-01-29 16:15 | 2021-01-29 18:15 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | JOHN CASABURRI;SAI TEAM;SCM TEAM;BRAD WYMAN;JOHN J SMITH;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-29 18:15 | SCM | CROSS | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95122 | WBS.2.1.13.1.3.3.6 | N | N | Planned | Validate production order in ICPAQS from S/4HANA-Semi Finished Goods | 0.25 | 2021-01-29 16:15 | 2021-01-29 16:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-29 16:30 | ICPAQS | PTH,HBG,SCH,BG,RCH,RVG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95736 | WBS.2.1.13.1.3.3.7 | N | N | Planned | D4 Sites - Delete SFG Planned Orders | 0.5 | 2021-01-28 11:30 | 2021-01-28 12:00 | ANUPAM SHRIVASTAVA | ANUPSHRIVASTAVA@DELOITTE.COM | CHIRAG PARIKH;SATISH KUMAR B;SAI TEAM;CHANDRA BALASUBRAMANIAN;SCM TEAM | CPARIKH@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com | SCM | 95314,97573 |  |  | * |  | 2021-01-28 11:30 | 2021-01-28 12:00 | SCM | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97148 | WBS.2.1.13.1.3.3.8 | N | N | Planned | Supply Planning - Communication; remove manual adjustments | 3 | 2021-01-28 06:45 | 2021-01-28 09:45 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 91863 |  |  | * |  | 2021-01-28 06:45 | 2021-01-28 09:45 | SCM | CROSS | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97172 | WBS.2.1.13.1.3.3.9 | N | N | Planned | Communicate Impact of IBP downtime to Demand Planners | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | David Rutan | dgrutan@gapac.com | ZACH WALKER;KRISTEN PAULY;SAI TEAM;JOHN CASABURRI;DON ABBOTT;BRAD WYMAN;MICHELLE SADLER | zach.walker@gapac.com;KRISTEN.PAULY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | SCM | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97349 | WBS.2.1.13.1.3.3.20 | N | N | Planned | Send list of Finite Planners User ID to Process team to add to C4 Settings table | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | JOHN J SMITH | JOHNJ.SMITH@GAPAC.COM | LISA SZCZUREK;MELISSA OLSEN;SAI TEAM | LISA.SZCZUREK@GAPAC.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | SCM - TTN | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97348 | WBS.2.1.13.1.3.3.19 | N | N | Planned | Finite Planers for next deployment to C4 Settings table | 1 | 2021-01-18 07:15 | 2021-01-18 08:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;MELISSA OLSEN;SAI TEAM;JOHN J SMITH | CBALASUBRAMANIAN@DELOITTE.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHNJ.SMITH@GAPAC.COM | Business | 97349 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 08:15 | SCM - TTN | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92033 | WBS.2.1.13.1.3.4 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Cut-Off Activities - OTC | 61 | 2021-01-27 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-30 19:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92326 | WBS.2.1.13.1.3.4.1 | N | N | Planned | Confirm delivery interim IDOCs in S4 are current – none in error status | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | AQUIL HUSAIN;EWM TEAM;OTC TEAM;SAI TEAM | AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 36501,81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EWM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90697 | WBS.2.1.13.1.3.4.2 | N | N | Planned | Delete deliveries in ECC (list provided by OTC-OM) | 2.75 | 2021-01-29 19:30 | 2021-01-30 06:15 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | CHRISTINE CROSBY;SAI TEAM;LSA TEAM;OTC TEAM;DOUG STANISLAWSKI;SUSAN RIELS;CHARLES SERWIN ;MARTY MURPHY ;EMANUEL VILLEGAS ;JAMES LANDRY | CCROSBY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;CHARLES.SERWIN@GAPAC.COM ;MURPHY.M@ELETTRIC80.IT ;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT | LSA | 36501,81706,95226,90694 |  |  | * |  | 2021-01-29 17:30 | 2021-01-29 20:15 | LSA | ALL | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
92324 | WBS.2.1.13.1.3.4.3 | N | N | Planned | Confirm shipment interim IDOCs in S4 are current – none in error status | 0.25 | 2021-01-29 14:30 | 2021-01-29 14:45 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | AQUIL HUSAIN;EWM TEAM;OTC TEAM;SAI TEAM | AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 95224,92228 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 14:45 | EWM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90694 | WBS.2.1.13.1.3.4.4 | N | N | Planned | Delete ECC shipments (list provided by OTC-OM) | 0.25 | 2021-01-29 19:15 | 2021-01-29 19:30 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | CHRISTINE CROSBY;SAI TEAM;LSA TEAM;OTC TEAM | CCROSBY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM | LSA | 95225,95226,90688 |  |  | * |  | 2021-01-29 17:15 | 2021-01-29 17:30 | LSA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92287 | WBS.2.1.13.1.3.4.5 | N | N | Planned | Validate Deliveries and Shipments are deleted in Legacy Systems JDA | 1 | 2021-01-30 06:15 | 2021-01-30 07:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;LSA TEAM;JACOB OWENS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JACOB.OWENS@GAPAC.COM | LSA | 90694,90697 |  |  | * |  | 2021-01-29 20:15 | 2021-01-29 21:15 | LSA | ALL | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
90858 | WBS.2.1.13.1.3.4.7 | N | N | Planned | Validate Deliveries and Shipments are deleted in Legacy Systems E80 | 1 | 2021-01-30 06:15 | 2021-01-30 07:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | LSA | 90697,90694 |  |  | * |  | 2021-01-29 20:15 | 2021-01-29 21:15 | E80 | ALL | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
10646 | WBS.2.1.13.1.3.4.8 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-**third party order cleanup** (page 14 of FDS) | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 07:15 | OTC - OM | ALL | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
10638 | WBS.2.1.13.1.3.4.15 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Clear all order blocks (ATP, Allocation, Partial, Pricing, Credit) Shipping from Deployment Facilities | 5.75 | 2021-01-29 06:15 | 2021-01-29 12:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 12:00 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
81826 | WBS.2.1.13.1.3.4.14 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Hold RELEASING Customer Orders from Deployment Facilities | 0.5 | 2021-01-29 12:00 | 2021-01-29 12:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10638 |  |  | * |  | 2021-01-29 12:00 | 2021-01-29 12:30 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91227 | WBS.2.1.13.1.3.4.9 | N | N | Planned | ATL - Complete FCS and LTL routing of outbound and transfers from PTH,HBG,SCH,BG,RNC,RVG,SAT,REX sites according to cutover routing schedule | 1 | 2021-01-29 12:30 | 2021-01-29 13:30 | ANNA LEISNER | ANNA.LEISNER@KBXLOGISTICS.COM | JOHN NATZKE;DON ABBOTT;JOHN CASABURRI;SAI TEAM;ANDREW HELMANN;KARI LADE | JOHN.NATZKE@KBXLOGISTICS.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Andrew.Helmann@kbxlogistics.com;kari.lade@kbxlogistics.com | Business | 81826 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:30 | OTC - KBX | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10615 | WBS.2.1.13.1.3.4.16 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Process all output documents (Proforma) | 0.5 | 2021-01-29 12:00 | 2021-01-29 12:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10638 |  |  | * |  | 2021-01-29 12:00 | 2021-01-29 12:30 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10604 | WBS.2.1.13.1.3.4.17 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Process/cancel/clear Deployment Facility orders from the EDI failure/workflow report | 0.5 | 2021-01-29 12:00 | 2021-01-29 12:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10638 |  |  | * |  | 2021-01-29 12:00 | 2021-01-29 12:30 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92310 | WBS.2.1.13.1.3.4.18 | N | N | Planned | Confirm order interim IDOCs in ECC – none in error status | 1 | 2021-01-29 12:30 | 2021-01-29 13:30 | VIVEK TALATI | VIVEK.TALATI@KOCHTC.COM | ONI BORCHERS;KYNDAL CODY;LSA TEAM;OTC TEAM;SAI TEAM | OCBORCHE@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 81826 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:30 | LSA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
82450 | WBS.2.1.13.1.3.4.20 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF - Ensure Open Orders have Plant assigned to order (To Non Deployment Facilities) | 2 | 2021-01-29 12:15 | 2021-01-29 14:15 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 14:15 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10661 | WBS.2.1.13.1.3.4.21 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Cancel or update all delivery relevant sales orders with delivery dates in the past (Deployment Facilities) | 0.25 | 2021-01-29 14:15 | 2021-01-29 14:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 82450 |  |  | * |  | 2021-01-29 14:15 | 2021-01-29 14:30 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
90688 | WBS.2.1.13.1.3.4.23 | N | N | Planned | Update variant - remove the D4 plants from ECC delivery due list | 1 | 2021-01-29 12:30 | 2021-01-29 13:30 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;ONI BORCHERS;VIVEK TALATI;ARNEL BAUTISTA;KYNDAL CODY;LSA TEAM;OTC TEAM;SAI TEAM | KEPRADHAN@DELOITTE.COM;OCBORCHE@GAPAC.COM;VIVEK.TALATI@KOCHTC.COM;AVBAUTIS@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 81826 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:30 | LSA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10652 | WBS.2.1.13.1.3.4.25 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Process, Cancel or PGI/Credit any open returns (Deployment Facilities) | 0.25 | 2021-01-29 14:30 | 2021-01-29 14:45 | RACHEL COLWITZ | RACHEL.COLWITZ@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10661 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 14:45 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10623 | WBS.2.1.13.1.3.4.26 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Hold processing of samples/no charge/OP5/intracompany orders and release by specified date from Deployment Facilities | 0.25 | 2021-01-29 14:45 | 2021-01-29 15:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10652 |  |  | * |  | 2021-01-29 14:45 | 2021-01-29 15:00 | OTC - OM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10600 | WBS.2.1.13.1.3.4.28 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF - Goods issue all CPU and delivery loads Shipping from Deployment Facilities | 2.75 | 2021-01-30 12:15 | 2021-01-30 15:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:00 | OTC - OM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
10643 | WBS.2.1.13.1.3.4.29 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Rerun Open Order List (Deployment Facilities) | 0.5 | 2021-01-30 15:00 | 2021-01-30 15:30 | CHRIS FRENCH | CFRENCH@GAPAC.COM | OTC TEAM;SAI TEAM;JEFF WAGNER | PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEFFREY.WAGNER@GAPAC.COM | Business | 10600,92324 |  |  | * |  | 2021-01-30 15:00 | 2021-01-30 15:30 | OTC - OM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
10592 | WBS.2.1.13.1.3.4.30 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Check for Shipped but not Invoiced and process billing for all goods issued loads (Deployment Facilities) | 1 | 2021-01-30 15:30 | 2021-01-30 16:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10643 |  |  | * |  | 2021-01-30 15:30 | 2021-01-30 16:30 | OTC - OM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92661 | WBS.2.1.13.1.3.4.31 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF-Communicate Late Deliveries to Customers for any Non-PGI'd orders from Deployment Facilities | 0.25 | 2021-01-30 15:30 | 2021-01-30 15:45 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10643 |  |  | * |  | 2021-01-30 15:30 | 2021-01-30 15:45 | OTC - OM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92578 | WBS.2.1.13.1.3.4.33 | N | N | Planned | Provide second list of deliveries to be held in TOPS & delete in ECC | 0.25 | 2021-01-30 15:30 | 2021-01-30 15:45 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KETAN PRADHAN;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 10643 |  |  | * |  | 2021-01-30 15:30 | 2021-01-30 15:45 | OTC | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90693 | WBS.2.1.13.1.3.4.34 | N | N | Planned | ATL - Within TOPS - Flag all D4 ECC DN's to wait for replacement DN (2nd list provided by OTC-OM) | 1 | 2021-01-30 15:45 | 2021-01-30 16:45 | DAVE LEGOIS | DAVID.LEGOIS@KBXLOGISTICS.COM | TOM OLIVE;JOHN NATZKE;OTC TEAM;SAI TEAM;ANDREW HELMANN | THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.NATZKE@KBXLOGISTICS.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Andrew.Helmann@kbxlogistics.com | Business | 92578 |  |  | * |  | 2021-01-30 15:45 | 2021-01-30 16:45 | OTC - KBX | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92322 | WBS.2.1.13.1.3.4.36 | N | N | Planned | Delete ECC shipments (list provided by OTC-OM) | 0.25 | 2021-01-30 16:45 | 2021-01-30 17:00 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | CHRISTINE CROSBY;OTC TEAM;SAI TEAM;LSA TEAM | CCROSBY@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 90693,94937,95226 |  |  | * |  | 2021-01-30 16:45 | 2021-01-30 17:00 | LSA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92317 | WBS.2.1.13.1.3.4.37 | N | N | Planned | Delete deliveries in ECC (list provided by OTC-OM) | 0.25 | 2021-01-30 18:45 | 2021-01-30 19:00 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | CHRISTINE CROSBY;OTC TEAM;SAI TEAM;LSA TEAM | CCROSBY@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 94937,95226,95230 |  |  | * |  | 2021-01-30 18:45 | 2021-01-30 19:00 | LSA | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92328 | WBS.2.1.13.1.3.4.38 | N | N | Planned | Validate delivery deletions updated the delivery xref table in ECC & S4 | 0.25 | 2021-01-30 19:00 | 2021-01-30 19:15 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | TRISHUL BUDDHA;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | TBUDDHA@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 92317,90697 |  |  | * |  | 2021-01-30 19:00 | 2021-01-30 19:15 | OTC | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95583 | WBS.2.1.13.1.3.4.40 | N | N | Planned | ATL - RETAIL/PRO - CUT OFF - Order Management out of S4 | 0.25 | 2021-01-30 16:30 | 2021-01-30 16:45 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 10592 |  |  | * |  | 2021-01-30 16:30 | 2021-01-30 16:45 | OTC - OM | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
90833 | WBS.2.1.13.1.3.5 | N | N |  | Ramp Down ¦ Inventory Validation Activities - Resync to be run on cutover day | 3 | 2021-01-29 06:15 | 2021-01-29 09:15 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-29 09:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95436 | WBS.2.1.13.1.3.5.2 | N | N | Planned | Location comparison between bins from ECC/JDA & EWM | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | ARNAB DEY;AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;DOUG STANISLAWSKI | ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | EWM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95437 | WBS.2.1.13.1.3.5.3 | N | N | Planned | Location comparison between bins from ECC/SAP-WM & EWM | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | EWM TEAM;JEFFREY GOLDMUNTZ;SAI TEAM;ALISON SMITH;DAVID HEILI | ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JGOLDMUNTZ@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ALISON.SMITH@GAPAC.COM;DAVID.HEILI@GAPAC.COM | LSA | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | LSA | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95438 | WBS.2.1.13.1.3.5.4 | N | N | Planned | Create bins in EWM for any identified bins from location comparison between legacy and EWM | 1 | 2021-01-29 08:15 | 2021-01-29 09:15 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;SHREYA NARULA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;shrenarula@deloitte.com | EWM | 95436,95437 |  |  | * |  | 2021-01-29 08:15 | 2021-01-29 09:15 | EWM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
91808 | WBS.2.1.13.1.4 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Communications | 152.5 | 2021-01-18 06:30 | 2021-01-29 15:00 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-29 15:00 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
11111 | WBS.2.1.13.1.4.1 | N | N |  | Ramp Down ¦ Business Activities - Atlanta - Communications - AC | 152.5 | 2021-01-18 06:30 | 2021-01-29 15:00 | [8 empty] | * |  | 2021-01-18 06:30 | 2021-01-29 15:00 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
11116 | WBS.2.1.13.1.4.1.1 | N | N | Planned | Communicate To DMAPS Sites That Conversion Is Coming - 2 Weeks Before Go-Live | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;GARY BENOIT | JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GARY.BENOIT@GAPAC.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | AC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
11115 | WBS.2.1.13.1.4.1.2 | N | N | Planned | Communicate to TRAX Sites That Conversion Is Coming - 2 Weeks Before Go-Live | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | TOM BRATTIN | TBRATTI@GAPAC.COM | JASON RAMSEY;DON ABBOTT;JOHN CASABURRI;SAI TEAM | JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 11116 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | AC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
11114 | WBS.2.1.13.1.4.1.3 | N | N | Planned | Communicate to OSIPI (OE) Sites That Conversion Is Coming - 2 Weeks Before Go-Live | 0.25 | 2021-01-18 07:00 | 2021-01-18 07:15 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;GARY BENOIT | JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GARY.BENOIT@GAPAC.COM | Business | 11115 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:15 | AC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
11113 | WBS.2.1.13.1.4.1.4 | N | N | Planned | Communicate to AA Sites That Conversion Is Coming - 2 Weeks Before Go-Live | 0.25 | 2021-01-18 07:15 | 2021-01-18 07:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;GARY BENOIT | JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GARY.BENOIT@GAPAC.COM | Business | 11114 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:30 | AC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
11112 | WBS.2.1.13.1.4.1.5 | N | N | Planned | Communicate to CLiP(LMM) Sites That Conversion Is Coming - 2 Weeks Before Go-Live | 0.25 | 2021-01-18 07:30 | 2021-01-18 07:45 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JASON RAMSEY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;GARY BENOIT | JCRAMSEY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GARY.BENOIT@GAPAC.COM | Business | 11113 |  |  | * |  | 2021-01-18 07:30 | 2021-01-18 07:45 | AC | ATL | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95221 | WBS.2.1.13.1.4.1.6 | N | N | Planned | Run open STO list for PTH, HBG, SCH, BG, RNC, RVG | 0.5 | 2021-01-29 14:30 | 2021-01-29 15:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | KRISTEN PAULY;PUNEET KUMAR;DON ABBOTT;JOHN NATZKE;TOM OLIVE;JOHN CASABURRI;SAI TEAM;BRAD WYMAN | KRISTEN.PAULY@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JOHN.NATZKE@KBXLOGISTICS.COM;THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | Business | 95224,92228 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 15:00 | SCM | ALL | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97742 | WBS.2.1.13.1.4.1.7 | N | N | Planned | Notify ICPAQS Team to create notifications for Production Orders that did not delete | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | JOHN J SMITH | JOHNJ.SMITH@GAPAC.COM | LISA SZCZUREK;SAI TEAM | LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | SCM - TTN | ATL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92043 | WBS.2.1.13.2 | N | N |  | Ramp Down ¦ Business Activities - South Chicago | 175.25 | 2021-01-18 06:15 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 22:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92042 | WBS.2.1.13.2.1 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Prep | 81.25 | 2021-01-18 06:15 | 2021-01-25 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:30 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92041 | WBS.2.1.13.2.1.1 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Prep Activities - EWM | 81.25 | 2021-01-18 06:15 | 2021-01-25 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:30 |  | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94426 | WBS.2.1.13.2.1.1.1 | N | N | Planned | SCH - Run SQL to check for pick faces with mixed items and have site correct any found in JDA before load | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92982 | WBS.2.1.13.2.1.1.2 | N | N | Planned | SCH - Communicate to Warehouse personnel during FCW any Q-hold that occur during FCW must be manually managed to ensure non-conforming materials are not used or shipped | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | ESSEX BRASSEL;TOMMY NEFFENDORF;JEREMY RAY;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | ESSEX.BRASSEL@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92974 | WBS.2.1.13.2.1.1.3 | N | N | Planned | SCH - Provide final list of site users | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | ESSEX BRASSEL | ESSEX.BRASSEL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92983 | WBS.2.1.13.2.1.1.4 | N | N | Planned | SCH - Update and validate site printers | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | ESSEX BRASSEL;TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX B;SAI TEAM;EWM TEAM | ESSEX.BRASSEL@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92973 | WBS.2.1.13.2.1.1.5 | N | N | Planned | SCH - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MATT STAMPER | MATTHEW.STAMPER@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92986 | WBS.2.1.13.2.1.1.6 | N | N | Planned | SCH - Remove duplicate or obsolete fixed bins/pickfaces | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;AARON HISSONG;GIOVANY CARVAJAL | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Aaron.Hissong@gapac.com;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92972 | WBS.2.1.13.2.1.1.7 | N | N | Planned | SCH - Review Lot Controlled items to verify that all lot controlled inventory have lot numbers and expiration dates (PR only) | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;AARON HISSONG;GIOVANY CARVAJAL | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Aaron.Hissong@gapac.com;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92985 | WBS.2.1.13.2.1.1.8 | N | N | Planned | SCH - Start Cycle count inventory - All Items | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92971 | WBS.2.1.13.2.1.1.9 | N | N | Planned | SCH - Provide approvers and levels for write-offs | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 92974 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92970 | WBS.2.1.13.2.1.1.10 | N | N | Planned | SCH - Provide final list of site resources and resource constraints (equipment names, types, numbers) | 0.25 | 2021-01-18 07:15 | 2021-01-18 07:30 | ESSEX BRASSEL | ESSEX.BRASSEL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 92973 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92984 | WBS.2.1.13.2.1.1.11 | N | N | Planned | SCH - Change inventory status for items set to expire during blackout period. | 1 | 2021-01-18 08:15 | 2021-01-18 09:15 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;DANIELLE MULLIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Danielle.Mulligan@gapac.com | Business | 92972 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 09:15 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92980 | WBS.2.1.13.2.1.1.12 | N | N | Planned | SCH - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92979 | WBS.2.1.13.2.1.1.13 | N | N | Planned | SCH - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | EWM | 93400,4501,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92978 | WBS.2.1.13.2.1.1.14 | N | N | Planned | SCH - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | EWM | 93400,4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92976 | WBS.2.1.13.2.1.1.15 | N | N | Planned | SCH - Setup Dock Door to Staging Lane determination in EWM | 0.5 | 2021-01-18 18:15 | 2021-01-18 18:45 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | EWM | 92977 |  |  | * |  | 2021-01-18 18:15 | 2021-01-18 18:45 | EWM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94427 | WBS.2.1.13.2.1.1.16 | N | N | Planned | SCH - Compare location bins defined between legacy and EWM to make sure none of them are missed in EWM bin load. | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;MICHAEL MATTHEWS;SAI TEAM;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | DAVID.BASCHE@GAPAC.COM;MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92969 | WBS.2.1.13.2.1.1.17 | N | N | Planned | SCH - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | ANDY KEOYOTHY | ANDY.KEOYOTHY@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92967 | WBS.2.1.13.2.1.1.18 | N | N | Planned | SCH - Shut co pack production (one week prior) | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Tristan.Clark@nfiindustries.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95275 | WBS.2.1.13.2.1.1.19 | N | N | Planned | SCH - Close out all existing subcontacting (copack) purchase orders. | 1 | 2021-01-25 06:30 | 2021-01-25 07:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Tristan.Clark@nfiindustries.com | Business | 92967 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 07:30 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92039 | WBS.2.1.13.2.1.2 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Prep Activities - SCM | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 |  | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94708 | WBS.2.1.13.2.1.2.1 | N | N | Planned | SCH -PRO avoid outbound STO's 1 wk b4 & 1 wk after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | DOMINIC MORRILL | DOMINIC.MORRILL@GAPAC.COM | KATIE MARKS;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | KATIE.MARKS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94706 | WBS.2.1.13.2.1.2.3 | N | N | Planned | SCH -RET Towel/Nap avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | ROBERT BLACKBURN | ROBERT.BLACKBURN@GAPAC.COM | LATISHA CHISHOLM;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | LATISHA.CHISHOLM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94705 | WBS.2.1.13.2.1.2.4 | N | N | Planned | SCH -Dixie avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | KAREN HERRING | KAREN.HERRING@GAPAC.COM | SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;MICHELLE SADLER;YUBIN KWON | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM;YUBIN.KWON@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92038 | WBS.2.1.13.2.2 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Clean-Up Activities | 175.25 | 2021-01-18 06:15 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:15 |  | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92964 | WBS.2.1.13.2.2.1 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Clean-Up Activities - EWM | 95 | 2021-01-25 06:30 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-25 06:30 | 2021-01-30 13:15 |  | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92962 | WBS.2.1.13.2.2.1.1 | N | N | Planned | SCH - Clear vendor bucket | 0.25 | 2021-01-25 06:30 | 2021-01-25 06:45 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM | Business | 92967 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 06:45 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93035 | WBS.2.1.13.2.2.1.2 | N | N | Planned | SCH - Identify pilot transactions to perform after system comes up on EWM | 0.25 | 2021-01-25 06:30 | 2021-01-25 06:45 | ANDY KEOYOTHY | ANDY.KEOYOTHY@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Tristan.Clark@nfiindustries.com | Business | 92969 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 06:45 | EWM | SCH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92961 | WBS.2.1.13.2.2.1.3 | N | N | Planned | SCH - Cleanup and cycle count repack area | 8 | 2021-01-27 06:15 | 2021-01-27 14:15 | AARON HISSONG | Aaron.Hissong@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;ALICIA BERNAL | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Alicia.Bernal@gapac.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 14:15 | EWM | SCH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
92960 | WBS.2.1.13.2.2.1.4 | N | N | Planned | SCH - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;SHELLEY GRAHAM;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Shelley.Graham@gapac.com;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EWM | SCH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
92959 | WBS.2.1.13.2.2.1.5 | N | N | Planned | SCH - Ensure all inventory in damaged status is in DAMG101 or DAMG201" | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | AARON HISSONG | Aaron.Hissong@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;ALICIA BERNAL;JEREMY RAY | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Alicia.Bernal@gapac.com;JEREMY.RAY@GAPAC.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | EWM | SCH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92958 | WBS.2.1.13.2.2.1.6 | N | N | Planned | SCH - End & validate Cycle count inventory - All Items | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;ALICIA BERNAL;JEREMY RAY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Alicia.Bernal@gapac.com;JEREMY.RAY@GAPAC.COM;Christopher.Jernigan@gapac.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | SCH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
92954 | WBS.2.1.13.2.2.1.7 | N | N | Planned | SCH - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;SHELLEY GRAHAM;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Shelley.Graham@gapac.com;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 12178 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
92956 | WBS.2.1.13.2.2.1.8 | N | N | Planned | SCH - Ensure all locations are not in blocked status | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | CHRISTOPHER JERNIGAN | Christopher.Jernigan@gapac.com | TOMMY NEFFENDORF;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;AARON HISSONG;GIOVANY CARVAJAL | TOMMY.NEFFENDORF@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Aaron.Hissong@gapac.com;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92955 | WBS.2.1.13.2.2.1.9 | N | N | Planned | SCH - Download open yard management operations and verify trailer status' are correct(MT's, Full, OOS) prior to upload file | 1 | 2021-01-30 12:30 | 2021-01-30 13:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;SHELLEY GRAHAM;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Shelley.Graham@gapac.com;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 92954 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93041 | WBS.2.1.13.2.2.1.10 | N | N | Planned | SCH - Pull GP LOT Controlled Report and upload to Teams Quality file | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Christopher.Jernigan@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92953 | WBS.2.1.13.2.2.1.11 | N | N | Planned | SCH - Start:Perform physical inventory on all pick face locations | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | RODOLFO CARBAJAL | rodolfo.carbajal@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;ALICIA BERNAL;JEREMY RAY | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Alicia.Bernal@gapac.com;JEREMY.RAY@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | EWM | SCH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93040 | WBS.2.1.13.2.2.1.12 | N | N | Planned | SCH - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 2 | 2021-01-30 13:30 | 2021-01-30 15:30 | JORDAN ALLEN | Jordan.Allen@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CARLA PERKINS;JEREMY RAY | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Carla.Perkins@gapac.com;JEREMY.RAY@GAPAC.COM | Business | 92955 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 15:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93039 | WBS.2.1.13.2.2.1.13 | N | N | Planned | SCH - Operations confirms all system activities to perform prior to cutover have been completed. | 1 | 2021-01-30 13:30 | 2021-01-30 14:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Tristan.Clark@nfiindustries.com | Business | 92955 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 14:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93038 | WBS.2.1.13.2.2.1.14 | N | N | Planned | SCH - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 1 | 2021-01-30 14:30 | 2021-01-30 15:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;SHELLEY GRAHAM;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Shelley.Graham@gapac.com;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 93039 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 15:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93037 | WBS.2.1.13.2.2.1.15 | N | N | Planned | SCH - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 2 | 2021-01-30 15:30 | 2021-01-30 17:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;SHELLEY GRAHAM;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Shelley.Graham@gapac.com;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 93038 |  |  | * |  | 2021-01-29 15:30 | 2021-01-29 17:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
92952 | WBS.2.1.13.2.2.1.16 | N | N | Planned | SCH - All shipments are load end and none started. | 4 | 2021-01-30 17:30 | 2021-01-30 21:30 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;DEMETRIUS HUGHES;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;DEMETRIUS.HUGHES@GAPAC.COM ;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 93037 |  |  | * |  | 2021-01-29 17:30 | 2021-01-29 21:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93036 | WBS.2.1.13.2.2.1.17 | N | N | Planned | SCH - Identify IB STO on Friday before cutover, flag trailer, and spot at door | 1 | 2021-01-30 13:30 | 2021-01-30 14:30 | ESSEX BRASSEL | ESSEX.BRASSEL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;GIOVANY CARVAJAL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;JORDAN ALLEN | TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Jordan.Allen@gapac.com | Business | 92955 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 14:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
10532 | WBS.2.1.13.2.2.2 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Clean-Up Activities - OTC | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 |  | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92963 | WBS.2.1.13.2.2.2.1 | N | N | Planned | SCH - Disposition (Clean up) Q-holds in existing system | 4 | 2021-01-18 06:15 | 2021-01-18 10:15 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;DANIELLE MULLIGAN;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Danielle.Mulligan@gapac.com;Christopher.Jernigan@gapac.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | OTC - Quality | SCH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
92036 | WBS.2.1.13.2.3 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Cut-Off Activities | 6.5 | 2021-01-30 14:30 | 2021-01-30 21:00 | [8 empty] | * |  | 2021-01-29 14:30 | 2021-01-30 22:15 |  | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
92032 | WBS.2.1.13.2.3.1 | N | N |  | Ramp Down ¦ Business Activities - South Chicago - Cut-Off Activities - EWM | 6.5 | 2021-01-30 14:30 | 2021-01-30 21:00 | [8 empty] | * |  | 2021-01-29 14:30 | 2021-01-30 22:15 |  | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93032 | WBS.2.1.13.2.3.1.1 | N | N | Planned | SCH - Upload to RDC SAP Network Teams Page under Inventory. | 2 | 2021-01-30 14:30 | 2021-01-30 16:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Tristan.Clark@nfiindustries.com | Business | 93039 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 16:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93031 | WBS.2.1.13.2.3.1.2 | N | N | Planned | SCH - Remove pallet tag/HU numbers from all case pick locations listed on the inventory file prior to submitting to GP. | 0.25 | 2021-01-30 16:30 | 2021-01-30 16:45 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com | Business | 93032 |  |  | * |  | 2021-01-29 16:30 | 2021-01-29 16:45 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93030 | WBS.2.1.13.2.3.1.3 | N | N | Planned | SCH - Verify there are no partial pallets located in bulk storage bays. | 1 | 2021-01-30 16:30 | 2021-01-30 17:30 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;AARON HISSONG | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Aaron.Hissong@gapac.com | Business | 93032 |  |  | * |  | 2021-01-29 16:30 | 2021-01-29 17:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93029 | WBS.2.1.13.2.3.1.4 | N | N | Planned | SCH - Submit inventory reports for upload to EWM. | 1 | 2021-01-30 17:30 | 2021-01-30 18:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com | Business | 93032,93031,93030,93039 |  |  | * |  | 2021-01-29 17:30 | 2021-01-29 18:30 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93028 | WBS.2.1.13.2.3.1.5 | N | N | Planned | SCH - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-30 18:30 | 2021-01-30 19:00 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Tristan.Clark@nfiindustries.com | Business | 93029 |  |  | * |  | 2021-01-29 18:30 | 2021-01-29 19:00 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
93027 | WBS.2.1.13.2.3.1.6 | N | N | Planned | SCH - Upload WMS extracted file to S Chicago channel on RDC SAP Network Teams Page | 0.5 | 2021-01-30 18:30 | 2021-01-30 19:00 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Tristan.Clark@nfiindustries.com | Business | 93029 |  |  | * |  | 2021-01-29 18:30 | 2021-01-29 19:00 | EWM | SCH | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
94626 | WBS.2.1.13.2.3.1.7 | N | N | Planned | SCH - Disable jobs in JDA for SCH to prevent unwanted EMS events or transactions from going out of system | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | JEFF DUCKETT;ARNAB DEY;AVINASH TALREJA;SAI TEAM;LSA TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | JEFFREY.DUCKETT@GAPAC.COM;ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 80967 |  |  | * |  | 2021-01-30 21:45 | 2021-01-30 22:15 | EWM | SCH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95899 | WBS.2.1.13.3 | N | N |  | Ramp Down ¦ Business Activities - Rancho | 175.25 | 2021-01-18 06:15 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 22:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95898 | WBS.2.1.13.3.1 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Prep | 83 | 2021-01-18 06:15 | 2021-01-25 09:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 09:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95897 | WBS.2.1.13.3.1.1 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Prep Activities - EWM | 83 | 2021-01-18 06:15 | 2021-01-25 09:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 09:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95896 | WBS.2.1.13.3.1.1.1 | N | N | Planned | RNC - Run SQL to check for pick faces with mixed items and have site correct any found in JDA before load | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95895 | WBS.2.1.13.3.1.1.2 | N | N | Planned | RNC - Communicate to Warehouse personnel during FCW any Q-hold that occur during FCW must be manually managed to ensure non-conforming materials are not used or shipped | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM | Business | 10531 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95894 | WBS.2.1.13.3.1.1.3 | N | N | Planned | RNC - Provide final list of site users | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | DANIEL OJEDA | DANIEL.OJEDA@GAPAC.COM | BRANDON SOTO;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DANIEL.OJEDA@NFIINDUSTRIES.COM;BRANDON.SOTO@GAPAC.COM;BRANDON.SOTO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95893 | WBS.2.1.13.3.1.1.4 | N | N | Planned | RNC - Update and validate site printers | 1 | 2021-01-18 08:00 | 2021-01-18 09:00 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM | Business | 10531 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 09:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95892 | WBS.2.1.13.3.1.1.5 | N | N | Planned | RNC - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 1 | 2021-01-18 08:00 | 2021-01-18 09:00 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 09:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95891 | WBS.2.1.13.3.1.1.6 | N | N | Planned | RNC - Remove duplicate or obsolete fixed bins/pickfaces | 2 | 2021-01-18 08:00 | 2021-01-18 10:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 10:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95890 | WBS.2.1.13.3.1.1.7 | N | N | Planned | RNC - Review Lot Controlled items to verify that all lot controlled inventory have lot numbers and expiration dates (PR only) | 2 | 2021-01-18 08:00 | 2021-01-18 10:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 10:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95889 | WBS.2.1.13.3.1.1.8 | N | N | Planned | RNC - Start Cycle count inventory - All Items | 1 | 2021-01-18 08:00 | 2021-01-18 09:00 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ;RICHARD ROMO;DERICK LOUGH | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;RICHARD.ROMO@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 09:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95888 | WBS.2.1.13.3.1.1.9 | N | N | Planned | RNC - Provide approvers and levels for write-offs | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | Business | 95894 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95887 | WBS.2.1.13.3.1.1.10 | N | N | Planned | RNC - Provide final list of site resources and resource constraints (equipment names, types, numbers) | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | DANIEL OJEDA | DANIEL.OJEDA@GAPAC.COM | BRANDON SOTO;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DANIEL.OJEDA@NFIINDUSTRIES.COM;BRANDON.SOTO@GAPAC.COM;BRANDON.SOTO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 36501 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95886 | WBS.2.1.13.3.1.1.11 | N | N | Planned | RNC - Change inventory status for items set to expire during blackout period. | 1 | 2021-01-18 10:00 | 2021-01-18 11:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 95890 |  |  | * |  | 2021-01-18 10:00 | 2021-01-18 11:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95885 | WBS.2.1.13.3.1.1.12 | N | N | Planned | RNC - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95884 | WBS.2.1.13.3.1.1.13 | N | N | Planned | RNC - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 93400,4501,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95883 | WBS.2.1.13.3.1.1.14 | N | N | Planned | RNC - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 93400,4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95882 | WBS.2.1.13.3.1.1.15 | N | N | Planned | RNC - Setup Dock Door to Staging Lane determination in EWM | 0.5 | 2021-01-18 20:15 | 2021-01-18 20:45 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | EWM | 96709 |  |  | * |  | 2021-01-18 20:15 | 2021-01-18 20:45 | EWM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95881 | WBS.2.1.13.3.1.1.16 | N | N | Planned | RNC - Compare location bins defined between legacy and EWM to make sure none of them are missed in EWM bin load. | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;MICHAEL MATTHEWS;SAI TEAM;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | DAVID.BASCHE@GAPAC.COM;MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95880 | WBS.2.1.13.3.1.1.17 | N | N | Planned | RNC - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-25 08:00 | 2021-01-25 08:15 | LILLIAN GARCIA | LILLIAN.GARCIA@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;ANA OLIVER;ELIZABETH PARDO;CASSANDRA OCHOA | LILLIAN.GARCIA@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ANA.OLIVER@GAPAC.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 08:00 | 2021-01-25 08:15 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95879 | WBS.2.1.13.3.1.1.18 | N | N | Planned | RNC - Shut co pack production (one week prior) | 0.25 | 2021-01-25 08:00 | 2021-01-25 08:15 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 08:00 | 2021-01-25 08:15 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95878 | WBS.2.1.13.3.1.1.19 | N | N | Planned | RNC - Close out all existing subcontacting (copack) purchase orders. | 1 | 2021-01-25 08:15 | 2021-01-25 09:15 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 95879 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 09:15 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95877 | WBS.2.1.13.3.1.2 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Prep Activities - SCM | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 |  | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95876 | WBS.2.1.13.3.1.2.1 | N | N | Planned | RNC -PRO avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | KATIE MARKS | KATIE.MARKS@GAPAC.COM | DOMINIC MORRILL;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | DOMINIC.MORRILL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95875 | WBS.2.1.13.3.1.2.2 | N | N | Planned | RNC -RET TIS avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | ROBERT BLACKBURN | ROBERT.BLACKBURN@GAPAC.COM | KELLY PATRICK;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | KELLY.PATRICK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95874 | WBS.2.1.13.3.1.2.3 | N | N | Planned | RNC -RET Towel/Nap avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | LATISHA CHISHOLM | LATISHA.CHISHOLM@GAPAC.COM | ROBERT BLACKBURN;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | ROBERT.BLACKBURN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95873 | WBS.2.1.13.3.1.2.4 | N | N | Planned | RNC -Dixie avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | BRANDY WARRIOR | BRANDY.WARRIOR1@GAPAC.COM | KAREN HERRING;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | KAREN.HERRING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95872 | WBS.2.1.13.3.1.2.5 | N | N | Planned | RNC -Align co-pack schedule to avoid 1 wk prior & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | Alexander Madueke | alexander.madueke@gapac.com | DEVON KUERTEN;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;JEREMY RAY;TOMMY NEFFENDORF;MICHELLE SADLER | DEVON.KUERTEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95871 | WBS.2.1.13.3.2 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Clean-Up Activities | 173.5 | 2021-01-18 08:00 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-18 08:00 | 2021-01-30 13:15 |  | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95870 | WBS.2.1.13.3.2.1 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Clean-Up Activities - EWM | 93.25 | 2021-01-25 08:15 | 2021-01-30 21:30 | [8 empty] | * |  | 2021-01-25 08:15 | 2021-01-30 13:15 |  | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95869 | WBS.2.1.13.3.2.1.1 | N | N | Planned | RNC - Clear vendor bucket | 0.25 | 2021-01-25 08:15 | 2021-01-25 08:30 | LILLIAN GARCIA | LILLIAN.GARCIA@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;ANA OLIVER;ELIZABETH PARDO;CASSANDRA OCHOA | LILLIAN.GARCIA@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ANA.OLIVER@GAPAC.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95879 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 08:30 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95868 | WBS.2.1.13.3.2.1.2 | N | N | Planned | RNC - Identify pilot transactions to perform after system comes up on EWM | 0.25 | 2021-01-25 08:15 | 2021-01-25 08:30 | DANIEL OJEDA | DANIEL.OJEDA@GAPAC.COM | BRANDON SOTO;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DANIEL.OJEDA@NFIINDUSTRIES.COM;BRANDON.SOTO@GAPAC.COM;BRANDON.SOTO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 95880 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 08:30 | EWM | RNC | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95867 | WBS.2.1.13.3.2.1.3 | N | N | Planned | RNC - Cleanup and cycle count repack area | 8 | 2021-01-27 08:00 | 2021-01-27 16:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10853 |  |  | * |  | 2021-01-27 08:00 | 2021-01-27 16:00 | EWM | RNC | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95866 | WBS.2.1.13.3.2.1.4 | N | N | Planned | RNC - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 08:00 | 2021-01-28 08:15 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;LILLIAN GARCIA;ELIZABETH PARDO;CASSANDRA OCHOA | MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;LILLIAN.GARCIA@GAPAC.COM;LILLIAN.GARCIA@NFIINDUSTRIES.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 08:15 | EWM | RNC | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95865 | WBS.2.1.13.3.2.1.5 | N | N | Planned | RNC - Ensure all inventory in damaged status is in DAMG101 or DAMG201" | 0.5 | 2021-01-29 08:00 | 2021-01-29 08:30 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10851 |  |  | * |  | 2021-01-29 08:00 | 2021-01-29 08:30 | EWM | RNC | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95864 | WBS.2.1.13.3.2.1.6 | N | N | Planned | RNC - End & validate Cycle count inventory - All Items | 1 | 2021-01-29 08:00 | 2021-01-29 09:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 10851 |  |  | * |  | 2021-01-29 08:00 | 2021-01-29 09:00 | EWM | RNC | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95863 | WBS.2.1.13.3.2.1.7 | N | N | Planned | RNC - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;LILLIAN GARCIA;ELIZABETH PARDO;CASSANDRA OCHOA | MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;LILLIAN.GARCIA@GAPAC.COM;LILLIAN.GARCIA@NFIINDUSTRIES.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 12178 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
97781 | WBS.2.1.13.3.2.1.24 | N | N | Planned | RCU-Notes on OOS trailers in JDA cannot be more than 40 characters | 0.5 | 2021-01-30 12:30 | 2021-01-30 13:00 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA;SAI TEAM;EWM TEAM | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 95863 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:00 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95862 | WBS.2.1.13.3.2.1.8 | N | N | Planned | RNC - Ensure all locations are not in blocked status | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95861 | WBS.2.1.13.3.2.1.9 | N | N | Planned | RNC - Download open yard management operations and verify trailer status' are correct(MT's, Full, OOS) prior to upload file | 1 | 2021-01-30 12:30 | 2021-01-30 13:30 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM | Business | 95863 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 13:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95859 | WBS.2.1.13.3.2.1.11 | N | N | Planned | RNC - Start:Perform physical inventory on all pick face locations | 0.5 | 2021-01-28 08:00 | 2021-01-28 08:30 | DERICK LOUGH | DERICK.LOUGH@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ;RICHARD ROMO;DALIA MIRANDA;KYNDAL CODY;ONI BORCHERS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 08:30 | EWM | RNC | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95858 | WBS.2.1.13.3.2.1.12 | N | N | Planned | RNC - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 2 | 2021-01-30 13:30 | 2021-01-30 15:30 | LILLIAN GARCIA | LILLIAN.GARCIA@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;ANA OLIVER;ELIZABETH PARDO;CASSANDRA OCHOA | LILLIAN.GARCIA@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ANA.OLIVER@GAPAC.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95861 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 15:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95857 | WBS.2.1.13.3.2.1.13 | N | N | Planned | RNC - Operations confirms all system activities to perform prior to cutover have been completed. | 1 | 2021-01-30 13:30 | 2021-01-30 14:30 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM | Business | 95861 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 14:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95856 | WBS.2.1.13.3.2.1.14 | N | N | Planned | RNC - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 1 | 2021-01-30 14:30 | 2021-01-30 15:30 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;LILLIAN GARCIA;ELIZABETH PARDO;CASSANDRA OCHOA | MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;LILLIAN.GARCIA@GAPAC.COM;LILLIAN.GARCIA@NFIINDUSTRIES.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95857 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 15:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95855 | WBS.2.1.13.3.2.1.15 | N | N | Planned | RNC - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 2 | 2021-01-30 15:30 | 2021-01-30 17:30 | LILLIAN GARCIA | LILLIAN.GARCIA@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;ANA OLIVER;ELIZABETH PARDO;CASSANDRA OCHOA | LILLIAN.GARCIA@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ANA.OLIVER@GAPAC.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95856 |  |  | * |  | 2021-01-29 15:30 | 2021-01-29 17:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95854 | WBS.2.1.13.3.2.1.16 | N | N | Planned | RNC - All shipments are load end and none started. | 4 | 2021-01-30 17:30 | 2021-01-30 21:30 | LILLIAN GARCIA | LILLIAN.GARCIA@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;ANA OLIVER;ELIZABETH PARDO;CASSANDRA OCHOA | LILLIAN.GARCIA@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ANA.OLIVER@GAPAC.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95855 |  |  | * |  | 2021-01-29 17:30 | 2021-01-29 21:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95853 | WBS.2.1.13.3.2.1.17 | N | N | Planned | RNC - Identify IB STO on Friday before cutover, flag trailer, and spot at door | 1 | 2021-01-30 13:30 | 2021-01-30 14:30 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;LILLIAN GARCIA;ELIZABETH PARDO;CASSANDRA OCHOA | MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;LILLIAN.GARCIA@GAPAC.COM;LILLIAN.GARCIA@NFIINDUSTRIES.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 95861 |  |  | * |  | 2021-01-29 13:30 | 2021-01-29 14:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95860 | WBS.2.1.13.3.2.1.23 | N | N | Planned | RNC - Pull GP LOT Controlled Report and upload to Teams Quality file | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95852 | WBS.2.1.13.3.2.2 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Clean-Up Activities - OTC | 4 | 2021-01-18 08:00 | 2021-01-18 12:00 | [8 empty] | * |  | 2021-01-18 08:00 | 2021-01-18 12:00 |  | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95851 | WBS.2.1.13.3.2.2.1 | N | N | Planned | RNC - Disposition (Clean up) Q-holds in existing system | 4 | 2021-01-18 08:00 | 2021-01-18 12:00 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 12:00 | OTC - Quality | RNC | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95850 | WBS.2.1.13.3.3 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Cut-Off Activities | 6.5 | 2021-01-30 14:30 | 2021-01-30 21:00 | [8 empty] | * |  | 2021-01-29 14:30 | 2021-01-30 22:15 |  | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95849 | WBS.2.1.13.3.3.1 | N | N |  | Ramp Down ¦ Business Activities - Rancho - Cut-Off Activities - EWM | 6.5 | 2021-01-30 14:30 | 2021-01-30 21:00 | [8 empty] | * |  | 2021-01-29 14:30 | 2021-01-30 22:15 |  | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95847 | WBS.2.1.13.3.3.1.2 | N | N | Planned | RNC - Remove pallet tag/HU numbers from all case pick locations listed on the inventory file prior to submitting to GP. | 0.25 | 2021-01-30 14:30 | 2021-01-30 14:45 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 95857 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 14:45 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95846 | WBS.2.1.13.3.3.1.3 | N | N | Planned | RNC - Verify there are no partial pallets located in bulk storage bays. | 1 | 2021-01-30 14:30 | 2021-01-30 15:30 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;MARIA MARQUEZ;RICHARD ROMO;DERICK LOUGH | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;RICHARD.ROMO@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 95857 |  |  | * |  | 2021-01-29 14:30 | 2021-01-29 15:30 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95844 | WBS.2.1.13.3.3.1.5 | N | N | Planned | RNC - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-30 15:30 | 2021-01-30 16:00 | DANIEL OJEDA | DANIEL.OJEDA@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DANIEL.OJEDA@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 95846 |  |  | * |  | 2021-01-29 15:30 | 2021-01-29 16:00 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95843 | WBS.2.1.13.3.3.1.6 | N | N | Planned | RNC - Upload WMS extracted file to Hutchins channel on RDC SAP Network Teams Page | 0.5 | 2021-01-30 15:30 | 2021-01-30 16:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 95846 |  |  | * |  | 2021-01-29 15:30 | 2021-01-29 16:00 | EWM | RNC | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95842 | WBS.2.1.13.3.3.1.7 | N | N | Planned | RNC - Disable jobs in JDA for Rancho to prevent unwanted EMS events or transactions from going out of system | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | JEFF DUCKETT;ARNAB DEY;AVINASH TALREJA;SAI TEAM;LSA TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | JEFFREY.DUCKETT@GAPAC.COM;ADEY@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 80967 |  |  | * |  | 2021-01-30 21:45 | 2021-01-30 22:15 | EWM | RNC | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95841 | WBS.2.1.13.4 | N | N |  | Ramp Down ¦ Business Activities - Rivergate | 179.5 | 2021-01-18 06:15 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 01:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95840 | WBS.2.1.13.4.1 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Prep | 130 | 2021-01-18 06:15 | 2021-01-28 08:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 08:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95839 | WBS.2.1.13.4.1.1 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Prep Activities - EWM | 130 | 2021-01-18 06:15 | 2021-01-28 08:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 08:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95838 | WBS.2.1.13.4.1.1.1 | N | N | Planned | RVG - Run SQL to check for pick faces with mixed items and have site correct any found in JDA before load | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95837 | WBS.2.1.13.4.1.1.2 | N | N | Planned | RVG - Communicate to Warehouse personnel during FCW any Q-hold that occur during FCW must be manually managed to ensure non-conforming materials are not used or shipped | 0.25 | 2021-01-28 08:00 | 2021-01-28 08:15 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;EWM TEAM;SAI TEAM | REBECCA.MORRIS@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846,10852 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 08:15 | EWM | RVG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95836 | WBS.2.1.13.4.1.1.3 | N | N | Planned | RVG - Provide final list of site users | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JULI LEWIS;SAI TEAM;EWM TEAM | JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95835 | WBS.2.1.13.4.1.1.4 | N | N | Planned | RVG - Update and validate site printers | 1 | 2021-01-18 08:00 | 2021-01-18 09:00 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | US GP BASIS;SAI TEAM | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 09:00 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95834 | WBS.2.1.13.4.1.1.5 | N | N | Planned | RVG - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 1 | 2021-01-18 08:00 | 2021-01-18 09:00 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER MCLEOD;JENNIFER NEWBERRY;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;JENNIFER.NEWBERRY@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 09:00 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95833 | WBS.2.1.13.4.1.1.6 | N | N | Planned | RVG - Remove duplicate or obsolete fixed bins/pickfaces | 2 | 2021-01-18 08:00 | 2021-01-18 10:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 10:00 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95830 | WBS.2.1.13.4.1.1.9 | N | N | Planned | RVG - Provide approvers and levels for write-offs | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95829 | WBS.2.1.13.4.1.1.10 | N | N | Planned | RVG - Provide final list of site resources and resource constraints (equipment names, types, numbers) | 0.25 | 2021-01-18 09:00 | 2021-01-18 09:15 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER MCLEOD;JENNIFER NEWBERRY;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;JENNIFER.NEWBERRY@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95834 |  |  | * |  | 2021-01-18 09:00 | 2021-01-18 09:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95827 | WBS.2.1.13.4.1.1.12 | N | N | Planned | RVG - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM;EWM TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95826 | WBS.2.1.13.4.1.1.13 | N | N | Planned | RVG - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM;EWM TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95825 | WBS.2.1.13.4.1.1.14 | N | N | Planned | RVG - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | SAI TEAM;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97191 | WBS.2.1.13.4.1.1.21 | N | N | Planned | BG - PTM_C0203 - MRO - Identify, validate and business sign-off - Stock and Non-Stock Storage bins | 5 | 2021-01-19 06:45 | 2021-01-19 11:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | MASON DRAKE;SAI TEAM;EWM TEAM;DEAN PIPER;LYNN MCMURDO;DOUG CARANGELLO;Mark Bernard | MASON.DRAKE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 96576 |  |  | * |  | 2021-01-19 06:45 | 2021-01-19 11:45 | EWM | BG | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
95823 | WBS.2.1.13.4.1.1.16 | N | N | Planned | RVG - Compare location bins defined between legacy and EWM to make sure none of them are missed in EWM bin load. | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;MICHAEL MATTHEWS;SAI TEAM;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS;JENNIFER MCLEOD;JULI LEWIS | DAVID.BASCHE@GAPAC.COM;MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | RVG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95822 | WBS.2.1.13.4.1.1.17 | N | N | Planned | RVG - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-25 06:15 | 2021-01-25 08:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;EWM TEAM;SAI TEAM;JULI LEWIS | JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JULI.LEWIS@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | RVG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95819 | WBS.2.1.13.4.1.2 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Prep Activities - SCM | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | [8 empty] | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 |  |  | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95814 | WBS.2.1.13.4.1.2.5 | N | N | Planned | RVG - align co- pack schedule to avoid 1 wk prior & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | PATRICK HOURIGAN | PATRICK.HOURIGAN@GAPAC.COM | LIZ HIETPAS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;JENNIFER MCLEOD;JULI LEWIS;MICHELLE SADLER | ELIZABETH.ARMSTRONG@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95813 | WBS.2.1.13.4.2 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Clean-Up Activities | 177.75 | 2021-01-18 08:00 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-18 08:00 | 2021-01-31 01:45 |  | RVG | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95812 | WBS.2.1.13.4.2.1 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Clean-Up Activities - EWM | 177.75 | 2021-01-18 08:00 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-18 08:00 | 2021-01-31 01:45 |  | RVG | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95810 | WBS.2.1.13.4.2.1.2 | N | N | Planned | RVG - Identify pilot transactions to perform after system comes up on EWM | 0.25 | 2021-01-18 08:00 | 2021-01-18 08:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 08:00 | 2021-01-18 08:15 | EWM | RVG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95808 | WBS.2.1.13.4.2.1.4 | N | N | Planned | RVG - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 08:00 | 2021-01-28 08:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;EWM TEAM;SAI TEAM;JULI LEWIS | JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JULI.LEWIS@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 08:15 | EWM | RVG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95805 | WBS.2.1.13.4.2.1.7 | N | N | Planned | RVG - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER NEWBERRY;EWM TEAM;SAI TEAM;JULI LEWIS | JENNIFER.NEWBERRY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JULI.LEWIS@GAPAC.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95804 | WBS.2.1.13.4.2.1.8 | N | N | Planned | RVG - Ensure all locations are not in blocked status | 0.5 | 2021-01-30 22:45 | 2021-01-30 23:15 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER NEWBERRY;JULI LEWIS;SAI TEAM;JENNIFER MCLEOD | JENNIFER.NEWBERRY@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM | Business | 10851,92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-30 23:15 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95803 | WBS.2.1.13.4.2.1.9 | N | N | Planned | RVG - Download open yard management operations and verify trailer status' are correct(MT's, Full, OOS) prior to upload file | 1 | 2021-01-30 22:45 | 2021-01-30 23:45 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-30 23:45 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95800 | WBS.2.1.13.4.2.1.12 | N | N | Planned | RVG - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95799 | WBS.2.1.13.4.2.1.13 | N | N | Planned | RVG - Operations confirms all system activities to perform prior to cutover have been completed. | 1 | 2021-01-31 00:45 | 2021-01-31 01:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95798,95800,95803,95804,95805,95797,95796,96523,96525 |  |  | * |  | 2021-01-31 00:45 | 2021-01-31 01:45 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
95798 | WBS.2.1.13.4.2.1.14 | N | N | Planned | RVG - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 3 | 2021-01-30 08:00 | 2021-01-30 11:00 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;EWM TEAM;SAI TEAM;JULI LEWIS | JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JULI.LEWIS@GAPAC.COM | Business | 10851 |  |  |  | 2021-01-30 08:00 | 2021-01-29 08:00 | 2021-01-29 09:00 | EWM | RVG | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95797 | WBS.2.1.13.4.2.1.15 | N | N | Planned | RVG - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 2 | 2021-01-30 11:00 | 2021-01-30 13:00 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95798 |  |  | * |  | 2021-01-29 09:00 | 2021-01-29 11:00 | EWM | RVG | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
96520 | WBS.2.1.13.4.2.1.18 | N | N | Planned | RVG - Schedule Resynch | 1 | 2021-01-27 08:00 | 2021-01-27 09:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 08:00 | 2021-01-27 09:00 | EWM | RVG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97408 | WBS.2.1.13.4.2.1.19 | N | N | Planned | RVG - Investigate/resolve Discrepancies | 2 | 2021-01-28 08:00 | 2021-01-28 10:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 10:00 | EWM | RVG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95796 | WBS.2.1.13.4.2.1.16 | N | N | Planned | RVG - All shipments are load end and none started. | 4 | 2021-01-30 13:00 | 2021-01-30 17:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95797 |  |  | * |  | 2021-01-29 11:00 | 2021-01-29 15:00 | EWM | RVG | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
95792 | WBS.2.1.13.4.3 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Cut-Off Activities | 92.25 | 2021-01-25 08:00 | 2021-01-30 20:15 | [8 empty] | * |  | 2021-01-25 08:00 | 2021-01-30 20:15 |  | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95791 | WBS.2.1.13.4.3.1 | N | N |  | Ramp Down ¦ Business Activities - Rivergate - Cut-Off Activities - EWM | 92.25 | 2021-01-25 08:00 | 2021-01-30 20:15 | [8 empty] | * |  | 2021-01-25 08:00 | 2021-01-30 20:15 |  | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96521 | WBS.2.1.13.4.3.1.8 | N | N | Planned | RVG - Run Final Resynch (Morning of Cutover) Investigate/Resolve Resynch Discprepancies | 1 | 2021-01-29 08:00 | 2021-01-29 09:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 08:00 | 2021-01-29 09:00 | EWM | RVG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97701 | WBS.2.1.13.4.3.1.15 | N | N | Planned | RVG - Schedule Resynch | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96520,10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | EWM | ATL | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96522 | WBS.2.1.13.4.3.1.9 | N | N | Planned | RVG - Complete all SAP workflows | 1 | 2021-01-28 08:00 | 2021-01-28 09:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852,10846 |  |  | * |  | 2021-01-28 08:00 | 2021-01-28 09:00 | EWM | RVG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96523 | WBS.2.1.13.4.3.1.10 | N | N | Planned | RVG - Delete Shipments/deliveries for orders not shipping prior to cutover | 1.5 | 2021-01-30 18:15 | 2021-01-30 19:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:45 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96524 | WBS.2.1.13.4.3.1.11 | N | N | Planned | RVG - Verify LGVs are idle and no work in the queue | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96525 | WBS.2.1.13.4.3.1.12 | N | N | Planned | RVG - All shipments are load end and none started | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96527 | WBS.2.1.13.4.3.1.14 | N | N | Planned | RVG - Verify LGV Missions complete and which LGV's are out of system prior to shutting down E80 | 1 | 2021-01-30 19:15 | 2021-01-30 20:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96525 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 20:15 | EWM | RVG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95790 | WBS.2.1.13.4.3.1.1 | N | N | Planned | RVG - Run inventory reports from WMS (inventory display). Upload to CPG Digital Core Home Page | 2 | 2021-01-25 08:00 | 2021-01-25 10:00 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER NEWBERRY;JULI LEWIS;SAI TEAM;JENNIFER MCLEOD | JENNIFER.NEWBERRY@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 08:00 | 2021-01-25 10:00 | EWM | RVG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95786 | WBS.2.1.13.4.3.1.5 | N | N | Planned | RVG - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-30 17:00 | 2021-01-30 17:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM | Business | 95796,95798 |  |  | * |  | 2021-01-29 15:00 | 2021-01-29 15:30 | EWM | RVG | 2021-01-30 | 2021-01-29 | 2 | Ramp Down
96041 | WBS.2.1.13.5 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green | 176 | 2021-01-18 06:15 | 2021-01-30 22:15 | [8 empty] | * |  | 2021-01-18 06:00 | 2021-01-30 22:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96040 | WBS.2.1.13.5.1 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities | 168.75 | 2021-01-18 06:15 | 2021-01-30 15:00 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:15 | 2021-01-30 15:00 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96039 | WBS.2.1.13.5.1.1 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities - EWM | 145 | 2021-01-18 06:15 | 2021-01-29 07:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:15 | 2021-01-29 07:15 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96037 | WBS.2.1.13.5.1.1.2 | N | N | Planned | BG - Ensure all vendors to provide HU's on all Raw Material inbounds (ASN's) | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96035 | WBS.2.1.13.5.1.1.4 | N | N | Planned | BG - Verify any new locations have signs/labels | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | BEAU EARLS;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96033 | WBS.2.1.13.5.1.1.6 | N | N | Planned | BG - Review all inbound STOs to have visibility of which inbounds are due during FCW, and send request to have as many inbounds as possible shipped early or late. | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96032 | WBS.2.1.13.5.1.1.7 | N | N | Planned | BG - Start pre-shipments of outbounds prior to cutover to minimize activity during cutover | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96031 | WBS.2.1.13.5.1.1.8 | N | N | Planned | BG - Disposition (Clean up) Q-holds in existing system | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | BEAU EARLS | Beau.Earls@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846,96032 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96030 | WBS.2.1.13.5.1.1.9 | N | N | Planned | BG - Ensure FGs that will go on mandatory Q-hold are placed in restricted inventory in existing system | 2 | 2021-01-18 08:45 | 2021-01-18 10:45 | BEAU EARLS | Beau.Earls@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846,96031 |  |  | * |  | 2021-01-18 08:45 | 2021-01-18 10:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96029 | WBS.2.1.13.5.1.1.10 | N | N | Planned | BG - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-18 10:45 | 2021-01-18 11:00 | BEAU EARLS | Beau.Earls@GAPAC.com | YUBIN KWON;LYNN MCMURDO;DEAN PIPER;SAI TEAM | YUBIN.KWON@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846,96030 |  |  | * |  | 2021-01-18 10:45 | 2021-01-18 11:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96028 | WBS.2.1.13.5.1.1.11 | N | N | Planned | BG - Provide final list of site users | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | JEANA HARRER;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96027 | WBS.2.1.13.5.1.1.12 | N | N | Planned | BG - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | DEREK SARGENT | Derek.Sargent@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96026 | WBS.2.1.13.5.1.1.13 | N | N | Planned | BG - Begin working on unloading Inbound STOs to ensure all are completed before FCW | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96025 | WBS.2.1.13.5.1.1.14 | N | N | Planned | BG - Meet with mill to ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | BEAU EARLS | Beau.Earls@GAPAC.com | YUBIN KWON;LYNN MCMURDO;DEAN PIPER;SAI TEAM | YUBIN.KWON@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96024 | WBS.2.1.13.5.1.1.15 | N | N | Planned | BG - Provide approvers and levels for write-offs | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | JEANA HARRER;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96023 | WBS.2.1.13.5.1.1.16 | N | N | Planned | BG - Provide final list of site resources and resource constraints (equipment names, types, numbers) | 0.25 | 2021-01-18 07:15 | 2021-01-18 07:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96027 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 07:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96022 | WBS.2.1.13.5.1.1.17 | N | N | Planned | BG - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97194 | WBS.2.1.13.5.1.1.24 | N | N | Planned | BG - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) - for MRO | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;LISA HAUSER;DEAN PIPER;LYNN MCMURDO;DOUG CARANGELLO;Mark Bernard | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;LISA.HAUSER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96021 | WBS.2.1.13.5.1.1.18 | N | N | Planned | BG - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96020 | WBS.2.1.13.5.1.1.19 | N | N | Planned | BG - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96019 | WBS.2.1.13.5.1.1.20 | N | N | Planned | BG - Create any new locations required by EWM & validate | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | BEAU EARLS | Beau.Earls@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96018 | WBS.2.1.13.5.1.1.21 | N | N | Planned | BG - Follow up on unloading Inbound STOs to ensure all are completed before FCW | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96017 | WBS.2.1.13.5.1.1.22 | N | N | Planned | BG - Provide final data for dock scheduling parameters/setup | 0.25 | 2021-01-29 06:15 | 2021-01-29 06:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:30 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96016 | WBS.2.1.13.5.1.1.23 | N | N | Planned | BG - Start Cycle count inventory - All Items | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | BEAU EARLS;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96015 | WBS.2.1.13.5.1.2 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities - AC | 2 | 2021-01-30 13:00 | 2021-01-30 15:00 |  |  |  |  | Business |  |  |  | * |  | 2021-01-30 13:00 | 2021-01-30 15:00 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96014 | WBS.2.1.13.5.1.2.1 | N | N | Planned | BG - CONVERTINNG Schedule and print work orders out 2 weeks | 2 | 2021-01-30 13:00 | 2021-01-30 15:00 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95968 |  |  | * |  | 2021-01-30 13:00 | 2021-01-30 15:00 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96766 | WBS.2.1.13.5.1.2.2 | N | N | Planned | BG - Printing Schedule and print work orders out 2 weeks | 2 | 2021-01-30 13:00 | 2021-01-30 15:00 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96775 |  |  | * |  | 2021-01-30 13:00 | 2021-01-30 15:00 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96013 | WBS.2.1.13.5.1.3 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities - PTP | 97.75 | 2021-01-18 06:30 | 2021-01-26 08:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:15 | 2021-01-26 08:15 |  | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96012 | WBS.2.1.13.5.1.3.1 | N | N | Planned | BG - Update and validate site printers - Stores | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | Jeron Wall | Jeron.wall@gapac.com | BRANDY MEREDITH;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Brandy.Meredith@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:00 | PTP - Procurement/Stores | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96034 | WBS.2.1.13.5.1.3.45 | N | N | Planned | BG - Update and validate site printers - SRW | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | DEREK SARGENT | Derek.Sargent@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM;Jeron Wall;KELLY LEWIS;JOHN WHITE | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Jeron.wall@gapac.com;kelly.lewis@gapac.com;JOHN.WHITE@GAPAC.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96010 | WBS.2.1.13.5.1.3.3 | N | N | Planned | BG - MRO - Create any new locations required by EWM | 1 | 2021-01-18 07:00 | 2021-01-18 08:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 96012,10531 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 08:00 | PTP | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96009 | WBS.2.1.13.5.1.3.4 | N | N | Planned | BG - Review open GRIR, and mark delivery complete any with final invoice received (greater than 60 days) | 2 | 2021-01-26 06:15 | 2021-01-26 08:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEBORAH HAMILTON;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | DEBORAH.HAMILTON@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 08:15 | PTP | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
96008 | WBS.2.1.13.5.1.3.5 | N | N | Planned | BG - Confirm all blanket PO/Framework orders have been updated to end on 1.31.2020 | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;Mark Bernard;DOUG CARANGELLO | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM;* | Business | 10845 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | PTP | BG | 2021-01-25 | 2021-01-18 | 1 | Ramp Down
96006 | WBS.2.1.13.5.1.3.7 | N | N | Planned | BG - Mill buyers to raise request to update material UoM | 0.5 | 2021-01-25 07:15 | 2021-01-25 07:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 95644,10845 |  |  | * |  | 2021-01-25 07:15 | 2021-01-25 07:45 | PTP | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96005 | WBS.2.1.13.5.1.4 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities - RTR | 145 | 2021-01-18 06:15 | 2021-01-29 07:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:15 | 2021-01-29 07:15 |  | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96003 | WBS.2.1.13.5.1.4.2 | N | N | Planned | BG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9447 - Round 1 | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM;LAURA FRY;DENISE MARSH | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | RTR - GL | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97775 | WBS.2.1.13.5.1.4.11 | N | N | Planned | BG - Clear Vendor Blocked Invoices (ZAP 32 - excludes IC) - Round 1 | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;LAURA FRY;DENISE MARSH;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96003 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | RTR - GL | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97776 | WBS.2.1.13.5.1.4.12 | N | N | Planned | BG - Clear Vendor Blocked Invoices (ZAP 32 - excludes IC) - Round 2 | 0.5 | 2021-01-25 08:15 | 2021-01-25 08:45 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;LAURA FRY;DENISE MARSH;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96001 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | RTR - GL | BG | 2021-01-25 | 2021-01-18 | 1 | Ramp Down
97777 | WBS.2.1.13.5.1.4.13 | N | N | Planned | BG - Clear Vendor Blocked Invoices (ZAP 32 - excludes IC) - Round 3 | 0.5 | 2021-01-28 08:15 | 2021-01-28 08:45 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;LAURA FRY;DENISE MARSH;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95999 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | RTR - GL | BG | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96004 | WBS.2.1.13.5.1.4.1 | N | N | Planned | BG - Perform ZMR11 Clearing in ECC for CC 9447 - Round 1 | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM;LAURA FRY;DENISE MARSH | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 96003 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | RTR - GL | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96001 | WBS.2.1.13.5.1.4.4 | N | N | Planned | BG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9447 - Round 2 | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | RTR - GL | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96002 | WBS.2.1.13.5.1.4.3 | N | N | Planned | BG - Perform ZMR11 Clearing in ECC for CC 9447 - Round 2 | 0.25 | 2021-01-25 08:15 | 2021-01-25 08:30 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96001 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 08:30 | RTR - GL | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95999 | WBS.2.1.13.5.1.4.6 | N | N | Planned | BG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9447 - Round 3 | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 08:15 | RTR - GL | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96000 | WBS.2.1.13.5.1.4.5 | N | N | Planned | BG - Perform ZMR11 Clearing in ECC for CC 9447 - Round 3 | 0.25 | 2021-01-28 08:15 | 2021-01-28 08:30 | DEBBIE HAMILTON | DEBORAH.HAMILTON@GAPAC.COM | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95999 |  |  | * |  | 2021-01-28 08:15 | 2021-01-28 08:30 | RTR - GL | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95998 | WBS.2.1.13.5.1.4.7 | N | N | Planned | BG - Cleanup moving average prices ECC (use SAP transaction MR21 if needed) | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | RTR - PC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95997 | WBS.2.1.13.5.1.5 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Prep Activities - SCM | 160 | 2021-01-18 06:15 | 2021-01-30 06:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:15 | 2021-01-30 06:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95996 | WBS.2.1.13.5.1.5.1 | N | N | Planned | BG - Communicate plans for frozen period | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SCM - TTN | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95995 | WBS.2.1.13.5.1.5.2 | N | N | Planned | BG - Execute deployments of printed board to outside facilities - prior to FCW - Last shipment 1/27/21 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;SAI TEAM;JOHN CASABURRI;DEAN PIPER;LISA SZCZUREK;JOHN J SMITH | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Dean.Piper@gapac.com;LISA.SZCZUREK@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM - TTN | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95994 | WBS.2.1.13.5.1.5.3 | N | N | Planned | BG - Dixie execute deployment aligning with ramp up | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | YUBIN KWON | YUBIN.KWON@GAPAC.COM | KAREN HERRING;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | KAREN.HERRING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95993 | WBS.2.1.13.5.1.5.4 | N | N | Planned | BG - Dixie confirm minimal changeover prior to and after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | BRIAN WHITE | BRIAN.WHITE@GAPAC.COM | ERIN MERLIE;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | erin.merlie@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95992 | WBS.2.1.13.5.1.5.5 | N | N | Planned | BG - Dixie: START schedule finalized through 3/13 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | BRIAN WHITE | BRIAN.WHITE@GAPAC.COM | ERIN MERLIE;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | erin.merlie@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95991 | WBS.2.1.13.5.1.5.6 | N | N | Planned | BG - Dixie: COMPLETE schedule finalized through 3/13 | 2 | 2021-01-25 09:15 | 2021-01-25 11:15 | BRIAN WHITE | BRIAN.WHITE@GAPAC.COM | ERIN MERLIE;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | erin.merlie@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 10845,95555,95992 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 11:15 | SCM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95989 | WBS.2.1.13.5.1.5.8 | N | N | Planned | BG - PPDS - Validate finished goods and printed board schedules are correct in S/4HANA | 4 | 2021-01-29 16:15 | 2021-01-29 20:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96566,95963,10851,95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-29 20:15 | SCM - TTN | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95988 | WBS.2.1.13.5.1.5.9 | N | N | Planned | BG - Check off with warehousing on incremental space requirements for Raw Materials | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | LYNN MCMURDO;JOHN J SMITH;LISA SZCZUREK;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SCM - TTN | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95987 | WBS.2.1.13.5.1.5.10 | N | N | Planned | BG - Export copy of production schedule to a file | 2 | 2021-01-29 20:15 | 2021-01-30 06:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,96566,95989 |  |  | * |  | 2021-01-29 20:15 | 2021-01-30 06:15 | SCM - TTN | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95985 | WBS.2.1.13.5.1.5.12 | N | N | Planned | BG - Validate advance orders for Raw Materials for appropriate build prior to cut over | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | SCM - TTN | BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95984 | WBS.2.1.13.5.1.5.13 | N | N | Planned | BG - Confirm - Plan inventory build for raw materials to support demand in first 2 weeks post Go-live | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | SCM - TTN | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97145 | WBS.2.1.13.5.1.5.14 | N | N | Planned | BG - Dixie ship D4 outbound STOs early to avoid FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | YUBIN KWON | YUBIN.KWON@GAPAC.COM | KAREN HERRING;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | KAREN.HERRING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97146 | WBS.2.1.13.5.1.5.15 | N | N | Planned | BG - Dixie remove manual adjustments in IBP on 1/28 (save a copy for reference) | 3 | 2021-01-28 09:45 | 2021-01-28 12:45 | BRIAN WHITE | BRIAN.WHITE@GAPAC.COM | Jeffrey Coy;SAI TEAM;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;BRAD WYMAN;LYNN MCMURDO;DEAN PIPER;MICHELLE SADLER | jeffrey.coy@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;BMSADLER@GAPAC.COM | Business | 91863,97148 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 12:45 | SCM | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96769 | WBS.2.1.13.5.7 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Clean-Up Activities | 160 | 2021-01-18 18:45 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-18 18:45 | 2021-01-30 18:45 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96768 | WBS.2.1.13.5.7.1 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Clean-Up Activities - EWM | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | [8 empty] | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96770 | WBS.2.1.13.5.7.1.1 | N | N | Planned | BG - Cleanup damaged and obsolete inventory | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96767 | WBS.2.1.13.5.7.2 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Clean-Up Activities - RTR | 160 | 2021-01-18 18:45 | 2021-01-30 18:45 | [8 empty] | * |  | 2021-01-18 18:45 | 2021-01-30 18:45 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96773 | WBS.2.1.13.5.7.2.1 | N | N | Planned | BG - Review and identify applicable open internal orders (that can be closed ) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - PS | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96772 | WBS.2.1.13.5.7.2.2 | N | N | Planned | BG - Run CKMTOPPRICDIFF in ECC and send to Buyers/Purchasing for review | 0.25 | 2021-01-29 06:15 | 2021-01-29 06:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:30 | RTR - PC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96771 | WBS.2.1.13.5.7.2.3 | N | N | Planned | BG - Review CKMTOPOPRICEDIFF for Storeroom Materials and communicate any needed adjustements to accounting | 1 | 2021-01-29 12:15 | 2021-01-29 13:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 96772,81706 |  |  | * |  | 2021-01-29 06:30 | 2021-01-29 07:30 | RTR - PC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97658 | WBS.2.1.13.5.7.2.5 | N | N | Planned | BG - Review Balance Sheet OIM accounts | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | RTR - GL | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97660 | WBS.2.1.13.5.7.2.7 | N | N | Planned | BG - Provide file for 1376 - SFG materials price, incl. purch board and printed board | 0.5 | 2021-01-18 18:45 | 2021-01-18 19:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 9178 |  |  | * |  | 2021-01-18 18:45 | 2021-01-18 19:15 | RTR - PC | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97661 | WBS.2.1.13.5.7.2.8 | N | N | Planned | BG - Run SM35 and correct any Posting Errors | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97662 | WBS.2.1.13.5.7.2.9 | N | N | Planned | BG - Check Acct 5999999 in ECC and clear | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95973 | WBS.2.1.13.5.3 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities | 175.75 | 2021-01-18 06:30 | 2021-01-30 22:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:00 | 2021-01-30 22:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95972 | WBS.2.1.13.5.3.1 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - AC | 86.75 | 2021-01-25 06:15 | 2021-01-30 13:00 |  |  |  |  | Business |  |  |  | * |  | 2021-01-25 06:15 | 2021-01-30 13:00 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95971 | WBS.2.1.13.5.3.1.1 | N | N | Planned | BG - Converting MRO - Confirm serialization for MRO | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | GERONIMO ROMERO | GERONIMO.ROMERO@GAPAC.COM | ROBBIE ISBELL;BRANDY MEREDITH;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Daniel.Isbell@GAPAC.com;Brandy.Meredith@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | AC | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95970 | WBS.2.1.13.5.3.1.2 | N | N | Planned | BG - Converting Final Work Order time confirmation | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | AC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95969 | WBS.2.1.13.5.3.1.3 | N | N | Planned | BG - Converting Close Open Work orders | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95968 | WBS.2.1.13.5.3.1.4 | N | N | Planned | BG - Converting MRO - Provide final list of equipment (name, type, number) | 0.75 | 2021-01-30 12:15 | 2021-01-30 13:00 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:00 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96778 | WBS.2.1.13.5.3.1.8 | N | N | Planned | BG - Printing Close Open Work orders | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96777 | WBS.2.1.13.5.3.1.7 | N | N | Planned | BG - Printing Final Work Order time confirmation | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | AC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96776 | WBS.2.1.13.5.3.1.6 | N | N | Planned | BG - Printing MRO - Confirm serialization for MRO | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | AC | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96775 | WBS.2.1.13.5.3.1.5 | N | N | Planned | BG - Printing MRO - Provide final list of equipment (name, type, number) | 0.75 | 2021-01-30 12:15 | 2021-01-30 13:00 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:00 | AC | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95967 | WBS.2.1.13.5.3.2 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - OTC | 2 | 2021-01-29 08:15 | 2021-01-29 10:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-29 08:15 | 2021-01-29 10:15 |  | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95966 | WBS.2.1.13.5.3.2.1 | N | N | Planned | BG - Validate quality entries on the Inventory preload file from Quality POV | 2 | 2021-01-29 08:15 | 2021-01-29 10:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95955 |  |  | * |  | 2021-01-29 08:15 | 2021-01-29 10:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95965 | WBS.2.1.13.5.3.3 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - SCM | 36 | 2021-01-27 06:15 | 2021-01-29 10:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-27 06:15 | 2021-01-29 10:15 |  | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95964 | WBS.2.1.13.5.3.3.1 | N | N | Planned | BG - Review Open PO's for Vitals - document status | 0.67 | 2021-01-27 06:15 | 2021-01-27 06:55 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:55 | SCM - TTN | BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95963 | WBS.2.1.13.5.3.3.2 | N | N | Planned | BG - Create Planned orders for Semi finished goods Bowling Green | 4 | 2021-01-29 06:15 | 2021-01-29 10:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | LYNN MCMURDO;JOHN J SMITH;LISA SZCZUREK;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 11032,95149,90831,9669,95314,96566,10852,97573,10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 10:15 | SCM - TTN | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95961 | WBS.2.1.13.5.3.4 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - EWM | 91.75 | 2021-01-25 06:15 | 2021-01-30 18:00 |  |  |  |  | Business |  |  |  | * |  | 2021-01-25 06:15 | 2021-01-30 18:00 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95959 | WBS.2.1.13.5.3.4.2 | N | N | Planned | BG - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EWM | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95958 | WBS.2.1.13.5.3.4.3 | N | N | Planned | BG - Validate storage location naming and sizes (if required) | 0.5 | 2021-01-28 06:30 | 2021-01-28 07:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852,95959 |  |  | * |  | 2021-01-28 06:30 | 2021-01-28 07:00 | EWM | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95956 | WBS.2.1.13.5.3.4.5 | N | N | Planned | BG - End & validate Cycle count inventory - All Items | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | BEAU EARLS;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95955 | WBS.2.1.13.5.3.4.6 | N | N | Planned | BG - Send Extracted WMS extracted file for finished goods to Quality | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95954 | WBS.2.1.13.5.3.4.7 | N | N | Planned | BG - Validate shipment doc deleted by KBX have been removed from ECC | 1 | 2021-01-30 17:00 | 2021-01-30 18:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,96017,92322,90697 |  |  | * |  | 2021-01-30 17:00 | 2021-01-30 18:00 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95953 | WBS.2.1.13.5.3.4.8 | N | N | Planned | BG - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 1 | 2021-01-30 13:15 | 2021-01-30 14:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,96770 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 14:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95951 | WBS.2.1.13.5.3.4.10 | N | N | Planned | BG - Run open inventory display by LPN detail and upload into Teams quality file | 1 | 2021-01-30 14:15 | 2021-01-30 15:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95953 |  |  | * |  | 2021-01-30 14:15 | 2021-01-30 15:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95949 | WBS.2.1.13.5.3.4.12 | N | N | Planned | BG - Ensure all locations are not in blocked status | 1 | 2021-01-30 15:15 | 2021-01-30 16:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95951 |  |  | * |  | 2021-01-30 15:15 | 2021-01-30 16:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95948 | WBS.2.1.13.5.3.4.13 | N | N | Planned | BG - Operations confirms all system activities to perform prior to cutover have been completed. | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95947 | WBS.2.1.13.5.3.4.14 | N | N | Planned | BG - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95946 | WBS.2.1.13.5.3.4.15 | N | N | Planned | BG - All shipments are load end and none started. | 0.5 | 2021-01-30 16:15 | 2021-01-30 16:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95949 |  |  | * |  | 2021-01-30 16:15 | 2021-01-30 16:45 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93258 | WBS.2.1.13.5.3.4.18 | N | N | Planned | BG - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;DEAN PIPER | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95943 | WBS.2.1.13.5.3.5 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - RTR | 31 | 2021-01-29 06:15 | 2021-01-30 21:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-29 06:15 | 2021-01-30 21:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95942 | WBS.2.1.13.5.3.5.1 | N | N | Planned | BG - Review CKMTOPOPRICEDIFF for Vital Supplies and communicate any needed adjustements to accounting | 1 | 2021-01-29 06:30 | 2021-01-29 07:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | Amanda Smith;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Amanda.Smith@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96772 |  |  | * |  | 2021-01-29 06:30 | 2021-01-29 07:30 | RTR - PC | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95941 | WBS.2.1.13.5.3.5.2 | N | N | Planned | BG - Check with Warehouse regarding any expected Board shipments which may be reconciling items for IC | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | RTR - GL | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95940 | WBS.2.1.13.5.3.5.3 | N | N | Planned | BG - Check with warehouse (for completion) then run MB5L and review all inventory balances prior to cutoff | 3 | 2021-01-30 18:15 | 2021-01-30 21:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 21:15 | RTR - GL | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95939 | WBS.2.1.13.5.3.5.4 | N | N | Planned | BG - Review month-end count and make MB1A adjustments - coating, sw, glue | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | RTR - GL | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95937 | WBS.2.1.13.5.3.5.6 | N | N | Planned | BG - Run ZAP34 and ZMR11 and tie GRIR to ledger before system cutover | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JoAnna.Johnson@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | RTR - GL | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95936 | WBS.2.1.13.5.3.6 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Cut-Off Activities - PTP | 52.5 | 2021-01-26 08:15 | 2021-01-29 12:45 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 08:30 | 2021-01-26 10:15 |  | BG | 2021-01-29 | 2021-01-26 | 2 | Ramp Down
95935 | WBS.2.1.13.5.3.6.1 | N | N | Planned | BG - Process Returns And Credit Memo For Bowling Green | 2 | 2021-01-26 08:15 | 2021-01-26 10:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | Mark Bernard;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO | MARK.BERNARD@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;* | Business | 96009 |  |  | * |  | 2021-01-26 08:15 | 2021-01-26 10:15 | PTP - Procurement/Stores | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95933 | WBS.2.1.13.5.3.6.3 | N | N | Planned | BG - Start Task - Record all Storeroom Transactions Using Business Continuity Forms | 0.25 | 2021-01-29 12:30 | 2021-01-29 12:45 | GERONIMO ROMERO | GERONIMO.ROMERO@GAPAC.COM | BRANDY MEREDITH;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Brandy.Meredith@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 95782,81706 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 08:45 | PTP - Procurement/Stores | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
95931 | WBS.2.1.13.5.3.7 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - EWM Inventory Conversion Precursor | 175.75 | 2021-01-18 06:30 | 2021-01-30 22:15 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 06:00 | 2021-01-30 22:15 |  | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95930 | WBS.2.1.13.5.3.7.1 | N | N | Planned | BG - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation (business continuity form) | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | BG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95929 | WBS.2.1.13.5.3.7.2 | N | N | Planned | BG - Confirm active items - Vitals that are currently running (things that cannot be cycle counted beforehand) | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 06:30 | EWM | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95928 | WBS.2.1.13.5.3.7.3 | N | N | Planned | BG - Block all non-current items to prevent movement or use | 2 | 2021-01-26 11:15 | 2021-01-26 13:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10854,95927 |  |  | * |  | 2021-01-26 11:15 | 2021-01-26 13:15 | EWM | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95927 | WBS.2.1.13.5.3.7.4 | N | N | Planned | BG - Cycle count and adjust all non-current items | 5 | 2021-01-26 06:15 | 2021-01-26 11:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 11:15 | EWM | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95926 | WBS.2.1.13.5.3.7.5 | N | N | Planned | BG - Run Inventory Reports for Raw Materials | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | EWM | BG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95924 | WBS.2.1.13.5.3.7.7 | N | N | Planned | BG - Confirm with the mill that we have communicated to Warehouse personnel that any inventory placed on Q-hold during the FCW must be manually managed to ensure no held items are shipped to the customer | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | BEAU EARLS;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EWM | BG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
95923 | WBS.2.1.13.5.3.7.8 | N | N | Planned | BG - Validate Empty Trailer Upload files (mill, DC, pulp) | 1 | 2021-01-30 18:00 | 2021-01-30 19:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,95954 |  |  | * |  | 2021-01-30 18:00 | 2021-01-30 19:00 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95922 | WBS.2.1.13.5.3.7.9 | N | N | Planned | BG - Ensure paper consumption is current - clear any open items ICPAQS | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | KELLY LEWIS | kelly.lewis@gapac.com | Chad Coy;Brad Young;DEAN PIPER;LYNN MCMURDO;SAI TEAM | CHAD.COY@GAPAC.com;Brad.YOUNG@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95921 | WBS.2.1.13.5.3.7.10 | N | N | Planned | BG - Identify pilot transactions to perform after system comes up on EWM | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:00 | 2021-01-18 06:15 | LSA | BG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95920 | WBS.2.1.13.5.3.7.11 | N | N | Planned | BG - Stage to converting lines raw materials needed during entire shutdown period | 4 | 2021-01-29 12:15 | 2021-01-29 16:15 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 16:15 | EWM | BG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95919 | WBS.2.1.13.5.3.7.12 | N | N | Planned | BG - Confirm last raw material receipt in ECC at shutdown | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95918 | WBS.2.1.13.5.3.7.13 | N | N | Planned | BG - Verify all picked inventory has been loaded and PGI | 0.5 | 2021-01-30 19:15 | 2021-01-30 19:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95233 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:45 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95917 | WBS.2.1.13.5.3.7.14 | N | N | Planned | BG - CLEAR ANY OPEN CYCLE COUNT TRANSACTIONS IN MI20 | 1 | 2021-01-26 08:15 | 2021-01-26 09:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 96009 |  |  | * |  | 2021-01-26 08:15 | 2021-01-26 09:15 | PTP - Procurement/Stores | BG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
95916 | WBS.2.1.13.5.3.7.15 | N | N | Planned | BG - Confirm last shipment complete in ECC at shutdown | 0.5 | 2021-01-30 19:45 | 2021-01-30 20:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95918 |  |  | * |  | 2021-01-30 19:45 | 2021-01-30 20:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95915 | WBS.2.1.13.5.3.7.16 | N | N | Planned | BG - iCPAQS - Production counts entered at the end of each shift in ICPAQS should not be submitted to SAP until the system is back up. | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95914 | WBS.2.1.13.5.3.7.17 | N | N | Planned | BG - Minimize open transactions (Open AR/AP) | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95912 | WBS.2.1.13.5.3.7.19 | N | N | Planned | BG - Delete shipments and deliveries for orders not shipping before cutover (mill only) | 1.5 | 2021-01-30 20:15 | 2021-01-30 21:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95916 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 21:45 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95911 | WBS.2.1.13.5.3.7.20 | N | N | Planned | BG - Final Cycle Count FGS and adjust | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95910 | WBS.2.1.13.5.3.7.21 | N | N | Planned | BG - Final Cycle Count WIP and adjust | 2 | 2021-01-30 12:15 | 2021-01-30 14:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95909 | WBS.2.1.13.5.3.7.22 | N | N | Planned | BG - Final Cycle Count Vital Supplies and adjust - Send Amanda final month-end counts | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Jeana.Harrer@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95908 | WBS.2.1.13.5.3.7.23 | N | N | Planned | BG - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 0.25 | 2021-01-30 21:45 | 2021-01-30 22:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95912 |  |  | * |  | 2021-01-30 21:45 | 2021-01-30 22:00 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95906 | WBS.2.1.13.5.3.7.25 | N | N | Planned | BG - Verify that the mill has downloaded the open yard management and verified trailer status' are correct prior to upload file | 0.25 | 2021-01-30 22:00 | 2021-01-30 22:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95908 |  |  | * |  | 2021-01-30 22:00 | 2021-01-30 22:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95905 | WBS.2.1.13.5.3.7.26 | N | N | Planned | BG - Communicate to Converting to Start Shutdown prior to Cutover Window | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95903 | WBS.2.1.13.5.3.7.28 | N | N | Planned | BG - At mills, operations confirms system activities to perform for mill production & converting prior to cutover have been completed | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 20:15 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95902 | WBS.2.1.13.5.3.7.29 | N | N | Planned | BG - Notify ICPAQS that Converting Operations have stopped | 0.25 | 2021-01-30 19:15 | 2021-01-30 19:30 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95905 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:30 | EWM | BG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95901 | WBS.2.1.13.5.4 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Communications | 0.5 | 2021-01-29 12:15 | 2021-01-29 12:45 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 |  | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
95783 | WBS.2.1.13.5.4.1 | N | N |  | Ramp Down ¦ Business Activities - Bowling Green - Communications - PTP | 0.5 | 2021-01-29 12:15 | 2021-01-29 12:45 |  |  |  |  | Business |  |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 |  | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
95782 | WBS.2.1.13.5.4.1.1 | N | N | Planned | BG - Send Communication - PLACEHOLDER for Goods Issue Communication; Who can do this in the system? | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 96008,81706 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | PTP | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
95781 | WBS.2.1.13.5.4.1.2 | N | N | Planned | BG - Send Communication - Approve PRs in Backlog, POs to Stop EOB 6/26 | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 96008,81706 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | PTP | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
95780 | WBS.2.1.13.5.4.1.3 | N | N | Planned | BG - Send Communication - Last POs Issued, Please Use Manual PO Process | 0.25 | 2021-01-29 12:30 | 2021-01-29 12:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 95781,81706 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 08:45 | PTP | BG | 2021-01-29 | 2021-01-18 | 1 | Ramp Down
96257 | WBS.2.1.13.7 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic | 71.25 | 2021-01-26 06:15 | 2021-01-30 13:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96256 | WBS.2.1.13.7.1 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Prep Activities | 36 | 2021-01-26 06:15 | 2021-01-28 10:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:30 |  |  | 2021-01-28 | 2021-01-25 | 2 | Ramp Down
96255 | WBS.2.1.13.7.1.1 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Prep Activities - OTC | 4 | 2021-01-28 06:15 | 2021-01-28 10:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 |  |  | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96254 | WBS.2.1.13.7.1.1.1 | N | N | Planned | SAT - Disposition (Clean up) Q-holds in existing system | 4 | 2021-01-28 06:15 | 2021-01-28 10:15 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SLADE HURST;SAI TEAM;KELLY JANSSEN | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MICHAEL.JANSSEN@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | OTC | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96253 | WBS.2.1.13.7.1.2 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Prep Activities - EWM | 33 | 2021-01-26 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:30 |  |  | 2021-01-28 | 2021-01-25 | 2 | Ramp Down
96252 | WBS.2.1.13.7.1.2.1 | N | N | Planned | SAT - Provide final list of site users | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | PAT GRANTHAM | Pat@southatlanticpackaging.com | RAMON MATHISON;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Ramon@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96109 | WBS.2.1.13.7.1.2.4 | N | N | Planned | SAT - Start Cycle count inventory - All Items | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | ROBERT TEAGUE | Robert@southatlanticpackaging.com | SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96108 | WBS.2.1.13.7.1.2.5 | N | N | Planned | SAT - Provide approvers and levels for write-offs | 0.25 | 2021-01-28 06:30 | 2021-01-28 06:45 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | TRENT SCHICK;SAI TEAM | Trent.Schick@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96252 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96106 | WBS.2.1.13.7.1.2.7 | N | N | Planned | SAT - Change inventory status for items set to expire during blackout period. | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SLADE HURST;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96105 | WBS.2.1.13.7.1.2.8 | N | N | Planned | SAT - Manual Config Steps (Maintain Users) | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SLADE HURST;TRENT SCHICK;PATRICK BROWNING;SAI TEAM;EWM TEAM | SLADE.HURST@GAPAC.COM;Trent.Schick@gapac.com;PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 93400,4501,10852 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96104 | WBS.2.1.13.7.1.2.9 | N | N | Planned | SAT - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SLADE HURST;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | SAT | 2021-01-28 | 2021-01-25 | 2 | Ramp Down
96103 | WBS.2.1.13.7.1.2.10 | N | N | Planned | SAT - Shut co pack production (one week prior) | 0.25 | 2021-01-26 06:15 | 2021-01-26 06:30 | JARED GORDON | jared.gordon@gapac.com | SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10854 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | SAT | 2021-01-26 | 2021-01-25 | 2 | Ramp Down
96102 | WBS.2.1.13.7.1.2.11 | N | N | Planned | SAT - Close out all existing subcontacting (copack) purchase orders. | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | JARED GORDON | jared.gordon@gapac.com | SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10853 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 07:30 | EWM | SAT | 2021-01-27 | 2021-01-25 | 2 | Ramp Down
96101 | WBS.2.1.13.7.1.3 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Prep Activities - SCM | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 |  |  | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96100 | WBS.2.1.13.7.1.3.1 | N | N | Planned | SAT -Dixie avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | SARA LUX | SARA.LUX@GAPAC.COM | KAREN HERRING;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;KELLY JANSSEN;MICHELLE SADLER | KAREN.HERRING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;MICHAEL.JANSSEN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 95147,10852 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96099 | WBS.2.1.13.7.1.3.2 | N | N | Planned | SAT - Align co-pack schedule to avoid 1 wk prior & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | JARED TAYLOR | JARED.TAYLOR@GAPAC.COM | Wilson Lyle;Brandon Tillett;KAITLYN JANSEN;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;MICHELLE SADLER | wilson.lyle@gapac.com;brandon.tillett@gapac.com;Kaitlyn.Jansen@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 95146,10852 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96098 | WBS.2.1.13.7.2 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Clean-Up Activities | 54 | 2021-01-26 06:30 | 2021-01-29 12:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 12:30 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96097 | WBS.2.1.13.7.2.1 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Clean-Up Activities - EWM | 54 | 2021-01-26 06:30 | 2021-01-29 12:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 12:30 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96096 | WBS.2.1.13.7.2.1.1 | N | N | Planned | SAT - Clear vendor bucket | 0.25 | 2021-01-26 06:30 | 2021-01-26 06:45 | SABRINA GRINDALL | Sabrina@southatlanticpackaging.com | SLADE HURST;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 96103 |  |  | * |  | 2021-01-25 06:30 | 2021-01-25 06:45 | EWM | SAT | 2021-01-26 | 2021-01-25 | 2 | Ramp Down
96093 | WBS.2.1.13.7.2.1.4 | N | N | Planned | SAT - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | SLADE HURST | SLADE.HURST@GAPAC.COM | PATRICK BROWNING;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EWM | SAT | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96091 | WBS.2.1.13.7.2.1.6 | N | N | Planned | SAT - End & validate Cycle count inventory - All Items | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | SABRINA GRINDALL | Sabrina@southatlanticpackaging.com | KAITLYN JANSEN;SAI TEAM;TRENT SCHICK | Kaitlyn.Jansen@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Trent.Schick@gapac.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | SAT | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96090 | WBS.2.1.13.7.2.1.7 | N | N | Planned | SAT - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EWM | SAT | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96086 | WBS.2.1.13.7.2.1.11 | N | N | Planned | SAT - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96085 | WBS.2.1.13.7.2.1.12 | N | N | Planned | SAT - Operations confirms all system activities to perform prior to cutover have been completed. | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96083 | WBS.2.1.13.7.2.1.14 | N | N | Planned | SAT - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96082 | WBS.2.1.13.7.2.1.15 | N | N | Planned | SAT - All shipments are load end and none started. | 4 | 2021-01-28 08:15 | 2021-01-28 12:15 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 96083 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 12:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96081 | WBS.2.1.13.7.2.1.16 | N | N | Planned | SAT - Identify IB STO on Friday before cutover, flag trailer, and spot at door | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | MICHAEL ROBICHAUD | Michael@southatlanticpackaging.com | SHIPPING DEPT;SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | Shippingwp@southatlanticpackaging.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96080 | WBS.2.1.13.7.2.2 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Clean-Up Activities - OTC | 4 | 2021-01-28 06:15 | 2021-01-28 10:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 |  |  | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96079 | WBS.2.1.13.7.2.2.1 | N | N | Planned | SAT - Disposition (Clean up) Q-holds in existing system | 4 | 2021-01-28 06:15 | 2021-01-28 10:15 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | SLADE HURST;SAI TEAM;KELLY JANSSEN | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MICHAEL.JANSSEN@GAPAC.COM | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 10:15 | OTC - Quality | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96078 | WBS.2.1.13.7.3 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Cut-Off Activities | 39.25 | 2021-01-28 06:15 | 2021-01-30 13:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96077 | WBS.2.1.13.7.3.1 | N | N |  | Ramp Down ¦ Business Activities - South Atlantic - Cut-Off Activities - EWM | 39.25 | 2021-01-28 06:15 | 2021-01-30 13:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96076 | WBS.2.1.13.7.3.1.1 | N | N | Planned | SAT - Send Extracted WMS extracted file for finished goods to Quality | 0.25 | 2021-01-30 13:15 | 2021-01-30 13:30 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | TRENT SCHICK;SAI TEAM | Trent.Schick@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96074 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 13:30 | EWM | SAT | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96075 | WBS.2.1.13.7.3.1.2 | N | N | Planned | SAT - Cleanup NOI inventory | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | TRENT SCHICK;SAI TEAM | Trent.Schick@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | SAT | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96074 | WBS.2.1.13.7.3.1.3 | N | N | Planned | SAT - Cleanup Damaged and obsolete inventory | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | TRENT SCHICK;SAI TEAM | Trent.Schick@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | SAT | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96072 | WBS.2.1.13.7.3.1.5 | N | N | Planned | SAT - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | SABRINA GRINDALL | Sabrina@southatlanticpackaging.com | SAI TEAM;KAITLYN JANSEN;TRENT SCHICK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | Business | 10852 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96071 | WBS.2.1.13.7.3.1.6 | N | N | Planned | SAT - Upload to RDC SAP Network Teams Page under Inventory. | 2 | 2021-01-28 07:15 | 2021-01-28 09:15 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SAI TEAM;TRENT SCHICK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Trent.Schick@gapac.com | Business | 96085 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 09:15 | EWM | SAT | 2021-01-28 | 2021-01-18 | 1 | Ramp Down
96142 | WBS.2.1.13.9 | N | N |  | Ramp Down ¦ Business Activities - Rexdale Dominion | 169.25 | 2021-01-18 06:15 | 2021-01-30 15:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 15:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96143 | WBS.2.1.13.9.1 | N | N |  | Ramp Down ¦ Business Activities - Rexdale Dominion - Prep Activities | 129 | 2021-01-18 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 07:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96146 | WBS.2.1.13.9.1.2 | N | N |  | Ramp Down ¦ Business Activities - Rexdale - Prep Activities - EWM | 129 | 2021-01-18 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 07:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96147 | WBS.2.1.13.9.1.2.1 | N | N | Planned | REX - Provide final list of site users | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | DILLON RAGHOONATHSINGH | dillon.rsingh@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | REX | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96148 | WBS.2.1.13.9.1.2.2 | N | N | Planned | REX - Update and validate site printers | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | DUY NGUYEN | duy.nguyen@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96150 | WBS.2.1.13.9.1.2.4 | N | N | Planned | REX - Start Cycle count inventory - All Items | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | JEFF BROWN | Jeff.martin@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | REX | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
96155 | WBS.2.1.13.9.1.2.9 | N | N | Planned | REX - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | REX | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
96158 | WBS.2.1.13.9.1.3 | N | N |  | Ramp Down ¦ Business Activities - Rexdale - Prep Activities - SCM | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | [8 empty] | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 |  |  | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96159 | WBS.2.1.13.9.1.3.1 | N | N | Planned | REX -Dixie avoid outbound STO's 1 wk b4 & 1 wk after FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | HANNAH NEIMAN | HANNAH.NEIMAN@GAPAC.COM | KAREN HERRING;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;DANIEL ROSS;MICHELLE SADLER | KAREN.HERRING@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;DANIEL.ROSS@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147,10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | SCM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96161 | WBS.2.1.13.9.2 | N | N |  | Ramp Down ¦ Business Activities - Rexdale - Clean-Up Activities | 38.25 | 2021-01-27 06:15 | 2021-01-29 12:30 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-29 12:30 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96162 | WBS.2.1.13.9.2.1 | N | N |  | Ramp Down ¦ Business Activities - Rexdale - Clean-Up Activities - EWM | 38.25 | 2021-01-27 06:15 | 2021-01-29 12:30 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-29 12:30 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96165 | WBS.2.1.13.9.2.1.3 | N | N | Planned | REX - Cleanup and cycle count repack area | 8 | 2021-01-27 06:15 | 2021-01-27 14:15 | JEFF BROWN | Jeff.martin@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 14:15 | EWM | REX | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
96166 | WBS.2.1.13.9.2.1.4 | N | N | Planned | REX - Verify all RSD's are complete & approved | 0.25 | 2021-01-28 06:15 | 2021-01-28 06:30 | SLADE HURST | SLADE.HURST@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:30 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96168 | WBS.2.1.13.9.2.1.6 | N | N | Planned | REX - End & validate Cycle count inventory - All Items | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | JEFF BROWN | Jeff.martin@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | REX | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96169 | WBS.2.1.13.9.2.1.7 | N | N | Planned | REX - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | EWM | REX | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
96174 | WBS.2.1.13.9.2.1.12 | N | N | Planned | REX - Operations confirms all system activities to perform prior to cutover have been completed. | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | DUY NGUYEN | duy.nguyen@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96175 | WBS.2.1.13.9.2.1.13 | N | N | Planned | REX - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 1 | 2021-01-28 07:15 | 2021-01-28 08:15 | DILLON RAGHOONATHSINGH | dillon.rsingh@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96174,10852 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 08:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96176 | WBS.2.1.13.9.2.1.14 | N | N | Planned | REX - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 2 | 2021-01-28 08:15 | 2021-01-28 10:15 | DUY NGUYEN | duy.nguyen@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96175 |  |  | * |  | 2021-01-28 08:15 | 2021-01-28 10:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96177 | WBS.2.1.13.9.2.1.15 | N | N | Planned | REX - All shipments are load end and none started. | 4 | 2021-01-28 10:15 | 2021-01-28 14:15 | DUY NGUYEN | duy.nguyen@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96176 |  |  | * |  | 2021-01-28 10:15 | 2021-01-28 14:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96181 | WBS.2.1.13.9.3 | N | N |  | Ramp Down ¦ Business Activities - Rexdale Dominion - Cut-Off Activities | 41.25 | 2021-01-28 06:15 | 2021-01-30 15:30 | [8 empty] | * |  | 2021-01-28 06:15 | 2021-01-30 15:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96182 | WBS.2.1.13.9.3.1 | N | N |  | Ramp Down ¦ Business Activities - Rexdale Dominion - Cut-Off Activities - EWM | 39.25 | 2021-01-28 06:15 | 2021-01-30 13:30 | [8 empty] | * |  | 2021-01-28 06:15 | 2021-01-30 13:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96183 | WBS.2.1.13.9.3.1.1 | N | N | Planned | REX - Send Extracted WMS extracted file for finished goods to Quality | 0.25 | 2021-01-30 13:15 | 2021-01-30 13:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96185 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 13:30 | EWM | REX | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96185 | WBS.2.1.13.9.3.1.3 | N | N | Planned | REX - Cleanup Damaged and obsolete inventory | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | DILLON RAGHOONATHSINGH | dillon.rsingh@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | REX | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96186 | WBS.2.1.13.9.3.1.4 | N | N | Planned | REX - Submit inventory reports for upload to EWM. | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96187 | WBS.2.1.13.9.3.1.5 | N | N | Planned | REX - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-28 07:15 | 2021-01-28 07:45 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96186 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 07:45 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96188 | WBS.2.1.13.9.3.1.6 | N | N | Planned | REX - Upload to RDC SAP Network Teams Page under Inventory. | 2 | 2021-01-28 07:15 | 2021-01-28 09:15 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96174,10852 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 09:15 | EWM | REX | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
96190 | WBS.2.1.13.9.3.2 | N | N |  | Ramp Down ¦ Business Activities - Rexdale Dominion - Cut-Off Activities - OTC | 2 | 2021-01-30 13:30 | 2021-01-30 15:30 | [8 empty] | * |  | 2021-01-30 13:30 | 2021-01-30 15:30 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
96191 | WBS.2.1.13.9.3.2.1 | N | N | Planned | REX - Validate quality entries on the Inventory preload file from Quality POV | 2 | 2021-01-30 13:30 | 2021-01-30 15:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | SLADE HURST;ELIZABETH JOHNSON;SAI TEAM | SLADE.HURST@GAPAC.COM;ELIZABETH.JOHNSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96183 |  |  | * |  | 2021-01-30 13:30 | 2021-01-30 15:30 | EWM | REX | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
91372 | WBS.2.1.13.11 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson | 186.5 | 2021-01-18 06:15 | 2021-01-31 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 03:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
12168 | WBS.2.1.13.11.1 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities | 173 | 2021-01-18 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:15 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
11101 | WBS.2.1.13.11.1.1 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities - AC | 96 | 2021-01-18 06:15 | 2021-01-26 06:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-26 06:15 |  | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
92988 | WBS.2.1.13.11.1.1.1 | N | N | Planned | PTH - MRO - Finalize final bin upload file | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93166 | WBS.2.1.13.11.1.1.2 | N | N | Planned | PTH - MRO - Cleanup AS8 quantity types | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93152 | WBS.2.1.13.11.1.1.3 | N | N | Planned | PTH - MRO - Provide final list of equipment (name, type, number) | 0.75 | 2021-01-25 06:15 | 2021-01-25 07:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;MASON DRAKE;Evan Preseau;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;EVAN.PRESEAU@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:00 | AC | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
92991 | WBS.2.1.13.11.1.1.4 | N | N | Planned | PTH - Close Open Work orders | 16 | 2021-01-25 06:15 | 2021-01-26 06:15 | RANDALL KNAPP | Randall.Knapp@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-26 06:15 | AC | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
11043 | WBS.2.1.13.11.1.2 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities - EWM | 10.25 | 2021-01-18 06:15 | 2021-01-18 16:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 16:30 |  | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93168 | WBS.2.1.13.11.1.2.3 | N | N | Planned | PTH - Transition to emergency PO process for outage | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | KATIE PARKER | Katie.Parker@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93164 | WBS.2.1.13.11.1.2.4 | N | N | Planned | PTH - MRO - Create any new locations required by EWM | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 08:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93163 | WBS.2.1.13.11.1.2.5 | N | N | Planned | PTH - Verify any new locations have signs/labels | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | DARRYL JOHNSON | DARRYL.JOHNSON@GAPAC.COM | ANDY JONES;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Gibson.Jones@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 08:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93161 | WBS.2.1.13.11.1.2.6 | N | N | Planned | PTH - Run Inventory Reports for MRO | 3 | 2021-01-18 06:30 | 2021-01-18 09:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 09:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93140 | WBS.2.1.13.11.1.2.7 | N | N | Planned | PTH - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule (Tissue) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93143 | WBS.2.1.13.11.1.2.8 | N | N | Planned | PTH - Provide final list of site users | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | CJ KAUTH | christopher.kauth@gapac.com | JT THOMAS;JAMES COWELL;SAI TEAM | Jerry.Thomas2@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93171 | WBS.2.1.13.11.1.2.9 | N | N | Planned | PTH - Begin working on unloading Inbound STOs to ensure all are completed before FCW (Tissue) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93170 | WBS.2.1.13.11.1.2.10 | N | N | Planned | PTH - Review all inbound STOs to have visibility of which inbounds are due during FCW, and send request to have as many inbounds as possible shipped early or late (Tissue) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93142 | WBS.2.1.13.11.1.2.11 | N | N | Planned | PTH - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | DARRYL JOHNSON | DARRYL.JOHNSON@GAPAC.COM | CJ KAUTH;ROBBIE GARNER;JAMES COWELL;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93169 | WBS.2.1.13.11.1.2.13 | N | N | Planned | PTH - Start pre-shipments of outbounds prior to cutover to minimize activity during cutover (Tissue) | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93159 | WBS.2.1.13.11.1.2.14 | N | N | Planned | PTH - Provide approvers and levels for write-offs | 2 | 2021-01-18 07:15 | 2021-01-18 09:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 93143 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 09:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93158 | WBS.2.1.13.11.1.2.15 | N | N | Planned | PTH - MRO - Cleanup obsolete storage locations from system | 8 | 2021-01-18 08:30 | 2021-01-18 16:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 93164 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 16:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
11123 | WBS.2.1.13.11.1.3 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities - PTP | 16 | 2021-01-25 07:15 | 2021-01-26 07:15 | [8 empty] | * |  | 2021-01-25 07:15 | 2021-01-26 07:15 |  | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
93175 | WBS.2.1.13.11.1.3.2 | N | N | Planned | PTH - Mill buyers to raise request to update material UoM | 0.5 | 2021-01-25 07:15 | 2021-01-25 07:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95644 |  |  | * |  | 2021-01-25 07:15 | 2021-01-25 07:45 | PTP | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93174 | WBS.2.1.13.11.1.3.3 | N | N | Planned | PTH - Review open GRIR, and close any with final invoice received | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | PTP | PTH | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
36507 | WBS.2.1.13.11.1.4 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities - RTR | 173 | 2021-01-18 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:15 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93147 | WBS.2.1.13.11.1.4.1 | N | N | Planned | PTH - Perform ZMR11 Clearing in ECC for CC 9275 - Round 1 | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Malinda Spaeth;ALYSHIA RASMUSSEN;JAZMINE STEINFELDT;LAURA FRY;DENISE MARSH | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Malinda.Spaeth@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;JAZMINE.STEINFELDT@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 93150 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | RTR - GL | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93150 | WBS.2.1.13.11.1.4.2 | N | N | Planned | PTH - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9275 - Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Malinda Spaeth;ALYSHIA RASMUSSEN;JAZMINE STEINFELDT;LAURA FRY;DENISE MARSH | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Malinda.Spaeth@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;JAZMINE.STEINFELDT@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97649 | WBS.2.1.13.11.1.4.36 | N | N | Planned | PTH - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule (Towel) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | marshal.savage@gapac.com;Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97650 | WBS.2.1.13.11.1.4.37 | N | N | Planned | PTH - Begin working on unloading Inbound STOs to ensure all are completed before FCW (Towel) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | marshal.savage@gapac.com;Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97651 | WBS.2.1.13.11.1.4.38 | N | N | Planned | PTH - Review all inbound STOs to have visibility of which inbounds are due during FCW, and send request to have as many inbounds as possible shipped early or late (Towel) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97652 | WBS.2.1.13.11.1.4.39 | N | N | Planned | PTH - Start pre-shipments of outbounds prior to cutover to minimize activity during cutover (Towel) | 3 | 2021-01-18 06:15 | 2021-01-18 09:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 09:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97665 | WBS.2.1.13.11.1.4.8 | N | N | Planned | PTH - Run BI reports for Inventory prior to cutoff | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | RTR - PC | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93145 | WBS.2.1.13.11.1.4.3 | N | N | Planned | PTH - Perform ZMR11 Clearing in ECC for CC 9275 - Round 3 | 0.25 | 2021-01-28 07:15 | 2021-01-28 07:30 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANDRE GONZAQUE;ANNETTE GONZALES;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93148 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 07:30 | RTR - GL | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
10849 | WBS.2.1.13.11.1.5 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Prep Activities - SCM | 161.25 | 2021-01-18 06:15 | 2021-01-30 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 07:30 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94712 | WBS.2.1.13.11.1.5.1 | N | N | Planned | PTH - RET/Towel Ship D4 outbound STOs early to avoid FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | VALERIE TURNER | VALERIE.TURNER@GAPAC.COM | TWANDA JENNINGS;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;MICHELLE SADLER | TDJENNIN@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94963 | WBS.2.1.13.11.1.5.3 | N | N | Planned | PTH - RET/Towel Execute deployment to align with ramp up | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | VALERIE TURNER | VALERIE.TURNER@GAPAC.COM | TWANDA JENNINGS;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;MICHELLE SADLER | TDJENNIN@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94965 | WBS.2.1.13.11.1.5.5 | N | N | Planned | PTH - RET/Tissue Execute depoyment to align with ramp up | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | TWANDA JENNINGS | TDJENNIN@GAPAC.com | VALERIE TURNER;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;MICHELLE SADLER | VALERIE.TURNER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94966 | WBS.2.1.13.11.1.5.6 | N | N | Planned | PTH - Ret/Tissue ship D4 outbound STOs early to avoid FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | TWANDA JENNINGS | TDJENNIN@GAPAC.com | VALERIE TURNER;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;MICHELLE SADLER | VALERIE.TURNER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94700 | WBS.2.1.13.11.1.5.8 | N | N | Planned | PTH - RET/Towel confirm minimal changeover prior to and after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | SYDNEY MAY | SYDNEY.MAY@GAPAC.COM | TAMMIE WILLIAMS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;DAVE LOPAS;MICHELLE SADLER | TAMMIE.WILLIAMS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;dave.lopas@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94970 | WBS.2.1.13.11.1.5.9 | N | N | Planned | PTH - RET/Tissue START schedule finalized through 3/13 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | VIVEK ANANTHAKRISHNAN | vivek.ananthakrishnan@gapac.com | Alexander Madueke;CJ KAUTH;ROBBIE GARNER;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;MICHELLE SADLER | alexander.madueke@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95477 | WBS.2.1.13.11.1.5.10 | N | N | Planned | PTH - RET/Tissue COMPLETE schedule finalized through 3/13 | 1 | 2021-01-25 09:15 | 2021-01-25 10:15 | VIVEK ANANTHAKRISHNAN | vivek.ananthakrishnan@gapac.com | Alexander Madueke;CJ KAUTH;ROBBIE GARNER;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;MICHELLE SADLER | alexander.madueke@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10845,94970,95555 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 10:15 | SCM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94971 | WBS.2.1.13.11.1.5.11 | N | N | Planned | PTH - RET/Tissue confirm minimal changeover prior to and after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | VIVEK ANANTHAKRISHNAN | vivek.ananthakrishnan@gapac.com | Alexander Madueke;CJ KAUTH;ROBBIE GARNER;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;MICHELLE SADLER | alexander.madueke@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94972 | WBS.2.1.13.11.1.5.12 | N | N | Planned | PTH - RET/Towel: START schedule finalized through 3/13 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | SYDNEY MAY | SYDNEY.MAY@GAPAC.COM | TAMMIE WILLIAMS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;DAVE LOPAS;MICHELLE SADLER | TAMMIE.WILLIAMS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;dave.lopas@gapac.com;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95476 | WBS.2.1.13.11.1.5.13 | N | N | Planned | PTH - RET/Towel: COMPLETE schedule finalized through 3/13 | 1 | 2021-01-25 09:15 | 2021-01-25 10:15 | SYDNEY MAY | SYDNEY.MAY@GAPAC.COM | TAMMIE WILLIAMS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;DAVE LOPAS;MICHELLE SADLER | TAMMIE.WILLIAMS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;dave.lopas@gapac.com;BMSADLER@GAPAC.COM | Business | 10845,94972,95555 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 10:15 | SCM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93203 | WBS.2.1.13.11.1.5.17 | N | N | Planned | PTH - Communicate plans for frozen period | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | Katie.Parker@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SCM - TTN | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93183 | WBS.2.1.13.11.1.5.18 | N | N | Planned | PTH - Confirm minimal changeovers during shutdown phase - Towel (Janet) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | SCM - TTN | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93182 | WBS.2.1.13.11.1.5.19 | N | N | Planned | PTH - Confirm minimal changeovers during shutdown phase - Tissue | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | SCM - TTN | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93210 | WBS.2.1.13.11.1.5.21 | N | N | Planned | PTH - Start Plan inventory build for raw materials to support demand in first 2 weeks post Go-live - Towel | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | SCM - TTN | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93209 | WBS.2.1.13.11.1.5.22 | N | N | Planned | PTH - Start Plan inventory build for raw materials to support demand in first 2 weeks post Go-live - Tissue | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | SCM - TTN | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93206 | WBS.2.1.13.11.1.5.24 | N | N | Planned | PTH - Validate advance orders for Raw Materials for appropriate build prior to cut over - Towel | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93210,10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | SCM - TTN | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93205 | WBS.2.1.13.11.1.5.25 | N | N | Planned | PTH - Validate advance orders for Raw Materials for appropriate build prior to cut over - Tissue | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93209,10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | SCM - TTN | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93187 | WBS.2.1.13.11.1.5.27 | N | N | Planned | PTH - Confirm - Plan inventory build for raw materials to support demand in first 2 weeks post Go-live - Towel | 0.67 | 2021-01-25 06:15 | 2021-01-25 06:55 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93210,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:55 | SCM - TTN | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93186 | WBS.2.1.13.11.1.5.28 | N | N | Planned | PTH - Confirm - Plan inventory build for raw materials to support demand in first 2 weeks post Go-live - Tissue | 0.67 | 2021-01-25 06:15 | 2021-01-25 06:55 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93209,10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:55 | SCM - TTN | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
94634 | WBS.2.1.13.11.1.5.32 | N | N | Planned | PTH - PPDS - Validate Finished Goods & Paper machine schedules are correct in S/4HANA - Towel | 7 | 2021-01-29 16:15 | 2021-01-30 07:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 97351,10851,95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-30 07:15 | SCM - TTN | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94635 | WBS.2.1.13.11.1.5.33 | N | N | Planned | PTH - PPDS - Validate Finished Goods & Paper machine schedules are correct in S/4HANA - Tissue | 7 | 2021-01-29 16:15 | 2021-01-30 07:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 97352,10852,95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-30 07:15 | SCM - TTN | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93192 | WBS.2.1.13.11.1.5.34 | N | N | Planned | PTH - Export copy of production schedule to a file - Tissue | 0.25 | 2021-01-30 07:15 | 2021-01-30 07:30 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,94635 |  |  | * |  | 2021-01-30 07:15 | 2021-01-30 07:30 | SCM - TTN | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93191 | WBS.2.1.13.11.1.5.35 | N | N | Planned | PTH - Export copy of production schedule to a file - Towel | 0.25 | 2021-01-30 07:15 | 2021-01-30 07:30 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,94634 |  |  | * |  | 2021-01-30 07:15 | 2021-01-30 07:30 | SCM - TTN | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97171 | WBS.2.1.13.11.1.5.38 | N | N | Planned | PTH - RET/Tissue remove manual adjustments in IBP on 1/28 (save a copy for reference) | 3 | 2021-01-28 09:45 | 2021-01-28 12:45 | VIVEK ANANTHAKRISHNAN | vivek.ananthakrishnan@gapac.com | Alexander Madueke;SAI TEAM;KRISTEN PAULY;JOHN CASABURRI;DON ABBOTT;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;MICHELLE SADLER | alexander.madueke@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;BMSADLER@GAPAC.COM | Business | 91863,97148 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 12:45 | SCM | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
10760 | WBS.2.1.13.11.2 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Clean-Up Activities | 82 | 2021-01-22 07:15 | 2021-01-29 09:15 | [8 empty] | * |  | 2021-01-22 07:15 | 2021-01-29 09:15 |  | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
11105 | WBS.2.1.13.11.2.2 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Clean-Up Activities - RTR | 82 | 2021-01-22 07:15 | 2021-01-29 09:15 | [8 empty] | * |  | 2021-01-22 07:15 | 2021-01-29 09:15 |  | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93218 | WBS.2.1.13.11.2.2.1 | N | N | Planned | PTH - Review and identify applicable open internal orders (that can be closed ) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | DANIELLE RAMSEY | DANIELLE.RAMSEY@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - PS | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93217 | WBS.2.1.13.11.2.2.2 | N | N | Planned | PTH -Cleanup moving average prices AS8 materials | 3 | 2021-01-29 06:15 | 2021-01-29 09:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 09:15 | RTR - PC | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95059 | WBS.2.1.13.11.2.2.3 | N | N | Planned | PTH - MRO - Serialization for MRO - Verify data for newly created GP ID materials | 2 | 2021-01-27 06:15 | 2021-01-27 08:15 | SEAN HERTZBURG | sean.hertzberg@gapac.com | TOMMY WOMACK;DARRELL WATSON;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER | tommy.womack@gapac.com;Darrell.watson@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 08:15 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
95062 | WBS.2.1.13.11.2.2.6 | N | N | Planned | PTH - Perform high level hierarchy review | 1 | 2021-01-22 07:15 | 2021-01-22 08:15 | DANIEL HENDERSON | daniel.henderson@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 5418 |  |  | * |  | 2021-01-22 07:15 | 2021-01-22 08:15 | AC | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
10766 | WBS.2.1.13.11.3 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities | 186.5 | 2021-01-18 06:15 | 2021-01-31 08:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 03:15 |  | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
11085 | WBS.2.1.13.11.3.1 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities - AC | 143.5 | 2021-01-18 07:15 | 2021-01-29 06:45 | [8 empty] | * |  | 2021-01-18 07:15 | 2021-01-29 06:45 |  | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93223 | WBS.2.1.13.11.3.1.1 | N | N | Planned | PTH - Schedule and print work orders out 1 week | 4 | 2021-01-18 07:15 | 2021-01-18 11:15 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93183 |  |  | * |  | 2021-01-18 07:15 | 2021-01-18 11:15 | AC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93222 | WBS.2.1.13.11.3.1.2 | N | N | Planned | PTH - MRO - Serialization for MRO | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 07:15 | AC | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93220 | WBS.2.1.13.11.3.1.3 | N | N | Planned | PTH - Final Work Order time confirmation | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | AC | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93151 | WBS.2.1.13.11.3.2 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities - RTR | 173.5 | 2021-01-18 06:15 | 2021-01-30 19:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 19:45 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93149 | WBS.2.1.13.11.3.2.1 | N | N | Planned | PTH - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9275 - Round 2 | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - GL | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93146 | WBS.2.1.13.11.3.2.2 | N | N | Planned | PTH - Perform ZMR11 Clearing in ECC for CC 9275 - Round 2 | 0.25 | 2021-01-25 07:15 | 2021-01-25 07:30 | ANGELA PENSIS | ANGELA.PENSIS@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93149 |  |  | * |  | 2021-01-25 07:15 | 2021-01-25 07:30 | RTR - GL | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93148 | WBS.2.1.13.11.3.2.3 | N | N | Planned | PTH - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9275 - Round 3 | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | RTR - GL | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93179 | WBS.2.1.13.11.3.2.4 | N | N | Planned | PTH - Cleanup moving average prices ECC (use SAP transaction MR21 if needed) | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | RTR - PC | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93267 | WBS.2.1.13.11.3.2.5 | N | N | Planned | PTH -Perform inventory cut-off and recon on intercompany purchased items (In-transit) | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | JEFF ROBINSON | JEFFREY.ROBINSON@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | RTR - GL | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
94762 | WBS.2.1.13.11.3.2.6 | N | N | Planned | PTH - Ensure that AS8 Accrual entries and any accounting adjustments have been entered in the AS8 tool | 1 | 2021-01-29 12:15 | 2021-01-29 13:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 13:15 | RTR - GL | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95268 | WBS.2.1.13.11.3.2.7 | N | N | Planned | PTH - Balance Sheet OIM Account Clearing (In-transit, etc.) | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | RTR - GL | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93177 | WBS.2.1.13.11.3.2.8 | N | N | Planned | PTH - Check for and Clear any Pbkin errors for last time prior to cutoff | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94788 | WBS.2.1.13.11.3.2.9 | N | N | Planned | PTH - Review month-end count and GI Chemicals prior to ECC cutoff | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94790 | WBS.2.1.13.11.3.2.11 | N | N | Planned | PTH - Review month-end count and GI Machine Clothing prior to ECC cutoff | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | JEFF ROBINSON | JEFFREY.ROBINSON@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94791 | WBS.2.1.13.11.3.2.12 | N | N | Planned | PTH - Review month-end count and GI Purchased Pulp prior to ECC cutoff | 3.5 | 2021-01-30 12:15 | 2021-01-30 15:45 | JEFF ROBINSON | JEFFREY.ROBINSON@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93266 | WBS.2.1.13.11.3.2.13 | N | N | Planned | PTH - Run SM35 and correct any Posting Errors | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95570 | WBS.2.1.13.11.3.2.14 | N | N | Planned | PTH - Check Acct 5999999 in ECC and clear | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94350 | WBS.2.1.13.11.3.2.15 | N | N | Planned | PTH - Run ZAP34 and ZMR11 and tie GRIR to ledger before system cutover | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94592 | WBS.2.1.13.11.3.2.16 | N | N | Planned | PTH - Ensure that all AS8 transactions (incliuding Accrual) are complete, then notify AS8 IT rep. | 0.25 | 2021-01-30 18:15 | 2021-01-30 18:30 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:30 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94346 | WBS.2.1.13.11.3.2.17 | N | N | Planned | PTH - Run UVL report in AS8 and tie to ledger FS10N-acct 3202000 before system cutover | 1 | 2021-01-30 18:45 | 2021-01-30 19:45 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93266 |  |  | * |  | 2021-01-30 18:45 | 2021-01-30 19:45 | RTR - GL | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95039 | WBS.2.1.13.11.3.2.18 | N | N | Planned | PTH - Cognos / Asset Suite Aging Report / AS8 UVL report- Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;Malinda Spaeth;ALYSHIA RASMUSSEN;JAZMINE STEINFELDT;LAURA FRY;DENISE MARSH | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Malinda.Spaeth@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;JAZMINE.STEINFELDT@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95040 | WBS.2.1.13.11.3.2.19 | N | N | Planned | PTH - Cognos / Asset Suite Aging Report / AS8 UVL report- Round 2 | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - GL | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95041 | WBS.2.1.13.11.3.2.20 | N | N | Planned | PTH - Cognos / Asset Suite Aging Report / AS8 UVL report- Round 3 | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 07:15 | RTR - GL | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
68365 | WBS.2.1.13.11.3.3 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities - SCM | 22.5 | 2021-01-27 06:15 | 2021-01-28 12:45 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-28 12:45 |  | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97187 | WBS.2.1.13.11.3.3.16 | N | N | Planned | PTH - RET/Towel remove manual adjustments in IBP on 1/28 (save a copy for reference) | 3 | 2021-01-28 09:45 | 2021-01-28 12:45 | SYDNEY MAY | SYDNEY.MAY@GAPAC.COM | TAMMIE WILLIAMS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CJ KAUTH;ROBBIE GARNER;DAVE LOPAS;MICHELLE SADLER | TAMMIE.WILLIAMS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;dave.lopas@gapac.com;BMSADLER@GAPAC.COM | Business | 91863,97148 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 12:45 | SCM | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93226 | WBS.2.1.13.11.3.3.1 | N | N | Planned | PTH - Review Open PO's for Vitals - document status - Towel | 0.67 | 2021-01-27 06:15 | 2021-01-27 06:55 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:55 | SCM - TTN | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93225 | WBS.2.1.13.11.3.3.2 | N | N | Planned | PTH - Review Open PO's for Vitals - document status - Tissue | 0.67 | 2021-01-27 06:15 | 2021-01-27 06:55 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:55 | SCM - TTN | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
12222 | WBS.2.1.13.11.3.4 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities - EWM | 106.5 | 2021-01-25 06:15 | 2021-01-31 08:45 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-31 03:15 |  | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
93259 | WBS.2.1.13.11.3.4.1 | N | N | Planned | PTH - Follow up on unloading Inbound STOs to ensure all are completed before FCW | 0.75 | 2021-01-25 06:15 | 2021-01-25 07:00 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JANET QUEBEDEAUX;KATIE PARKER;MARSHAL SAVAGE | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;janet.quebedeaux@gapac.com;Katie.Parker@gapac.com;marshal.savage@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:00 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93257 | WBS.2.1.13.11.3.4.3 | N | N | Planned | PTH - Cleanup damaged, q-hold, and obsolete inventory | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JANET QUEBEDEAUX;KATIE PARKER;MARSHAL SAVAGE | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;janet.quebedeaux@gapac.com;Katie.Parker@gapac.com;marshal.savage@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93256 | WBS.2.1.13.11.3.4.4 | N | N | Planned | PTH - Minimize open transactions (Open AR/AP) | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | DONNA RABALAIS | DONNA.RABALAIS@GAPAC.com | CHARLES DUPRE;PAUL CARTER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | charles.dupre@gapac.com;PGCarter@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93255 | WBS.2.1.13.11.3.4.5 | N | N | Planned | PTH - Cleanup NOI inventory | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | KATIE PARKER | Katie.Parker@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93254 | WBS.2.1.13.11.3.4.6 | N | N | Planned | PTH - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation (business continuity form) | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JANET QUEBEDEAUX;KATIE PARKER;MARSHAL SAVAGE | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;janet.quebedeaux@gapac.com;Katie.Parker@gapac.com;marshal.savage@gapac.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93250 | WBS.2.1.13.11.3.4.7 | N | N | Planned | PTH - Confirm active items - Vitals that are currently running (things that cannot be cycle counted beforehand) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93246 | WBS.2.1.13.11.3.4.9 | N | N | Planned | PTH - Run Inventory Reports for Raw Materials (Elixir) | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;DARRYL JOHNSON;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DARRYL.JOHNSON@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | EWM | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97653 | WBS.2.1.13.11.3.4.40 | N | N | Planned | PTH - Run Inventory Reports for Raw Materials (E80) | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | HADYN HUGHES | CHRISTOPHER.HUGHES@GAPAC.COM | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;ANDY JONES;DARRYL JOHNSON;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | EWM | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
97836 | WBS.2.1.13.11.3.4.44 | N | N | Planned | PTH - Bring new 4Sight YMS server online and verify connection and security | 1 | 2021-01-27 06:15 | 2021-01-27 07:15 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 07:15 | EWM | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93245 | WBS.2.1.13.11.3.4.10 | N | N | Planned | PTH - Communicate to Warehouse personnel of any Q-holds that occur during the blackout periods must be manually managed to ensure non-conforming materials are not used or shipped | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | EWM | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93244 | WBS.2.1.13.11.3.4.11 | N | N | Planned | PTH - Verify all RSD's (Return Short or Damaged) are complete & approved | 8 | 2021-01-28 06:15 | 2021-01-28 14:15 | KATIE PARKER | Katie.Parker@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 14:15 | EWM | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97352 | WBS.2.1.13.11.3.4.34 | N | N | Planned | PTH - Create Planned Orders for Semi finished goods Tissue | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 11032,95149,90831,9669,95314,97573,10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | SCM - TTN | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97351 | WBS.2.1.13.11.3.4.33 | N | N | Planned | PTH - Create Planned Orders for Semi finished goods Towel (Janet) | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM;CHANDRA BALASUBRAMANIAN | marshal.savage@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM | Business | 11032,95149,90831,9669,95314,97573,10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | SCM - TTN | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93242 | WBS.2.1.13.11.3.4.12 | N | N | Planned | PTH - Review and Validate Customer Specific Requirements | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 08:15 | EWM | PTH | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93240 | WBS.2.1.13.11.3.4.14 | N | N | Planned | PTH - Validate shipment doc deleted by KBX has been removed from ECC | 1 | 2021-01-30 17:00 | 2021-01-30 18:00 | KATIE PARKER | Katie.Parker@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,92322,90697 |  |  | * |  | 2021-01-30 17:00 | 2021-01-30 18:00 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93238 | WBS.2.1.13.11.3.4.15 | N | N | Planned | PTH - End & validate Cycle count inventory - All Items | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | EWM | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93235 | WBS.2.1.13.11.3.4.18 | N | N | Planned | PTH - Operations notifies cutover team that they are ready for the cutover work to begin for mill and DC | 0.25 | 2021-01-25 06:15 | 2021-01-25 06:30 | KATIE PARKER | Katie.Parker@gapac.com | CJ KAUTH;ROBBIE GARNER;JAMES COWELL;SAI TEAM | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:30 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93234 | WBS.2.1.13.11.3.4.19 | N | N | Planned | PTH - Mill communicates to all constituencies (mill and DC) to begin manual processes through system shutdown | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JAMES COWELL;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93317 | WBS.2.1.13.11.3.4.22 | N | N | Planned | PTH - Verify that LGVs are idle and no work is in the queue | 0.5 | 2021-01-30 20:00 | 2021-01-30 20:30 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94946 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | PTH | 2021-01-30 | 2021-01-31 | 3 | Ramp Down
93318 | WBS.2.1.13.11.3.4.23 | N | N | Planned | PTH - Validate Empty Trailer Upload files | 2 | 2021-01-31 06:45 | 2021-01-31 08:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;KATIE PARKER;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;Katie.Parker@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 93271 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97159 | WBS.2.1.13.11.3.4.32 | N | N | Planned | PTH - Carwash Needs to be cleared out, product written off or put back into production | 4 | 2021-01-30 12:15 | 2021-01-30 16:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 16:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97158 | WBS.2.1.13.11.3.4.31 | N | N | Planned | PTH - Parent rolls need to be removed from backstand and sent back to Warehouse or fully consumed - Tissue | 1 | 2021-01-30 22:45 | 2021-01-30 23:45 | Jon Stalder | jon.stalder@gapac.com | Nick Anders;Caitlin George;CJ KAUTH;ROBBIE GARNER;SAI TEAM | nickolas.anders@gapac.com;caitlin.george@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-30 | 2021-01-31 | 3 | Ramp Down
97157 | WBS.2.1.13.11.3.4.30 | N | N | Planned | PTH - Parent rolls need to be removed from backstand and sent back to Warehouse or fully consumed - Towel | 1 | 2021-01-30 22:45 | 2021-01-30 23:45 | Doug Covington | douglas.covington@gapac.com | RHETT CHARLEVILLE;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Rhett.Charleville@GAPAC.com ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-30 | 2021-01-31 | 3 | Ramp Down
97156 | WBS.2.1.13.11.3.4.29 | N | N | Planned | PTH - Validate through SC777 that all schedules and shipments have been deleted (if E80 production order has started will have to manually delete) | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97837 | WBS.2.1.13.11.3.4.45 | N | N | Planned | PTH - 4Sight - Complete Open Tasks | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97838 | WBS.2.1.13.11.3.4.36 | N | N | Planned | PTH - Spotters Shutdown Yard Pilots | 0.25 | 2021-01-30 19:15 | 2021-01-30 19:30 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 97837 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:30 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97839 | WBS.2.1.13.11.3.4.37 | N | N | Planned | PTH - 4Sight - Document Physical Trailer and Equipment details if at the dock door | 0.5 | 2021-01-30 19:30 | 2021-01-30 20:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;KATIE PARKER;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;Katie.Parker@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 97838 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 20:00 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97840 | WBS.2.1.13.11.3.4.38 | N | N | Planned | PTH - 4Sight - Shutdown GP Hosted YMS Tomcat service on App Server | 0.25 | 2021-01-30 20:00 | 2021-01-30 20:15 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 97839 |  |  | * |  | 2021-01-30 20:00 | 2021-01-30 20:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97843 | WBS.2.1.13.11.3.4.46 | N | N | Planned | PTH - 4Sight - Register new version of Yard Pilot on Spotter Tablets to new Core | 1 | 2021-01-30 20:15 | 2021-01-30 21:15 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 97840 |  |  | * |  | 2021-01-30 20:15 | 2021-01-30 21:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97155 | WBS.2.1.13.11.3.4.28 | N | N | Planned | PTH - Clear out Globe queue, ensure all rolls have been removed from conveyor system | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | Mark Williams | mark.williams3@gapac.com | Darcy Perry;CJ KAUTH;ROBBIE GARNER;SAI TEAM | darcy.perry@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 23:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-30 | 2021-01-31 | 3 | Ramp Down
97153 | WBS.2.1.13.11.3.4.26 | N | N | Planned | PTH - Clear out all production lines of product through stretchwrappers - Tissue | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | Caitlin George | caitlin.george@gapac.com | Jon Stalder;Nick Anders;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jon.stalder@gapac.com;nickolas.anders@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97152 | WBS.2.1.13.11.3.4.25 | N | N | Planned | PTH - Clear out all production lines of product through stretchwrappers - Towel | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | Doug Covington | douglas.covington@gapac.com | ANDY JONES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Gibson.Jones@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97151 | WBS.2.1.13.11.3.4.24 | N | N | Planned | PTH - Ensure all trailers are full and pulled away before Elixir is shutdown | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | KATIE PARKER | Katie.Parker@gapac.com | MARCUS MARTINEZ;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 22:45 | 2021-01-31 00:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
97654 | WBS.2.1.13.11.3.4.41 | N | N | Planned | PTH - Confirm last shipment complete in ECC at shutdown (Towel) | 0.5 | 2021-01-30 22:45 | 2021-01-30 23:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97655 | WBS.2.1.13.11.3.4.42 | N | N | Planned | PTH - Delete shipments and deliveries for orders not shipping before cutover (Towel) | 8 | 2021-01-30 18:15 | 2021-01-31 02:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 20:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
97656 | WBS.2.1.13.11.3.4.43 | N | N | Planned | PTH - Identify IB STO on Friday before cutover, flag trailer (Towel) | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 14:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93261 | WBS.2.1.13.11.3.5 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - EWM Inventory Conversion Precursor | 184.5 | 2021-01-18 06:15 | 2021-01-31 06:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-31 01:15 |  | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
93308 | WBS.2.1.13.11.3.5.2 | N | N | Planned | PTH - Stage to converting lines raw materials needed during entire shutdown period | 5 | 2021-01-29 12:15 | 2021-01-29 17:15 | ANDY JONES | Gibson.Jones@gapac.com | RHETT CHARLEVILLE;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Rhett.Charleville@GAPAC.com ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 17:15 | EWM | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
94945 | WBS.2.1.13.11.3.5.3 | N | N | Planned | PTH - Notify E80 that Converting Operations have stopped | 0.25 | 2021-01-30 19:15 | 2021-01-30 19:30 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94944 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:30 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94946 | WBS.2.1.13.11.3.5.4 | N | N | Planned | PTH - Validate no more LGV Movements | 0.5 | 2021-01-30 19:30 | 2021-01-30 20:00 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94945 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 20:00 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93307 | WBS.2.1.13.11.3.5.5 | N | N | Planned | PTH - Identify pilot transactions to perform after system comes up on eWM | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93305 | WBS.2.1.13.11.3.5.6 | N | N | Planned | PTH - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93303 | WBS.2.1.13.11.3.5.8 | N | N | Planned | PTH - Run open inventory display by LPN detail and upload into Teams quality file | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93302 | WBS.2.1.13.11.3.5.9 | N | N | Planned | PTH - Download open yard management operations and verify trailer status' are correct(MT's, Full, OOS) prior to upload file | 2 | 2021-01-30 12:15 | 2021-01-30 14:15 | KATIE PARKER | Katie.Parker@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93301 | WBS.2.1.13.11.3.5.10 | N | N | Planned | PTH - Ensure all locations are not in blocked status | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93300 | WBS.2.1.13.11.3.5.11 | N | N | Planned | PTH - Operations confirms all system activities to perform prior to cutover have been completed. | 3 | 2021-01-30 22:45 | 2021-01-31 01:45 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JAMES COWELL;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93299 | WBS.2.1.13.11.3.5.12 | N | N | Planned | PTH - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 3 | 2021-01-30 22:45 | 2021-01-31 01:45 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JAMES COWELL;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93298 | WBS.2.1.13.11.3.5.13 | N | N | Planned | PTH - Operations notifies cutover team that they are ready for the cutover work to begin. | 3 | 2021-01-30 22:45 | 2021-01-31 01:45 | CJ KAUTH | christopher.kauth@gapac.com | JAMES COWELL;SAI TEAM | James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93297 | WBS.2.1.13.11.3.5.14 | N | N | Planned | PTH - All shipments are load end and none started. | 3 | 2021-01-30 23:45 | 2021-01-31 02:45 | KATIE PARKER | Katie.Parker@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95633 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93296 | WBS.2.1.13.11.3.5.15 | N | N | Planned | PTH - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 1 | 2021-01-30 23:45 | 2021-01-31 00:45 | KATIE PARKER | Katie.Parker@gapac.com | MARCUS MARTINEZ;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95633 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 18:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93294 | WBS.2.1.13.11.3.5.16 | N | N | Planned | PTH - Review site specific Pacspec for PTH and ensure information is uploaded prior to go live. | 4 | 2021-01-30 12:15 | 2021-01-30 16:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 16:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93293 | WBS.2.1.13.11.3.5.17 | N | N | Planned | PTH - Verify all picked inventory has been loaded and PGI | 2 | 2021-01-31 00:45 | 2021-01-31 02:45 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95233,97153,97152 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 21:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93292 | WBS.2.1.13.11.3.5.18 | N | N | Planned | PTH - Confirm last raw material receipt in ECC at shutdown | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | DONNA RABALAIS | DONNA.RABALAIS@GAPAC.com | CHARLES DUPRE;PAUL CARTER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | charles.dupre@gapac.com;PGCarter@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93291 | WBS.2.1.13.11.3.5.19 | N | N | Planned | PTH - Confirm last shipment complete in ECC at shutdown (Tissue) | 0.5 | 2021-01-30 22:45 | 2021-01-30 23:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93287 | WBS.2.1.13.11.3.5.20 | N | N | Planned | PTH - Redirect RF units/tablets to EWM | 2 | 2021-01-30 22:45 | 2021-01-31 00:45 | JERRY LEBLANC | Jerry.Leblanc@gapac.com | KARL SEYMOUR;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | KARL.SEYMOUR@GAPAC.com ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92449 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93286 | WBS.2.1.13.11.3.5.21 | N | N | Planned | PTH - MRO - Operations confirms all system activities to perform prior to cutover have been completed | 2 | 2021-01-30 12:15 | 2021-01-30 14:15 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93285 | WBS.2.1.13.11.3.5.22 | N | N | Planned | PTH - Delete shipments and deliveries for orders not shipping before cutover (Tissue) | 8 | 2021-01-30 12:15 | 2021-01-30 20:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 20:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93284 | WBS.2.1.13.11.3.5.23 | N | N | Planned | PTH - Final Cycle Count FGS and adjust | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93283 | WBS.2.1.13.11.3.5.24 | N | N | Planned | PTH - Final Cycle Count WIP and adjust | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | MOE ABDELWHAB | MOWAFEG.ABDELWHAB@gapac.com | BILL MCGRAW;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | *;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93282 | WBS.2.1.13.11.3.5.25 | N | N | Planned | PTH - Final Cycle Count Vital Supplies and adjust | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93281 | WBS.2.1.13.11.3.5.26 | N | N | Planned | PTH - Validate with Mill on yard checks | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | KATIE PARKER | Katie.Parker@gapac.com | MARCUS MARTINEZ;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93280 | WBS.2.1.13.11.3.5.27 | N | N | Planned | PTH - Ensure all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 6 | 2021-01-30 18:15 | 2021-01-31 00:15 | KATIE PARKER | Katie.Parker@gapac.com | MARCUS MARTINEZ;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 18:15 | EWM | PTH | 2021-01-31 | 2021-01-30 | 2 | Ramp Down
93279 | WBS.2.1.13.11.3.5.28 | N | N | Planned | PTH - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | KATIE PARKER | Katie.Parker@gapac.com | MARCUS MARTINEZ;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94938 | WBS.2.1.13.11.3.5.31 | N | N | Planned | PTH - Final Cycle Count MRO and adjust | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93275 | WBS.2.1.13.11.3.5.32 | N | N | Planned | PTH - Validate Inventory Upload files downloaded from Elixir before shutdown | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 90821 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93274 | WBS.2.1.13.11.3.5.33 | N | N | Planned | PTH - Sync up E80 to Elixir | 0.5 | 2021-01-30 19:15 | 2021-01-30 19:45 | HADYN HUGHES | CHRISTOPHER.HUGHES@GAPAC.COM | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93284 |  |  | * |  | 2021-01-30 13:15 | 2021-01-30 13:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93273 | WBS.2.1.13.11.3.5.34 | N | N | Planned | PTH - Run Final Resync and cleanup discrepancies | 0.5 | 2021-01-30 19:45 | 2021-01-30 20:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 93274 |  |  | * |  | 2021-01-30 13:45 | 2021-01-30 20:45 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93272 | WBS.2.1.13.11.3.5.35 | N | N | Planned | PTH - Identify IB STO on Friday before cutover, flag trailer (Tissue) | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MARSHAL SAVAGE | marshal.savage@gapac.com | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 14:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93271 | WBS.2.1.13.11.3.5.36 | N | N | Planned | PTH - Complete all SAP workflows/MIST interface errors | 4 | 2021-01-31 02:45 | 2021-01-31 06:45 | KRISTIE DOIRON | KRISTIE.DOIRON@GAPAC.COM | KATIE PARKER;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93293 |  |  | * |  | 2021-01-30 21:15 | 2021-01-31 01:15 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Ramp Down
93269 | WBS.2.1.13.11.3.5.38 | N | N | Planned | PTH - Verify that the mill has downloaded the open yard management operations and verified trailer status' are correct(MT's, Full, OOS) prior to upload file | 1 | 2021-01-30 14:15 | 2021-01-30 15:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;KATIE PARKER;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;Katie.Parker@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 93302 |  |  | * |  | 2021-01-30 14:15 | 2021-01-30 15:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93276 | WBS.2.1.13.11.3.5.41 | N | N | Planned | PTH - Send Extracted WMS extracted file for finished goods to Quality | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94944 | WBS.2.1.13.11.3.5.39 | N | N | Planned | PTH - Communicate to Converting to Start Shutdown prior to Cutover Window | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JAMES COWELL;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93268 | WBS.2.1.13.11.3.5.40 | N | N | Planned | PTH - At mills, operations confirms system activities to perform for mill production & converting prior to cutover have been completed | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | CJ KAUTH | christopher.kauth@gapac.com | KATIE PARKER;JAMES COWELL;SAI TEAM | Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 20:15 | EWM | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
68378 | WBS.2.1.13.11.3.6 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Cut-Off Activities - PTP | 6.5 | 2021-01-29 06:15 | 2021-01-29 12:45 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-29 12:45 |  | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93265 | WBS.2.1.13.11.3.6.1 | N | N | Planned | PTH - Confirm receiving is complete in AS8 and ECC | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93216 | WBS.2.1.13.11.3.6.2 | N | N | Planned | PTH - Process Open Purchase Requisitions To Purchase Orders | 0.25 | 2021-01-29 06:15 | 2021-01-29 06:30 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PGCarter@gapac.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:30 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93369 | WBS.2.1.13.11.3.6.3 | N | N | Planned | PTH - Start Task - Record all Storeroom Transactions Using Business Continuity Forms | 0.25 | 2021-01-29 12:30 | 2021-01-29 12:45 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 93314 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 12:45 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
10835 | WBS.2.1.13.11.4 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Communications | 94 | 2021-01-25 06:15 | 2021-01-30 20:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-30 20:15 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
29697 | WBS.2.1.13.11.4.1 | N | N |  | Ramp Down ¦ Business Activities - Port Hudson - Communications - PTP | 94 | 2021-01-25 06:15 | 2021-01-30 20:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-30 20:15 |  | PTH | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93173 | WBS.2.1.13.11.4.1.1 | N | N | Planned | PTH - Send Communication - Approve PRs in Backlog, POs to Stop EOB 9/29 | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | PTP | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93316 | WBS.2.1.13.11.4.1.2 | N | N | Planned | PTH - Send Communication - Last POs Issued, Please Use Manual PO Process | 0.25 | 2021-01-29 06:30 | 2021-01-29 06:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93216 |  |  | * |  | 2021-01-29 06:30 | 2021-01-29 06:45 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93315 | WBS.2.1.13.11.4.1.3 | N | N | Planned | PTH - Start Task - Record all Procurement Transactions Using Business Continuity Forms | 0.25 | 2021-01-29 06:45 | 2021-01-29 07:00 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93316 |  |  | * |  | 2021-01-29 06:45 | 2021-01-29 07:00 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93314 | WBS.2.1.13.11.4.1.4 | N | N | Planned | PTH - Final Communication - Parts Issuing to Begin Following Manual Process | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | PTP | PTH | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
95306 | WBS.2.1.13.11.4.1.5 | N | N | Planned | PTH - Mill buyers to confirm requisitioner is populated and validate accuracy of P.Group for Service POs | 0.5 | 2021-01-27 08:15 | 2021-01-27 08:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 97454 |  |  | * |  | 2021-01-27 08:15 | 2021-01-27 08:45 | PTP | PTH | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93312 | WBS.2.1.13.11.4.1.6 | N | N | Planned | PTH - Process Returns And Credit Memo | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | PTP | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93311 | WBS.2.1.13.11.4.1.7 | N | N | Planned | PTH - Confirm all blanket PO/Framework orders have been updated to end on 1.31.2021 | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | PTP | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97494 | WBS.2.1.13.11.4.1.8 | N | N | Planned | Reprocess failed CI9 messages in POP Middleware - Round 1 | 2 | 2021-01-30 18:15 | 2021-01-30 20:15 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;ANKIT SONI;PAYEL GHOSH;RADHIKA RASTOGI;SUVENDU KUMAR;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANKISONI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 20:15 | DEV-INT | ALL | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93727 | WBS.2.1.13.12 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg | 175 | 2021-01-18 06:15 | 2021-01-30 21:15 | [8 empty] | * |  | 2021-01-18 06:00 | 2021-01-30 21:15 |  |  | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93726 | WBS.2.1.13.12.1 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities | 157.75 | 2021-01-18 06:15 | 2021-01-29 20:00 | [8 empty] | * |  | 2021-01-18 06:00 | 2021-01-29 20:00 |  |  | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93729 | WBS.2.1.13.12.1.1 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities - AC | 81 | 2021-01-18 06:15 | 2021-01-25 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 07:15 |  |  | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93744 | WBS.2.1.13.12.1.1.1 | N | N | Planned | HBG - Identify Pilot transactions | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | AC | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93745 | WBS.2.1.13.12.1.1.2 | N | N | Planned | HBG - MRO - Provide final list of equipment (name, type, number) | 0.75 | 2021-01-25 06:15 | 2021-01-25 07:00 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:00 | AC | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93973 | WBS.2.1.13.12.1.1.3 | N | N | Planned | HBG - Close Open Work orders | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | AC | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
95273 | WBS.2.1.13.12.1.1.4 | N | N | Planned | HBG - Confirm - Plan inventory build for raw materials to support demand in first 2 weeks post Go-live | 0.67 | 2021-01-25 06:15 | 2021-01-25 06:55 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:55 | SCM - TTN | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93728 | WBS.2.1.13.12.1.2 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities - EWM | 10.25 | 2021-01-18 06:15 | 2021-01-18 16:30 | [8 empty] | * |  | 2021-01-18 06:00 | 2021-01-18 16:30 |  | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94949 | WBS.2.1.13.12.1.2.1 | N | N | Planned | HBG - Validate data file to upload Parent Rolls and Vital Supplies, including lot# and location, into S4 is developed and accurate | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 08:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93834 | WBS.2.1.13.12.1.2.2 | N | N | Planned | HBG - CONFIRM apply new LPN to all finished good HU's with hand applied WM labels | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93765 | WBS.2.1.13.12.1.2.3 | N | N | Planned | HBG - Begin working on unloading Inbound STOs to ensure all are completed before FCW | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93764 | WBS.2.1.13.12.1.2.4 | N | N | Planned | HBG - Review all inbound STOs to have visibility of which inbounds are due during FCW, and send request to have as many inbounds as possible shipped early or late. | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93763 | WBS.2.1.13.12.1.2.5 | N | N | Planned | HBG - Start pre-shipments of outbounds prior to cutover to minimize activity during cutover | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93762 | WBS.2.1.13.12.1.2.6 | N | N | Planned | HBG - Transition to emergency PO process for outage | 0.25 | 2021-01-18 06:30 | 2021-01-18 06:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 06:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93761 | WBS.2.1.13.12.1.2.7 | N | N | Planned | HBG - Ensure all vendors to provide HU's on all Raw Material inbounds (ASN's) | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93760 | WBS.2.1.13.12.1.2.8 | N | N | Planned | HBG - Remove duplicate or obsolete fixed bins/pick faces | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93759 | WBS.2.1.13.12.1.2.9 | N | N | Planned | HBG - MRO - Create any new locations required by EWM | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 08:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93758 | WBS.2.1.13.12.1.2.10 | N | N | Planned | HBG - Verify any new locations have signs/labels | 1 | 2021-01-18 06:30 | 2021-01-18 07:30 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93757 | WBS.2.1.13.12.1.2.11 | N | N | Planned | HBG - Update and validate site printers | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | BRUCE EASTERLING | BRUCE.EASTERLING@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 08:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93756 | WBS.2.1.13.12.1.2.12 | N | N | Planned | HBG - Run Inventory Reports for MRO | 3 | 2021-01-18 06:30 | 2021-01-18 09:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 09:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93981 | WBS.2.1.13.12.1.2.13 | N | N | Planned | HBG - Provide final list of site users (use formatted file for business processor load) | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | BRUCE EASTERLING | BRUCE.EASTERLING@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93978 | WBS.2.1.13.12.1.2.14 | N | N | Planned | HBG - Start Cycle count inventory - All Items | 0.33 | 2021-01-18 06:15 | 2021-01-18 06:35 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:35 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93977 | WBS.2.1.13.12.1.2.15 | N | N | Planned | HBG - Provide final data for dock scheduling parameters/setup | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93976 | WBS.2.1.13.12.1.2.16 | N | N | Planned | HBG - MRO - Finalize final bin upload file | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93753 | WBS.2.1.13.12.1.2.17 | N | N | Planned | HBG - Provide approvers and levels for write-offs | 2 | 2021-01-18 06:30 | 2021-01-18 08:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10531 |  |  | * |  | 2021-01-18 06:00 | 2021-01-18 08:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93752 | WBS.2.1.13.12.1.2.18 | N | N | Planned | HBG - Provide final list of site resources and resource constraints (equipment names, types, numbers) | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93980 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93751 | WBS.2.1.13.12.1.2.19 | N | N | Planned | HBG - MRO - Cleanup obsolete storage locations from system | 8 | 2021-01-18 08:30 | 2021-01-18 16:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93759 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 16:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93749 | WBS.2.1.13.12.1.2.20 | N | N | Planned | HBG - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93748 | WBS.2.1.13.12.1.2.21 | N | N | Planned | HBG - Manual Config Steps (Maintain Users) | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95597 | WBS.2.1.13.12.1.2.22 | N | N | Planned | HBG - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) - MRO | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95596 | WBS.2.1.13.12.1.2.23 | N | N | Planned | HBG - Manual Config Steps (Maintain Users) - MRO | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97195 | WBS.2.1.13.12.1.2.28 | N | N | Planned | HBG - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) - for MRO | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;MITCH DEATON;CHRIS ZUMWALT;SANTOSH KUPPILI;KEN LITTLES | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;VKUPPILI@DELOITTE.COM;Kenneth.Littles@GAPAC.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93747 | WBS.2.1.13.12.1.2.24 | N | N | Planned | HBG - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | CHRIS ZUMWALT;SAI TEAM;EWM TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93974 | WBS.2.1.13.12.1.2.25 | N | N | Planned | HBG - Shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93980 | WBS.2.1.13.12.1.2.26 | N | N | Planned | HBG - Create and validate list of all lift truck equipment, attachments, RF/VUMs, printers dock/label (including spares) & validate equipment is labeled | 2 | 2021-01-18 06:15 | 2021-01-18 08:15 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 08:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93833 | WBS.2.1.13.12.1.2.27 | N | N | Planned | HBG - Scan Reworked HU's with new LPN's into data file for upload into EWM | 0.5 | 2021-01-18 07:00 | 2021-01-18 07:30 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93834 |  |  | * |  | 2021-01-18 07:00 | 2021-01-18 07:30 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93732 | WBS.2.1.13.12.1.3 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities - PTP | 64.5 | 2021-01-25 07:15 | 2021-01-29 07:45 | [8 empty] | * |  | 2021-01-25 07:15 | 2021-01-29 07:45 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93768 | WBS.2.1.13.12.1.3.2 | N | N | Planned | HBG - Mill buyers to raise request to update material UoM | 0.5 | 2021-01-25 07:15 | 2021-01-25 07:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95644 |  |  | * |  | 2021-01-25 07:15 | 2021-01-25 07:45 | PTP | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93767 | WBS.2.1.13.12.1.3.3 | N | N | Planned | HBG - Review open GRIR, and close any with final invoice received | 1 | 2021-01-26 06:15 | 2021-01-26 07:15 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10854 |  |  | * |  | 2021-01-26 06:15 | 2021-01-26 07:15 | PTP | HBG | 2021-01-26 | 2021-01-26 | 2 | Ramp Down
93766 | WBS.2.1.13.12.1.3.4 | N | N | Planned | HBG - Send Communication - Last POs Issued, Please Use Manual PO Process | 0.25 | 2021-01-29 07:15 | 2021-01-29 07:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93876 |  |  | * |  | 2021-01-29 07:15 | 2021-01-29 07:30 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93903 | WBS.2.1.13.12.1.3.5 | N | N | Planned | HBG - Start Task - Record all Procurement Transactions Using Business Continuity Forms | 0.25 | 2021-01-29 07:30 | 2021-01-29 07:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93766 |  |  | * |  | 2021-01-29 07:30 | 2021-01-29 07:45 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93731 | WBS.2.1.13.12.1.4 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities - RTR | 129.25 | 2021-01-18 06:15 | 2021-01-28 07:30 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-28 07:30 |  | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93719 | WBS.2.1.13.12.1.4.1 | N | N | Planned | HBG - Perform ZMR11 Clearing in ECC for CC 9466 - Round 1 | 0.25 | 2021-01-18 06:45 | 2021-01-18 07:00 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;BRUCE KIRKLEWSKI;JAZMINE STEINFELDT;NICOLE FARLEY;LAURA FRY;DENISE MARSH | Avie.Lindsey@gapac.com;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JAZMINE.STEINFELDT@GAPAC.COM;NICOLE.FARLEY@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 93722 |  |  | * |  | 2021-01-18 06:45 | 2021-01-18 07:00 | RTR - GL | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93722 | WBS.2.1.13.12.1.4.2 | N | N | Planned | HBG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9466 - Round 1 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM;LAURA FRY;DENISE MARSH | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | RTR - GL | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93718 | WBS.2.1.13.12.1.4.3 | N | N | Planned | HBG - Perform ZMR11 Clearing in ECC for CC 9466 - Round 2 | 0.25 | 2021-01-25 07:15 | 2021-01-25 07:30 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;BRUCE KIRKLEWSKI;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | Avie.Lindsey@gapac.com;BRUCE.KIRKLEWSKI@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93721 |  |  | * |  | 2021-01-25 07:15 | 2021-01-25 07:30 | RTR - GL | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93721 | WBS.2.1.13.12.1.4.4 | N | N | Planned | HBG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9466 - Round 2 | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - GL | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93717 | WBS.2.1.13.12.1.4.5 | N | N | Planned | HBG - Perform ZMR11 Clearing in ECC for CC 9466 - Round 3 | 0.25 | 2021-01-28 07:15 | 2021-01-28 07:30 | Malinda Spaeth | Malinda.Spaeth@GAPAC.COM | AVIE LINDSEY;HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | Avie.Lindsey@gapac.com;HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93720 |  |  | * |  | 2021-01-28 07:15 | 2021-01-28 07:30 | RTR - GL | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93720 | WBS.2.1.13.12.1.4.6 | N | N | Planned | HBG - Run Summary PO Aging GRIR Report ZAP34 in ECC for CC 9466 - Round 3 | 1 | 2021-01-28 06:15 | 2021-01-28 07:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:15 | RTR - GL | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93730 | WBS.2.1.13.12.1.5 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Prep Activities - SCM | 157.75 | 2021-01-18 06:15 | 2021-01-29 20:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 20:00 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93773 | WBS.2.1.13.12.1.5.1 | N | N | Planned | HBG - Confirm minimal changeovers during shutdown phase | 1 | 2021-01-18 06:15 | 2021-01-18 07:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 07:15 | SCM - TTN | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93783 | WBS.2.1.13.12.1.5.2 | N | N | Planned | HBG - Communicate plans for frozen period | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SCM - TTN | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94699 | WBS.2.1.13.12.1.5.3 | N | N | Planned | HBG - PRO confirm minimal changeover prior to and after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | PATRICK HOURIGAN | PATRICK.HOURIGAN@GAPAC.COM | LIZ HIETPAS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | ELIZABETH.ARMSTRONG@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94974 | WBS.2.1.13.12.1.5.4 | N | N | Planned | HBG - PRO: START schedule finalized through 3/13 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | PATRICK HOURIGAN | PATRICK.HOURIGAN@GAPAC.COM | LIZ HIETPAS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | ELIZABETH.ARMSTRONG@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
95474 | WBS.2.1.13.12.1.5.5 | N | N | Planned | HBG - PRO: COMPLETE schedule finalized through 3/13 | 1 | 2021-01-25 09:15 | 2021-01-25 10:15 | PATRICK HOURIGAN | PATRICK.HOURIGAN@GAPAC.COM | LIZ HIETPAS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | ELIZABETH.ARMSTRONG@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10845,94974,95555 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 10:15 | SCM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93788 | WBS.2.1.13.12.1.5.7 | N | N | Planned | HBG - Check off with warehousing on incremental space requirements for Raw Materials | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | SCM - TTN | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94967 | WBS.2.1.13.12.1.5.8 | N | N | Planned | HBG - PRO Execute deployment aligning with ramp up | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | DOMINIC MORRILL | DOMINIC.MORRILL@GAPAC.COM | Mary Belschner;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | mary.belschner@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93787 | WBS.2.1.13.12.1.5.9 | N | N | Planned | HBG - Start Plan inventory build for raw materials to support demand in first 2 weeks post Go-live | 0.5 | 2021-01-18 06:30 | 2021-01-18 07:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93788 |  |  | * |  | 2021-01-18 06:30 | 2021-01-18 07:00 | SCM - TTN | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93780 | WBS.2.1.13.12.1.5.10 | N | N | Planned | HBG - Validate advance orders for Raw Materials for appropriate build prior to cut over | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93787,10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | SCM - TTN | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93778 | WBS.2.1.13.12.1.5.11 | N | N | Planned | HBG - PPDS - Validate finished goods schedules are correct in S/4HANA | 3.5 | 2021-01-29 16:15 | 2021-01-29 19:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92236,10852,95256,95123 |  |  | * |  | 2021-01-29 16:15 | 2021-01-29 19:45 | SCM - TTN | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93777 | WBS.2.1.13.12.1.5.12 | N | N | Planned | HBG - Export copy of production schedule to a file | 0.25 | 2021-01-29 19:45 | 2021-01-29 20:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,93778 |  |  | * |  | 2021-01-29 19:45 | 2021-01-29 20:00 | SCM - TTN | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97140 | WBS.2.1.13.12.1.5.15 | N | N | Planned | HBG - RET/Nap confirm minimal changeover prior to and after FCW | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | TAMMIE WILLIAMS | TAMMIE.WILLIAMS@GAPAC.COM | SYDNEY MAY;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | SYDNEY.MAY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97139 | WBS.2.1.13.12.1.5.14 | N | N | Planned | HBG - RET/Nap: START schedule finalized through 3/13 | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | TAMMIE WILLIAMS | TAMMIE.WILLIAMS@GAPAC.COM | SYDNEY MAY;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | SYDNEY.MAY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95146 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97138 | WBS.2.1.13.12.1.5.13 | N | N | Planned | HBG - RET/Nap: COMPLETE schedule finalized through 3/13 | 1 | 2021-01-25 09:15 | 2021-01-25 10:15 | TAMMIE WILLIAMS | TAMMIE.WILLIAMS@GAPAC.COM | SYDNEY MAY;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | SYDNEY.MAY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10845,95555,97139 |  |  | * |  | 2021-01-25 09:15 | 2021-01-25 10:15 | SCM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97141 | WBS.2.1.13.12.1.5.16 | N | N | Planned | HBG - RET/Nap Execute deployment aligning with ramp up | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | LATISHA CHISHOLM | LATISHA.CHISHOLM@GAPAC.COM | VALERIE TURNER;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | VALERIE.TURNER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97144 | WBS.2.1.13.12.1.5.18 | N | N | Planned | HBG - PRO ship D4 outbound STOs early to avoid FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | DOMINIC MORRILL | DOMINIC.MORRILL@GAPAC.COM | Mary Belschner;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | mary.belschner@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97143 | WBS.2.1.13.12.1.5.17 | N | N | Planned | HBG - RET/Nap ship D4 outbound STOs early to avoid FCW(Avoid 1/31 inbounds or outbounds) | 1 | 2021-01-18 09:15 | 2021-01-18 10:15 | LATISHA CHISHOLM | LATISHA.CHISHOLM@GAPAC.COM | VALERIE TURNER;SAI TEAM;JOHN CASABURRI;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | VALERIE.TURNER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 10846,95147 |  |  | * |  | 2021-01-18 09:15 | 2021-01-18 10:15 | SCM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97170 | WBS.2.1.13.12.1.5.20 | N | N | Planned | HBG - PRO remove manual adjustments in IBP on 1/28 (save a copy for reference) | 3 | 2021-01-28 09:45 | 2021-01-28 12:45 | PATRICK HOURIGAN | PATRICK.HOURIGAN@GAPAC.COM | LIZ HIETPAS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;MICHELLE SADLER | ELIZABETH.ARMSTRONG@GAPAC.COM ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;BMSADLER@GAPAC.COM | Business | 91863,97148 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 12:45 | SCM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93725 | WBS.2.1.13.12.2 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Clean-Up Activities | 145 | 2021-01-18 06:15 | 2021-01-29 07:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-29 07:15 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93734 | WBS.2.1.13.12.2.1 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Clean-Up Activities - EWM | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 |  | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93790 | WBS.2.1.13.12.2.1.1 | N | N | Planned | HBG - Create any new locations required by EWM & validate | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | MITCH DEATON;SAI TEAM | MITCHELL.DEATON@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93789 | WBS.2.1.13.12.2.1.2 | N | N | Planned | HBG - Follow up on unloading shuttle trailers to ensure all are completed before FCW | 0.5 | 2021-01-25 06:15 | 2021-01-25 06:45 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | MITCH DEATON;SAI TEAM | MITCHELL.DEATON@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 06:45 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93733 | WBS.2.1.13.12.2.2 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Clean-Up Activities - RTR | 65 | 2021-01-25 06:15 | 2021-01-29 07:15 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-29 07:15 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93794 | WBS.2.1.13.12.2.2.1 | N | N | Planned | HBG - Review and identify applicable open internal orders (that can be closed ) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | RTR - PS | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93772 | WBS.2.1.13.12.2.2.2 | N | N | Planned | HBG - Cleanup moving average prices ECC (use SAP transaction MR21 if needed) | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | RTR - PC | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
94401 | WBS.2.1.13.12.2.3 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Clean-Up Activities - OTC | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 |  | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
94402 | WBS.2.1.13.12.2.3.1 | N | N | Planned | HBG - Disposition (Clean up) Q-holds in existing system | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | OTC - Quality | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93724 | WBS.2.1.13.12.3 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities | 175 | 2021-01-18 06:15 | 2021-01-30 21:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 21:15 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93737 | WBS.2.1.13.12.3.1 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - AC | 63.75 | 2021-01-25 07:00 | 2021-01-29 06:45 | [8 empty] | * |  | 2021-01-25 07:00 | 2021-01-29 06:45 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93799 | WBS.2.1.13.12.3.1.1 | N | N | Planned | HBG - Schedule and print work orders out 1 week | 4 | 2021-01-25 07:00 | 2021-01-25 11:00 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 93745 |  |  | * |  | 2021-01-25 07:00 | 2021-01-25 11:00 | AC | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93798 | WBS.2.1.13.12.3.1.2 | N | N | Planned | HBG - MRO - Serialization for MRO | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | AC | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93796 | WBS.2.1.13.12.3.1.3 | N | N | Planned | HBG - Final Work Order time confirmation | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | AC | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93736 | WBS.2.1.13.12.3.2 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - OTC | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | [8 empty] | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93800 | WBS.2.1.13.12.3.2.1 | N | N | Planned | HBG - Validate quality entries on the Inventory preload file from Quality POV | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93735 | WBS.2.1.13.12.3.3 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - SCM | 22.5 | 2021-01-27 06:15 | 2021-01-28 12:45 | [8 empty] | * |  | 2021-01-27 06:15 | 2021-01-28 12:45 |  | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
97186 | WBS.2.1.13.12.3.3.17 | N | N | Planned | HBG - RET/Nap remove manual adjustments in IBP on 1/28 (save a copy for reference) | 3 | 2021-01-28 09:45 | 2021-01-28 12:45 | SYDNEY MAY | SYDNEY.MAY@GAPAC.COM | TAMMIE WILLIAMS;SAI TEAM;KRISTEN PAULY;BRAD WYMAN;CHRIS ZUMWALT;GLEN RICHARDSON;DAVE LOPAS;MICHELLE SADLER | TAMMIE.WILLIAMS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTEN.PAULY@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;GLEN.RICHARDSON@GAPAC.COM;dave.lopas@gapac.com;BMSADLER@GAPAC.COM | Business | 91863,97148 |  |  | * |  | 2021-01-28 09:45 | 2021-01-28 12:45 | SCM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93802 | WBS.2.1.13.12.3.3.1 | N | N | Planned | HBG - Review Open PO's for Vitals - document status | 0.67 | 2021-01-27 06:15 | 2021-01-27 06:55 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:55 | SCM - TTN | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93738 | WBS.2.1.13.12.3.4 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - EWM | 94.75 | 2021-01-25 06:15 | 2021-01-30 21:00 | [8 empty] | * |  | 2021-01-25 06:15 | 2021-01-30 21:00 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93832 | WBS.2.1.13.12.3.4.1 | N | N | Planned | HBG - Follow up on unloading Inbound STOs to ensure all are completed before FCW | 0.75 | 2021-01-25 06:15 | 2021-01-25 07:00 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:00 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93831 | WBS.2.1.13.12.3.4.2 | N | N | Planned | HBG - Cleanup damaged and obsolete inventory | 4 | 2021-01-25 06:15 | 2021-01-25 10:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 10:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93829 | WBS.2.1.13.12.3.4.3 | N | N | Planned | HBG - Minimize open transactions (Open AR/AP) | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93828 | WBS.2.1.13.12.3.4.4 | N | N | Planned | HBG - Cleanup NOI inventory | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93827 | WBS.2.1.13.12.3.4.5 | N | N | Planned | HBG - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation (business continuity form) | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93826 | WBS.2.1.13.12.3.4.6 | N | N | Planned | HBG - Cleanup obsolete storage locations from system | 1 | 2021-01-25 08:15 | 2021-01-25 09:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93790 |  |  | * |  | 2021-01-25 08:15 | 2021-01-25 09:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93823 | WBS.2.1.13.12.3.4.7 | N | N | Planned | HBG - Confirm active items - Vitals that are currently running (things that cannot be cycle counted beforehand) | 1 | 2021-01-25 06:15 | 2021-01-25 07:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 07:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93822 | WBS.2.1.13.12.3.4.8 | N | N | Planned | HBG - Block all non-current items to prevent movement or use | 2 | 2021-01-25 06:15 | 2021-01-25 08:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 06:15 | 2021-01-25 08:15 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93820 | WBS.2.1.13.12.3.4.9 | N | N | Planned | HBG - Cleanup and cycle count repack area | 3 | 2021-01-27 06:15 | 2021-01-27 09:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 09:15 | EWM | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93819 | WBS.2.1.13.12.3.4.10 | N | N | Planned | HBG - Run Inventory Reports for Raw Materials | 0.25 | 2021-01-27 06:15 | 2021-01-27 06:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853 |  |  | * |  | 2021-01-27 06:15 | 2021-01-27 06:30 | EWM | HBG | 2021-01-27 | 2021-01-27 | 2 | Ramp Down
93818 | WBS.2.1.13.12.3.4.11 | N | N | Planned | HBG - Communicate to Warehouse personnel of any Q-holds that occur during the blackout periods must be manually managed to ensure non-conforming materials are not used or shipped | 0.5 | 2021-01-28 06:15 | 2021-01-28 06:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 06:45 | EWM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93817 | WBS.2.1.13.12.3.4.12 | N | N | Planned | HBG - Validate storage location naming and sizes (if required) | 1.5 | 2021-01-28 06:15 | 2021-01-28 07:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 07:45 | EWM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93816 | WBS.2.1.13.12.3.4.13 | N | N | Planned | HBG - Verify all RSD's are complete & approved | 8 | 2021-01-28 06:15 | 2021-01-28 14:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 14:15 | EWM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93815 | WBS.2.1.13.12.3.4.14 | N | N | Planned | HBG - Review and Validate Customer Specific Requirements | 2 | 2021-01-28 06:15 | 2021-01-28 08:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 08:15 | EWM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93814 | WBS.2.1.13.12.3.4.15 | N | N | Planned | HBG - Confirm All Shipments/Deliveries For Orders Not Shipping Before Cutover Deleted | 0.5 | 2021-01-29 07:30 | 2021-01-29 08:00 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93766 |  |  | * |  | 2021-01-29 07:30 | 2021-01-29 08:00 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93813 | WBS.2.1.13.12.3.4.16 | N | N | Planned | HBG - Vaidate shipment doc deleted by KBX has been removed from ECC | 1 | 2021-01-30 17:00 | 2021-01-30 18:00 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851,92322,90697 |  |  | * |  | 2021-01-30 17:00 | 2021-01-30 18:00 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93812 | WBS.2.1.13.12.3.4.17 | N | N | Planned | HBG - Ensure all damaged inventory is in "repack, or repackQS" | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93811 | WBS.2.1.13.12.3.4.18 | N | N | Planned | HBG - End & validate Cycle count inventory - All Items. Validate WM inventory matches ECC SAP for finished goods | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93810 | WBS.2.1.13.12.3.4.19 | N | N | Planned | HBG - Ensure paper consumption is current - clear any open items ICPAQS | 2 | 2021-01-29 06:15 | 2021-01-29 08:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 08:15 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93807 | WBS.2.1.13.12.3.4.23 | N | N | Planned | HBG - Mill communicates to all constituencies (mill and DC) to begin manual processes through system shutdown | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94728 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 21:00 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93855 | WBS.2.1.13.12.3.4.25 | N | N | Planned | HBG - MRO - Operations confirms all system activities to perform prior to cutover have been completed | 2 | 2021-01-30 12:15 | 2021-01-30 14:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 14:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94113 | WBS.2.1.13.12.3.4.26 | N | N | Planned | HBG - Ensure shipping capacity buckets are set to agreed upon ramp down and ramp up schedule | 0.5 | 2021-01-25 08:00 | 2021-01-25 08:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10845 |  |  | * |  | 2021-01-25 08:00 | 2021-01-25 08:30 | EWM | HBG | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
93741 | WBS.2.1.13.12.3.5 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - RTR | 29 | 2021-01-29 06:15 | 2021-01-30 19:15 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-30 19:15 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93887 | WBS.2.1.13.12.3.5.1 | N | N | Planned | HBG - Run SM35 and correct any Posting Errors | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94348 | WBS.2.1.13.12.3.5.2 | N | N | Planned | HBG - Run ZAP34 and ZMR11 and tie GRIR to ledger FS10N-acct 3202000 before system cutover | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | RTR - GL | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95569 | WBS.2.1.13.12.3.5.3 | N | N | Planned | HBG - Check Acct 5999999 in ECC and clear | 0.5 | 2021-01-30 18:15 | 2021-01-30 18:45 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 18:45 | RTR - GL | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
97363 | WBS.2.1.13.12.3.5.4 | N | N | Planned | HBG - Review Balance Sheet OIM accounts | 0.5 | 2021-01-29 06:15 | 2021-01-29 06:45 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:45 | RTR - GL | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
97504 | WBS.2.1.13.12.3.5.5 | N | N | Planned | HBG - Review month-end count and make MI10 adjustments | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | RTR - GL | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93740 | WBS.2.1.13.12.3.6 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Cut-Off Activities - PTP | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | [8 empty] | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 |  | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93877 | WBS.2.1.13.12.3.6.1 | N | N | Planned | HBG - Confirm receiving is complete in ECC | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM;BRETT WILBERDING | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RICHARD.WILBERDING@GAPAC.com | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93793 | WBS.2.1.13.12.3.6.2 | N | N | Planned | HBG - Send Final Communication - Requisitions/Requisition Approval | 0.25 | 2021-01-29 06:15 | 2021-01-29 06:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:30 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93876 | WBS.2.1.13.12.3.6.3 | N | N | Planned | HBG - Process Open Purchase Requisitions To Purchase Orders | 1 | 2021-01-29 06:15 | 2021-01-29 07:15 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 07:15 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93739 | WBS.2.1.13.12.3.7 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - EWM Inventory Conversion Precursor | 175 | 2021-01-18 06:15 | 2021-01-30 21:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 21:15 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93875 | WBS.2.1.13.12.3.7.1 | N | N | Planned | HBG - Run inventory reports for out of ECC for parent rolls and vital supplies prior to cutover. | 1 | 2021-01-29 12:15 | 2021-01-29 13:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 13:15 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93874 | WBS.2.1.13.12.3.7.2 | N | N | Planned | HBG - Stage to converting lines raw materials needed during entire shutdown period | 0.5 | 2021-01-29 12:15 | 2021-01-29 12:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:45 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93873 | WBS.2.1.13.12.3.7.3 | N | N | Planned | HBG - Identify pilot transactions to perform after system comes up on eWM | 0.5 | 2021-01-29 13:15 | 2021-01-29 13:45 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93875 |  |  | * |  | 2021-01-29 13:15 | 2021-01-29 13:45 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93915 | WBS.2.1.13.12.3.7.4 | N | N | Planned | HBG - Final Cycle Count MRO and adjust | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93871 | WBS.2.1.13.12.3.7.5 | N | N | Planned | HBG - Purchase Orders: Print the Open STO/PO Detail Report prior to SAP shutdown. | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93869 | WBS.2.1.13.12.3.7.7 | N | N | Planned | HBG - Run open inventory display by LPN detail and upload into Teams quality file | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93868 | WBS.2.1.13.12.3.7.8 | N | N | Planned | HBG - Ensure all locations are not in blocked status | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93867 | WBS.2.1.13.12.3.7.9 | N | N | Planned | HBG - Operations confirms all system activities to perform prior to cutover have been completed. | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93866 | WBS.2.1.13.12.3.7.10 | N | N | Planned | HBG - Operations confirms any trailers needing to be checked in/out prior to cutover have been addressed | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93865 | WBS.2.1.13.12.3.7.11 | N | N | Planned | HBG - Operations notifies cutover team that they are ready for the cutover work to begin. | 0.5 | 2021-01-30 20:30 | 2021-01-30 21:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94728 |  |  | * |  | 2021-01-30 20:30 | 2021-01-30 21:00 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
95266 | WBS.2.1.13.12.3.7.12 | N | N | Planned | HBG - Cycle count all Finished Goods and make sure SAP inventory is matching current WM system | 8 | 2021-01-18 06:15 | 2021-01-18 14:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10846 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 14:15 | EWM | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
93864 | WBS.2.1.13.12.3.7.13 | N | N | Planned | HBG - All shipments are load end and none started. | 3 | 2021-01-30 12:15 | 2021-01-30 15:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 15:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93863 | WBS.2.1.13.12.3.7.14 | N | N | Planned | HBG - Nothing allocated, no picks in queue, no trailer moves in transit, staging lanes clear | 6 | 2021-01-30 12:15 | 2021-01-30 18:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 18:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93861 | WBS.2.1.13.12.3.7.15 | N | N | Planned | HBG - Review site specific Pacspec and ensure information is uploaded prior to go live. | 4 | 2021-01-28 06:15 | 2021-01-28 10:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10852 |  |  | * |  | 2021-01-28 06:15 | 2021-01-28 10:15 | EWM | HBG | 2021-01-28 | 2021-01-28 | 2 | Ramp Down
93860 | WBS.2.1.13.12.3.7.16 | N | N | Planned | HBG - Verify all picked inventory has been loaded and PGI | 2 | 2021-01-30 19:15 | 2021-01-30 21:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,95233 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 21:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93859 | WBS.2.1.13.12.3.7.17 | N | N | Planned | HBG - Confirm last raw material receipt in ECC at shutdown | 0.25 | 2021-01-30 12:15 | 2021-01-30 12:30 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:30 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93858 | WBS.2.1.13.12.3.7.18 | N | N | Planned | HBG - Confirm last shipment complete in ECC at shutdown | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93857 | WBS.2.1.13.12.3.7.19 | N | N | Planned | HBG - iCPAQS - Production counts entered at the end of each shift in ICPAQS should not be submitted to SAP until the system is back up. | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93854 | WBS.2.1.13.12.3.7.20 | N | N | Planned | HBG - Delete shipments and deliveries for orders not shipping before cutover (mill only) | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93852 | WBS.2.1.13.12.3.7.22 | N | N | Planned | HBG - Final Resync of WIP between upload file and ECC SAP and adjust | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93851 | WBS.2.1.13.12.3.7.23 | N | N | Planned | HBG - Final Resync of Vital Supplies between upload file and ECC SAP and adjust | 4 | 2021-01-30 12:15 | 2021-01-30 16:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 16:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93845 | WBS.2.1.13.12.3.7.24 | N | N | Planned | HBG - Stop Staging Loads for Outbound | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93844 | WBS.2.1.13.12.3.7.25 | N | N | Planned | HBG - Move all Outbound Loads to Trailers (staging lanes should be empty) | 0.5 | 2021-01-30 12:15 | 2021-01-30 12:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 12:45 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93835 | WBS.2.1.13.12.3.7.26 | N | N | Planned | HBG - Scan all Parent Rolls and Vital Supplies including lot # and location into data base for upload to EWM | 8 | 2021-01-29 06:15 | 2021-01-29 14:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10851 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 14:15 | EWM | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93839 | WBS.2.1.13.12.3.7.28 | N | N | Planned | HBG - Identify IB STO on Friday before cutover, flag trailer | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93837 | WBS.2.1.13.12.3.7.29 | N | N | Planned | HBG - Validate shipment doc deleted by KBX has been removed from ECC (mill only)** add validation task | 0.5 | 2021-01-30 17:00 | 2021-01-30 17:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 12178,92322,90697 |  |  | * |  | 2021-01-30 17:00 | 2021-01-30 17:30 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93842 | WBS.2.1.13.12.3.7.30 | N | N | Planned | HBG - Communicate to Converting to Start Shutdown prior to Cutover Window | 1 | 2021-01-30 18:15 | 2021-01-30 19:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90821 |  |  | * |  | 2021-01-30 18:15 | 2021-01-30 19:15 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
94943 | WBS.2.1.13.12.3.7.31 | N | N | Planned | HBG - Notify E80/ICPAQS that Converting Operations have stopped | 0.25 | 2021-01-30 19:15 | 2021-01-30 19:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93842 |  |  | * |  | 2021-01-30 19:15 | 2021-01-30 19:30 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93841 | WBS.2.1.13.12.3.7.32 | N | N | Planned | HBG - Validate no more LGV Movements (For HBG this means No more production putaway) | 0.5 | 2021-01-30 19:30 | 2021-01-30 20:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94943 |  |  | * |  | 2021-01-30 19:30 | 2021-01-30 20:00 | EWM | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93723 | WBS.2.1.13.12.4 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Communications | 167 | 2021-01-18 06:15 | 2021-01-30 13:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:15 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93742 | WBS.2.1.13.12.4.2 | N | N |  | Ramp Down ¦ Business Activities - Hattiesburg - Communications - PTP | 167 | 2021-01-18 06:15 | 2021-01-30 13:15 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-30 13:15 |  | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93884 | WBS.2.1.13.12.4.2.1 | N | N | Planned | HBG - Send Communication - Last POs Issued, Please Use Manual PO Process | 0.25 | 2021-01-29 07:15 | 2021-01-29 07:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93876 |  |  | * |  | 2021-01-29 07:15 | 2021-01-29 07:30 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93882 | WBS.2.1.13.12.4.2.2 | N | N | Planned | HBG - Final Communication - Parts Issuing to Begin Following Manual Process | 0.25 | 2021-01-29 12:15 | 2021-01-29 12:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 81706 |  |  | * |  | 2021-01-29 12:15 | 2021-01-29 12:30 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93902 | WBS.2.1.13.12.4.2.3 | N | N | Planned | HBG - Start Task - Record all Storeroom Transactions Using Business Continuity Forms | 0.25 | 2021-01-29 12:30 | 2021-01-29 12:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93882 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 12:45 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93880 | WBS.2.1.13.12.4.2.4 | N | N | Planned | HBG - Process Returns And Credit Memo | 2 | 2021-01-29 12:30 | 2021-01-29 14:30 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM;BRETT WILBERDING | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RICHARD.WILBERDING@GAPAC.com | Business | 93882 |  |  | * |  | 2021-01-29 12:30 | 2021-01-29 14:30 | PTP | HBG | 2021-01-29 | 2021-01-29 | 2 | Ramp Down
93878 | WBS.2.1.13.12.4.2.5 | N | N | Planned | HBG - Complete Manual Tracking Spreadsheet for any AS8 materials or services received during dark period | 1 | 2021-01-30 12:15 | 2021-01-30 13:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM;BRETT WILBERDING | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RICHARD.WILBERDING@GAPAC.com | Business | 12178 |  |  | * |  | 2021-01-30 12:15 | 2021-01-30 13:15 | PTP | HBG | 2021-01-30 | 2021-01-30 | 2 | Ramp Down
93879 | WBS.2.1.13.12.4.2.6 | N | N | Planned | HBG - Confirm all blanket PO/Framework orders have been updated to end on 6.31.2020 | 0.5 | 2021-01-18 06:15 | 2021-01-18 06:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:45 | PTP | HBG | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97785 | WBS.2.1.13.12.6 | N | N |  | Ramp Down ¦ Central Storeroom Tasks | 86.75 | 2021-01-18 06:15 | 2021-01-25 13:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 13:00 |  | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97784 | WBS.2.1.13.12.6.19 | N | N |  | Ramp Down ¦ Central Storeroom Tasks | 86.75 | 2021-01-18 06:15 | 2021-01-25 13:00 | [8 empty] | * |  | 2021-01-18 06:15 | 2021-01-25 13:00 |  | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97801 | WBS.2.1.13.12.6.19.44 | N | N | Planned | CSR - Manual Config Steps (Assign User to Tolerance Group for Difference Analyzer and Recount/Clearing) - MRO | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;AVINASH TALREJA;LEM LANCASTER;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AVTALREJA@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501,93400,4573 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97800 | WBS.2.1.13.12.6.19.45 | N | N | Planned | CSR - Manual Config Steps (Maintain Resources; Resource Group; Maintain Queue Sequence for Resource Group) - for MRO | 0.25 | 2021-01-18 14:30 | 2021-01-18 14:45 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501,93400 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 14:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97799 | WBS.2.1.13.12.6.19.46 | N | N | Planned | CSR - Manual Config Steps (Maintain Users) - MRO | 1 | 2021-01-18 14:30 | 2021-01-18 15:30 | Danny Dixon | Daniel.Dixon2@gapac.com | SAI TEAM;EWM TEAM;AVINASH TALREJA;LEM LANCASTER;NAWIETA HAMILTON-MATHIS;PAUL CARTER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AVTALREJA@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 93400,4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97798 | WBS.2.1.13.12.6.19.47 | N | N | Planned | CSR - Default printer for MRO labels ( Material label/pick HU label/serial number label) | 0.25 | 2021-01-18 06:15 | 2021-01-18 06:30 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 36501 |  |  | * |  | 2021-01-18 06:15 | 2021-01-18 06:30 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97797 | WBS.2.1.13.12.6.19.48 | N | N | Planned | CSR MRO - Manual Config Steps (Maintain Resources; Resource Group) | 0.5 | 2021-01-18 14:30 | 2021-01-18 15:00 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 4501 |  |  | * |  | 2021-01-18 14:30 | 2021-01-18 15:00 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97796 | WBS.2.1.13.12.6.19.49 | N | N | Planned | CSR - PTM_C0205 - Manually Update, Validate & Business Sign-Off Fixed Bin MRO Data on Product Master File - SCM MDM | 3 | 2021-01-21 19:00 | 2021-01-21 22:00 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 3955 |  |  | * |  | 2021-01-21 19:00 | 2021-01-21 22:00 | EWM | PTH | 2021-01-21 | 2021-01-21 | 1 | Ramp Down
97795 | WBS.2.1.13.12.6.19.50 | N | N | Planned | CSR - PTM_C0205 - (MRO) Validate Preload Transform - Convert Product Master | 4 | 2021-01-22 12:00 | 2021-01-22 16:00 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 95361 |  |  | * |  | 2021-01-22 12:00 | 2021-01-22 16:00 | EWM | PTH | 2021-01-22 | 2021-01-22 | 1 | Ramp Down
97794 | WBS.2.1.13.12.6.19.51 | N | N | Planned | CSR - PTM_C0205 - Validate Load MRO - Convert Product Master | 3 | 2021-01-25 10:00 | 2021-01-25 13:00 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;LEM LANCASTER;LISA HAUSER;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEM.LANCASTER@GAPAC.COM;LISA.HAUSER@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 5229 |  |  | * |  | 2021-01-25 10:00 | 2021-01-25 13:00 | EWM | PTH | 2021-01-25 | 2021-01-25 | 2 | Ramp Down
97793 | WBS.2.1.13.12.6.19.52 | N | N | Planned | CSR - PTM_C0203 - Manual conversion of Warehouse bins - MRO | 2 | 2021-01-19 14:45 | 2021-01-19 16:45 | Wesley Dean | wdean@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97788 |  |  | * |  | 2021-01-19 14:45 | 2021-01-19 16:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97792 | WBS.2.1.13.12.6.19.53 | N | N | Planned | CSR - PTM_C0203 - Extract and Prepare Storage Bin upload file (MRO) | 3 | 2021-01-18 19:45 | 2021-01-19 06:45 | KRISTINA KAUTH | KRISTINA.KAUTH@GAPAC.COM | DOUG STANISLAWSKI;AVINASH TALREJA;SAI TEAM;EWM TEAM;SANTOSH KUPPILI | DOUG.STANISLAWSKI@GAPAC.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM | EWM | 36501,97353 |  |  | * |  | 2021-01-18 19:45 | 2021-01-19 06:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97791 | WBS.2.1.13.12.6.19.54 | N | N | Planned | CSR - PTM_C0203 - MRO - Identify, validate and business sign-off - Stock and Non-Stock Storage bins | 5 | 2021-01-19 06:45 | 2021-01-19 11:45 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 97792 |  |  | * |  | 2021-01-19 06:45 | 2021-01-19 11:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97790 | WBS.2.1.13.12.6.19.55 | N | N | Planned | CSR - PTM_C0203 - MRO - Validate Storage Bins Loaded Properly - EWM | 1 | 2021-01-19 18:15 | 2021-01-19 19:15 | Danny Dixon | Daniel.Dixon2@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 97789 |  |  | * |  | 2021-01-19 18:15 | 2021-01-19 19:15 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97789 | WBS.2.1.13.12.6.19.56 | N | N | Planned | CSR - PTM_C0203 - Prepare Bin Validation file - MRO | 1.5 | 2021-01-19 16:45 | 2021-01-19 18:15 | Wesley Dean | wdean@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97793 |  |  | * |  | 2021-01-19 16:45 | 2021-01-19 18:15 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97788 | WBS.2.1.13.12.6.19.57 | N | N | Planned | CSR - PTM_C0203 - Validate Storage bin file with EWM Configuration - for MRO | 3 | 2021-01-19 11:45 | 2021-01-19 14:45 | Wesley Dean | wdean@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 4100,97791 |  |  | * |  | 2021-01-19 11:45 | 2021-01-19 14:45 | EWM | PTH | 2021-01-19 | 2021-01-19 | 1 | Ramp Down
97830 | WBS.2.1.13.12.6.19.73 | N | N | Planned | CSR - Extend cocode to the relevant supplier records and extend sales org to relevant returns customers | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | DENISE ROBINSON | DOROBINS@GAPAC.COM | SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli;JON LUKE DAVILA;SAI TEAM | SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JONLUKE.DAVILA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97829 | WBS.2.1.13.12.6.19.72 | N | N | Planned | CSR - Add route code for CSR 1840 | 1 | 2021-01-18 08:15 | 2021-01-18 09:15 | LISA KOENIG | lisa.koenig@gapac.com | ONI BORCHERS;KYNDAL CODY;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM;VIVEK TALATI | OCBORCHE@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VIVEK.TALATI@KOCHTC.COM | OTC | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 09:15 | OTC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97828 | WBS.2.1.13.12.6.19.71 | N | N | Planned | CSR - Create plant customer 1840 | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | DENISE ROBINSON | DOROBINS@GAPAC.COM | SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli;JON LUKE DAVILA;SAI TEAM | SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JONLUKE.DAVILA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97827 | WBS.2.1.13.12.6.19.70 | N | N | Planned | CSR - Extend Finance master data to Company Code 5102 (Profit center, Cost center) | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | VIVEK TALATI;ONI BORCHERS;KYNDAL CODY;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM | VIVEK.TALATI@KOCHTC.COM;OCBORCHE@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | RTR | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97826 | WBS.2.1.13.12.6.19.69 | N | N | Planned | CSR - Extend GL accounts to Company Code 5102 | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli;JOAN SEIDL;SAI TEAM | SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JOAN.SEIDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | RTR | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97825 | WBS.2.1.13.12.6.19.68 | N | N | Planned | CSR - Maintain G1/G2 for plants in MDM for procurement reporting | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DANNY NGUYEN | DANNY.NGUYEN@GAPAC.COM | BRETT DETTMERING;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM | BRETT.DETTMERING@GAPAC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | RTR | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97824 | WBS.2.1.13.12.6.19.67 | N | N | Planned | CSR - Extend CoCd 5102 to Motion, GBB and SAV vendors | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DENISE ROBINSON | DOROBINS@GAPAC.COM | BRETT DETTMERING;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM | BRETT.DETTMERING@GAPAC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97823 | WBS.2.1.13.12.6.19.66 | N | N | Planned | CSR - Create IV5102 in master data and extend to GBB, SAV and CSR | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DENISE ROBINSON | DOROBINS@GAPAC.COM | BRETT DETTMERING;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM | BRETT.DETTMERING@GAPAC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97822 | WBS.2.1.13.12.6.19.65 | N | N | Planned | CSR - Create IC5102 in master data and extend to GBB, SAV and CSR | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DENISE ROBINSON | DOROBINS@GAPAC.COM | JON LUKE DAVILA;SAI TEAM;SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli | JONLUKE.DAVILA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97821 | WBS.2.1.13.12.6.19.64 | N | N | Planned | CSR - Assignment of a special procurement key to a material | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | SHANKAR RAMNARAYANAN | SRAMNARAYANAN@DELOITTE.COM | SANDRA RICHARDS;Ramya Mathukumilli;JON LUKE DAVILA;SAI TEAM | SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JONLUKE.DAVILA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97820 | WBS.2.1.13.12.6.19.63 | N | N | Planned | CSR - Add CoCode 5102 to ZTDAT_I0313_REGN | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | DENISE ROBINSON | DOROBINS@GAPAC.COM | JOAN SEIDL;SAI TEAM;SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli | JOAN.SEIDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com | Data | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | Data | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97819 | WBS.2.1.13.12.6.19.62 | N | N | Planned | CSR - Validate inbound and outbound delivery batch job for plant 1840 | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | Wesley Dean | wdean@deloitte.com | DENISE ROBINSON;Ramya Mathukumilli;MARCOS MIRANDA;SAI TEAM | DOROBINS@GAPAC.COM;rmathukumilli@deloitte.com;MARCOS.MIRANDA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97818 | WBS.2.1.13.12.6.19.61 | N | N | Planned | CSR - BRF tables updates | 1 | 2021-01-18 08:15 | 2021-01-18 09:15 | Wesley Dean | wdean@deloitte.com | SHANKAR RAMNARAYANAN;SANDRA RICHARDS;Ramya Mathukumilli;COURTNEY ANDERSON;SAI TEAM | SRAMNARAYANAN@DELOITTE.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;COURTNEY.ANDERSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 09:15 | EWM | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97817 | WBS.2.1.13.12.6.19.60 | N | N | Planned | CSR - Create Billing Job variant for Atlanta Central Storeroom | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | ONI BORCHERS | OCBORCHE@GAPAC.COM | AVINASH TALREJA;Ramya Mathukumilli;SANDRA RICHARDS;SAI TEAM | AVTALREJA@DELOITTE.COM;rmathukumilli@deloitte.com;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | OTC | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | OTC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97816 | WBS.2.1.13.12.6.19.59 | N | N | Planned | CSR - Add Central Storeroom billing variant to the intercompany batch job in Stone Branch | 0.5 | 2021-01-18 08:15 | 2021-01-18 08:45 | NNEKA MBA | NEMBA@GAPAC.COM | ONI BORCHERS;KYNDAL CODY;LISA KOENIG;VIVEK TALATI;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM | OCBORCHE@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;lisa.koenig@gapac.com;VIVEK.TALATI@KOCHTC.COM;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | OTC | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:45 | OTC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97815 | WBS.2.1.13.12.6.19.58 | N | N | Planned | CSR - Add RD04 billing output record for the Central Storeroom sales area 5102/90/99 | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | ONI BORCHERS | OCBORCHE@GAPAC.COM | LISA KOENIG;SANDRA RICHARDS;Ramya Mathukumilli;SAI TEAM;VIVEK TALATI | lisa.koenig@gapac.com;SARICHARDS@DELOITTE.COM;rmathukumilli@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VIVEK.TALATI@KOCHTC.COM | OTC | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | OTC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97851 | WBS.2.1.13.12.6.19.75 | N | N | Planned | CSR - Maintain EDI partner profiles for KU IC5102 and LI IV5102 | 0.25 | 2021-01-18 08:15 | 2021-01-18 08:30 | CYNDI HOTTENSTINE | CYNDI.HOTTENSTINE@GAPAC.COM | ONI BORCHERS;KYNDAL CODY;Ramya Mathukumilli;SANDRA RICHARDS;SAI TEAM | OCBORCHE@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;rmathukumilli@deloitte.com;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | OTC | 7819 |  |  | * |  | 2021-01-18 08:15 | 2021-01-18 08:30 | OTC | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
97850 | WBS.2.1.13.12.6.19.74 | N | N | Planned | CSR - Maintain EDI tables for Intercompany Invoices using OBCD, OBCE, OBCA for company code 5102 | 1.5 | 2021-01-18 08:30 | 2021-01-18 10:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;DENISE ROBINSON;SRUTHI SRINIVASAN;YUDI MITRA;SANDEEP A;Ramya Mathukumilli;SANDRA RICHARDS;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;DOROBINS@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;YMITRA@DELOITTE.COM;SANDEEP.A@KOCHGS.COM;rmathukumilli@deloitte.com;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 7819,97851 |  |  | * |  | 2021-01-18 08:30 | 2021-01-18 10:00 | PTP | PTH | 2021-01-18 | 2021-01-18 | 1 | Ramp Down
5664 | WBS.2.2 | N | N |  | FCW ¦ Final Cutover Window / Shutdown Phase | 54.5 | 2021-01-31 01:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-01-30 22:15 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91470 | WBS.2.2.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions | 50.25 | 2021-01-31 01:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-30 22:15 | 2021-02-02 05:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91002 | WBS.2.2.1.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports | 44.25 | 2021-01-31 01:15 | 2021-02-01 21:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90626 | WBS.2.2.1.1.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports | 44.25 | 2021-01-31 01:15 | 2021-02-01 21:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91467 | WBS.2.2.1.1.1.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - S/4HANA | 44.25 | 2021-01-31 01:15 | 2021-02-01 21:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97277 | WBS.2.2.1.1.1.1.110 | N | N | Planned | Import CRM FCW TRs | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | SRINIVAS KAKUTURU | SKAKUTURU@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91486 | WBS.2.2.1.1.1.1.174 | N | N | Planned | Open SAP CRM Client | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4323 | WBS.2.2.1.1.1.1.175 | N | N | Planned | Send SAP CRM Transports Results To Teams | 0.5 | 2021-01-31 02:15 | 2021-01-31 02:45 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4424,7867,97277 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4326 | WBS.2.2.1.1.1.1.180 | N | N | Planned | Validate Security Transports For SAP CRM | 1 | 2021-01-31 02:45 | 2021-01-31 03:45 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SAI TEAM;GREG CAPPS;SOUMYA PANDA;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4323 |  |  | * |  | 2021-01-31 02:45 | 2021-01-31 03:45 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91074 | WBS.2.2.1.1.1.1.181 | N | N | Planned | Backup CRM System - Post Transports - FCW | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4326,91499 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4324 | WBS.2.2.1.1.1.1.176 | N | N | Planned | Confirm CRM Client is Open | 0.25 | 2021-01-31 02:45 | 2021-01-31 03:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4323 |  |  | * |  | 2021-01-31 02:45 | 2021-01-31 03:00 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82732 | WBS.2.2.1.1.1.1.177 | N | N | Planned | Validate/ Add document categories to document classes in SAP CRM. (SPRO-->SAP NetWeaver-->Application Server-->Basis Services-->Knowledge Provider-->Document Management Service-->Define Standard Category) - Mock Cutover Only | 0.25 | 2021-01-31 03:00 | 2021-01-31 03:15 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | NAVJOT SHARMA;VINOTH NAGARAJAN;ARUN GANGADHARAN;US GP BASIS;DON ABBOTT;SAI TEAM;SUVENDU KUMAR;DEV TEAM;CHIRAG GUPTA | NASHARMA@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;USGPBASIS@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;CHIRGUPTA@DELOITTE.COM | DEV | 4324 |  |  | * |  | 2021-01-31 03:00 | 2021-01-31 03:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91499 | WBS.2.2.1.1.1.1.178 | N | N | Planned | Close SAP CRM Client | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91486 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97264 | WBS.2.2.1.1.1.1.97 | N | N | Planned | Import BW FCW TRs | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4319 | WBS.2.2.1.1.1.1.173 | N | N | Planned | Validate Security Transports for SAP BW | 1 | 2021-01-31 02:15 | 2021-01-31 03:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 97264 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 03:15 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91079 | WBS.2.2.1.1.1.1.179 | N | N | Planned | Backup BW System - Post Transports - FCW | 0.5 | 2021-01-31 03:15 | 2021-01-31 03:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4319 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 03:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95181 | WBS.2.2.1.1.1.1.1 | N | N | Planned | Update web dispatcher configuration (MC Only) | 2 | 2021-01-31 01:15 | 2021-01-31 03:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95615 | WBS.2.2.1.1.1.1.2 | N | N | Planned | Maintaining HTTPURLOC Table and login/ticket_only_by_https parameter change (MC Only) | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95181,94798,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95621 | WBS.2.2.1.1.1.1.4 | N | N | Planned | Update S/4 Host/port new URLs in Cloud Connector | 1 | 2021-01-31 03:15 | 2021-01-31 04:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | HEMACHANDAN AS;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;US GP BASIS;SAI TEAM;DEV TEAM | HEMACAS@DELOITTE.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95181 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 04:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95179 | WBS.2.2.1.1.1.1.5 | N | N | Planned | Update logon procedure for getserverinfo service in S/4 HANA (for seach connector) (MC Only) | 2 | 2021-01-31 03:15 | 2021-01-31 05:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95181 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 05:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95177 | WBS.2.2.1.1.1.1.7 | N | N | Planned | Validate search connectors | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94798 | WBS.2.2.1.1.1.1.8 | N | N | Planned | Stop S4 receiver channels : Generic SOAP Receiver , Idoc Receiver , E80 SOAP Receiver, ICPAQS SOAP Receiver | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | ANKIT SONI;SAI TEAM;SUVENDU KUMAR;SANDEEP THARWANI;PAYEL GHOSH;ARUN GANGADHARAN;RAKESH MAKKAPATI | ANKISONI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;STHARWANI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10008 | WBS.2.2.1.1.1.1.9 | N | N | Planned | Transport S/4HANA related iFlows to Prod (with credentials) | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | ANKIT SONI | ANKISONI@DELOITTE.COM | TED ZEIDLER;HEMACHANDAN AS;BRIAN DOBASH;SANDEEP THARWANI;NAVJOT SHARMA;DANI SIMMONS;SAI TEAM;US GP BASIS;SUVENDU KUMAR;PAYEL GHOSH;DEV TEAM;RAMYA IYER | TED.ZEIDLER@GAPAC.COM;HEMACAS@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 36505,93067,91838,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97345 | WBS.2.2.1.1.1.1.34 | N | N | Planned | Update VIZI Query Engine on Windows Server | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | CONNER KING | conner.king@gapac.com | BRIAN RIDENHOUR;SAI TEAM | BRIAN.RIDENHOUR@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RPT | 94798 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | RPT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97697 | WBS.2.2.1.1.1.1.199 | N | N | Planned | Establish VIZI Connection | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | CONNER KING | conner.king@gapac.com | BRIAN RIDENHOUR;SAI TEAM | BRIAN.RIDENHOUR@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | NTO | 97696,97345 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:45 | NTO | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97740 | WBS.2.2.1.1.1.1.200 | N | N | Planned | To update and re create some of the ROS batch job variants. | 3 | 2021-02-01 18:30 | 2021-02-01 21:30 | ABHISHEK NIMBALKAR | abhishek.nimbalkar@kochtc.com | VIPUL GANDHI;SAI TEAM | vipulkumar.gandhi@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | NTO | 95766 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 21:30 | NTO | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91479 | WBS.2.2.1.1.1.1.13 | N | N | Planned | Open S/4HANA Client | 0.25 | 2021-01-31 17:00 | 2021-01-31 17:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92637 | WBS.2.2.1.1.1.1.14 | N | N | Planned | Update and Validate BRF+ tables for Order Acknowledgement Workflow object | 2 | 2021-01-31 17:00 | 2021-01-31 19:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 19:00 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90653 | WBS.2.2.1.1.1.1.15 | N | N | Planned | Send S/4HANA Transport Results To Business / Teams | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,96903,97475 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90867 | WBS.2.2.1.1.1.1.16 | N | N | Planned | Validate/Create New ports CPI_CSTHIE & CPI_AGRMNT | 0.5 | 2021-01-31 17:00 | 2021-01-31 17:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM;DEV TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92354 | WBS.2.2.1.1.1.1.17 | N | N | Planned | Validate/Update XDC settings for QR Code Label Printing | 0.5 | 2021-01-31 17:15 | 2021-01-31 17:45 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | SAI TEAM;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 91479,93067 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
7878 | WBS.2.2.1.1.1.1.18 | N | N | Planned | Update EWM Custom Tables | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;TEJAS THORAT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TTHORAT@DELOITTE.COM | EWM | 90653 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4140 | WBS.2.2.1.1.1.1.19 | N | N | Planned | Validate AIF Alert set-up S/4HANA | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | ARUN GANGADHARAN;VENKATESH GANESHAN;SUVENDU KUMAR;RAKESH MAKKAPATI;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;DEV TEAM | ARGANGADHARAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91494 | WBS.2.2.1.1.1.1.20 | N | N | Planned | Close S/4HANA Client | 0.25 | 2021-01-31 17:45 | 2021-01-31 18:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 36505,92354,96904,97475 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 18:00 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94797 | WBS.2.2.1.1.1.1.21 | N | N | Planned | Start receiver channels : Generic SOAP Receiver , Idoc Receiver , E80 SOAP Receiver, ICPAQS SOAP Receiver | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | ANKIT SONI;SAI TEAM;SUVENDU KUMAR;SANDEEP THARWANI;PAYEL GHOSH;ARUN GANGADHARAN;RAKESH MAKKAPATI | ANKISONI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;STHARWANI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM | DEV | 90653,95429,95519 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | INT | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
36660 | WBS.2.2.1.1.1.1.22 | N | N | Planned | Configure Partner profiles in S/4HANA | 2 | 2021-01-31 19:00 | 2021-01-31 21:00 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | SUVENDU KUMAR;GUNEET ARORA;RAKESH MAKKAPATI;SANDEEP THARWANI;SAI TEAM;DEV TEAM | SUVKUMAR@DELOITTE.COM;GUNEARORA@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4151,4105,90867,36505 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 21:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95710 | WBS.2.2.1.1.1.1.23 | N | N | Planned | Clear cache by running /AIF/DEL_STRUC_CACHE for all interfaces | 0.5 | 2021-01-31 21:00 | 2021-01-31 21:30 | ARAVIND KANAPARTHI | karavindkumar@deloitte.com | GUNEET ARORA;RAKESH MAKKAPATI;SUVENDU KUMAR;ARUN GANGADHARAN;SANDEEP THARWANI;VINOTH NAGARAJAN;VENKATESH GANESHAN;SAI TEAM;DEV TEAM | GUNEARORA@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36660,36505 |  |  | * |  | 2021-01-31 21:00 | 2021-01-31 21:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82256 | WBS.2.2.1.1.1.1.24 | N | N | Planned | Validate / Add AIF Interface determination for IDOCS in /AIF/CUST transaction. | 0.5 | 2021-01-31 21:00 | 2021-01-31 21:30 | ARUN GANGADHARAN | ARGANGADHARAN@DELOITTE.COM | GUNEET ARORA;NAVJOT SHARMA;RAKESH MAKKAPATI;SAI TEAM;SANDEEP THARWANI;NEHA RAUT;SUVENDU KUMAR;DEV TEAM;VENKATESH GANESHAN | GUNEARORA@DELOITTE.COM;NASHARMA@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;STHARWANI@DELOITTE.COM;NEHAHEMANT.RAUT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VGANESHAN@DELOITTE.COM | DEV | 36660,36505 |  |  | * |  | 2021-01-31 21:00 | 2021-01-31 21:30 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95421 | WBS.2.2.1.1.1.1.25 | N | N | Planned | Update Hostname and port in (H) types RFC in Gateway system (MC Only) | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM;DEV TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95179,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95420 | WBS.2.2.1.1.1.1.26 | N | N | Planned | Update SAML for RF Services (ZRFUI*) (MC Only) | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM;DEV TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95421 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
89749 | WBS.2.2.1.1.1.1.27 | N | N | Planned | Configure RF URL on Handheld and Vehicle Mount devices | 2 | 2021-01-31 18:30 | 2021-01-31 20:30 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | BRIAN DOBASH;SAI TEAM;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | BJDOBASH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 89750,95420 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 20:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95419 | WBS.2.2.1.1.1.1.28 | N | N | Planned | Validate Single Logout Endpoints for all backend systems | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | PRASHANTH TUMMALA;SAI TEAM;DEV TEAM | PTUMMALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 95420 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95456 | WBS.2.2.1.1.1.1.29 | N | N | Planned | Update OData service new URL in DMAPS/OE system for S/4 Notification service (ITR_I0245/ITR_I0345) (MC Only) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | JEY MURUGESH;ALEX MEDVEDEV;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;TED ZEIDLER;SAI TEAM | JMURUGESH@DELOITTE.COM;ALEX.MEDVEDEV@GAPAC.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 95181,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | AC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95457 | WBS.2.2.1.1.1.1.30 | N | N | Planned | Update SAP S/4 OData services new URL in GPX system (MC Only) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | CLAY DAVIS | CLAY.DAVIS@GAPAC.COM | GPXPRESSDEVELOPERS;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;SAI TEAM;TED ZEIDLER;SATISH KUMAR B;ANUPAM SHRIVASTAVA | GPXpressDevelopers@GAPAC.com;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 95181,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95458 | WBS.2.2.1.1.1.1.31 | N | N | Planned | Update OData services new URL in TOPS system for Delivery Notes (PTM_I0214) (MC Only) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | DAVE LEGOIS | DAVID.LEGOIS@KBXLOGISTICS.COM | TOM OLIVE;ANDREW ENGELKING;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;TED ZEIDLER;ANDREW HELMANN;JOHN NATZKE;SAI TEAM | THOMAS.OLIVE@KBXLOGISTICS.COM;ANDREW.ENGELKING@KBXLOGISTICS.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;TED.ZEIDLER@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | OTC | 95181,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | OTC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95459 | WBS.2.2.1.1.1.1.32 | N | N | Planned | Update S/4 SOA services Datastores new URLs in SCPI DS (MC Only) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | VENKATA SREEKANTH GOLLAPROLU | GOLLAPROLU.SREEKANTH@KOCHTC.COM | VENKATA KUPPILI;PAYEL GHOSH;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;SAI TEAM;TED ZEIDLER | vkuppili@deloitte.com;PAYGHOSH@DELOITTE.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 95181,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95460 | WBS.2.2.1.1.1.1.33 | N | N | Planned | Update OData service new URL in TRAX system for S/4 Notification service (ITR_I0298) (MC Only) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | TOM BRATTIN | TBRATTI@GAPAC.COM | JEY MURUGESH;ALEX MEDVEDEV;SANDEEP THARWANI;ANKIT SONI;RAMYA IYER;SUVENDU KUMAR;PANKAJ KUMAR;TED ZEIDLER;SAI TEAM | JMURUGESH@DELOITTE.COM;ALEX.MEDVEDEV@GAPAC.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PANKAJ.KUMAR@KOCHTC.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 95181,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | AC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90994 | WBS.2.2.1.1.1.2 | N | N |  | FCW ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SAP IBP | 2.75 | 2021-01-31 01:30 | 2021-01-31 04:15 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-01-31 04:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81164 | WBS.2.2.1.1.1.2.1 | N | N | Planned | IBP - Transports (Z9Y --> Z7X) - IBP DP | 0.75 | 2021-01-31 01:30 | 2021-01-31 02:15 | PRASANNA KAPANIGOWDA | PKAPANIGOWDA@DELOITTE.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;BRAD WYMAN;US GP BASIS;SUVENDU KUMAR;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 82958,36505,82959 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:15 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92717 | WBS.2.2.1.1.1.2.2 | N | N | Planned | Promotion of Stonebranch Tasks to production | 2 | 2021-01-31 02:15 | 2021-01-31 04:15 | DON BIGALKE | DONALD.BIGALKE@KBSLP.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;KELLY HINSON | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;KSHINSON@GAPAC.COM | Batch | 81164 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 04:15 | Batch | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90982 | WBS.2.2.1.1.1.3 | N | N |  | FCW ¦ Tech Build Activities - Pre-Conversions - Transports - Import Transports - SCP DS | 4 | 2021-01-31 01:15 | 2021-01-31 05:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 05:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4219 | WBS.2.2.1.1.1.3.1 | N | N | Planned | SCP-DS - Import transport(s) With Basis Team | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANKIT SONI | ANKISONI@DELOITTE.COM | HEMACHANDAN AS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;RAMYA IYER;SUVENDU KUMAR;PAYEL GHOSH;RADHIKA RASTOGI;TED ZEIDLER;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;DEV TEAM | HEMACAS@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4220 | WBS.2.2.1.1.1.3.2 | N | N | Planned | SCP-DS - Configure Data Stores and Validate RFC Connections | 3 | 2021-01-31 02:15 | 2021-01-31 05:15 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;TED ZEIDLER;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;ANKIT SONI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | RADHRASTOGI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ANKISONI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 4219,91838 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 05:15 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91466 | WBS.2.2.1.1.1.4 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - SAP MDG | 16 | 2021-01-31 01:15 | 2021-01-31 17:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 17:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92751 | WBS.2.2.1.1.1.4.1 | N | N | Planned | MDP - Lock Out All Users Not Needing Access during Transports | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | ANTHONY GORDON;GREG CAPPS;SEC TEAM;SAI TEAM;KIRAN GANNAVARAPU;PALLAVI YELLAYI;MOHAMMED ABDULLAHI;CARLOS ROBELO TEJADA | ADGORDON@GAPAC.COM;GREG.CAPPS@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;PYELLAYI@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM | SECURITY | 92676,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92752 | WBS.2.2.1.1.1.4.3 | N | N | Planned | MDG - Unlock Cutover users | 0.5 | 2021-01-31 09:30 | 2021-01-31 10:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | ANTHONY GORDON;GREG CAPPS;SEC TEAM;SAI TEAM;KIRAN GANNAVARAPU;PALLAVI YELLAYI;MOHAMMED ABDULLAHI;CARLOS ROBELO TEJADA | ADGORDON@GAPAC.COM;GREG.CAPPS@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;PYELLAYI@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM | SECURITY | 96892 |  |  | * |  | 2021-01-31 09:30 | 2021-01-31 10:00 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91471 | WBS.2.2.1.1.1.4.4 | N | N | Planned | Send SAP MDG Transport Results To Teams | 0.5 | 2021-01-31 10:00 | 2021-01-31 10:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 96892,96891 |  |  | * |  | 2021-01-31 10:00 | 2021-01-31 10:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82260 | WBS.2.2.1.1.1.4.5 | N | N | Planned | Validate/ Regenerate BRF+ function for MDG | 0.25 | 2021-01-31 17:00 | 2021-01-31 17:15 | SUVENDU KUMAR | SUVKUMAR@DELOITTE.COM | RAKESH MAKKAPATI;SRINIVAS KATA;SAI TEAM;ARUN GANGADHARAN;SANDEEP THARWANI;DEV TEAM | RMAKKAPATI@DELOITTE.COM;SKATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91465 | WBS.2.2.1.1.1.5 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - SAP PO | 5.75 | 2021-01-31 14:15 | 2021-01-31 20:00 | [8 empty] | * |  | 2021-01-31 14:15 | 2021-01-31 20:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92447 | WBS.2.2.1.1.1.5.2 | N | N | Planned | SAP PO - Refresh Idoc Meta data In SAP PO | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | ANKIT SONI;SUVENDU KUMAR;SANDEEP THARWANI;ARUN GANGADHARAN;RAMYA IYER;DEV TEAM;SAI TEAM;RAKESH MAKKAPATI | ANKISONI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RAMYIYER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM | DEV | 90653,96878,96877 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | INT | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90704 | WBS.2.2.1.1.1.5.3 | N | N | Planned | SAP PO - Configure channels to connected applications (FCW) | 2 | 2021-01-31 14:15 | 2021-01-31 16:15 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | RADHIKA RASTOGI;SAI TEAM;TED ZEIDLER;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;RAMYA IYER | RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM | DEV | 96878,96877 |  |  | * |  | 2021-01-31 14:15 | 2021-01-31 16:15 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4265 | WBS.2.2.1.1.1.5.4 | N | N | Planned | SAP PO - Setup alert configuration | 1 | 2021-01-31 16:15 | 2021-01-31 17:15 | PAYEL GHOSH | PAYGHOSH@DELOITTE.COM | SANDEEP THARWANI;RADHIKA RASTOGI;SAI TEAM;TED ZEIDLER;SUVENDU KUMAR;ARUN GANGADHARAN;RAKESH MAKKAPATI;DEV TEAM | STHARWANI@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;SUVKUMAR@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90704 |  |  | * |  | 2021-01-31 16:15 | 2021-01-31 17:15 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4267 | WBS.2.2.1.1.1.5.5 | N | N | Planned | SAP - Validate AIF XREF Table | 1 | 2021-01-31 19:00 | 2021-01-31 20:00 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | VENKATESH GANESHAN;SAI TEAM;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4246,4105,36505 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91463 | WBS.2.2.1.1.1.7 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - SAP GW | 0.5 | 2021-01-31 14:00 | 2021-01-31 14:30 | [8 empty] | * |  | 2021-01-31 14:00 | 2021-01-31 14:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4292 | WBS.2.2.1.1.1.7.2 | N | N | Planned | Send SAP GW Transport Results To Teams | 0.5 | 2021-01-31 14:00 | 2021-01-31 14:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | US GP BASIS;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;SAI TEAM;SUVENDU KUMAR;ARUN GANGADHARAN;RAKESH MAKKAPATI;LOKESH KAMANA;DEV TEAM;TED ZEIDLER | USGPBASIS@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4424,7867,96885,96884,97476 |  |  | * |  | 2021-01-31 14:00 | 2021-01-31 14:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91461 | WBS.2.2.1.1.1.9 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - SAP GRC | 31 | 2021-01-31 01:15 | 2021-02-01 08:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 08:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4307 | WBS.2.2.1.1.1.9.1 | N | N | Planned | Import Transports For SAP GRC | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91487 | WBS.2.2.1.1.1.9.2 | N | N | Planned | Open SAP GRC Client | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4307 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4308 | WBS.2.2.1.1.1.9.3 | N | N | Planned | Confirm SAP GRC Client is Open | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 4307 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91472 | WBS.2.2.1.1.1.9.4 | N | N | Planned | Send SAP GRC Transport Results To Teams | 0.5 | 2021-01-31 02:15 | 2021-01-31 02:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4307 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91500 | WBS.2.2.1.1.1.9.5 | N | N | Planned | Close SAP GRC Client | 0.25 | 2021-02-01 08:00 | 2021-02-01 08:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;US GP BASIS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 08:15 | DEV - INFRA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91508 | WBS.2.2.1.1.1.10 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - EHANA | 24.25 | 2021-01-31 01:15 | 2021-02-01 01:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 01:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90836 | WBS.2.2.1.1.1.10.1 | N | N | Planned | Import Transports For EHANA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94852 | WBS.2.2.1.1.1.10.2 | N | N | Planned | Maintain output conditions for output type ZMBL | 8 | 2021-01-31 17:30 | 2021-02-01 01:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com | EWM | 90836,95542,95539,95538,95536,95534,96561,96562,96697,96698,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-02-01 01:30 | EWM | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92198 | WBS.2.2.1.1.1.11 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - SAP SLT | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92197 | WBS.2.2.1.1.1.11.1 | N | N | Planned | Import Transports For SAP SLT | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91468 | WBS.2.2.1.1.1.12 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Transports - Import Transports - Multi-System Activities | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4115 | WBS.2.2.1.1.1.12.1 | N | N | Planned | Distribution Model and filters (transport and change logical system) post trans | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | RAKESH MAKKAPATI;VENKATESH GANESHAN;SAI TEAM;SWAMI RAJASEKAR;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM;BEENA ABRAHAM | RMAKKAPATI@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;BEABRAHAM@DELOITTE.COM | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4137 | WBS.2.2.1.1.1.12.2 | N | N | Planned | Mass Activate BRF+ using FDT_HELPERS transaction | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | SUVENDU KUMAR | SUVKUMAR@DELOITTE.COM | RAKESH MAKKAPATI;ARUN GANGADHARAN;SANDEEP THARWANI;SAI TEAM;SRINIVAS KATA;DEV TEAM | RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SKATA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4156 | WBS.2.2.1.1.1.12.3 | N | N | Planned | RV80GHEN program to be run after all the transports are imported . | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SRINIVAS KATA;SWAMI RAJASEKAR;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SKATA@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90167 | WBS.2.2.1.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports | 49 | 2021-01-31 02:30 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 02:30 | 2021-02-02 05:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91469 | WBS.2.2.1.2.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports | 37 | 2021-01-31 14:30 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 14:30 | 2021-02-02 05:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90627 | WBS.2.2.1.2.1.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - AC | 34.25 | 2021-01-31 17:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-02 05:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90008 | WBS.2.2.1.2.1.1.1 | N | N | Planned | Confirm OE database is updated in Legacy System | 1 | 2021-01-31 19:15 | 2021-01-31 20:15 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;TAJINDER KOHLI;DON ABBOTT;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO | DAVID.MCGINNIS@GAPAC.COM;TKOHLI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 95497 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 20:15 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95497 | WBS.2.2.1.2.1.1.2 | N | N | Planned | Process a minor change on SAP side to update OE table | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | DAVID MCGINNIS | DAVID.MCGINNIS@GAPAC.COM | AC TEAM;SAI TEAM | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 95498,36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | AC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92241 | WBS.2.2.1.2.1.1.3 | N | N | Planned | Update ZITR_CC_ACT_TYP - cost center and activity type for time confirmations | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | PRASANNA KANNAN | PK@DELOITTE.COM | AC TEAM;JASON RAMSEY;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5781,90653 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90643 | WBS.2.2.1.2.1.1.4 | N | N | Planned | Validate S/4HANA Configuration Transports - AC | 0.33 | 2021-01-31 18:00 | 2021-01-31 18:20 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | SAI TEAM;JASON RAMSEY;AC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:20 | AC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95750 | WBS.2.2.1.2.1.1.5 | N | N | Planned | Schedule PTM and Maintelligence plans | 2 | 2021-01-31 18:20 | 2021-01-31 20:20 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | BOB BROWN;SAI TEAM;AC TEAM | ROBERT.BROWN4@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | AC | 90643 |  |  | * |  | 2021-01-31 18:20 | 2021-01-31 20:20 | AC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92076 | WBS.2.2.1.2.1.1.6 | N | N | Planned | Create Qualification Catalog | 1 | 2021-01-31 18:20 | 2021-01-31 19:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90643 |  |  | * |  | 2021-01-31 18:20 | 2021-01-31 19:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92077 | WBS.2.2.1.2.1.1.7 | N | N | Planned | Confirm MRS is active for all D1, D2, D3 and D4 plants only | 1 | 2021-01-31 18:20 | 2021-01-31 19:20 | PAVAN KUMAR | PAVAN.KUMARCS@KOCHTC.COM | TAJINDER KOHLI;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90643 |  |  | * |  | 2021-01-31 18:20 | 2021-01-31 19:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92072 | WBS.2.2.1.2.1.1.8 | N | N | Planned | Request Fire Fighter to run LSMW to update PERNR | 1 | 2021-01-31 18:20 | 2021-01-31 19:20 | JEY MURUGESH | JMURUGESH@DELOITTE.COM | TAJINDER KOHLI;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | TKOHLI@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 90643 |  |  | * |  | 2021-01-31 18:20 | 2021-01-31 19:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92075 | WBS.2.2.1.2.1.1.9 | N | N | Planned | Create Qualification Matrix | 1 | 2021-01-31 19:20 | 2021-01-31 20:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92076 |  |  | * |  | 2021-01-31 19:20 | 2021-01-31 20:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92074 | WBS.2.2.1.2.1.1.10 | N | N | Planned | Create Requirement Profile | 1 | 2021-01-31 20:20 | 2021-01-31 21:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92075 |  |  | * |  | 2021-01-31 20:20 | 2021-01-31 21:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92073 | WBS.2.2.1.2.1.1.11 | N | N | Planned | Create Employee Profile | 1 | 2021-01-31 21:20 | 2021-01-31 22:20 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM;DEAN PIPER;LYNN MCMURDO | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92074 |  |  | * |  | 2021-01-31 21:20 | 2021-01-31 22:20 | AC | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91023 | WBS.2.2.1.2.1.1.12 | N | N | Planned | Backup S/4HANA System - Post Data Conversions | 2.5 | 2021-02-02 01:00 | 2021-02-02 03:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5430,5379,5388,89997,5385,5382,5408,82905,89619,9811,8932,4056,8936,89981,5481,5456,82900,5763,5441,5438,90008,5393,4974,7902,7906,5128,29561,5783,5261,5256,5251,5246,5236,5231,8864,5230,89806,11032,89804,5476,5471,5451,5403,5418,5398,94320,94323,9698,9... |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 05:00 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90921 | WBS.2.2.1.2.1.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - DEV | 2 | 2021-01-31 17:00 | 2021-01-31 19:00 | [8 empty] | * |  | 2021-01-31 17:00 | 2021-01-31 19:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4105 | WBS.2.2.1.2.1.2.1 | N | N | Planned | Validate transports, warnings and errors S/4HANA and MDG | 2 | 2021-01-31 17:00 | 2021-01-31 19:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | ARUN GANGADHARAN;VENKATESH GANESHAN;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;LOKESH KAMANA;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | ARGANGADHARAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;LKAMANA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 19:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4104 | WBS.2.2.1.2.1.2.2 | N | N | Planned | Validate OSS Notes Were Transported S/4HANA | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | SANDEEP THARWANI;ARUN GANGADHARAN;DIGITAL CORE UX TEAM;SAI TEAM;RAKESH MAKKAPATI;SUVENDU KUMAR;DEV TEAM | STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;DIGITALCOREUXTEAM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4158 | WBS.2.2.1.2.1.2.3 | N | N | Planned | Open S/4HANA System For Manual Configuration | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97758 | WBS.2.2.1.2.1.2.4 | N | N | Planned | Adjust the CDS view for BOP Variant Fiori App | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | VONALD RAUGHN;SAI TEAM | *;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 90648 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | UX | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90919 | WBS.2.2.1.2.1.3 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - OTC | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90648 | WBS.2.2.1.2.1.3.1 | N | N | Planned | OTC - Validate S/4HANA Config Transports | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | MICHELLE SADLER;TRISHUL BUDDHA;SAI TEAM;OTC TEAM;KYNDAL CODY;ONI BORCHERS | BMSADLER@GAPAC.COM;TBUDDHA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | OTC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95278 | WBS.2.2.1.2.1.3.2 | N | N | Planned | Maintain BRF+ tables for OTC - post FCW transports | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | KETAN PRADHAN | KEPRADHAN@DELOITTE.COM | OTC TEAM;SAI TEAM;TRISHUL BUDDHA;KYNDAL CODY;ONI BORCHERS | PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TBUDDHA@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 90648,96904,97475 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | OTC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90918 | WBS.2.2.1.2.1.4 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - RTR | 27.25 | 2021-01-31 17:15 | 2021-02-01 20:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-01 20:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94565 | WBS.2.2.1.2.1.4.1 | N | N | Planned | Validation of OBYC between pre transport S4P and QA environment | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92146,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 | RTR - GL | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90646 | WBS.2.2.1.2.1.4.2 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - CO | 0.75 | 2021-01-31 18:00 | 2021-01-31 18:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:45 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90644 | WBS.2.2.1.2.1.4.3 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - PS | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;AFSAR ALI MD;BRENDA STAGGS;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;md.afsarali@kochtc.com;BRENDA.STAGGS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | RTR - PS | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90645 | WBS.2.2.1.2.1.4.4 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - GL | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90647 | WBS.2.2.1.2.1.4.5 | N | N | Planned | Validate S/4HANA Configuration Transports - RTR - PC | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;RTR TEAM;SANDRA RICHARDS;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97778 | WBS.2.2.1.2.1.4.20 | N | N | Planned | Provide GP Splitting Structure Profile for Validation (to R. Bertolino) | 0.25 | 2021-01-31 18:30 | 2021-01-31 18:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;SANDRA RICHARDS;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;SAI TEAM;RTR TEAM | ksingareddy@deloitte.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR | 90647 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 18:45 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97779 | WBS.2.2.1.2.1.4.21 | N | N | Planned | Validate/update GP Splitting Structure Profile | 0.25 | 2021-01-31 18:45 | 2021-01-31 19:00 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | KRISHNA RAVI;KRISHNA SINGAREDDY;JACKIE ADAMS;RANJAI JOHN;BOATENG LAWRENCE;SAI TEAM;RTR TEAM | KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;Jacqueline.Adams@GAPAC.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR | 97778 |  |  | * |  | 2021-01-31 18:45 | 2021-01-31 19:00 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97636 | WBS.2.2.1.2.1.4.18 | N | N | Planned | Prepare file to load, mark and release Parent roll Standard to DC’s that receive paper from D4 plants | 1 | 2021-01-31 18:30 | 2021-01-31 19:30 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF;RANJAI JOHN;BOATENG LAWRENCE | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90647 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:30 | RTR | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97637 | WBS.2.2.1.2.1.4.19 | N | N | Planned | Load, mark and release Parent roll Standard to DC’s that receive paper from D4 plants | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | NOEL CLARK;SANDRA RICHARDS;SAI TEAM;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 97636 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:30 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97462 | WBS.2.2.1.2.1.4.16 | N | N | Planned | Maintain BRF+ setting for DT_RTR_E0336_DEP_PLANTS – Maintain New Deployed plants number for E0336 | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | KRISHNA SINGAREDDY | ksingareddy@deloitte.com | SANDRA RICHARDS;RTR TEAM;SAI TEAM;Pratik R Soni;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PRATIK.SONI@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90647 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97463 | WBS.2.2.1.2.1.4.17 | N | N | Planned | Maintain BRF+ settings for ZDT_MFLE_MKLE_XREF – Maintain MFLE to MKLE mapping for E0456 and E0457 | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | KRISHNA SINGAREDDY | ksingareddy@deloitte.com | SANDRA RICHARDS;RTR TEAM;SAI TEAM;Pratik R Soni;KRISHNA RAVI;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PRATIK.SONI@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90647 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92539 | WBS.2.2.1.2.1.4.6 | N | N | Planned | Verify BRF+ Entries - RTR - GL | 0.5 | 2021-01-31 18:45 | 2021-01-31 19:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90646 |  |  | * |  | 2021-01-31 18:45 | 2021-01-31 19:15 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94564 | WBS.2.2.1.2.1.4.7 | N | N | Planned | Confirm OBYC transport changes | 0.5 | 2021-01-31 18:15 | 2021-01-31 18:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90645 |  |  | * |  | 2021-01-31 18:15 | 2021-01-31 18:45 | RTR - GL | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92541 | WBS.2.2.1.2.1.4.8 | N | N | Planned | Maintain/Transport Sets for Validation/Substitution rules | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;RTR TEAM;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92539 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92478 | WBS.2.2.1.2.1.4.10 | N | N | Planned | Open OB52 for all MNFG Co Cds to accommodate Release of Cost Estimate for MFLE plant | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;RTR TEAM;NOEL CLARK;ASHLEY SEWELL;PMO TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;ASHLEYLUCKIE.SEWELL@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96992 | WBS.2.2.1.2.1.4.15 | N | N | Planned | Validate orders have been re-costed during FCW | 1 | 2021-02-01 19:30 | 2021-02-01 20:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | JACOB DENNIS;KRISHNA SINGAREDDY;MANOJ ANNAJI;RTR TEAM;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | JACOB.DENNIS@GAPAC.COM;ksingareddy@deloitte.com;MANOJ.ANNAJI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90647,97005,95719,95720,95722 |  |  | * |  | 2021-02-01 19:30 | 2021-02-01 20:30 | RTR - PC | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95452 | WBS.2.2.1.2.1.5 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - EWM | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95453 | WBS.2.2.1.2.1.5.1 | N | N | Planned | EWM - Validate S/4HANA Config Transports | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | AVINASH TALREJA | AVTALREJA@DELOITTE.COM | DOUG STANISLAWSKI;DEEPIKA ARRABOLU;DEEPAK SABNANI;EWM TEAM;SANTOSH KUPPILI;SAI TEAM | DOUG.STANISLAWSKI@GAPAC.COM;DREDDYARRABOLU@DELOITTE.COM;DSABNANI@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VKUPPILI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95454 | WBS.2.2.1.2.1.6 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - S/4HANA - SCM | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95455 | WBS.2.2.1.2.1.6.1 | N | N | Planned | SCM - Validate S/4HANA Config Transports | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | CHANDRA BALASUBRAMANIAN | CBALASUBRAMANIAN@DELOITTE.COM | SCM TEAM;SAI TEAM;SATISH KUMAR B;ANUPAM SHRIVASTAVA | DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 90653,92742 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91521 | WBS.2.2.1.2.1.10 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - SAP GW - DEV | 0.25 | 2021-01-31 14:30 | 2021-01-31 14:45 | [8 empty] | * |  | 2021-01-31 14:30 | 2021-01-31 14:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4305 | WBS.2.2.1.2.1.10.1 | N | N | Planned | Validate OSS Notes Were Transported To SAP GW | 0.25 | 2021-01-31 14:30 | 2021-01-31 14:45 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RAKESH MAKKAPATI;SANDEEP THARWANI;ARUN GANGADHARAN;DIGITAL CORE UX TEAM;SAI TEAM;SUVENDU KUMAR;DEV TEAM | RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;DIGITALCOREUXTEAM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4292 |  |  | * |  | 2021-01-31 14:30 | 2021-01-31 14:45 | UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91511 | WBS.2.2.1.2.1.11 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports - Validate Transports - SAP GW - SEC | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4294 | WBS.2.2.1.2.1.11.1 | N | N | Planned | Validate Security Transports For SAP GW | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SOUMYA PANDA;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4292,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91080 | WBS.2.2.1.2.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups | 21.75 | 2021-01-31 02:30 | 2021-02-01 00:15 | [8 empty] | * |  | 2021-01-31 02:30 | 2021-02-01 01:45 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91094 | WBS.2.2.1.2.2.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups - S/4HANA | 2.5 | 2021-01-31 21:45 | 2021-02-01 00:15 | [8 empty] | * |  | 2021-01-31 21:45 | 2021-02-01 01:45 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91078 | WBS.2.2.1.2.2.1.1 | N | N | Planned | Backup S/4HANA System - Post Transports - FCW | 2.5 | 2021-01-31 21:45 | 2021-02-01 00:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90644,90645,90646,90647,4104,4105,4151,4152,4157,4144,4141,4147,10006,91494,94564,94565 |  |  | * |  | 2021-01-31 21:45 | 2021-02-01 01:45 | DEV - INFRA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91089 | WBS.2.2.1.2.2.4 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups - SAP GRC | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | [8 empty] | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4694 | WBS.2.2.1.2.2.4.1 | N | N | Planned | Backup GRC System - Post Transports - FCW | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4307,4308 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91091 | WBS.2.2.1.2.2.5 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups - SAP GW | 2 | 2021-01-31 20:45 | 2021-01-31 22:45 | [8 empty] | * |  | 2021-01-31 20:45 | 2021-01-31 22:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91075 | WBS.2.2.1.2.2.5.1 | N | N | Planned | Backup GW System - Post Transports - FCW | 2 | 2021-01-31 20:45 | 2021-01-31 22:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4300,4305 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 22:45 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91093 | WBS.2.2.1.2.2.6 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups - SAP MDG | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91077 | WBS.2.2.1.2.2.6.1 | N | N | Planned | Backup MDG System - Post Transports - FCW | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4105,4151,4147 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91092 | WBS.2.2.1.2.2.7 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Post Transports – System Back-Ups - SAP PO | 2 | 2021-01-31 16:15 | 2021-01-31 18:15 | [8 empty] | * |  | 2021-01-31 16:15 | 2021-01-31 18:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91076 | WBS.2.2.1.2.2.7.1 | N | N | Planned | Backup PO System - Post Transports - FCW | 2 | 2021-01-31 16:15 | 2021-01-31 18:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90704 |  |  | * |  | 2021-01-31 16:15 | 2021-01-31 18:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91525 | WBS.2.2.1.3 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity | 34.75 | 2021-01-31 01:15 | 2021-02-01 12:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 12:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91532 | WBS.2.2.1.3.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - General | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
83023 | WBS.2.2.1.3.1.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - General - INT & EDI Shut Down | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
83022 | WBS.2.2.1.3.1.1.1 | N | N | Planned | RTR_I0073 - Update Company Code Channels for Fixed Assets | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SUVENDU KUMAR;BRIAN DOBASH;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;PAYEL GHOSH;HEMACHANDAN AS;RADHIKA RASTOGI;ARUN GANGADHARAN;RAKESH MAKKAPATI;TED ZEIDLER | SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PAYGHOSH@DELOITTE.COM;HEMACAS@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
83021 | WBS.2.2.1.3.1.1.2 | N | N | Planned | RTR_I0074 - Update Company Code for Payroll Processing | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | GOLLAPROLU SREEKANTH | GOLLAPROLU.SREEKANTH@KOCHTC.COM | SUVENDU KUMAR;BRIAN DOBASH;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;RAMYA IYER;SRINIVAS KATA;TED ZEIDLER | SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RAMYIYER@DELOITTE.COM;SKATA@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91531 | WBS.2.2.1.3.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - Non-Digital Core Systems | 34.75 | 2021-01-31 01:15 | 2021-02-01 12:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 12:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80984 | WBS.2.2.1.3.2.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversion - Tech Activities - Non-Digital Core Systems - Raise Fences | 17.25 | 2021-01-31 01:15 | 2021-01-31 18:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 18:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90542 | WBS.2.2.1.3.2.1.1 | N | N | Planned | Request ECC to S4 End of Day Snapshot | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;DOUG STANISLAWSKI;CHRISTINE CROSBY | AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;CCROSBY@GAPAC.COM | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90064 | WBS.2.2.1.3.2.1.2 | N | N | Planned | Deploy webMethods ASN trigger filter changes for newly deployed EWM sites | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | RON MASON | RONMASON@GAPAC.COM | SANDEEP THARWANI;BRIAN DOBASH;TED ZEIDLER;DON ABBOTT;SUVENDU KUMAR;SAI TEAM;DEV TEAM;KELLY HINSON;WILL COLEMAN | STHARWANI@DELOITTE.COM;BJDOBASH@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94412 | WBS.2.2.1.3.2.1.3 | N | N | Planned | Execute FCW Extracts from MP2 for ITR_C0067.1 and ITR_C0062.1 | 3.5 | 2021-01-31 01:15 | 2021-01-31 04:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 04:45 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92575 | WBS.2.2.1.3.2.1.4 | N | N | Planned | Set ECC partner profile S4PCLNT100 interim outbound interfaces to collect mode. DESADV, SHPMNT, ZMBGMCR, ZPHYINVINT | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SWAMI RAJASEKAR | swaminath.rajasekar@kochgs.com | GUNEET ARORA;BRIAN DOBASH;SAI TEAM;LSA TEAM;TED ZEIDLER | GUNEARORA@DELOITTE.COM;BJDOBASH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;TED.ZEIDLER@GAPAC.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90543 | WBS.2.2.1.3.2.1.5 | N | N | Planned | LSA - Run ECC to S4 End of Day Snapshot | 0.5 | 2021-01-31 01:30 | 2021-01-31 02:00 | WILL COLEMAN | WCOLEMA@GAPAC.COM | LSA TEAM;SAI TEAM;CYNDI HOTTENSTINE | MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CYNDI.HOTTENSTINE@GAPAC.COM | LSA | 90542,94798 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:00 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81867 | WBS.2.2.1.3.2.1.7 | N | N | Planned | Legacy Task - Security run MASS GRC requests to change users to Display access only | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | ANTHONY GORDON | ADGORDON@GAPAC.COM | LATONYA JONES;SAI TEAM;SEC TEAM | LADJONES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95439 | WBS.2.2.1.3.2.1.8 | N | N | Planned | Kick D4 Users Off ECC | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | ANTHONY GORDON | ADGORDON@GAPAC.COM | LATONYA JONES;SAI TEAM;SEC TEAM | LADJONES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 81867 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | SECURITY | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97813 | WBS.2.2.1.3.2.1.13 | N | N | Planned | Execute RTR AP jobs in ECC after GR and before inventory extract | 0.5 | 2021-01-31 01:45 | 2021-01-31 02:15 | WILL COLEMAN | WCOLEMA@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;RANJAI JOHN;BOATENG LAWRENCE;CINDY HOTTENSTINE;SAI TEAM;RTR TEAM | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;*;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR-GL | 95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:15 | RTR | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81865 | WBS.2.2.1.3.2.1.9 | N | N | Planned | Legacy Task - Security Validates locked users and role changes | 3 | 2021-01-31 01:30 | 2021-01-31 04:30 | ANTHONY GORDON | ADGORDON@GAPAC.COM | LATONYA JONES;SAI TEAM;SEC TEAM | LADJONES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 81867 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 04:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92455 | WBS.2.2.1.3.2.1.10 | N | N | Planned | Validate ECC Transports | 1 | 2021-01-31 02:15 | 2021-01-31 03:15 | SWAMI RAJASEKAR | swaminath.rajasekar@kochgs.com | VINOTH NAGARAJAN;MAMIE TREZVANT;GAURAV DESAI;LSA TEAM;DEV TEAM;SAI TEAM | VINAGARAJAN@DELOITTE.COM;MATREZVA@GAPAC.COM;GAURAV.DESAI@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 68349 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 03:15 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
21137 | WBS.2.2.1.3.2.1.11 | N | N | Planned | Maintain variants for EOD snapshot interface batch job in S/4HANA | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5797,90653 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80990 | WBS.2.2.1.3.2.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversion - Tech Activities - Non-Digital Core Systems - Lower Fences | 16.5 | 2021-01-31 19:30 | 2021-02-01 12:00 | [8 empty] | * |  | 2021-01-31 19:30 | 2021-02-01 12:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94588 | WBS.2.2.1.3.2.2.1 | N | N | Planned | Run MB5T for each D4 site to get a list of inbound ASNs that need to be retriggered | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | Uday Athwal | uathwal@deloitte.com | AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM | EWM | 90845 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94587 | WBS.2.2.1.3.2.2.2 | N | N | Planned | Send list of inbound ASNs to D4 sites from Elixir sites to the Elixir team for retriggering | 0.5 | 2021-01-31 20:30 | 2021-01-31 21:00 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 94588 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94586 | WBS.2.2.1.3.2.2.3 | N | N | Planned | Retrigger Elixir site ASNs for D4 sites | 1 | 2021-01-31 21:00 | 2021-01-31 22:00 | MINT VICKERY | MINT.VICKERY@GAPAC.COM | SAI TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94587 |  |  | * |  | 2021-01-31 21:00 | 2021-01-31 22:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94585 | WBS.2.2.1.3.2.2.4 | N | N | Planned | Re-Trigger ASNs For D4 Receiving Sites From Legacy SAP System (Lava output) | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM | EWM | 94588 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82121 | WBS.2.2.1.3.2.2.5 | N | N | Planned | Re-Trigger ASNs For D4 Receiving Sites From JDA Systems | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS;DOUG STANISLAWSKI | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM | EWM | 94588 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:30 | EWM | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94584 | WBS.2.2.1.3.2.2.6 | N | N | Planned | Send list of all ASNs retriggered to sites for checking in trailer and moving to proper yard location | 1 | 2021-01-31 22:00 | 2021-01-31 23:00 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;SAI TEAM;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM | EWM | 94586,94585,82121 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 23:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94583 | WBS.2.2.1.3.2.2.7 | N | N | Planned | PTH - Check-in Inbound ASN trailers and move to proper yard location | 1 | 2021-01-31 23:00 | 2021-02-01 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 94584 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95402 | WBS.2.2.1.3.2.2.8 | N | N | Planned | HBG - Action - Generate Materials Used Export for the dark period | 1 | 2021-02-01 11:00 | 2021-02-01 12:00 | BOBBY WHITE | Bobby.White@gapac.com | SAI TEAM;MITCH DEATON;CHRIS ZUMWALT | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com | Business | 90616,94548,94728,93916 |  |  | * |  | 2021-02-01 11:00 | 2021-02-01 12:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96628 | WBS.2.2.1.3.2.2.12 | N | N | Planned | BG - Check-in Inbound ASN trailers and move to proper yard location | 1 | 2021-01-31 23:00 | 2021-02-01 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;SAI TEAM;DEAN PIPER | LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com | Business | 94584,96688 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94580 | WBS.2.2.1.3.2.2.10 | N | N | Planned | SCH - Check-in Inbound ASN trailers and move to proper yard location | 1 | 2021-01-31 23:00 | 2021-02-01 | JORDAN ALLEN | Jordan.Allen@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CARLA PERKINS;GIOVANY CARVAJAL | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Carla.Perkins@gapac.com;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 94584 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96711 | WBS.2.2.1.3.2.2.13 | N | N | Planned | RNC - Check-in Inbound ASN trailers and move to proper yard location | 1 | 2021-01-31 23:00 | 2021-02-01 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | DILLON RAGHOONATHSINGH;DANIEL ROSS;TOMMY NEFFENDORF;SAI TEAM;JEREMY RAY;DAVID ALENCASTRO | dillon.rsingh@nfiindustries.com;DANIEL.ROSS@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | Business | 94584 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96712 | WBS.2.2.1.3.2.2.14 | N | N | Planned | RVG - Check-in Inbound ASN trailers and move to proper yard location | 1 | 2021-01-31 23:00 | 2021-02-01 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94584 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94579 | WBS.2.2.1.3.2.2.11 | N | N | Planned | Extract all Trailers from all sites and compare to initial Extract from each location to validate that all trailers are accounted for | 2 | 2021-02-01 | 2021-02-01 02:00 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 94583,94580,96628,96711,96712 |  |  | * |  | 2021-02-01 | 2021-02-01 02:00 | EWM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80666 | WBS.2.2.1.3.2.3 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activities - Non-Digital Core - Asset Availability | 1.5 | 2021-01-31 01:15 | 2021-01-31 02:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 02:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80699 | WBS.2.2.1.3.2.3.1 | N | N | Planned | Update Facility ERP System settings | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | HOWARD ZAHORIK | HOWARD.ZAHORIK@GAPAC.COM | MAMIE TREZVANT;SAI TEAM;ETHAN ROBB;LSA TEAM | MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ETHAN.ROBB@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ASSET AVAILABILITY | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80700 | WBS.2.2.1.3.2.3.2 | N | N | Planned | Rename assets to align with SAP naming | 1.5 | 2021-01-31 01:15 | 2021-01-31 02:45 | HOWARD ZAHORIK | HOWARD.ZAHORIK@GAPAC.COM | MAMIE TREZVANT;SAI TEAM;ETHAN ROBB;LSA TEAM | MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ETHAN.ROBB@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:45 | ASSET AVAILABILITY | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80977 | WBS.2.2.1.3.2.4 | N | N |  | FCW ¦ Tech Activities - Pre-Conversion - Technical Activities - Non-Digital Core - SAP ECC | 16.5 | 2021-01-31 01:15 | 2021-01-31 17:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 17:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81840 | WBS.2.2.1.3.2.4.1 | N | N | Planned | Remove S4 live sites from: Condition Records: ZEDL, ZTS4, LAVA, ZMGR TVARV: Z_GOODS_MVMT_INTERIM_PLANT | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | KAREN HUNNICUTT;PUNEET KUMAR;CHRISTINE CROSBY;SAI TEAM;MAMIE TREZVANT;RYAN ORR;LSA TEAM | KRHUNNIC@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;CCROSBY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;RDORR@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
89641 | WBS.2.2.1.3.2.4.2 | N | N | Planned | Maintain entries in table ZTPTM_I0311_PLOR | 0.25 | 2021-01-31 17:30 | 2021-01-31 17:45 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | CHIRAG PARIKH;DON ABBOTT;SAI TEAM;LSA TEAM;MAMIE TREZVANT;RYAN ORR;RAGHAVA GARRE;BRAD WYMAN;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;RDORR@GAPAC.COM;RAGHAVA.GARRE@KOCHTC.COM;BRAD.WYMAN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36505,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 17:45 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
68349 | WBS.2.2.1.3.2.4.3 | N | N | Planned | Basis to apply All ECC Digital Core Transports via SNOW ticket (Development/Config/logical systems) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | PRASHANT NAMBIAR | PRASHANT.NAMBIAR@KOCHTC.COM | GRP_SAP BASIS TECHNICAL SERVICES;SAI TEAM;MAMIE TREZVANT;DEV TEAM | GRPSAPTECHNICALSERVICES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | INFRA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | CAPGEMINI BASIS | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92362 | WBS.2.2.1.3.2.4.4 | N | N | Planned | Functional Update Job Variants SD in ECC | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | LISA KOENIG | lisa.koenig@gapac.com | ONI BORCHERS;VIVEK TALATI;ARNEL BAUTISTA;KYNDAL CODY;LSA TEAM;OTC TEAM;SAI TEAM | OCBORCHE@GAPAC.COM;VIVEK.TALATI@KOCHTC.COM;AVBAUTIS@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92361 | WBS.2.2.1.3.2.4.5 | N | N | Planned | Functional Update Job Variants PTP in ECC | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | DAVID MILLER;JON LUKE DAVILA;DENISE ROBINSON;AMY EL-BASSIONI;SAI TEAM;ARUN SHARMA;PTP TEAM;SANDEEP A | DAVID.MILLER@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;DOROBINS@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ARUN.SHARMA@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | PTP | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82217 | WBS.2.2.1.3.2.4.6 | N | N | Planned | ECC Inventory Posting Block - Execute transaction MMRV to turn off 'Allow posting to previous per' check box for the deployed company codes. | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | RANJAI JOHN | RANJAI.JOHN@KOCHTC.COM | WENTAO TANG;AGNES DEBO;SAI TEAM;LSA TEAM | WTANG@GAPAC.COM;ADEBO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91526 | WBS.2.2.1.3.3 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - SAP Systems | 24.75 | 2021-01-31 01:15 | 2021-02-01 02:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 02:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92145 | WBS.2.2.1.3.3.1 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - SAP Systems - Raise Fences | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92146 | WBS.2.2.1.3.3.1.1 | N | N | Planned | All ABAP Systems - Lock Out All Users Not Needing Access during Transports | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | ANTHONY GORDON;GREG CAPPS;SEC TEAM;SAI TEAM;KIRAN GANNAVARAPU;PALLAVI YELLAYI;MOHAMMED ABDULLAHI;CARLOS ROBELO TEJADA | ADGORDON@GAPAC.COM;GREG.CAPPS@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;PYELLAYI@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM | SECURITY | 92676,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92150 | WBS.2.2.1.3.3.2 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activitiy - SAP Systems - Lower Fences | 9 | 2021-01-31 17:00 | 2021-02-01 02:00 | [8 empty] | * |  | 2021-01-31 17:00 | 2021-02-01 02:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92742 | WBS.2.2.1.3.3.2.1 | N | N | Planned | All ABAP Systems - Unlock Cutover users | 0.25 | 2021-01-31 17:00 | 2021-01-31 17:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | ANTHONY GORDON;GREG CAPPS;SEC TEAM;SAI TEAM;PMO TEAM | ADGORDON@GAPAC.COM;GREG.CAPPS@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 4219,4307,92197,96904,96892,96878,96885,96877,97475,97476 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:15 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4121 | WBS.2.2.1.3.3.2.2 | N | N | Planned | Update variants for batch jobs - PE | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | SAI TEAM;JENNIFER LI;ANUPAM SHRIVASTAVA;SCM TEAM;RAGHAVA GARRE;CHIRAG PARIKH;BRAD WYMAN;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JQLI@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;RAGHAVA.GARRE@KOCHTC.COM;CPARIKH@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | SCM | 92742,91838 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SCM | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93403 | WBS.2.2.1.3.3.2.3 | N | N | Planned | Validate Security Transports for SAP S4 | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 90653,92742,97509 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93402 | WBS.2.2.1.3.3.2.4 | N | N | Planned | Validate Security Transports for SAP MDG | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 91471,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93401 | WBS.2.2.1.3.3.2.5 | N | N | Planned | Validate Security Transports for SAP GRC | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 91471,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93405 | WBS.2.2.1.3.3.2.6 | N | N | Planned | Perform Business Role Upload in GRC | 6 | 2021-01-31 19:00 | 2021-02-01 01:00 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;SOUMYA PANDA | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;SOPANDA@DELOITTE.COM | SECURITY | 4326,4294,4319,93398,93403,93402,93401 |  |  | * |  | 2021-01-31 19:00 | 2021-02-01 01:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92152 | WBS.2.2.1.3.3.2.7 | N | N | Planned | Prod Task - Unlock users deployed in previous releases | 0.25 | 2021-01-31 18:45 | 2021-01-31 19:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | ANTHONY GORDON;GREG CAPPS;SEC TEAM;SAI TEAM;PMO TEAM | ADGORDON@GAPAC.COM;GREG.CAPPS@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 90643,90647,90646,90645,90644,94564,94565,95453,95455,90648 |  |  | * |  | 2021-01-31 18:45 | 2021-01-31 19:00 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92407 | WBS.2.2.1.3.3.2.8 | N | N | Planned | Send email when Digital Core Systems S4P, MDP, GWP,PO, and HAP become available after FCW outage | 0.5 | 2021-01-31 19:00 | 2021-01-31 19:30 | KYNDAL CODY | KYNDAL.CODY@GAPAC.COM | DANI SIMMONS;MAMIE TREZVANT;LSA TEAM;SAI TEAM;PMO TEAM | DWSIMMON@GAPAC.COM;MATREZVA@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 92152 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92153 | WBS.2.2.1.3.3.2.9 | N | N | Planned | Restart batch jobs for all affected Digital Core Envionments for previous deployments | 0.25 | 2021-01-31 18:45 | 2021-01-31 19:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 92148,90643,90647,90646,90645,90644,94564,94565,95453,95455,90648 |  |  | * |  | 2021-01-31 18:45 | 2021-01-31 19:00 | BATCH | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93404 | WBS.2.2.1.3.3.2.10 | N | N | Planned | Run Repository Role Synch in GRC | 1 | 2021-02-01 01:00 | 2021-02-01 02:00 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;SOUMYA PANDA | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;SOPANDA@DELOITTE.COM | SECURITY | 93405 |  |  | * |  | 2021-02-01 01:00 | 2021-02-01 02:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91527 | WBS.2.2.1.3.3.3 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - SAP Systems - S/4HANA | 4.75 | 2021-01-31 17:00 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 17:00 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10006 | WBS.2.2.1.3.3.3.1 | N | N | Planned | SCP-PI Validate HTTP Destination For S/4HANA Connections | 0.5 | 2021-01-31 19:30 | 2021-01-31 20:00 | ANKIT SONI | ANKISONI@DELOITTE.COM | TED ZEIDLER;HEMACHANDAN AS;BRIAN DOBASH;SANDEEP THARWANI;NAVJOT SHARMA;DANI SIMMONS;SAI TEAM;SUVENDU KUMAR;DEV TEAM | TED.ZEIDLER@GAPAC.COM;HEMACAS@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 10008,93067,91838,94798 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:00 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4144 | WBS.2.2.1.3.3.3.2 | N | N | Planned | Validation of SICF For RF (To be done when basis complete activation) S/4HANA | 0.5 | 2021-01-31 17:00 | 2021-01-31 17:30 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | SATHISH S;ASWATHI RAVINDRAN;SAI TEAM;SWAMI RAJASEKAR;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | SATS@DELOITTE.COM;ASWATHI.RAVINDRAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:30 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4146 | WBS.2.2.1.3.3.3.3 | N | N | Planned | Validation of SICF For BRF+ | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | SUVENDU KUMAR | SUVKUMAR@DELOITTE.COM | RAKESH MAKKAPATI;SAI TEAM;DANI SIMMONS;SRINIVAS KATA;ARUN GANGADHARAN;DEV TEAM | RMAKKAPATI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;SKATA@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
9415 | WBS.2.2.1.3.3.3.4 | N | N | Planned | Validate MARA & BUT000 to see if they are active. | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | SRINIVAS KATA | SKATA@DELOITTE.COM | PRASHANTH TUMMALA;ARUN GANGADHARAN;VENKATESH GANESHAN;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | PTUMMALA@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81567 | WBS.2.2.1.3.3.3.5 | N | N | Planned | Provide Webdispatcher URL For RF Devices | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;SUVENDU KUMAR;LOKESH KAMANA;MARK WACHTMAN;OLEG MERKOULOV;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;MRWACHTM@GAPAC.COM;OLEG.MERKOULOV@GAPAC.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95297 | WBS.2.2.1.3.3.3.6 | N | N | Planned | Run program /UI2/GET_APP_DESCR_REMOTE_DEV Replicate Backend Technical Catalog from Remote System | 0.75 | 2021-01-31 19:00 | 2021-01-31 19:45 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RONNIE VAUGHN;SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;DEV TEAM | RLVAUGHN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4105,36505 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:45 | UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4150 | WBS.2.2.1.3.3.3.7 | N | N | Planned | Validate physical file Folder creation | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | GUNEET ARORA;SRINIVAS KATA;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SUVENDU KUMAR;DEV TEAM | GUNEARORA@DELOITTE.COM;SKATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4151 | WBS.2.2.1.3.3.3.8 | N | N | Planned | Validate WE21 Port set up S/4HANA MDG | 0.5 | 2021-01-31 18:00 | 2021-01-31 18:30 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | VENKATESH GANESHAN;ARUN GANGADHARAN;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:30 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4152 | WBS.2.2.1.3.3.3.9 | N | N | Planned | Validate Partner Profiles S/4HANA (GL/PC/CC/Bank/Class & Chars/Employee) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | ARUN GANGADHARAN;VENKATESH GANESHAN;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | ARGANGADHARAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4141 | WBS.2.2.1.3.3.3.10 | N | N | Planned | Validate Adobe form test print S/4HANA for all sites | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | RAKESH MAKKAPATI;VENKATESH GANESHAN;SAI TEAM;SWAMI RAJASEKAR;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | RMAKKAPATI@DELOITTE.COM;VGANESHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4149 | WBS.2.2.1.3.3.3.11 | N | N | Planned | Validate Logical File Path | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | GUNEET ARORA;SRINIVAS KATA;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | GUNEARORA@DELOITTE.COM;SKATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90653,36505,91838 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96926 | WBS.2.2.1.3.3.3.14 | N | N | Planned | Enable shortcut field for ZH presentation device using transaction /SCWM/PRDVC | 0.25 | 2021-01-31 20:30 | 2021-01-31 20:45 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | GUNEET ARORA;SRINIVAS KATA;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | GUNEARORA@DELOITTE.COM;SKATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4144,89749,4105 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 20:45 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4157 | WBS.2.2.1.3.3.3.12 | N | N | Planned | Validate RF Launch on hand held S/4HANA check | 1 | 2021-01-31 20:45 | 2021-01-31 21:45 | ARVIND KUMAR KANAPARTHI | KARAVINDKUMAR@DELOITTE.COM | SATHISH S;ASWATHI RAVINDRAN;SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;STEVE TAYLOR;ARUN GANGADHARAN;RAKESH MAKKAPATI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | SATS@DELOITTE.COM;ASWATHI.RAVINDRAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SSTAYLOR@GAPAC.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4144,89749,4105,96926 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 21:45 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4147 | WBS.2.2.1.3.3.3.13 | N | N | Planned | Validation of SICF Services for Gateway, S/4HANA, MDG, CRQ | 0.25 | 2021-01-31 19:00 | 2021-01-31 19:15 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RAKESH MAKKAPATI;SANDEEP THARWANI;ARUN GANGADHARAN;DIGITAL CORE UX TEAM;SAI TEAM;SUVENDU KUMAR;DEV TEAM | RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;DIGITALCOREUXTEAM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 82244,4105 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:15 | UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91528 | WBS.2.2.1.3.3.4 | N | N |  | FCW ¦ Tech Activities - Pre-Conversions - Technical Activity - SAP Systems - SAP GW | 1.5 | 2021-01-31 19:45 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92477 | WBS.2.2.1.3.3.4.1 | N | N | Planned | Open SAP GW Client | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;SUVENDU KUMAR;LOKESH KAMANA;DEV TEAM;ARUN GANGADHARAN;RONNIE VAUGHN | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;ARGANGADHARAN@DELOITTE.COM;RLVAUGHN@GAPAC.COM | DEV | 4105,95297 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4300 | WBS.2.2.1.3.3.4.2 | N | N | Planned | Validate Tile Groups - Catalog/Groups For Fiori Launchpad in SAP GW | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | LOKESH KAMANA | LKAMANA@DELOITTE.COM | RAKESH MAKKAPATI;SANDEEP THARWANI;ARUN GANGADHARAN;DIGITAL CORE UX TEAM;SAI TEAM;SUVENDU KUMAR;DEV TEAM | RMAKKAPATI@DELOITTE.COM;STHARWANI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;DIGITALCOREUXTEAM@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 4105,95297 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92476 | WBS.2.2.1.3.3.4.3 | N | N | Planned | Close SAP GW Client | 0.5 | 2021-01-31 20:45 | 2021-01-31 21:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;SUVENDU KUMAR;LOKESH KAMANA;DEV TEAM;ARUN GANGADHARAN;RONNIE VAUGHN | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;ARGANGADHARAN@DELOITTE.COM;RLVAUGHN@GAPAC.COM | DEV | 4300 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 21:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96873 | WBS.2.2.1.4 | N | N |  | FCW ¦ Tech Activities - Technical System Upgrade Activity | 19.75 | 2021-01-31 01:30 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-30 22:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96875 | WBS.2.2.1.4.1 | N | N |  | FCW ¦ Tech Activities - Technical System Upgrade Tasks | 19.75 | 2021-01-31 01:30 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-30 22:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96874 | WBS.2.2.1.4.1.1 | N | N |  | FCW ¦ Tech Activities - Technical System Upgrade Tasks | 19.75 | 2021-01-31 01:30 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-30 22:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96911 | WBS.2.2.1.4.1.1.36 | N | N | Planned | Downtime - Downtime phase - Monitor for import of SPAU TR (S4) | 5.5 | 2021-01-31 02:00 | 2021-01-31 07:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 90542,90543,92146,92148,97395,97394,96913,97420,97761 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 07:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97756 | WBS.2.2.1.4.1.1.140 | N | N | Planned | Basis Parameter rdisp/server_startup/user = STARTUP_USER, rdisp/abap_user_for_sidadm = STARTUP_USER | 0.75 | 2021-01-31 07:30 | 2021-01-31 08:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:15 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96910 | WBS.2.2.1.4.1.1.35 | N | N | Planned | Downtime - SCM optimizer 14.0 patching - S4 | 1 | 2021-01-31 07:30 | 2021-01-31 08:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96909 | WBS.2.2.1.4.1.1.34 | N | N | Planned | Downtime - Validate SPAU TR and SPAU, SPAU_ENH Transactions (S4) | 1 | 2021-01-31 07:30 | 2021-01-31 08:30 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96908 | WBS.2.2.1.4.1.1.33 | N | N | Planned | Downtime - Deployment of iflows for CIG in CPI | 1 | 2021-01-31 07:30 | 2021-01-31 08:30 | ANKIT SONI | ANKISONI@DELOITTE.COM | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:30 | DEV-INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96907 | WBS.2.2.1.4.1.1.32 | N | N | Planned | Downtime - Connection validation between S4 and CPI for CIG | 0.5 | 2021-01-31 07:30 | 2021-01-31 08:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96906 | WBS.2.2.1.4.1.1.31 | N | N | Planned | Downtime - Import Ariba manual activity TRs | 0.5 | 2021-01-31 08:30 | 2021-01-31 09:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 96907,96909 |  |  | * |  | 2021-01-31 08:30 | 2021-01-31 09:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96905 | WBS.2.2.1.4.1.1.30 | N | N | Planned | Downtime - Validate ARIBA manual activity TR's and RFCs | 0.25 | 2021-01-31 09:00 | 2021-01-31 09:15 | VINOTH NAGARAJAN | VINAGARAJAN@DELOITTE.COM | SAI TEAM;DEV TEAM;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM | DEV | 96906 |  |  | * |  | 2021-01-31 09:00 | 2021-01-31 09:15 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97475 | WBS.2.2.1.4.1.1.127 | N | N | Planned | Downtime - Import D4 FCW TRs for S4 | 2 | 2021-01-31 15:00 | 2021-01-31 17:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 97425 |  |  | * |  | 2021-01-31 15:00 | 2021-01-31 17:00 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97833 | WBS.2.2.1.4.1.1.144 | N | N | Planned | Downtime - Instance Type change for R4 to R5 for Application Servers | 0.75 | 2021-01-31 15:00 | 2021-01-31 15:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 97425 |  |  | * |  | 2021-01-31 15:00 | 2021-01-31 17:00 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97757 | WBS.2.2.1.4.1.1.141 | N | N | Planned | Apply Open text BAS version | 0.5 | 2021-01-31 17:00 | 2021-01-31 17:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96904,97475,96908,96902,96900 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97509 | WBS.2.2.1.4.1.1.129 | N | N | Planned | Import Remaining Security Transport after downtime window FCW transports | 1.5 | 2021-01-31 17:00 | 2021-01-31 18:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 18:30 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97804 | WBS.2.2.1.4.1.1.143 | N | N | Planned | Validate Autocash setup | 1.5 | 2021-01-31 18:30 | 2021-01-31 20:00 | NAVEEN CHEPURI | NAVCHEPURI@DELOITTE.COM | DEV TEAM;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97509 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 20:00 | DEV | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96904 | WBS.2.2.1.4.1.1.29 | N | N | Planned | Downtime - Import Post upgrade TRs (S4) | 0.5 | 2021-01-31 08:30 | 2021-01-31 09:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 96909,36505,92148,92575,94798,97756 |  |  | * |  | 2021-01-31 08:30 | 2021-01-31 09:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96903 | WBS.2.2.1.4.1.1.28 | N | N | Planned | Downtime - Validate Post upgrade TRs, SAMT, ATC checks S4 and D4 FCW TR's, Fix repaired objects | 0.5 | 2021-01-31 17:00 | 2021-01-31 17:30 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | SAI TEAM;DEV TEAM;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM | DEV | 96904,97475,96908,96902,96900 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97728 | WBS.2.2.1.4.1.1.133 | N | N | Planned | Validate Repository Connectivity for S4/MDG/CRM/BW | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | JOAN SMITH | JBSMITH@GAPAC.com | DEV TEAM;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | DEV | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97729 | WBS.2.2.1.4.1.1.134 | N | N | Planned | Move API development S4 | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | ANKIT SONI | ANKISONI@DELOITTE.COM | TED ZEIDLER;HEMACHANDAN;RAMYA IYER;SEC TEAM;SAI TEAM;DEV TEAM | TED.ZEIDLER@GAPAC.COM;HEMACAS@DELOITTE.COM;RAMYIYER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | DEV | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97730 | WBS.2.2.1.4.1.1.135 | N | N | Planned | Confirm correct security in place S4 | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | ANKIT SONI | ANKISONI@DELOITTE.COM | TED ZEIDLER;HEMACHANDAN;RAMYA IYER;SEC TEAM;SAI TEAM;DEV TEAM | TED.ZEIDLER@GAPAC.COM;HEMACAS@DELOITTE.COM;RAMYIYER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96903,97729 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | DEV | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97731 | WBS.2.2.1.4.1.1.136 | N | N | Planned | Repoint internal API S4 | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | LUIS VELEZ | luis.velez@gapac.com | MARSEL KHAMIDULLIN;SAI TEAM | Marsel.Khamidullin@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA - Cloud Ops | 96903,97729 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | LSA - Cloud Ops | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97732 | WBS.2.2.1.4.1.1.137 | N | N | Planned | Validate SSO_RESOLVER OTMM-QA | 0.25 | 2021-01-31 19:00 | 2021-01-31 19:15 | BULENT DOGAN | bdogan@cyangate.com | MERT CAN SATIOGLU;SAI TEAM | msatioglu@cyangate.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Cyngate | 97729,97730,97731 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:15 | Cyngate | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97733 | WBS.2.2.1.4.1.1.138 | N | N | Planned | Validate DamLink Connectivity S4 | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | PRERNA BODKHE;SAI TEAM | PRERNA.BODKHE@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 97732 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | DATA | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96902 | WBS.2.2.1.4.1.1.27 | N | N | Planned | Downtime - Execute Programs to revert back source systems to avoid Deletion of Ariba/MRS/IDT,/IDT/DEL_ALL_DYN_PROGS to regenerate onssource programs | 0.25 | 2021-01-31 08:30 | 2021-01-31 08:45 | VINOTH NAGARAJAN | VINAGARAJAN@DELOITTE.COM | ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;RAKESH MAKKAPATI;US GP BASIS | ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RMAKKAPATI@DELOITTE.COM;USGPBASIS@DELOITTE.COM | DEV | 96909 |  |  | * |  | 2021-01-31 08:30 | 2021-01-31 08:45 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96901 | WBS.2.2.1.4.1.1.26 | N | N | Planned | Downtime - Vistex Conversion Program | 0.5 | 2021-01-31 17:00 | 2021-01-31 17:30 | RAMARAJU CHAMPATI | ramaraju.champati@gapac.com | SRINIVASA KANUGANTI;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;RAKESH MAKKAPATI;US GP BASIS;VINOTH NAGARAJAN | srinivasa.kanuganti@gapac.com;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RMAKKAPATI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM | DEV | 96909,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96900 | WBS.2.2.1.4.1.1.25 | N | N | Planned | Downtime - CIDEON + post CIDEON steps like executing programs and all | 1 | 2021-01-31 06:30 | 2021-01-31 07:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM;SHARATH RENIKUNTA;LOKESH KAMANA;PRASHANTH TUMMALA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SRENIKUNTA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM | DEV | 96894 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 07:30 | CTM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96899 | WBS.2.2.1.4.1.1.24 | N | N | Planned | Downtime - Validate ADS RFCs - S4 | 0.5 | 2021-01-31 07:30 | 2021-01-31 08:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;FAROOQ SYED | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SYFAROOQ@DELOITTE.COM | DEV | 96911 |  |  | * |  | 2021-01-31 07:30 | 2021-01-31 08:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96898 | WBS.2.2.1.4.1.1.23 | N | N | Planned | Uptime - Activate CIG SOA services & validate CIG setup | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;ANKIT SONI;PAYEL GHOSH;RADHIKA RASTOGI;SUVENDU KUMAR;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANKISONI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | DEV-INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96897 | WBS.2.2.1.4.1.1.22 | N | N | Planned | Uptime - Validate SSO post upgrade | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;DEV TEAM;RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM | DEV | 96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | DEV-UX | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96896 | WBS.2.2.1.4.1.1.21 | N | N | Planned | ARBCIG - Uptime - S/4 manual adaptations | 0.5 | 2021-01-31 09:15 | 2021-01-31 09:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 96905 |  |  | * |  | 2021-01-31 09:15 | 2021-01-31 09:45 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96894 | WBS.2.2.1.4.1.1.19 | N | N | Planned | Downtime - Downtime phase - Monitor for import of SPAU TR (MDG) | 5 | 2021-01-31 01:30 | 2021-01-31 06:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM;SHARATH RENIKUNTA;LOKESH KAMANA;PRASHANTH TUMMALA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SRENIKUNTA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM | DEV | 96895,92751,92146,92148,36505 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 06:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96893 | WBS.2.2.1.4.1.1.18 | N | N | Planned | Downtime - Validate SPAU TR and SPAU, SPAU_ENH Transactions (MDG) | 2 | 2021-01-31 06:30 | 2021-01-31 08:30 | SUVENDU KUMAR | SUVKUMAR@DELOITTE.COM | US GP BASIS;SAI TEAM;DEV TEAM;RAKESH MAKKAPATI;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;RMAKKAPATI@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM | DEV | 96894 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 08:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96892 | WBS.2.2.1.4.1.1.17 | N | N | Planned | Downtime - Import Post upgrade TRs (MDG) and D4 FCW TRs | 1 | 2021-01-31 08:30 | 2021-01-31 09:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;SHARATH RENIKUNTA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SRENIKUNTA@DELOITTE.COM | DEV | 96893,36505 |  |  | * |  | 2021-01-31 08:30 | 2021-01-31 09:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97755 | WBS.2.2.1.4.1.1.139 | N | N | Planned | In MDG - execute transaction MDGM_METADATA_INV for clearing buffer and execute report ESH_CDSABAP_ACTIVATION for CDS entity: ESH_S_DOCINFORECORD for activation of search connector program | 0.25 | 2021-01-31 09:30 | 2021-01-31 09:45 | GUNEET ARORA | GUNEARORA@DELOITTE.COM | SAI TEAM;SWAMI RAJASEKAR;NAVJOT SHARMA;DANI SIMMONS;VENKATESH GANESHAN;ARUN GANGADHARAN;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;swaminath.rajasekar@kochgs.com ;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;VGANESHAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96892 |  |  | * |  | 2021-01-31 09:30 | 2021-01-31 09:45 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96891 | WBS.2.2.1.4.1.1.16 | N | N | Planned | Downtime - Validate Post upgrade TRs, SAMT, ATC checks MDG | 0.5 | 2021-01-31 09:30 | 2021-01-31 10:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | SAI TEAM;DEV TEAM;CHIRAG GUPTA;VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;CHIRGUPTA@DELOITTE.COM;VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM | DEV | 96892 |  |  | * |  | 2021-01-31 09:30 | 2021-01-31 10:00 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97630 | WBS.2.2.1.4.1.1.130 | N | N | Planned | Provide CTM/Leverx Team with system information (application server, instance number and system ID for MD2) | 1 | 2021-01-31 10:00 | 2021-01-31 11:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;CTM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKWALL@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DEV | 96891,96900 |  |  | * |  | 2021-01-31 10:00 | 2021-01-31 11:00 | CTM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97631 | WBS.2.2.1.4.1.1.131 | N | N | Planned | Update ECTR connections | 2 | 2021-01-31 11:00 | 2021-01-31 13:00 | ANDREW STYER | Andrew.Styer@leverx.com | ARLENE WALL;SAI TEAM;DEV TEAM;TODD SCHUELKE | AKWALL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;Todd.Schuelke@GAPAC.com | CTM | 97630 |  |  | * |  | 2021-01-31 11:00 | 2021-01-31 13:00 | CTM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97632 | WBS.2.2.1.4.1.1.132 | N | N | Planned | Validate ECTR Connections | 1 | 2021-01-31 13:00 | 2021-01-31 14:00 | TODD SCHUELKE | Todd.Schuelke@GAPAC.com | ANDREW STYER;Sarvanakumar Gnanamohan;SAI TEAM | Andrew.Styer@leverx.com;Sarvanakumar.Gnanamohan@kochtc.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | CTM | 97631 |  |  | * |  | 2021-01-31 13:00 | 2021-01-31 14:00 | CTM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96890 | WBS.2.2.1.4.1.1.15 | N | N | Planned | Downtime - Validate ADS RFCs - MDG | 0.5 | 2021-01-31 06:30 | 2021-01-31 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;SHARATH RENIKUNTA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;SRENIKUNTA@DELOITTE.COM | DEV | 96894 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 07:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97409 | WBS.2.2.1.4.1.1.115 | N | N | Planned | Confirm BP Replication is working | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | COURTNEY ANDERSON | COURTNEY.ANDERSON@GAPAC.COM | PRERNA BODKHE;SHANKAR RAMNARAYANAN;AMY EL-BASSIONI;SAI TEAM | PRERNA.BODKHE@KOCHTC.COM;SRAMNARAYANAN@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 96899,96890,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96888 | WBS.2.2.1.4.1.1.13 | N | N | Planned | Downtime - Downtime phase - Monitor for import of SPAU TR (GW) | 5 | 2021-01-31 01:30 | 2021-01-31 06:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM;PRASANNA KAPANIGOWDA;LOKESH KAMANA;PRASHANTH TUMMALA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM | DEV | 96889,92146,92148,36505 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 06:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96887 | WBS.2.2.1.4.1.1.12 | N | N | Planned | Downtime - Validate SPAU TR and SPAU, SPAU_ENH Transactions (GW) | 2 | 2021-01-31 06:30 | 2021-01-31 08:30 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;GUNEET ARORA;SAI TEAM;DEV TEAM;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM | DEV | 96888 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 08:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96886 | WBS.2.2.1.4.1.1.11 | N | N | Planned | Downtime - Gateway MRSS add on upgrade and UI5 library - GW | 0.5 | 2021-01-31 08:30 | 2021-01-31 09:00 | DEV TEAM | NASHARMA@DELOITTE.COM | PRASANNA KAPANIGOWDA;LOKESH KAMANA;PRASHANTH TUMMALA;US GP BASIS;SAI TEAM | STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96887 |  |  | * |  | 2021-01-31 08:30 | 2021-01-31 09:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96885 | WBS.2.2.1.4.1.1.10 | N | N | Planned | Downtime - Import Post upgrade TRs (GW) | 1 | 2021-01-31 09:00 | 2021-01-31 10:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM;PRASANNA KAPANIGOWDA;LOKESH KAMANA;PRASHANTH TUMMALA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM | DEV | 96886 |  |  | * |  | 2021-01-31 09:00 | 2021-01-31 10:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97476 | WBS.2.2.1.4.1.1.128 | N | N | Planned | Downtime - Import D4 FCW TRs For GW | 1 | 2021-01-31 12:00 | 2021-01-31 13:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;DEV TEAM;PRASANNA KAPANIGOWDA;LOKESH KAMANA;PRASHANTH TUMMALA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM | DEV | 97428 |  |  | * |  | 2021-01-31 12:00 | 2021-01-31 13:00 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96884 | WBS.2.2.1.4.1.1.9 | N | N | Planned | Downtime - Validate Post upgrade TRs, SAMT, ATC checks GW | 1 | 2021-01-31 13:00 | 2021-01-31 14:00 | RAKESH MAKKAPATI | RMAKKAPATI@DELOITTE.COM | VINOTH NAGARAJAN;ARUN GANGADHARAN;SAI TEAM;DEV TEAM;LOKESH KAMANA;GUNEET ARORA;US GP BASIS | VINAGARAJAN@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LKAMANA@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM | DEV | 96885,97476 |  |  | * |  | 2021-01-31 13:00 | 2021-01-31 14:00 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96883 | WBS.2.2.1.4.1.1.8 | N | N | Planned | Downtime - Validate ADS RFCs - GW | 0.5 | 2021-01-31 06:30 | 2021-01-31 07:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;PRASANNA KAPANIGOWDA | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PKAPANIGOWDA@DELOITTE.COM | DEV | 96888 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 07:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96881 | WBS.2.2.1.4.1.1.6 | N | N | Planned | Downtime - Disable PI - AN integration Iflows | 1 | 2021-01-31 02:00 | 2021-01-31 03:00 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;ANKIT SONI;PAYEL GHOSH;RADHIKA RASTOGI;SUVENDU KUMAR;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANKISONI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96882,92148,97394,97395,36505,92575,83019,92146,94798,90542,90543,97420 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 03:00 | DEV-INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96880 | WBS.2.2.1.4.1.1.5 | N | N | Planned | Downtime - Downtime phase - PO | 5 | 2021-01-31 03:00 | 2021-01-31 08:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;Sujit Sandbhor | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;ssandbhor@deloitte.com | DEV | 96881,92148,36505,97394,97395 |  |  | * |  | 2021-01-31 03:00 | 2021-01-31 08:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96879 | WBS.2.2.1.4.1.1.4 | N | N | Planned | Downtime - PO Post upgrade Adapter addons installation | 2 | 2021-01-31 08:00 | 2021-01-31 10:00 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96880 |  |  | * |  | 2021-01-31 08:00 | 2021-01-31 10:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96878 | WBS.2.2.1.4.1.1.3 | N | N | Planned | Downtime - Import Post upgrade TRs (PO) and D4 FCW TRs | 1 | 2021-01-31 11:15 | 2021-01-31 12:15 | Sujit Sandbhor | ssandbhor@deloitte.com | LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM;US GP BASIS;SAI TEAM | LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96879,97387,97384,4245,4424,7867,36505 |  |  | * |  | 2021-01-31 11:15 | 2021-01-31 12:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96877 | WBS.2.2.1.4.1.1.2 | N | N | Planned | Downtime - Validate PO channels after upgrade | 2 | 2021-01-31 12:15 | 2021-01-31 14:15 | RAMYA IYER | RAMYIYER@DELOITTE.COM | SAI TEAM;ANKIT SONI;PAYEL GHOSH;RADHIKA RASTOGI;SUVENDU KUMAR;US GP BASIS;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANKISONI@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;USGPBASIS@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 96878 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 14:15 | DEV-INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97422 | WBS.2.2.1.4.1.1.118 | N | N | Planned | S4 - Start 1910 Vistex Patch & Import SPDD 1910 TR | 3.5 | 2021-01-31 10:15 | 2021-01-31 13:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96904,97393,96896 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 13:45 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97423 | WBS.2.2.1.4.1.1.119 | N | N | Planned | S4 - Import & Validate of SPAU TR (S4) - VISTEX PATCH 1910 | 0.5 | 2021-01-31 13:45 | 2021-01-31 14:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97422 |  |  | * |  | 2021-01-31 13:45 | 2021-01-31 14:15 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97424 | WBS.2.2.1.4.1.1.120 | N | N | Planned | VISTEX - /IRM/GPR_1909SP1_RQTAB_STAGE - Need to run this report for backup of condition tables after 1910 SPAU TR import. | 0.25 | 2021-01-31 14:15 | 2021-01-31 14:30 | SRINIVASA.KANUGANTI@VISTEX.COM | SRINIVASA.KANUGANTI@VISTEX.COM | RAMARAJU.CHAMPATI@VISTEX.COM;SANTOSH.VEMPATY@VISTEX.COM;SRINIVASA.KANUGANTI@VISTEX.COM;RAMARAJU.CHAMPATI@VISTEX.COM;SANTOSH.VEMPATY@VISTEX.COM;DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;SAI TEAM | RAMARAJU.CHAMPATI@VISTEX.COM;SANTOSH.VEMPATY@VISTEX.COM;SRINIVASA.KANUGANTI@VISTEX.COM;RAMARAJU.CHAMPATI@VISTEX.COM;SANTOSH.VEMPATY@VISTEX.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97423 |  |  | * |  | 2021-01-31 14:15 | 2021-01-31 14:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97425 | WBS.2.2.1.4.1.1.121 | N | N | Planned | S4 - Import Post upgrade - VISTEX PATCH 1910 | 0.5 | 2021-01-31 14:30 | 2021-01-31 15:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97424 |  |  | * |  | 2021-01-31 14:30 | 2021-01-31 15:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97426 | WBS.2.2.1.4.1.1.122 | N | N | Planned | GW- Start 1910 Vistex Patch & Import SPDD 1910 TR | 1 | 2021-01-31 10:00 | 2021-01-31 11:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 96885 |  |  | * |  | 2021-01-31 10:00 | 2021-01-31 11:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97427 | WBS.2.2.1.4.1.1.123 | N | N | Planned | GW - Import & Validate of SPAU TR (GW) - VISTEX PATCH 1910 | 0.5 | 2021-01-31 11:00 | 2021-01-31 11:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97426 |  |  | * |  | 2021-01-31 11:00 | 2021-01-31 11:30 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97428 | WBS.2.2.1.4.1.1.124 | N | N | Planned | GW - Import Post upgrade - VISTEX PATCH 1910 | 0.5 | 2021-01-31 11:30 | 2021-01-31 12:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | DEV TEAM;VINOTH NAGARAJAN;VENKATESH GANESHAN;RAKESH MAKKAPATI;ARUN GANGADHARAN;GUNEET ARORA;US GP BASIS;SAI TEAM | NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;VINAGARAJAN@DELOITTE.COM;VGANESHAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;GUNEARORA@DELOITTE.COM;USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DEV | 97427 |  |  | * |  | 2021-01-31 11:30 | 2021-01-31 12:00 | DEV - INFRA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91512 | WBS.2.2.2 | N | N |  | FCW ¦ Pre-Conversions Configuration | 4 | 2021-01-31 17:15 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91513 | WBS.2.2.2.1 | N | N |  | FCW ¦ Pre-Conversions Configuration - SAP Systems | 4 | 2021-01-31 17:15 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91514 | WBS.2.2.2.1.1 | N | N |  | FCW ¦ Pre-Conversions Configuration - SAP Systems - S/4HANA | 4 | 2021-01-31 17:15 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91515 | WBS.2.2.2.1.1.1 | N | N |  | FCW ¦ Pre-Conversions Configuration - SAP Systems - S/4HANA - EWM | 4 | 2021-01-31 17:15 | 2021-01-31 21:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 21:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4585 | WBS.2.2.2.1.1.1.1 | N | N | Planned | Maintain/Validate BRF+ parameter values for interfaces - EWM | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA;NIMISHA KAPADIA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM;nikapadia@deloitte.com | EWM | 96904,97475,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4586 | WBS.2.2.2.1.1.1.2 | N | N | Planned | Maintain/Validate BRF+ Parameter Values For Enhancements - EWM | 4 | 2021-01-31 17:15 | 2021-01-31 21:15 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA;NIMISHA KAPADIA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM;nikapadia@deloitte.com | EWM | 96904,97475,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 21:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97375 | WBS.2.2.18 | N | N |  | FCW ¦ Ariba CIG Tasks | 28.25 | 2021-01-31 01:15 | 2021-02-01 05:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 05:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97374 | WBS.2.2.18.17 | N | N |  | FCW ¦ Ariba CIG Tasks | 28.25 | 2021-01-31 01:15 | 2021-02-01 05:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 05:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97373 | WBS.2.2.18.17.1 | N | N |  | FCW ¦ Ariba CIG Tasks | 28.25 | 2021-01-31 01:15 | 2021-02-01 05:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 05:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97372 | WBS.2.2.18.17.1.1 | N | N |  | FCW ¦ Ariba CIG Tasks | 28.25 | 2021-01-31 01:15 | 2021-02-01 05:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 05:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97371 | WBS.2.2.18.17.1.1.1 | N | N | Planned | ARBCIG - Stop PTP batch job for Ariba invoice status and Ariba master data to Ariba | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | NNEKA MBA | NEMBA@GAPAC.COM | YUDHAJIT MITRA;ERIC BARSTOW;PTP TEAM;PAM NIX;MASON DRAKE;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;PSNIX@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | BATCH | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97395 | WBS.2.2.18.17.1.1.21 | N | N | Planned | ARBCIG - Execute CI9 Ariba invoice status job to clear pending invoice statuses in S4P | 0.5 | 2021-01-31 01:30 | 2021-01-31 02:00 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97371 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:00 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97394 | WBS.2.2.18.17.1.1.20 | N | N | Planned | ARBCIG - Execute CI9 Ariba master data job to clear pending change docs in S4P | 0.5 | 2021-01-31 01:30 | 2021-01-31 02:00 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97371 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:00 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97393 | WBS.2.2.18.17.1.1.19 | N | N | Planned | ARBCIG - Validate entries in ARBCIG_AUTHPARAM and ARBCIG_TVARV post migration | 0.5 | 2021-01-31 09:45 | 2021-01-31 10:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36505,96896 |  |  | * |  | 2021-01-31 09:45 | 2021-01-31 10:15 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5572 | WBS.2.2.18.17.1.1.29 | N | N | Planned | Update ARBCIG_AUTHPARAM with quality values and Validate Master Data Interface Connectivity - all Ariba master data including Ariba Invoice Management | 1 | 2021-01-31 10:15 | 2021-01-31 11:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;CHARLES BLUMREICH;CASEY HERMANSEN;DOROTHY RUSSELL;YUDI MITRA;PARUL CHOUDHARY;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 90775,97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 11:15 | ARIBA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4342 | WBS.2.2.18.17.1.1.30 | N | N | Planned | MC Task ¦ Validate and update Work Order OCI Call Structure Configuration in S/4HANA for Ariba APC (MC only) | 0.25 | 2021-01-31 11:15 | 2021-01-31 11:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;PTP TEAM;SAI TEAM;MONICA CUEVAS;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5572 |  |  | * |  | 2021-01-31 11:15 | 2021-01-31 11:30 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10234 | WBS.2.2.18.17.1.1.31 | N | N | Planned | MC Task ¦ Validate Catalog Integration (including SSO) - PR | 0.25 | 2021-01-31 12:00 | 2021-01-31 12:15 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | CASEY HERMANSEN;PTP TEAM;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10229 |  |  | * |  | 2021-01-31 12:00 | 2021-01-31 12:15 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10235 | WBS.2.2.18.17.1.1.32 | N | N | Planned | MC Task ¦ Validate Catalog Integration (including SSO) - Ariba Spend Management Fiori | 0.25 | 2021-01-31 12:15 | 2021-01-31 12:30 | SRUTHI SRINIVASAN | SRUSRINIVASAN@DELOITTE.COM | CASEY HERMANSEN;PTP TEAM;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 10234 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 12:30 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10229 | WBS.2.2.18.17.1.1.33 | N | N | Planned | MC Task ¦ Validate and update PR OCI Call Structure Configuration in S/4HANA for Ariba APC (MC only) | 0.5 | 2021-01-31 11:30 | 2021-01-31 12:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;PTP TEAM;SAI TEAM;MONICA CUEVAS;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 4342 |  |  | * |  | 2021-01-31 11:30 | 2021-01-31 12:00 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90778 | WBS.2.2.18.17.1.1.34 | N | N | Planned | Confirm S/4HANA Client Is Closed - Task 1 | 0.25 | 2021-01-31 12:00 | 2021-01-31 12:15 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;SANDEEP THARWANI;US GP BASIS;SUVENDU KUMAR;DEV TEAM;TED ZEIDLER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;TED.ZEIDLER@GAPAC.COM | DEV | 10229,4342,95625,4628 |  |  | * |  | 2021-01-31 12:00 | 2021-01-31 12:15 | DEV - INFRA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97392 | WBS.2.2.18.17.1.1.18 | N | N | Planned | ARBCIG - Validate entries in ARBCIG_AN_VENDOR post migration | 1 | 2021-01-31 11:15 | 2021-01-31 12:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97383,5572 |  |  | * |  | 2021-01-31 11:15 | 2021-01-31 12:15 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97391 | WBS.2.2.18.17.1.1.17 | N | N | Planned | ARBCIG - Validate CIG output types for ZSR, ZQA, ZSPN, ZGRA | 0.5 | 2021-01-31 12:45 | 2021-01-31 13:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97378,97377 |  |  | * |  | 2021-01-31 12:45 | 2021-01-31 13:15 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97390 | WBS.2.2.18.17.1.1.16 | N | N | Planned | ARBCIG - Manually update condition records for ZSR, ZQA, ZSPN, ZGRA | 0.5 | 2021-01-31 13:15 | 2021-01-31 13:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;CASEY HERMANSEN;YUDHAJIT MITRA;MONICA CUEVAS;PARUL CHOUDHARY;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;parchoudhary@deloitte.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 97391 |  |  | * |  | 2021-01-31 13:15 | 2021-01-31 13:45 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97389 | WBS.2.2.18.17.1.1.15 | N | N | Planned | ARBCIG - Activate CIG in GP EIM S4HANA realm | 0.25 | 2021-01-31 10:15 | 2021-01-31 10:30 | RICHARD WORTMAN | RWORTMAN@GAPAC.COM | YUDHAJIT MITRA;ERIC BARSTOW;PTP TEAM;PAM NIX;MASON DRAKE;SAI TEAM;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;PSNIX@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 10:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97388 | WBS.2.2.18.17.1.1.14 | N | N | Planned | ARBCIG - Activate CIG in GP Buyer Account | 0.25 | 2021-01-31 10:15 | 2021-01-31 10:30 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | MARGARET OLIVER;YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;PARUL CHOUDHARY | MARGARET.OLIVER@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 10:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97387 | WBS.2.2.18.17.1.1.13 | N | N | Planned | ARBCIG - Set CIG as default end point and update routing rules on GP buyer account | 0.25 | 2021-01-31 10:30 | 2021-01-31 10:45 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | MARGARET OLIVER;YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;PARUL CHOUDHARY | MARGARET.OLIVER@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 97389,97388 |  |  | * |  | 2021-01-31 10:30 | 2021-01-31 10:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97386 | WBS.2.2.18.17.1.1.12 | N | N | Planned | ARBCIG - Activate CIG in Koch parent realm | 0.25 | 2021-01-31 10:15 | 2021-01-31 10:30 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;ABBY DREVIK;CHARLES BLUMREICH;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com;CHARLES.BLUMREICH@GAPAC.COM;parchoudhary@deloitte.com | PTP | 97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 10:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97385 | WBS.2.2.18.17.1.1.11 | N | N | Planned | ARBCIG - Activate CIG in Koch Buyer Account | 0.5 | 2021-01-31 10:15 | 2021-01-31 10:45 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | MARGARET OLIVER;YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;PARUL CHOUDHARY | MARGARET.OLIVER@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 10:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97384 | WBS.2.2.18.17.1.1.10 | N | N | Planned | ARBCIG - Set CIG as default end point and update routing rules on Koch buyer account | 0.5 | 2021-01-31 10:45 | 2021-01-31 11:15 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | MARGARET OLIVER;YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;PARUL CHOUDHARY | MARGARET.OLIVER@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 97386,97385 |  |  | * |  | 2021-01-31 10:45 | 2021-01-31 11:15 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97383 | WBS.2.2.18.17.1.1.9 | N | N | Planned | ARBCIG - Update EDI setting for incoming invoices (OBCA, OBCD, OBCE) | 0.5 | 2021-01-31 10:15 | 2021-01-31 10:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 10:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97381 | WBS.2.2.18.17.1.1.7 | N | N | Planned | ARBCIG - Smoke Test Sourcing transaction | 1 | 2021-01-31 21:00 | 2021-01-31 22:00 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;ABBY DREVIK;CHARLES BLUMREICH;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com;CHARLES.BLUMREICH@GAPAC.COM;parchoudhary@deloitte.com | PTP | 97390,97376,96898,36660 |  |  | * |  | 2021-01-31 21:00 | 2021-01-31 22:00 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97380 | WBS.2.2.18.17.1.1.6 | N | N | Planned | ARBCIG - Smoke Test Quote Automation transaction | 1 | 2021-01-31 22:00 | 2021-01-31 23:00 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;ABBY DREVIK;CHARLES BLUMREICH;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com;CHARLES.BLUMREICH@GAPAC.COM;parchoudhary@deloitte.com | PTP | 97381,96898,36660 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 23:00 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97379 | WBS.2.2.18.17.1.1.5 | N | N | Planned | ARBCIG - Validate TVARV config moved to GP CIG | 0.5 | 2021-01-31 12:15 | 2021-01-31 12:45 | RICHARD WORTMAN | RWORTMAN@GAPAC.COM | YUDHAJIT MITRA;BRUCE KIRKLEWSKI;SAI TEAM;PTP TEAM;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com | PTP | 96878 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 12:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97378 | WBS.2.2.18.17.1.1.4 | N | N | Planned | ARBCIG - Add new CIG SPRO config for Koch interfaces | 0.5 | 2021-01-31 12:15 | 2021-01-31 12:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;CHARLES BLUMREICH;CASEY HERMANSEN;DOROTHY RUSSELL;YUDI MITRA;PARUL CHOUDHARY;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;YMITRA@DELOITTE.COM;parchoudhary@deloitte.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 97392 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 12:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97377 | WBS.2.2.18.17.1.1.3 | N | N | Planned | ARBCIG - Add new CIG SPRO config for GP interfaces | 0.5 | 2021-01-31 12:15 | 2021-01-31 12:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;CASEY HERMANSEN;YUDHAJIT MITRA;MONICA CUEVAS;PARUL CHOUDHARY;PTP TEAM;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;parchoudhary@deloitte.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 97392 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 12:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97376 | WBS.2.2.18.17.1.1.2 | N | N | Planned | ARBCIG - Validate TVARV config moved to Koch CIG | 0.5 | 2021-01-31 12:15 | 2021-01-31 12:45 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;ABBY DREVIK;CHARLES BLUMREICH;PARUL CHOUDHARY | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com;CHARLES.BLUMREICH@GAPAC.COM;parchoudhary@deloitte.com | PTP | 96878 |  |  | * |  | 2021-01-31 12:15 | 2021-01-31 12:45 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81871 | WBS.2.2.18.17.1.1.22 | N | N | Planned | Update ARBCIG* entries in S/4HANA (week leading up to FCW - add go-live company code to TVARV table) | 1 | 2021-01-31 10:15 | 2021-01-31 11:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | ERIC BARSTOW;RICHARD WORTMAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PARUL CHOUDHARY;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;RWORTMAN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;parchoudhary@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10852,95288,97393 |  |  | * |  | 2021-01-31 10:15 | 2021-01-31 11:15 | ARIBA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95490 | WBS.2.2.18.17.1.1.23 | N | N | Planned | S/4HANA - Execute Master Data load for the S4HANA EIM realm | 3 | 2021-01-31 17:30 | 2021-01-31 20:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MONICA CUEVAS;SAI TEAM;PTP TEAM;SANDEEP A | MONICA.CUEVAS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 81871,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 20:30 | PTP | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
83214 | WBS.2.2.18.17.1.1.24 | N | N | Planned | EIM - Validate the Master Data loaded in the S4HANA EIM realm | 4 | 2021-01-31 20:30 | 2021-02-01 00:30 | PAM NIX | PSNIX@GAPAC.COM | MYRA BATES;SAI TEAM;PTP TEAM | MYRA.BATES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 95490 |  |  | * |  | 2021-01-31 20:30 | 2021-02-01 00:30 | EIM | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90286 | WBS.2.2.18.17.1.1.25 | N | N | Planned | Add dummy Suspense Accounts in S4 Ariba for new company codes to support Freight Account Code automation | 3 | 2021-02-01 00:30 | 2021-02-01 03:30 | TERESA FOWLER | TERESA.FOWLER@KBSLP.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 83214 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 03:30 | EIM | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90285 | WBS.2.2.18.17.1.1.26 | N | N | Planned | Remove dummy suspense accounts for ECC Ariba based on migration to S4 to prevent Freight Account Code automation | 2 | 2021-02-01 03:30 | 2021-02-01 05:30 | TERESA FOWLER | TERESA.FOWLER@KBSLP.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 90286 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 05:30 | EIM | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
89498 | WBS.2.2.18.17.1.1.27 | N | N | Planned | Ariba Sourcing integration - Execute master data transfer transactions in S4 (ARBCIG_MASTER_DATA_EXPORT) | 5 | 2021-01-31 17:30 | 2021-01-31 22:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;PTP TEAM;SAI TEAM;MONICA CUEVAS;SANDEEP A;PARUL CHOUDHARY | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM;parchoudhary@deloitte.com | PTP | 81871,97378,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 22:30 | ARIBA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
89499 | WBS.2.2.18.17.1.1.28 | N | N | Planned | Ariba Sourcing integration - Validate master data in Ariba for all | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | MARGARET OLIVER | MARGARET.OLIVER@GAPAC.COM | YUDHAJIT MITRA;SAI TEAM;RICHARD WORTMAN;PTP TEAM;ABBY DREVIK;CHARLES BLUMREICH | YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RWORTMAN@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;abigail.drevik@gapac.com;CHARLES.BLUMREICH@GAPAC.COM | PTP | 89498 |  |  | * |  | 2021-01-31 22:30 | 2021-02-01 00:30 | ARIBA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95322 | WBS.2.2.4 | N | N |  | FCW ¦ D1, D2 and D3 Facility Smoke Test – Post-Transports | 20.75 | 2021-01-31 01:30 | 2021-01-31 22:15 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-02-01 00:15 |  |  | 2021-01-31 | 2021-02-01 | 3 | Shutdown
92606 | WBS.2.2.4.14 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly | 19.25 | 2021-01-31 01:30 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92607 | WBS.2.2.4.14.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly | 19.25 | 2021-01-31 01:30 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92608 | WBS.2.2.4.14.1.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Shipping | 1 | 2021-01-31 01:30 | 2021-01-31 02:30 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-01-31 02:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95435 | WBS.2.2.4.14.1.1.1 | N | N | Planned | Smoke Test: Send out Mt. Holly communication of system shutdown / use of manual processes | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | ALISON SMITH | ALISON.SMITH@GAPAC.COM | RYAN MYERS;JOHN CASABURRI;SAI TEAM | CHARLES.MYERS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92609 | WBS.2.2.4.14.1.1.2 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - Mt. Holly | 1 | 2021-01-31 01:30 | 2021-01-31 02:30 | WINSTON CONRAD | WINSTON.CONRAD@GAPAC.COM | SHAWN MARTIN;ALISON SMITH;JOHN CASABURRI;SAI TEAM | STEVEN.MARTIN@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:30 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91294 | WBS.2.2.4.14.1.21 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Receiving | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91196 | WBS.2.2.4.14.1.21.13 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALISON SMITH | ALISON.SMITH@GAPAC.COM | JACK MANFREDI;SAI TEAM;JOHN CASABURRI | JACK.MANFREDI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91306 | WBS.2.2.4.14.1.21.14 | N | N | Planned | MRO: receiving on RF device correctly and scanner working - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91293 | WBS.2.2.4.14.1.21.15 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91295 | WBS.2.2.4.14.1.22 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91300 | WBS.2.2.4.14.1.22.21 | N | N | Planned | Smoke Test: Picks are printing correctly - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91302 | WBS.2.2.4.14.1.22.23 | N | N | Planned | Smoke Test: Labels printing correctly - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91303 | WBS.2.2.4.14.1.22.24 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91304 | WBS.2.2.4.14.1.22.25 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LISA VAUGHN | Lisa.Vaughn@gapac.com | WANDA POWELL;ALISON SMITH;JOHN CASABURRI;SAI TEAM;URSULA JENKINS | WANDA.POWELL@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;URSULA.JENKINS@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91299 | WBS.2.2.4.14.1.23 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Customer Service | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91291 | WBS.2.2.4.14.1.23.13 | N | N | Planned | Smoke Test: Enter a sales order and ensure order acknowledgement is generated - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | BRENDA SUMMERLIN | BRENDA.SUMMERLIN@GAPAC.COM | DAWN PERRY;KEN STRINGFIELD;ALISON SMITH;SAI TEAM;JOHN CASABURRI | DAWN.PERRY@GAPAC.COM;KENNETH.STRINGFIELD@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | OTC - OM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91292 | WBS.2.2.4.14.1.23.14 | N | N | Planned | Smoke Test: Ensure that packing slip is generated and is correct once the first trucks ship - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | WINSTON CONRAD | WINSTON.CONRAD@GAPAC.COM | SHAWN MARTIN;ALISON SMITH;SAI TEAM;JOHN CASABURRI | STEVEN.MARTIN@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91285 | WBS.2.2.4.14.1.23.15 | N | N | Planned | Smoke Test: Ensure that invoice is generated and is correct once the first trucks ship - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | BRENDA SUMMERLIN | BRENDA.SUMMERLIN@GAPAC.COM | DAWN PERRY;KEN STRINGFIELD;ALISON SMITH;SAI TEAM;JOHN CASABURRI | DAWN.PERRY@GAPAC.COM;KENNETH.STRINGFIELD@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | OTC - OM | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91296 | WBS.2.2.4.14.1.24 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91286 | WBS.2.2.4.14.1.24.13 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | WANDA POWELL | WANDA.POWELL@GAPAC.COM | ERICA BURKE;ALISON SMITH;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91287 | WBS.2.2.4.14.1.24.14 | N | N | Planned | Smoke Test: PR's are not stuck in release - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | WANDA POWELL | WANDA.POWELL@GAPAC.COM | ERICA BURKE;ALISON SMITH;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91288 | WBS.2.2.4.14.1.24.15 | N | N | Planned | Smoke Test: PO's are emailing to vendors - Mt. Holly | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | WANDA POWELL | WANDA.POWELL@GAPAC.COM | ERICA BURKE;ALISON SMITH;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91297 | WBS.2.2.4.14.1.25 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Mt. Holly - Maintenance & Reliability | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91290 | WBS.2.2.4.14.1.25.13 | N | N | Planned | Smoke Test: Verify notifications, work orders and Issue item from stores to work order - Mt. Holly | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | RYAN MYERS | CHARLES.MYERS@GAPAC.COM | TOMMIE BRIGHT;ALISON SMITH;SAI TEAM;JOHN CASABURRI;DENNIS JOHNSON | TOMMIE.BRIGHT@GAPAC.COM;ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DENNIS.JOHNSON@GAPAC.COM | Business | 96654,92593 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | AC | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94525 | WBS.2.2.4.14.1.25.15 | N | N | Planned | Smoke Test: Send out Mt. Holly communication to restart AC work in system | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | RYAN MYERS | CHARLES.MYERS@GAPAC.COM | ALISON SMITH;SAI TEAM;JOHN CASABURRI;KEVIN RATLIFF | ALISON.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;KEVIN.RATLIFF@GAPAC.COM | Business | 95525,96654,92593 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | AC | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91192 | WBS.2.2.4.15 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91193 | WBS.2.2.4.15.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91740 | WBS.2.2.4.15.1.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Shipping | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91194 | WBS.2.2.4.15.1.1.1 | N | N | Planned | Manually load truck and validate paperwork - Plattsburgh | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | CHRIS HARTIGAN | CHRISTOPHER.HARTIGAN@GAPAC.COM | JEFF REVILLE;ERIK LANZER;JOHN CASABURRI;SAI TEAM;LEONARD GIBSON | JEFFREY.REVILLE@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LEONARD.GIBSON@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91308 | WBS.2.2.4.15.1.2 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Operations | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91309 | WBS.2.2.4.15.1.2.1 | N | N | Planned | Reprocess transactions and validate postings - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | JEFF REVILLE | JEFFREY.REVILLE@GAPAC.COM | CHRIS HARTIGAN;ERIK LANZER;JOHN CASABURRI;SAI TEAM;PAT HOLLAND | CHRISTOPHER.HARTIGAN@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Patrick.Holland@GAPAC.com | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91333 | WBS.2.2.4.15.1.3 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Receiving | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91334 | WBS.2.2.4.15.1.3.1 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | JOHN LAFOUNTAIN | John.LaFountain@GAPAC.com | RANDY HOLLOWAY;REBECCA EMRICK;ERIK LANZER;SAI TEAM | RANDOLPH.HOLLOWAY@GAPAC.com;rebecca.emrick@gapac.com;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91335 | WBS.2.2.4.15.1.3.2 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | CHRIS HARTIGAN | CHRISTOPHER.HARTIGAN@GAPAC.COM | LEONARD GIBSON;ERIK LANZER;JOHN CASABURRI;SAI TEAM | LEONARD.GIBSON@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91336 | WBS.2.2.4.15.1.4 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91337 | WBS.2.2.4.15.1.4.1 | N | N | Planned | Smoke Test: Picks are printing correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | RANDY HOLLOWAY | RANDOLPH.HOLLOWAY@GAPAC.com | NEAL BUSHEY;JOHN LAFOUNTAIN;ERIK LANZER;SAI TEAM | NEAL.BUSHEY@GAPAC.COM;John.LaFountain@GAPAC.com;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91327 | WBS.2.2.4.15.1.4.2 | N | N | Planned | Smoke Test: RF Scanners working - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | JOHN LAFOUNTAIN | John.LaFountain@GAPAC.com | REBECCA EMRICK;ERIK LANZER;RANDY HOLLOWAY;SAI TEAM | rebecca.emrick@gapac.com;ERIK.LANZER@GAPAC.COM;RANDOLPH.HOLLOWAY@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91328 | WBS.2.2.4.15.1.4.3 | N | N | Planned | Smoke Test: Labels printing correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | JOHN LAFOUNTAIN | John.LaFountain@GAPAC.com | REBECCA EMRICK;ERIK LANZER;RANDY HOLLOWAY;SAI TEAM | rebecca.emrick@gapac.com;ERIK.LANZER@GAPAC.COM;RANDOLPH.HOLLOWAY@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91329 | WBS.2.2.4.15.1.4.4 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | REBECCA EMRICK | rebecca.emrick@gapac.com | ERICA BURKE;MARK BLOZINSKI;ERIK LANZER;SAI TEAM | ERICA.BURKE@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91330 | WBS.2.2.4.15.1.4.5 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | REBECCA EMRICK | rebecca.emrick@gapac.com | ERICA BURKE;MARK BLOZINSKI;ERIK LANZER;SAI TEAM | ERICA.BURKE@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91331 | WBS.2.2.4.15.1.5 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91332 | WBS.2.2.4.15.1.5.1 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | REBECCA EMRICK | rebecca.emrick@gapac.com | ERICA BURKE;MARK BLOZINSKI;ERIK LANZER;SAI TEAM | ERICA.BURKE@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91322 | WBS.2.2.4.15.1.5.2 | N | N | Planned | Smoke Test: PR's are not stuck in release -- Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | REBECCA EMRICK | rebecca.emrick@gapac.com | ERICA BURKE;MARK BLOZINSKI;ERIK LANZER;SAI TEAM | ERICA.BURKE@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91323 | WBS.2.2.4.15.1.5.3 | N | N | Planned | Smoke Test: PO's are emailing to vendors - Plattsburgh | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | REBECCA EMRICK | rebecca.emrick@gapac.com | ERICA BURKE;MARK BLOZINSKI;ERIK LANZER;SAI TEAM | ERICA.BURKE@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;ERIK.LANZER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91320 | WBS.2.2.4.15.1.6 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Plattsburgh - Maintenance & Reliability | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94527 | WBS.2.2.4.15.1.6.1 | N | N | Planned | Smoke Test: Verify notifications, work orders, etc. - Plattsburgh | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | NEAL BUSHEY | NEAL.BUSHEY@GAPAC.COM | RANDY HOLLOWAY;JOHN LACY;SAI TEAM | RANDOLPH.HOLLOWAY@GAPAC.com;JOHN.LACY@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | AC | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94528 | WBS.2.2.4.15.1.6.2 | N | N | Planned | Smoke Test: Send out Plattsburgh communication to restart AC work in system | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | ERIK LANZER | ERIK.LANZER@GAPAC.COM | NEAL BUSHEY;SAI TEAM;JOHN CASABURRI | NEAL.BUSHEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | AC | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94529 | WBS.2.2.4.15.1.6.3 | N | N | Planned | Smoke Test: Send out Plattsburgh communication that system is back up | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | ERIK LANZER | ERIK.LANZER@GAPAC.COM | NEAL BUSHEY;CHRIS HARTIGAN;SAI TEAM;JOHN CASABURRI | NEAL.BUSHEY@GAPAC.COM;CHRISTOPHER.HARTIGAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | AC | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91321 | WBS.2.2.4.15.1.6.4 | N | N | Planned | Smoke Test: Issue item from stores to work order - Plattsburgh | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | RANDY HOLLOWAY | RANDOLPH.HOLLOWAY@GAPAC.com | JEFF REVILLE;PAT HOLLAND;TOM SHAVER;ERIK LANZER;JOHN CASABURRI;SAI TEAM | JEFFREY.REVILLE@GAPAC.COM;Patrick.Holland@GAPAC.com;THOMAS.SHAVER@gapac.com;ERIK.LANZER@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | AC | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92694 | WBS.2.2.4.16 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Elwood | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92665 | WBS.2.2.4.16.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Elwood | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92664 | WBS.2.2.4.16.1.1 | N | N |  | FCW ¦ D1 Facility Smoke Test – Post-Transport - Elwood | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92667 | WBS.2.2.4.16.1.1.1 | N | N | Planned | Smoke Test: Cycle count and confirm posting in S4 - Elwood | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MIKE MCFALLS | MIKE.MCFALLS@RYDER.COM | JOSEPH GRILLI;SAI TEAM | JOSEPH_M_GRILLI@RYDER.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | ELW | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92666 | WBS.2.2.4.16.1.1.2 | N | N | Planned | Smoke Test: Goods issue co-pack purchase order and confirm withdrawal quantity - Elwood | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | MIKE MCFALLS | MIKE.MCFALLS@RYDER.COM | JOSEPH GRILLI;SAI TEAM | JOSEPH_M_GRILLI@RYDER.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | ELW | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92669 | WBS.2.2.4.16.1.1.3 | N | N | Planned | Smoke Test: EWM Load and ship order - Elwood | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | MIKE MCFALLS | MIKE.MCFALLS@RYDER.COM | JOSEPH GRILLI;SAI TEAM | JOSEPH_M_GRILLI@RYDER.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | ELW | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92668 | WBS.2.2.4.16.1.1.4 | N | N | Planned | Smoke Test: Identify/Receive using new STO number in S4 - Elwood | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | MIKE MCFALLS | MIKE.MCFALLS@RYDER.COM | JOSEPH GRILLI;SAI TEAM | JOSEPH_M_GRILLI@RYDER.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | ELW | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95323 | WBS.2.2.4.1 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah | 2.5 | 2021-01-31 19:45 | 2021-01-31 22:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-02-01 00:15 |  |  | 2021-01-31 | 2021-02-01 | 3 | Shutdown
95324 | WBS.2.2.4.1.1 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah | 2.5 | 2021-01-31 19:45 | 2021-01-31 22:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-02-01 00:15 |  |  | 2021-01-31 | 2021-02-01 | 3 | Shutdown
95325 | WBS.2.2.4.1.1.1 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah - Shipping | 1 | 2021-01-31 21:15 | 2021-01-31 22:15 | [8 empty] | * |  | 2021-01-31 23:15 | 2021-02-01 00:15 |  |  | 2021-01-31 | 2021-02-01 | 3 | Shutdown
95326 | WBS.2.2.4.1.1.1.1 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - Savannah | 1 | 2021-01-31 21:15 | 2021-01-31 22:15 | WILL LONG | WILLIAM.Long@GAPAC.com | PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654,97693 |  |  | * |  | 2021-01-31 23:15 | 2021-02-01 00:15 | EWM | SAV | 2021-01-31 | 2021-02-01 | 3 | Shutdown
95327 | WBS.2.2.4.1.1.2 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah - Operations | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95328 | WBS.2.2.4.1.1.2.1 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - Savannah | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | WILL LONG | WILLIAM.Long@GAPAC.com | PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654,97693 |  |  | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 | EWM | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95339 | WBS.2.2.4.1.1.17 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah - Receiving | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95340 | WBS.2.2.4.1.1.17.9 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - Savannah | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | WILL LONG | WILLIAM.Long@GAPAC.com | PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654,97693 |  |  | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95341 | WBS.2.2.4.1.1.17.10 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - Savannah | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | WILL LONG | WILLIAM.Long@GAPAC.com | PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654,97693 |  |  | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 | EWM | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95342 | WBS.2.2.4.1.1.18 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95343 | WBS.2.2.4.1.1.18.21 | N | N | Planned | Smoke Test: Picks are printing correctly - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALLEN MIDDLETON | ALLEN.MIDDLETON@GAPAC.COM | PAUL DICKERSON;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PAUL.DICKERSON@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95344 | WBS.2.2.4.1.1.18.22 | N | N | Planned | Smoke Test: RF Scanners working - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALLEN MIDDLETON | ALLEN.MIDDLETON@GAPAC.COM | PAUL DICKERSON;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PAUL.DICKERSON@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95345 | WBS.2.2.4.1.1.18.23 | N | N | Planned | Smoke Test: Labels printing correctly - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALLEN MIDDLETON | ALLEN.MIDDLETON@GAPAC.COM | PAUL DICKERSON;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PAUL.DICKERSON@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95346 | WBS.2.2.4.1.1.18.24 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALLEN MIDDLETON | ALLEN.MIDDLETON@GAPAC.COM | PAUL DICKERSON;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PAUL.DICKERSON@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95347 | WBS.2.2.4.1.1.18.25 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ALLEN MIDDLETON | ALLEN.MIDDLETON@GAPAC.COM | PAUL DICKERSON;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PAUL.DICKERSON@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95348 | WBS.2.2.4.1.1.19 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - Savannah - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95349 | WBS.2.2.4.1.1.19.13 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | CORY COMBS | CORY.COMBS@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95350 | WBS.2.2.4.1.1.19.14 | N | N | Planned | Smoke Test: PR's are not stuck in release - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | CORY COMBS | CORY.COMBS@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95351 | WBS.2.2.4.1.1.19.15 | N | N | Planned | Smoke Test: PO's are emailing to vendors - Savannah | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | CORY COMBS | CORY.COMBS@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95329 | WBS.2.2.4.2 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - McDonough | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95330 | WBS.2.2.4.2.1 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - McDonough | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95331 | WBS.2.2.4.2.1.1 | N | N |  | FCW ¦ D2 Facility Smoke Test – Post-Transport - McDonough | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95332 | WBS.2.2.4.2.1.1.1 | N | N | Planned | Smoke Test: Cycle count and confirm posting in S4 - McDonough | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | ZURI PETERSON | ZURI.PETERSON@DSCLOGISTICS.COM | DEAN WHITACRE;AARON SIMMS;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;AARON.SIMMS@DSCLOGISTICS.COM;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | McD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95333 | WBS.2.2.4.2.1.1.2 | N | N | Planned | Smoke Test: Goods issue co-pack purchase order and confirm withdrawal quantity - McDonough | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | ZURI PETERSON | ZURI.PETERSON@DSCLOGISTICS.COM | DEAN WHITACRE;AARON SIMMS;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;AARON.SIMMS@DSCLOGISTICS.COM;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | McD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95334 | WBS.2.2.4.2.1.1.3 | N | N | Planned | Smoke Test: EWM Load and ship order - McDonough | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | ZURI PETERSON | ZURI.PETERSON@DSCLOGISTICS.COM | DEAN WHITACRE;AARON SIMMS;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;AARON.SIMMS@DSCLOGISTICS.COM;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | McD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95335 | WBS.2.2.4.2.1.1.4 | N | N | Planned | Smoke Test: Identify/Receive using new STO number in S4 - McDonough | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | ZURI PETERSON | ZURI.PETERSON@DSCLOGISTICS.COM | DEAN WHITACRE;AARON SIMMS;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;AARON.SIMMS@DSCLOGISTICS.COM;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | McD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97767 | WBS.2.2.4.17 | N | N |  | FCW ¦ D2 Facility Smoke Test – Validate Business Operations - Jacksonville | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97768 | WBS.2.2.4.17.11 | N | N |  | FCW ¦ D2 Facility Smoke Test – Validate Business Operations - Jacksonville | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97769 | WBS.2.2.4.17.11.11 | N | N |  | FCW ¦ D2 Facility Smoke Test – Validate Business Operations - Jacksonville | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97770 | WBS.2.2.4.17.11.11.38 | N | N | Planned | Smoke Test: Cycle count and confirm posting in S4 - Jacksonville | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | AARON SIMMS | AARON.SIMMS@DSCLOGISTICS.COM | DEAN WHITACRE;LYNN PENNY;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;lynnette.padron@dsclogistics.com ;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | JAX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97771 | WBS.2.2.4.17.11.11.39 | N | N | Planned | Smoke Test: Goods issue co-pack purchase order and confirm withdrawal quantity - Jacksonville | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | AARON SIMMS | AARON.SIMMS@DSCLOGISTICS.COM | DEAN WHITACRE;LYNN PENNY;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;lynnette.padron@dsclogistics.com ;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | JAX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97772 | WBS.2.2.4.17.11.11.40 | N | N | Planned | Smoke Test: EWM Load and ship order - Jacksonville | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | AARON SIMMS | AARON.SIMMS@DSCLOGISTICS.COM | DEAN WHITACRE;LYNN PENNY;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;lynnette.padron@dsclogistics.com ;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | JAX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97773 | WBS.2.2.4.17.11.11.41 | N | N | Planned | Smoke Test: Identify/Receive using new STO number in S4 - Jacksonville | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | AARON SIMMS | AARON.SIMMS@DSCLOGISTICS.COM | DEAN WHITACRE;LYNN PENNY;AUTUMN BRUCE;SAI TEAM;JOHN CASABURRI | DEAN.WHITACRE@DSCLOGISTICS.COM;lynnette.padron@dsclogistics.com ;AUTUMN.BRUCE@DSCLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | JAX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97029 | WBS.2.2.4.3 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97030 | WBS.2.2.4.3.5 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97031 | WBS.2.2.4.3.5.9 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Shipping | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97032 | WBS.2.2.4.3.5.9.5 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - GBD | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | TOM MARCHANT | THOMAS.MARCHANT@GAPAC.COM | TIM NOVOSELATZ;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | TIMOTHY.NOVOSELATZ@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97033 | WBS.2.2.4.3.5.10 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Operations | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97034 | WBS.2.2.4.3.5.10.5 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97055 | WBS.2.2.4.3.5.30 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Receiving | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97056 | WBS.2.2.4.3.5.30.17 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | TOM MARCHANT | THOMAS.MARCHANT@GAPAC.COM | TIM NOVOSELATZ;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | TIMOTHY.NOVOSELATZ@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97057 | WBS.2.2.4.3.5.30.18 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | TOM MARCHANT | THOMAS.MARCHANT@GAPAC.COM | TIM NOVOSELATZ;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | TIMOTHY.NOVOSELATZ@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97058 | WBS.2.2.4.3.5.31 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97059 | WBS.2.2.4.3.5.31.41 | N | N | Planned | Smoke Test: Picks are printing correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97060 | WBS.2.2.4.3.5.31.42 | N | N | Planned | Smoke Test: RF Scanners working - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97061 | WBS.2.2.4.3.5.31.43 | N | N | Planned | Smoke Test: Labels printing correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97062 | WBS.2.2.4.3.5.31.44 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97063 | WBS.2.2.4.3.5.31.45 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97064 | WBS.2.2.4.3.5.32 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97065 | WBS.2.2.4.3.5.32.28 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97066 | WBS.2.2.4.3.5.32.29 | N | N | Planned | Smoke Test: PR's are not stuck in release - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97067 | WBS.2.2.4.3.5.32.30 | N | N | Planned | Smoke Test: PO's are emailing to vendors - GBD | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | ERICA BURKE;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97035 | WBS.2.2.4.4 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 23:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97036 | WBS.2.2.4.4.9 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 23:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97037 | WBS.2.2.4.4.9.17 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB - Shipping | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97038 | WBS.2.2.4.4.9.17.9 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - GBB | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97039 | WBS.2.2.4.4.9.18 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB - Operations | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97040 | WBS.2.2.4.4.9.18.9 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97070 | WBS.2.2.4.4.9.42 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB - Receiving | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 23:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97071 | WBS.2.2.4.4.9.42.25 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - GBB | 0.5 | 2021-01-31 21:15 | 2021-01-31 21:45 | WILL LONG | WILLIAM.Long@GAPAC.com | PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654,97693 |  |  | * |  | 2021-01-31 23:15 | 2021-01-31 23:45 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97072 | WBS.2.2.4.4.9.42.26 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97073 | WBS.2.2.4.4.9.43 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97074 | WBS.2.2.4.4.9.43.61 | N | N | Planned | Smoke Test: Picks are printing correctly - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97075 | WBS.2.2.4.4.9.43.62 | N | N | Planned | Smoke Test: RF Scanners working - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97076 | WBS.2.2.4.4.9.43.63 | N | N | Planned | Smoke Test: Labels printing correctly - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97077 | WBS.2.2.4.4.9.43.64 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97078 | WBS.2.2.4.4.9.43.65 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97079 | WBS.2.2.4.4.9.44 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBB - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97080 | WBS.2.2.4.4.9.44.40 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97081 | WBS.2.2.4.4.9.44.41 | N | N | Planned | Smoke Test: PR's are not stuck in release - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97082 | WBS.2.2.4.4.9.44.42 | N | N | Planned | Smoke Test: PO's are emailing to vendors - GBB | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97041 | WBS.2.2.4.5 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97042 | WBS.2.2.4.5.9 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97043 | WBS.2.2.4.5.9.17 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP - Shipping | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97044 | WBS.2.2.4.5.9.17.9 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - GBP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | SHANE GARDNER | Shane.gardner@GAPAC.com | BRITTANY WOODLAND;SAI TEAM;JOHN CASABURRI;MELISSA KOTAREK | Brittany.woodland@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97045 | WBS.2.2.4.5.9.18 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBD - Operations | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97046 | WBS.2.2.4.5.9.18.9 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | JEREMY HEYDEN | JEREMY.HEYDEN@GAPAC.COM | Helen Prohaska;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | HELEN.PROHASKA@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97085 | WBS.2.2.4.5.9.54 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP - Receiving | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97086 | WBS.2.2.4.5.9.54.33 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | GREGG GENTILE | GREGG.GENTILE@GAPAC.COM | LYNN BRAATZ;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | LYNN.BRAATZ@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97087 | WBS.2.2.4.5.9.54.34 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | TRENT WILLIAMS | Trent.Williams@GAPAC.com | BRITTANY WOODLAND;SHANE GARDNER;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | Brittany.woodland@GAPAC.com;Shane.gardner@GAPAC.com;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97088 | WBS.2.2.4.5.9.55 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97089 | WBS.2.2.4.5.9.55.81 | N | N | Planned | Smoke Test: Picks are printing correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97090 | WBS.2.2.4.5.9.55.82 | N | N | Planned | Smoke Test: RF Scanners working - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97091 | WBS.2.2.4.5.9.55.83 | N | N | Planned | Smoke Test: Labels printing correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97092 | WBS.2.2.4.5.9.55.84 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97093 | WBS.2.2.4.5.9.55.85 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | LYNN BRAATZ | LYNN.BRAATZ@GAPAC.COM | ERICA BURKE;MELISSA KOTAREK;SAI TEAM;JOHN CASABURRI | ERICA.BURKE@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97094 | WBS.2.2.4.5.9.56 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - GBP - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97095 | WBS.2.2.4.5.9.56.52 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM;JOHN CASABURRI;MELISSA KOTAREK | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97096 | WBS.2.2.4.5.9.56.53 | N | N | Planned | Smoke Test: PR's are not stuck in release - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM;MELISSA KOTAREK | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97097 | WBS.2.2.4.5.9.56.54 | N | N | Planned | Smoke Test: PO's are emailing to vendors - GBP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | MARK BLOZINSKI | MARK.BLOZINSKI@GAPAC.COM | DAROLD FORD;PHILIP GAGLIA;SAI TEAM;MELISSA KOTAREK | DAROLD.FORD@GAPAC.COM;PHILIP.GAGLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97047 | WBS.2.2.4.6 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97048 | WBS.2.2.4.6.9 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97049 | WBS.2.2.4.6.9.17 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP - Shipping | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97050 | WBS.2.2.4.6.9.17.9 | N | N | Planned | Smoke Test: Manually load truck and validate paperwork - LVP | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | SAMUEL CHAMBERS | SAMUEL.CHAMBERS@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97051 | WBS.2.2.4.6.9.18 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP - Operations | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97052 | WBS.2.2.4.6.9.18.9 | N | N | Planned | Smoke Test: Reprocess transactions and validate postings - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | SAMUEL CHAMBERS | SAMUEL.CHAMBERS@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97100 | WBS.2.2.4.6.9.54 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP - Receiving | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97101 | WBS.2.2.4.6.9.54.33 | N | N | Planned | Smoke Test: MRO: Receiving on RF device correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97102 | WBS.2.2.4.6.9.54.34 | N | N | Planned | Smoke Test: Vitals: Receiving using MIGO correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | SAMUEL CHAMBERS | SAMUEL.CHAMBERS@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97103 | WBS.2.2.4.6.9.55 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP - Store-room | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97104 | WBS.2.2.4.6.9.55.81 | N | N | Planned | Smoke Test: Picks are printing correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97105 | WBS.2.2.4.6.9.55.82 | N | N | Planned | Smoke Test: RF Scanners working - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | SAMUEL CHAMBERS | SAMUEL.CHAMBERS@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97106 | WBS.2.2.4.6.9.55.83 | N | N | Planned | Smoke Test: Labels printing correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | SAMUEL CHAMBERS | SAMUEL.CHAMBERS@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97107 | WBS.2.2.4.6.9.55.84 | N | N | Planned | Smoke Test: MRO: Purchase requisition process flows correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97108 | WBS.2.2.4.6.9.55.85 | N | N | Planned | Smoke Test: MRO: Batch job creates replenishment requisitions - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97109 | WBS.2.2.4.6.9.56 | N | N |  | FCW ¦ D3 Facility Smoke Test – Post-Transport - LVP - Procurement | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97110 | WBS.2.2.4.6.9.56.52 | N | N | Planned | Smoke Test: PR can process into PO with all data coming through correctly - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;JOHN CASABURRI;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97111 | WBS.2.2.4.6.9.56.53 | N | N | Planned | Smoke Test: PR's are not stuck in release - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97112 | WBS.2.2.4.6.9.56.54 | N | N | Planned | Smoke Test: PO's are emailing to vendors - LVP | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | DOUGLAS CARANGELO | DOUGLAS.CARANGELO@GAPAC.COM | KRISTEN MOLL;SAI TEAM;Mark Bernard | KLMOLL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | PTP - Procurement/Stores | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95522 | WBS.2.2.4.8 | N | N |  | FCW ¦ H3 Facility Smoke Test – Post-Transport - CLV | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95523 | WBS.2.2.4.8.5 | N | N |  | FCW ¦ H3 Facility Smoke Test – Post-Transport - CLV | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95524 | WBS.2.2.4.8.5.5 | N | N |  | FCW ¦ H3 Facility Smoke Test – Post-Transport - CLV | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95525 | WBS.2.2.4.8.5.5.17 | N | N | Planned | Smoke Test: Cycle count and confirm posting in S4 - Cleveland Rd | 0.5 | 2021-01-31 19:45 | 2021-01-31 20:15 | SHANNON SMITH | Shannon_Smith@ryder.com | CASSIE VANATTA;JEREMY SIMS;MIKE MCFALLS;DON ABBOTT;JOHN CASABURRI;SAI TEAM;JUSTIN KAINZ;PATRICK WEAVER;JORDAN SCHILLING;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | CASSANDRA.VANATTA@GAPAC.COM;JEREMY.SIMS@GAPAC.COM;MIKE.MCFALLS@RYDER.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JUSTIN.KAINZ1@GAPAC.COM;PATRICK_WEAVER@RYDER.COM;JORDAN_A_SCHILLING@RYDER.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:15 | EWM | CLV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95526 | WBS.2.2.4.8.5.5.18 | N | N | Planned | Smoke Test: Goods issue co-pack purchase order and confirm withdrawal quantity - Cleveland Rd | 1 | 2021-01-31 19:45 | 2021-01-31 20:45 | SHANNON SMITH | Shannon_Smith@ryder.com | CASSIE VANATTA;JEREMY SIMS;MIKE MCFALLS;DON ABBOTT;JOHN CASABURRI;SAI TEAM;JUSTIN KAINZ;PATRICK WEAVER;JORDAN SCHILLING;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | CASSANDRA.VANATTA@GAPAC.COM;JEREMY.SIMS@GAPAC.COM;MIKE.MCFALLS@RYDER.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JUSTIN.KAINZ1@GAPAC.COM;PATRICK_WEAVER@RYDER.COM;JORDAN_A_SCHILLING@RYDER.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | CLV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95527 | WBS.2.2.4.8.5.5.19 | N | N | Planned | Smoke Test: EWM Load and ship order - Cleveland Rd | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | SHANNON SMITH | Shannon_Smith@ryder.com | CASSIE VANATTA;JEREMY SIMS;MIKE MCFALLS;DON ABBOTT;JOHN CASABURRI;SAI TEAM;JUSTIN KAINZ;PATRICK WEAVER;JORDAN SCHILLING;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | CASSANDRA.VANATTA@GAPAC.COM;JEREMY.SIMS@GAPAC.COM;MIKE.MCFALLS@RYDER.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JUSTIN.KAINZ1@GAPAC.COM;PATRICK_WEAVER@RYDER.COM;JORDAN_A_SCHILLING@RYDER.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | CLV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95528 | WBS.2.2.4.8.5.5.20 | N | N | Planned | Smoke Test: Identify/Receive using new STO number in S4 - Cleveland Rd | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | SHANNON SMITH | Shannon_Smith@ryder.com | CASSIE VANATTA;JEREMY SIMS;MIKE MCFALLS;DON ABBOTT;JOHN CASABURRI;SAI TEAM;JUSTIN KAINZ;PATRICK WEAVER;JORDAN SCHILLING;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | CASSANDRA.VANATTA@GAPAC.COM;JEREMY.SIMS@GAPAC.COM;MIKE.MCFALLS@RYDER.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JUSTIN.KAINZ1@GAPAC.COM;PATRICK_WEAVER@RYDER.COM;JORDAN_A_SCHILLING@RYDER.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 92593,96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | CLV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91005 | WBS.2.2.5 | N | N |  | FCW ¦ Pre-Conversions Activity | 50 | 2021-01-31 01:15 | 2021-02-02 03:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:45 |  | CROSS | 2021-02-02 | 2021-02-01 | 3 | Shutdown
91003 | WBS.2.2.5.1 | N | N |  | FCW ¦ Pre-Conversions Activity - Non-Digital Core Systems | 50 | 2021-01-31 01:15 | 2021-02-02 03:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:45 |  | CROSS | 2021-02-02 | 2021-02-01 | 3 | Shutdown
29579 | WBS.2.2.5.1.1 | N | N |  | FCW ¦ Pre-Conversions Activity - Non-Digital Core - Load Prep Tasks | 44 | 2021-01-31 01:15 | 2021-02-01 21:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:45 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80818 | WBS.2.2.5.1.1.1 | N | N |  | FCW ¦ Pre-Conversions Activity - Legacy Systems - Load Prep Tasks - ICPAQS | 44 | 2021-01-31 01:15 | 2021-02-01 21:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:45 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94960 | WBS.2.2.5.1.1.1.69 | N | N | Planned | HBG - Action - Turn on U2I to ICPAQS Finshed Goods Integration (Configure and turn on U2I for Production) | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | MINT VICKERY | MINT.VICKERY@GAPAC.COM | SUSAN RIELS;TODD DAKINS;DORESA WARD;SAI TEAM | SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM;DVWARD@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 94548,94905 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97356 | WBS.2.2.5.1.1.1.192 | N | N | Planned | HBG - Send Test finished goods transaction to ICPAQS / Test Communication | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;TODD DAKINS;SAI TEAM | MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 94548,94960 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97358 | WBS.2.2.5.1.1.1.193 | N | N | Planned | PTH - Send Test finished goods transaction to ICPAQS / Test Communication | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;TODD DAKINS;SAI TEAM | MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 97022,97684 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97584 | WBS.2.2.5.1.1.1.156 | N | N | Planned | PTH - Set test finished goods transaction to ignore in ICPAQs | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM;PHIL RACINE;FRANZ JURVA | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;phil.racine@gapac.com;FRANZ.JURVA@GAPAC.COM | ICPAQS | 97358 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | ICPAQS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97585 | WBS.2.2.5.1.1.1.157 | N | N | Planned | HBG - Set test finished goods transaction to ignore in ICPAQS | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;MINT VICKERY;SAI TEAM;PHIL RACINE;FRANZ JURVA | TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;phil.racine@gapac.com;FRANZ.JURVA@GAPAC.COM | ICPAQS | 97356 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | ICPAQS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94388 | WBS.2.2.5.1.1.1.145 | N | N | Planned | Communication to Paper Machine Operators: PTH - Communication to Operators start new S4 orders and create reels, rolls. | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com | Business | 94893,92262 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95611 | WBS.2.2.5.1.1.1.51 | N | N | Planned | MC TASK - Create PTH Paper Machine Data (1 day) | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 94731 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92262 | WBS.2.2.5.1.1.1.53 | N | N | Planned | PTH - Task - Purge Transaction Queue | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97599 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97684 | WBS.2.2.5.1.1.1.186 | N | N | Planned | PTH - Action - Turn on PTH to ICPAQS Finished Goods Integration (Configure and turn on U2I for Production) | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | MINT VICKERY | MINT.VICKERY@GAPAC.COM | SUSAN RIELS;TODD DAKINS;DORESA WARD;SAI TEAM | SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM;DVWARD@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 92262 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94732 | WBS.2.2.5.1.1.1.188 | N | N | Planned | PTH - Validation - All Paper Making S4 Production Orders are started | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com | Business | 94388 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94905 | WBS.2.2.5.1.1.1.65 | N | N | Planned | HBG - Task - Purge Transaction Queue | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;TODD DAKINS;MINT VICKERY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TODD.DAKINS@GAPAC.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 97597 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96598 | WBS.2.2.5.1.1.1.97 | N | N | Planned | BG - Task - Purge Transaction Queue | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | ICPAQS | 97596 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96630 | WBS.2.2.5.1.1.1.206 | N | N | Planned | BG - Communicate to Converting to Start-Up for FCW Production if Required | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | KELLY LEWIS;SAI TEAM;DEAN PIPER | kelly.lewis@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com | Business | 96598 |  |  | * |  | 2021-01-29 06:15 | 2021-01-29 06:30 | EWM | BG | 2021-01-31 | 2021-01-29 | 2 | Shutdown
97587 | WBS.2.2.5.1.1.1.159 | N | N | Planned | Put workflows in sleep and put logic monitor or server or services in downtime (All sites (D1-D4) | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | ICPAQS | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97588 | WBS.2.2.5.1.1.1.160 | N | N | Planned | Decommission services, update Azure Devops Variables (Configuration change on server to decommission unneeded services, and auto release) - Technical team to validate release | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | DORESA WARD | DVWARD@GAPAC.COM | MINT VICKERY;TODD DAKINS;SAI TEAM | MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | ICPAQS | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97589 | WBS.2.2.5.1.1.1.161 | N | N | Planned | PLT - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97590 | WBS.2.2.5.1.1.1.162 | N | N | Planned | MTH - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97591 | WBS.2.2.5.1.1.1.163 | N | N | Planned | SAV - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97592 | WBS.2.2.5.1.1.1.164 | N | N | Planned | GBB- Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97593 | WBS.2.2.5.1.1.1.165 | N | N | Planned | GBD - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97594 | WBS.2.2.5.1.1.1.166 | N | N | Planned | GBP- Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;MELISSA KOTAREK | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97595 | WBS.2.2.5.1.1.1.167 | N | N | Planned | LVP - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97596 | WBS.2.2.5.1.1.1.168 | N | N | Planned | BG - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505,95902 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97597 | WBS.2.2.5.1.1.1.169 | N | N | Planned | HBG - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505,94943 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97599 | WBS.2.2.5.1.1.1.171 | N | N | Planned | PTH - Action - Turn off Transaction Service | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505,94945 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | ICPAQS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94385 | WBS.2.2.5.1.1.1.4 | N | N | Planned | Communication to Converting Operators: HBG - Communication to Operators to start the new production S4 order/run | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 93865,94798,94905 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS OPERATIONS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95608 | WBS.2.2.5.1.1.1.5 | N | N | Planned | MC TASK - Create HBG Converting Data (1 day) | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | BOBBY WHITE | Bobby.White@gapac.com | CHRIS ZUMWALT;JOHN CASABURRI;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 94385 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95606 | WBS.2.2.5.1.1.1.10 | N | N | Planned | MC TASK - Create PTH Converting Data (1 day) | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97160 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94731 | WBS.2.2.5.1.1.1.11 | N | N | Planned | PTH - Validation - All Converting S4 Production Orders are started | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com | Business | 97160 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96617 | WBS.2.2.5.1.1.1.24 | N | N | Planned | Communication to Converting Operators: BG - Communication to Operators to start the new production S4 order/run | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | KELLY LEWIS | kelly.lewis@gapac.com | JOHN CASABURRI;SAI TEAM;LYNN MCMURDO;DEAN PIPER;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 94798,96593,96598 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS OPERATIONS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96616 | WBS.2.2.5.1.1.1.23 | N | N | Planned | MC TASK - Create BG Converting Data (1 day) | 0.25 | 2021-01-31 02:00 | 2021-01-31 02:15 | KELLY LEWIS | kelly.lewis@gapac.com | SAI TEAM;LYNN MCMURDO;DEAN PIPER;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 96617 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:15 | ICPAQS OPERATIONS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96618 | WBS.2.2.5.1.1.1.25 | N | N | Planned | BG - Validation - All Converting S4 Production Orders are started | 0.5 | 2021-01-31 02:00 | 2021-01-31 02:30 | KELLY LEWIS | kelly.lewis@gapac.com | SAI TEAM;LYNN MCMURDO;DEAN PIPER | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com | Business | 96617 |  |  | * |  | 2021-01-31 02:00 | 2021-01-31 02:30 | ICPAQS OPERATIONS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95591 | WBS.2.2.5.1.1.1.16 | N | N | Planned | SAV - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96619 | WBS.2.2.5.1.1.1.26 | N | N | Planned | GBB - Clean-up vitals moved to staging while S/4 EWM wasn’t available | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 21:30 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96620 | WBS.2.2.5.1.1.1.27 | N | N | Planned | GBB - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96621 | WBS.2.2.5.1.1.1.28 | N | N | Planned | GBD - Clean-up vitals moved to staging while S/4 EWM wasn’t available | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 21:30 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97668 | WBS.2.2.5.1.1.1.142 | N | N | Planned | GBD - Stop EWM manual processes and return to using SAP | 0.5 | 2021-01-31 19:30 | 2021-01-31 20:00 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | TOM MARCHANT;JOHN TILLEMAN;SAI TEAM;JOHN CASABURRI | THOMAS.MARCHANT@GAPAC.COM;JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:00 | EWM | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97669 | WBS.2.2.5.1.1.1.143 | N | N | Planned | GBD - Stop Manual AC Processes and complete catch-up transactions | 0.5 | 2021-01-31 19:30 | 2021-01-31 20:00 | Nate Wogsland | Nathan.wogsland@gapac.com | JOHN TILLEMAN;SAI TEAM | JOHN.TILLEMAN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:00 | AC | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97677 | WBS.2.2.5.1.1.1.144 | N | N | Planned | GBB - Stop Manual AC Processes and complete catch-up transactions | 0.5 | 2021-01-31 19:30 | 2021-01-31 20:00 | CHRIS KANE | CHRIS.KANE@GAPAC.COM | RYAN VANCAMPENHOUT;KIM VANWYCHEN;SAI TEAM | RYAN.VANCAMPENHOUT2@GAPAC.COM;KIM.VANWYCHEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:00 | AC | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96622 | WBS.2.2.5.1.1.1.29 | N | N | Planned | GBD - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96623 | WBS.2.2.5.1.1.1.30 | N | N | Planned | GBP - Clean-up vitals moved to staging while S/4 EWM wasn’t available | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | DERRICK KESSLER | VAN.Kessler@GAPAC.com | PHILIP GAGLIA;EWM TEAM;SAI TEAM;PAUL DICKERSON;MELISSA KOTAREK | PHILIP.GAGLIA@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PAUL.DICKERSON@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 21:30 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96624 | WBS.2.2.5.1.1.1.31 | N | N | Planned | GBP - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;MELISSA KOTAREK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97642 | WBS.2.2.5.1.1.1.135 | N | N | Planned | *Prod Only* - RVG - Turn on LGVs to begin Receiving/Shipping Missions | 0.25 | 2021-01-31 05:00 | 2021-01-31 05:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 97641 |  |  | * |  | 2021-01-31 05:00 | 2021-01-31 05:15 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97643 | WBS.2.2.5.1.1.1.136 | N | N | Planned | *Mock Only* - GBB - E80 - Send Catch Up transactions to ICPAQs (ProduceHU) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 96620 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97644 | WBS.2.2.5.1.1.1.137 | N | N | Planned | *Mock Only* - GBB - E80 - Send Catch Up transactions to SAP (Inventory Transfers) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 96620 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97645 | WBS.2.2.5.1.1.1.138 | N | N | Planned | *Mock Only* - SAV - E80 - Send Catch Up transactions to ICPAQs (ProduceHU) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 95591 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97646 | WBS.2.2.5.1.1.1.139 | N | N | Planned | *Mock Only* - SAV - E80 - Send Catch Up transactions to SAP (Inventory Transfers) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 95591 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97647 | WBS.2.2.5.1.1.1.140 | N | N | Planned | *Mock Only* - PLT - E80 - Send Catch Up transactions to ICPAQs (ProduceHU) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 95592 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97648 | WBS.2.2.5.1.1.1.141 | N | N | Planned | *Mock Only* - GBP - E80 - Send Catch Up transactions to ICPAQs (ProduceHU) | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 96624 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | E80 | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96625 | WBS.2.2.5.1.1.1.32 | N | N | Planned | LVP - Clean-up vitals moved to staging while S/4 EWM wasn’t available | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | ANDREW WARREN | ANDREW.WARREN@GAPAC.COM | SAMUEL CHAMBERS;KRISTEN MOLL;EWM TEAM;SAI TEAM | SAMUEL.CHAMBERS@GAPAC.COM;KLMOLL@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92593 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 21:30 | EWM | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97693 | WBS.2.2.5.1.1.1.194 | N | N | Planned | SAV - Clean-up Group1 Vitals moved to staging while S/4 EWM wasn’t available | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | WILL LONG | WILLIAM.Long@GAPAC.com | DELL BRABHAM;SAI TEAM | Dell.Brabhamjr@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | EWM | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96626 | WBS.2.2.5.1.1.1.33 | N | N | Planned | LVP - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80819 | WBS.2.2.5.1.1.1.17 | N | N | Planned | EAI to turn off pulling gross production | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | RON MASON | RONMASON@GAPAC.COM | TED ZEIDLER;SAI TEAM;SUVENDU KUMAR;DEV TEAM;KELLY HINSON;WILL COLEMAN | TED.ZEIDLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM | DEV | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | INT | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90881 | WBS.2.2.5.1.1.1.19 | N | N | Planned | Turn on real time S4 gross production - notification service configuration | 0.25 | 2021-02-01 21:00 | 2021-02-01 21:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;DEAN PIPER;LYNN MCMURDO;RICK HOAGLAND;JAMES COWELL;JERRY (JT) THOMAS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;rick.hoagland@gapac.com ;James.Cowell@gapac.com;jerry.thomas@gapac.com | ICPAQS | 94919,94915,94917,94913 |  |  | * |  | 2021-02-01 21:00 | 2021-02-01 21:15 | ICPAQS | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96969 | WBS.2.2.5.1.1.1.58 | N | N | Planned | MC TASK - Create SAV Converting Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | LYDIA BOWERS | LYDIA.BOWERS@GAPAC.COM | PHILIP GAGLIA;KRISTIE PRESCOTT;SAI TEAM;DERRICK KESSLER;PAUL DICKERSON;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | PHILIP.GAGLIA@GAPAC.COM;KRISTIE.PRESCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VAN.Kessler@GAPAC.com;PAUL.DICKERSON@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97591,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97430 | WBS.2.2.5.1.1.1.134 | N | N | Planned | MC TASK - Create SAV Paper Machine Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | LYDIA BOWERS | LYDIA.BOWERS@GAPAC.COM | PHILIP GAGLIA;KRISTIE PRESCOTT;SAI TEAM;DERRICK KESSLER;PAUL DICKERSON;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | PHILIP.GAGLIA@GAPAC.COM;KRISTIE.PRESCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VAN.Kessler@GAPAC.com;PAUL.DICKERSON@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97591,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96967 | WBS.2.2.5.1.1.1.56 | N | N | Planned | MC TASK - Create PLT Converting Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | JEFF REVILLE | JEFFREY.REVILLE@GAPAC.COM | PAT HOLLAND;ERIK LANZER;TOM SHAVER;MELISSA OLSEN;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | Patrick.Holland@GAPAC.com;ERIK.LANZER@GAPAC.COM;THOMAS.SHAVER@gapac.com;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97589,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96965 | WBS.2.2.5.1.1.1.54 | N | N | Planned | MC TASK - Create GBB Converting Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | SUE MASTEY | SUSAN.MASTEY@GAPAC.COM | JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;CAMI BRATZ;ALYSHIA RASMUSSEN;MELISSA SAPULPA;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;CAMILLA.BRATZ@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;melissa.sapulpa@gapac.com ;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97592,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96963 | WBS.2.2.5.1.1.1.52 | N | N | Planned | MC TASK - Create GBD Converting Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | JOHN TILLEMAN;JOHN CASABURRI;SAI TEAM;FRANZ JURVA;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.TILLEMAN@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;FRANZ.JURVA@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97593,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96959 | WBS.2.2.5.1.1.1.48 | N | N | Planned | MC TASK - Create LVP Converting Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | ANDREW WARREN | ANDREW.WARREN@GAPAC.COM | SAMUEL CHAMBERS;KRISTEN MOLL;JOHN CASABURRI;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | SAMUEL.CHAMBERS@GAPAC.COM;KLMOLL@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97595,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96957 | WBS.2.2.5.1.1.1.46 | N | N | Planned | SAV -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 95591 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96956 | WBS.2.2.5.1.1.1.45 | N | N | Planned | SAV - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96957 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | SAV | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96955 | WBS.2.2.5.1.1.1.44 | N | N | Planned | PLT -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 95592,90616 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96954 | WBS.2.2.5.1.1.1.43 | N | N | Planned | PLT - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96955,90616 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96953 | WBS.2.2.5.1.1.1.42 | N | N | Planned | GBB -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96620 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96952 | WBS.2.2.5.1.1.1.41 | N | N | Planned | GBB - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96953 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96951 | WBS.2.2.5.1.1.1.40 | N | N | Planned | GBD -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96622 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96950 | WBS.2.2.5.1.1.1.39 | N | N | Planned | GBD - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96951 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96949 | WBS.2.2.5.1.1.1.38 | N | N | Planned | GBP -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;MELISSA KOTAREK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | ICPAQS | 96624 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96948 | WBS.2.2.5.1.1.1.37 | N | N | Planned | GBP - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;MELISSA KOTAREK | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM | ICPAQS | 96949 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97736 | WBS.2.2.5.1.1.1.202 | N | N | Planned | GBP - Communicate when to start manual parts and work tracking processes | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | MATT WENDRICKS | MATT.WENDRICKS@GAPAC.COM | MARK WILINSKI;MELISSA KOTAREK;SAI TEAM | Mark.Wilinski@GAPAC.com;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | AC | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97737 | WBS.2.2.5.1.1.1.203 | N | N | Planned | GBP - Stop Manual AC Processes and complete catch-up transactions | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | MATT WENDRICKS | MATT.WENDRICKS@GAPAC.COM | MARK WILINSKI;MELISSA KOTAREK;SAI TEAM | Mark.Wilinski@GAPAC.com;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | AC | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97738 | WBS.2.2.5.1.1.1.204 | N | N | Planned | GBP- Communicate to converting 1 hour warning for assets coming back up | 0.25 | 2021-01-31 18:00 | 2021-01-31 18:15 | GREGG GENTILE | GREGG.GENTILE@GAPAC.COM | JEREMY HEYDEN;MELISSA KOTAREK;SAI TEAM | JEREMY.HEYDEN@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 90653 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 18:15 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97739 | WBS.2.2.5.1.1.1.205 | N | N | Planned | GBP- Communicate to converting to start bringing assets up | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | GREGG GENTILE | GREGG.GENTILE@GAPAC.COM | JEREMY HEYDEN;MELISSA KOTAREK;SAI TEAM | JEREMY.HEYDEN@GAPAC.COM;MELISSA.KOTAREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | ICPAQS | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | EWM | GBP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96947 | WBS.2.2.5.1.1.1.36 | N | N | Planned | LVP -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96626 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96946 | WBS.2.2.5.1.1.1.35 | N | N | Planned | LVP - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 96947 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | LVP | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97370 | WBS.2.2.5.1.1.1.133 | N | N | Planned | MC TASK - Create GBD Paper Machine Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | TIM NOVOSELATZ | TIMOTHY.NOVOSELATZ@GAPAC.COM | JOHN TILLEMAN;JOHN CASABURRI;SAI TEAM;FRANZ JURVA;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.TILLEMAN@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;FRANZ.JURVA@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97593,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | GBD | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97368 | WBS.2.2.5.1.1.1.131 | N | N | Planned | MC TASK - Create GBB Paper Machine Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | Alyshia Rassmussen | Alyshia.Rasmussen@gapac.com | JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;CAMI BRATZ;ALYSHIA RASMUSSEN;MELISSA SAPULPA;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;CAMILLA.BRATZ@GAPAC.COM;ALYSHIA.RASMUSSEN@GAPAC.COM;melissa.sapulpa@gapac.com ;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97592,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97367 | WBS.2.2.5.1.1.1.130 | N | N | Planned | MC TASK - Create PLT Paper Machine Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | JEFF REVILLE | JEFFREY.REVILLE@GAPAC.COM | PAT HOLLAND;ERIK LANZER;TOM SHAVER;MELISSA OLSEN;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | Patrick.Holland@GAPAC.com;ERIK.LANZER@GAPAC.COM;THOMAS.SHAVER@gapac.com;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97589,97616 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97723 | WBS.2.2.5.1.1.1.197 | N | N | Planned | GBB - Communicate to Converting to Start-Up for FCW Production if Required | 0.25 | 2021-01-31 07:15 | 2021-01-31 07:30 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 36505,90476,94798 |  |  | * |  | 2021-01-31 07:15 | 2021-01-31 07:30 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97724 | WBS.2.2.5.1.1.1.198 | N | N | Planned | GBB - Start Task - Track any movements of FG's/RM/PR | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97725 | WBS.2.2.5.1.1.1.199 | N | N | Planned | GBB - Start Task - Record inbound/outbound Freight by using business continuity form - S2P | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | MIKE DEPREZ | MICHAEL.DEPREZ@GAPAC.COM | PATRICK RIETZ;SAI TEAM;KIM VANWYCHEN;EWM TEAM;MELISSA SAPULPA | PATRICK.RIETZ@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;melissa.sapulpa@gapac.com | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EWM | GBB | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97727 | WBS.2.2.5.1.1.1.201 | N | N | Planned | GBB - Validate PR and Vital Consumption from ICPAQ's to S4/EWM | 0.25 | 2021-02-01 20:45 | 2021-02-01 21:00 | PATRICK RIETZ | PATRICK.RIETZ@GAPAC.COM | MIKE DEPREZ;JOHN CASABURRI;SAI TEAM;KIM VANWYCHEN;EWM TEAM | MICHAEL.DEPREZ@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 90616,90412,94483,94513,94480,94781,94554 |  |  | * |  | 2021-02-01 20:45 | 2021-02-01 21:00 | EWM | GBB | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91004 | WBS.2.2.5.1.2 | N | N |  | FCW ¦ Pre-Conversions Activity - E80 | 50 | 2021-01-31 01:15 | 2021-02-02 03:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 20:30 |  |  | 2021-02-02 | 2021-02-01 | 3 | Shutdown
90510 | WBS.2.2.5.1.2.1 | N | N |  | FCW ¦ Pre-Conversions Activity - E80 - Transition Server, LGV Prep & Catch-Up Transaction Prep | 50 | 2021-01-31 01:15 | 2021-02-02 03:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 20:30 |  |  | 2021-02-02 | 2021-02-01 | 3 | Shutdown
94864 | WBS.2.2.5.1.2.1.1 | N | N | Planned | Prod Only - Verify LGV missions complete and which LGV's are out of system prior to shutting down E80 | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | E80 | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94859 | WBS.2.2.5.1.2.1.4 | N | N | Planned | Prod Only - Block positions in E80 storage to quarantine cutover production | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | E80 | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94861 | WBS.2.2.5.1.2.1.3 | N | N | Planned | Prod Only - Insure Client and SMART access is available on terminal server | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | E80 | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94863 | WBS.2.2.5.1.2.1.5 | N | N | Planned | Prod Only - Extract for inventory for Port Hudson Mill from E80 system - Send to EWM team for loading in SAP | 1 | 2021-01-31 01:30 | 2021-01-31 02:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 94859 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:30 | E80 | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92709 | WBS.2.2.5.1.2.1.7 | N | N | Planned | Restore DB to Live Server | 2 | 2021-01-31 04:00 | 2021-01-31 06:00 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 90479 |  |  | * |  | 2021-01-31 04:00 | 2021-01-31 06:00 | E80 | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90478 | WBS.2.2.5.1.2.1.8 | N | N | Planned | Prod Only - Validate the E80 server code fro PTH systems | 0.5 | 2021-01-31 06:00 | 2021-01-31 06:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 92709 |  |  | * |  | 2021-01-31 06:00 | 2021-01-31 06:30 | E80 | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90477 | WBS.2.2.5.1.2.1.9 | N | N | Planned | *Prod Only* - PTH - Verify Communication between Live Server and Applications from E80 Server | 0.25 | 2021-01-31 06:30 | 2021-01-31 06:45 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 90478 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 06:45 | E80 | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94862 | WBS.2.2.5.1.2.1.10 | N | N | Planned | Prod Only - Apply Programming Changes to Live Servers for PTH | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 94863 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | E80 | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94991 | WBS.2.2.5.1.2.1.11 | N | N | Planned | Prod Only - Apply Programming Changes to Live Servers for RVG | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 94863 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97638 | WBS.2.2.5.1.2.1.29 | N | N | Planned | Prod Only - Restart E80 servers for RVG | 0.5 | 2021-01-31 03:30 | 2021-01-31 04:00 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 94991 |  |  | * |  | 2021-01-31 03:30 | 2021-01-31 04:00 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97639 | WBS.2.2.5.1.2.1.30 | N | N | Planned | Prod Only - Validate the E80 server code for RVG systems | 0.25 | 2021-01-31 04:00 | 2021-01-31 04:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 97638 |  |  | * |  | 2021-01-31 04:00 | 2021-01-31 04:15 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97640 | WBS.2.2.5.1.2.1.31 | N | N | Planned | *Prod Only* - RVG - Verify Communication between Live Server and Applications from E80 Server | 0.25 | 2021-01-31 04:15 | 2021-01-31 04:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 97639 |  |  | * |  | 2021-01-31 04:15 | 2021-01-31 04:30 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97641 | WBS.2.2.5.1.2.1.32 | N | N | Planned | Prod Only - RVG - Smoke Test LGVs | 0.5 | 2021-01-31 04:30 | 2021-01-31 05:00 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 97640 |  |  | * |  | 2021-01-31 04:30 | 2021-01-31 05:00 | E80 | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90479 | WBS.2.2.5.1.2.1.12 | N | N | Planned | Prod Only - Restart E80 servers for PTH | 0.5 | 2021-01-31 03:30 | 2021-01-31 04:00 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 94991 |  |  | * |  | 2021-01-31 03:30 | 2021-01-31 04:00 | E80 | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90476 | WBS.2.2.5.1.2.1.16 | N | N | Planned | Prod Only - PTH - Smoke Test LGVs | 0.5 | 2021-01-31 06:45 | 2021-01-31 07:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 90477 |  |  | * |  | 2021-01-31 06:45 | 2021-01-31 07:15 | E80 | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90474 | WBS.2.2.5.1.2.1.19 | N | N | Planned | Prod Only - PTH - Turn on LGVs to begin Receiving/Shipping, PR, and Vitals Missions | 0.25 | 2021-01-31 07:15 | 2021-01-31 07:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 90476 |  |  | * |  | 2021-01-31 07:15 | 2021-01-31 07:30 | E80 | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92711 | WBS.2.2.5.1.2.1.20 | N | N | Planned | *Prod Only* - Insure Client and SMART access is available on terminal server | 0.5 | 2021-01-31 06:45 | 2021-01-31 07:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 90477 |  |  | * |  | 2021-01-31 06:45 | 2021-01-31 07:15 | E80 | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92710 | WBS.2.2.5.1.2.1.21 | N | N | Planned | Validate Production Material as production lines start back up | 0.25 | 2021-01-31 07:15 | 2021-01-31 07:30 | WILL LONG | WILLIAM.Long@GAPAC.com | DERRICK KESSLER;EWM TEAM;SAI TEAM | VAN.Kessler@GAPAC.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 92711 |  |  | * |  | 2021-01-31 07:15 | 2021-01-31 07:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90877 | WBS.2.2.5.1.2.1.22 | N | N | Planned | Start All D4 Channels | 1 | 2021-02-01 19:30 | 2021-02-01 20:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | ANKIT SONI;BRIAN DOBASH;SANDEEP THARWANI;DON ABBOTT;SUVENDU KUMAR;SAI TEAM;DEV TEAM;PAYEL GHOSH;ARUN GANGADHARAN;RAKESH MAKKAPATI;TED ZEIDLER | ANKISONI@DELOITTE.COM;BJDOBASH@GAPAC.COM;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;PAYGHOSH@DELOITTE.COM;ARGANGADHARAN@DELOITTE.COM;RMAKKAPATI@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DEV | 94561,94563 |  |  | * |  | 2021-02-01 19:30 | 2021-02-01 20:30 | INT | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95516 | WBS.2.2.5.1.2.1.23 | N | N | Planned | PTH - Communicate to Converting to Start-Up for FCW Production if Required | 0.25 | 2021-01-31 07:15 | 2021-01-31 07:30 | CJ KAUTH | christopher.kauth@gapac.com | JAMES COWELL;SAI TEAM | James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,90476,94798 |  |  | * |  | 2021-01-31 07:15 | 2021-01-31 07:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93843 | WBS.2.2.5.1.2.1.25 | N | N | Planned | HBG - Communicate to Converting Lines to Start Up for Dark Production | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93865,36505,94798 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95580 | WBS.2.2.5.1.2.1.27 | N | N | Planned | PLT - Communicate to Converting to Start-Up for production after start of FCW | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | ERIK LANZER | ERIK.LANZER@GAPAC.COM | JEFF REVILLE;PAT HOLLAND;SAI TEAM;EWM TEAM | JEFFREY.REVILLE@GAPAC.COM;Patrick.Holland@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 36505,94798 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | EWM | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97835 | WBS.2.2.5.1.2.1.33 | N | N | Planned | PTH - Convert E80 Extract to ISU Format | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | AVINASH TALREJA;SAI TEAM;EWM TEAM;MITCH DEATON;CHRIS ZUMWALT;SANTOSH KUPPILI;GLEN RICHARDSON | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;VKUPPILI@DELOITTE.COM;GLEN.RICHARDSON@GAPAC.COM | EWM | 94863 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97841 | WBS.2.2.5.1.2.1.39 | N | N | Planned | PTH - 4Sight - Verify YMS Data and Functions | 1 | 2021-02-02 02:15 | 2021-02-02 03:15 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 97809 |  |  | * |  | 2021-02-02 02:15 | 2021-02-02 03:15 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97842 | WBS.2.2.5.1.2.1.40 | N | N | Planned | PTH - Spot any trailers located at dock doors | 0.5 | 2021-01-31 22:30 | 2021-01-31 23:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;KATIE PARKER;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;Katie.Parker@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 94331 |  |  | * |  | 2021-01-31 22:30 | 2021-01-31 23:00 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97844 | WBS.2.2.5.1.2.1.42 | N | N | Planned | PTH - 4Sight - Have Drivers perform spotter drive bys to update trailer locations in the Yard | 1 | 2021-02-01 20:00 | 2021-02-01 21:00 | BILL BROUGHTON | Bill.Broughton@4FrontES.com | SUJATHA KANNAN;MURALIDHAR KELLA;GRACE BALDASSARRE;EWM TEAM;SAI TEAM | SUJATHA.KANNAN@4FrontES.com;Muralidhar.Kella@4frontes.com;Grace.Baldassarre@4FrontES.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 21:00 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91006 | WBS.2.2.6 | N | N |  | FCW ¦ Multi-Team Plan Activities | 54.5 | 2021-01-31 01:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
89826 | WBS.2.2.6.1 | N | N |  | FCW ¦ Multi-Team Plan Activities | 54.5 | 2021-01-31 01:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90945 | WBS.2.2.6.1.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - Data | 44.25 | 2021-01-31 01:15 | 2021-02-01 21:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91720 | WBS.2.2.6.1.1.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - Data | 44.25 | 2021-01-31 01:15 | 2021-02-01 21:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 21:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92169 | WBS.2.2.6.1.1.1.1 | N | N | Planned | Turn OFF DRFOUT in MDG for all Material Updates | 0.25 | 2021-01-31 10:30 | 2021-01-31 10:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DATA | 91471,36505,92752,96892 |  |  | * |  | 2021-01-31 10:30 | 2021-01-31 10:45 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95767 | WBS.2.2.6.1.1.1.2 | N | N | Planned | Turn OFF job in S4 for MDG – S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL | 0.25 | 2021-01-31 10:30 | 2021-01-31 10:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;LSA TEAM;KESAVA BATTINA;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;KESAVAMANI.BATTINA@KOCHTC.COM;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 91471,36505,92752,96892 |  |  | * |  | 2021-01-31 10:30 | 2021-01-31 10:45 | BATCH | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95766 | WBS.2.2.6.1.1.1.3 | N | N | Planned | Turn ON job in S4 for MDG -S4 replication: S4_DATA_RBDSER04_MDGS4_MATERIAL | 0.25 | 2021-02-01 18:15 | 2021-02-01 18:30 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;AMY EL-BASSIONI;DATA ETL TEAM;SANDEEP THARWANI;DON ABBOTT;SAI TEAM;DEV TEAM;LINDSAY SAVAGE;COURTNEY ANDERSON;ARUN SHARMA;JON LUKE DAVILA;TED ZEIDLER;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;STHARWANI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;LINDSAY.SAVAGE@GAPAC.COM;COURTNEY.ANDERSON@GAPAC.COM;ARUN.SHARMA@GAPAC.COM;JONLUKE.DAVILA@GAPAC.COM;TED.ZEIDLER@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 90894,90895,90896 |  |  | * |  | 2021-02-01 18:15 | 2021-02-01 18:30 | BATCH | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90038 | WBS.2.2.6.1.1.1.4 | N | N | Planned | Update materials that have LGORT 9999 in each deployment for new live sites | 3 | 2021-01-31 10:45 | 2021-01-31 13:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 92169,36505,92752,95767,96892 |  |  | * |  | 2021-01-31 10:45 | 2021-01-31 13:45 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90068 | WBS.2.2.6.1.1.1.5 | N | N | Planned | Update materials that have Production SLOC (LGPRO) and EP SLOC (LGFSB) 9999 in each deployment for new live sites | 3.5 | 2021-01-31 13:45 | 2021-01-31 17:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 91471,92169,36505,92752,95767,90038,96892 |  |  | * |  | 2021-01-31 13:45 | 2021-01-31 17:15 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97704 | WBS.2.2.6.1.1.1.16 | N | N | Planned | WM Team to provide list of Port Hudson materials that need Loading Group updated to 0009 Diamond | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | CJ KAUTH | christopher.kauth@gapac.com | MICHAEL MATTHEWS;SAI TEAM | MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97705 | WBS.2.2.6.1.1.1.17 | N | N | Planned | MDG Team to update Loading Group to 0009 Diamond for the list of materials provided by WM | 0.5 | 2021-01-31 17:15 | 2021-01-31 17:45 | JIM KIJEK | JEKIJEK@GAPAC.COM | DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 97704,90068 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:45 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97706 | WBS.2.2.6.1.1.1.18 | N | N | Planned | SCM Team to identify and update open STO’s relevant for shipping from E80 Diamond line (A034 Shipping Point) | 1.5 | 2021-01-31 17:45 | 2021-01-31 19:15 | TWANDA JENNINGS | TDJENNIN@GAPAC.com | THEASUS PAUL;MICHELLE SADLER;SAI TEAM;AQUIL HUSAIN;CAROLYN THOMPKINS | TTPAUL@GAPAC.COM;BMSADLER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;CSTHOMPK@gapac.com | SCM | 92322,97705 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 19:15 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90851 | WBS.2.2.6.1.1.1.6 | N | N | Planned | Update Frozen Horizon for deployment live sites Materials | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | SHANKAR RAMNARAYANAN;DENISE ROBINSON;SAI TEAM;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 92236,91471,92169,36505,92752,95767,90038,90068,96892 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94725 | WBS.2.2.6.1.1.1.7 | N | N | Planned | Flag SLOC 9999 for deletion for materials at New Live Sites in each deployment | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | JIM KIJEK | JEKIJEK@GAPAC.COM | DENISE ROBINSON;DON ABBOTT;SAI TEAM;DATA ETL TEAM | DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 90038,90068 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90893 | WBS.2.2.6.1.1.1.8 | N | N | Planned | Review DQ report and Update material order UOM/AUOM in MDG needed for PO conversion | 1 | 2021-01-31 19:00 | 2021-01-31 20:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;SAI TEAM;JON PINYON;DATA ETL TEAM;SHANKAR RAMNARAYANAN | DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM | DATA | 90892,91850,92169,95767 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 20:00 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90894 | WBS.2.2.6.1.1.1.9 | N | N | Planned | Replicate materials with Order UOM updates from MDG to S4 for PO conversion | 0.5 | 2021-01-31 20:00 | 2021-01-31 20:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SHANKAR RAMNARAYANAN;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90893 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:30 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90147 | WBS.2.2.6.1.1.1.10 | N | N | Planned | Replicate materials with EP/Production SLOC & Frozen Horizon updates from MDG to S4 & Also replicate the loading group changes | 3 | 2021-01-31 19:15 | 2021-01-31 22:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;JIM KIJEK;DENISE ROBINSON;DON ABBOTT;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JEKIJEK@GAPAC.COM;DOROBINS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90038,90068,90851,92742,94725,97705 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 22:15 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90895 | WBS.2.2.6.1.1.1.11 | N | N | Planned | Revert Order UOM and AUOM updates in MDG after PO conversion | 1 | 2021-02-01 12:15 | 2021-02-01 13:15 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE ROBINSON;SAI TEAM;JON PINYON;DATA ETL TEAM;SHANKAR RAMNARAYANAN | DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JWPINYON@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM | DATA | 5696,82652,92169,95767 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 13:15 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90896 | WBS.2.2.6.1.1.1.12 | N | N | Planned | Replicate materials after reverting order UOM and AUOM updates from MDG to S4 | 5 | 2021-02-01 13:15 | 2021-02-01 18:15 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SHANKAR RAMNARAYANAN;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SRAMNARAYANAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 90895 |  |  | * |  | 2021-02-01 13:15 | 2021-02-01 18:15 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92172 | WBS.2.2.6.1.1.1.13 | N | N | Planned | Turn ON DRFOUT in MDG after All Material Updates | 0.25 | 2021-02-01 18:15 | 2021-02-01 18:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | COURTNEY ANDERSON;SANDEEP THARWANI;SUVENDU KUMAR;BRIAN DOBASH;NAVJOT SHARMA;DATA ETL TEAM;DON ABBOTT;SAI TEAM;TED ZEIDLER | COURTNEY.ANDERSON@GAPAC.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM | DATA | 90894,90895,90896 |  |  | * |  | 2021-02-01 18:15 | 2021-02-01 18:30 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92396 | WBS.2.2.6.1.1.1.14 | N | N | Planned | Check for Material Change Requests and Manually Updated Materials that may not have Replicated Downstream | 1 | 2021-02-01 18:30 | 2021-02-01 19:30 | SHANKAR RAMNARAYANAN | SRAMNARAYANAN@DELOITTE.COM | PHANI GHANTASALA;DENISE ROBINSON;DATA ETL TEAM;SAI TEAM;COURTNEY ANDERSON | PGHANTASALA@DELOITTE.COM;DOROBINS@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;COURTNEY.ANDERSON@GAPAC.COM | DATA | 92172,95766 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 19:30 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92397 | WBS.2.2.6.1.1.1.15 | N | N | Planned | Push materials out from S/4 to Downstream Systems | 2 | 2021-02-01 19:30 | 2021-02-01 21:30 | TED ZEIDLER | TED.ZEIDLER@GAPAC.COM | SUVENDU KUMAR;SANDEEP THARWANI;RAMYA IYER;ANKIT SONI;SAI TEAM;BRIAN DOBASH;DEV TEAM | SUVKUMAR@DELOITTE.COM;STHARWANI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;ANKISONI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BJDOBASH@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 92396 |  |  | * |  | 2021-02-01 19:30 | 2021-02-01 21:30 | DEV | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92517 | WBS.2.2.6.1.2 | N | N |  | FCW ¦ Multi-Team Plan Activities - RTR | 11.25 | 2021-01-31 17:15 | 2021-02-01 04:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-01 04:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92516 | WBS.2.2.6.1.2.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - RTR | 11.25 | 2021-01-31 17:15 | 2021-02-01 04:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-01 04:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97618 | WBS.2.2.6.1.2.1.24 | N | N | Planned | PTH-Load standard prices for SFG in Plant 1034 AND SEND successful load data to plant accounting | 0.25 | 2021-01-31 20:30 | 2021-01-31 20:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | NOEL CLARK;SANDRA RICHARDS;SAI TEAM;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90499 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 20:45 | RTR - PC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97619 | WBS.2.2.6.1.2.1.25 | N | N | Planned | BG-Load standard prices for SFG in Plant 1376 AND SEND successful load data to plant accounting | 0.25 | 2021-01-31 20:30 | 2021-01-31 20:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | NOEL CLARK;SANDRA RICHARDS;SAI TEAM;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96642 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 20:45 | RTR - PC | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97620 | WBS.2.2.6.1.2.1.26 | N | N | Planned | HBG-Load standard prices for SFG in Plant 1459 AND SEND successful load data to plant accounting | 0.25 | 2021-01-31 20:30 | 2021-01-31 20:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | NOEL CLARK;SANDRA RICHARDS;SAI TEAM;DONNA SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94952 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 20:45 | RTR - PC | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93716 | WBS.2.2.6.1.2.1.15 | N | N | Planned | HBG - Validate Standard Prices For 1459 - SFG Materials | 0.5 | 2021-01-31 20:45 | 2021-01-31 21:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 97620 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 21:15 | RTR - PC | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93138 | WBS.2.2.6.1.2.1.16 | N | N | Planned | PTH - Validate Standard Prices For 1034- SFG Materials | 1.5 | 2021-01-31 20:45 | 2021-01-31 22:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 97618 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 22:15 | RTR - PC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96565 | WBS.2.2.6.1.2.1.18 | N | N | Planned | BG - Validate Standard Prices For 1376 - SFG Materials | 1 | 2021-01-31 20:45 | 2021-01-31 21:45 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 97619 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 21:45 | RTR - PC | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
8935 | WBS.2.2.6.1.2.1.13 | N | N | Planned | RTR_E0201_Update of BRF+ (1. Utility materials – SKF, 2. Handling Unit – SKF, 3. Business category SKF) | 0.25 | 2021-01-31 18:30 | 2021-01-31 18:45 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | KRISHNA RAVI;KRISHNA SINGAREDDY;VISHNU CHIRALA;SAI TEAM;RTR TEAM;JACKIE ADAMS;RANJAI JOHN;BOATENG LAWRENCE | KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Jacqueline.Adams@GAPAC.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90647 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 18:45 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91804 | WBS.2.2.6.1.2.1.1 | N | N | Planned | RTR_E0201 - Validate - BRF+ Entries for Plants 1106,1104,1357,1462,1101,1503 | 1 | 2021-01-31 19:00 | 2021-01-31 20:00 | RACHEL BERTOLINO | RACHEL.BERTOLINO@GAPAC.COM | SANDRA RICHARDS;SAI TEAM;DONNA SMITH;NOEL CLARK;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92152,96904,97475 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 20:00 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93321 | WBS.2.2.6.1.2.1.4 | N | N | Planned | PTH - Validate moving average prices for ECC materials | 2 | 2021-02-01 01:30 | 2021-02-01 03:30 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 29571 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 03:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96631 | WBS.2.2.6.1.2.1.12 | N | N | Planned | BG-Validate moving average prices for ECC Procured materials | 3 | 2021-02-01 01:30 | 2021-02-01 04:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 29571 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 04:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93904 | WBS.2.2.6.1.2.1.6 | N | N | Planned | HBG -Validate moving average prices for ECC materials | 2 | 2021-02-01 01:30 | 2021-02-01 03:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 29571 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 03:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92184 | WBS.2.2.6.1.2.1.7 | N | N | Planned | Ink consignment materials at plants need to have MRP2 special procurement key to be 10 and stock determination group should have Z001 added, SLOC 4500 | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | VISHNU CHIRALA;RTR TEAM;SAI TEAM;KRISHNA SINGAREDDY;JIM KIJEK;DENISE ROBINSON;SHANKAR RAMNARAYANAN;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ksingareddy@deloitte.com;JEKIJEK@GAPAC.COM;DOROBINS@GAPAC.COM;SRAMNARAYANAN@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 90068 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95519 | WBS.2.2.6.1.2.1.9 | N | N | Planned | Open New posting period and validate for all S4 company codes | 0.25 | 2021-01-31 17:30 | 2021-01-31 17:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | VISHNU CHIRALA;SANDRA RICHARDS;RTR TEAM;SAI TEAM;BRETT DETTMERING;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36505,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 17:45 | RTR | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5798 | WBS.2.2.6.1.3 | N | N |  | FCW ¦ Multi-Team Plan Activities - Basis and Security | 53.5 | 2021-01-31 01:15 | 2021-02-02 06:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 06:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91722 | WBS.2.2.6.1.3.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - Basis and Security | 53.5 | 2021-01-31 01:15 | 2021-02-02 06:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 06:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
4507 | WBS.2.2.6.1.3.1.1 | N | N | Planned | MC Task - Validate Connections With GRC And HANA DB | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4502 | WBS.2.2.6.1.3.1.2 | N | N | Planned | Assign Access Manually To Systems Which Auto-Provisioning Is Not Possible | 2 | 2021-02-01 08:00 | 2021-02-01 10:00 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4501,82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 10:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4505 | WBS.2.2.6.1.3.1.3 | N | N | Planned | Validate profiles are generated and transport ungenerated profiles if needed | 2 | 2021-02-01 08:00 | 2021-02-01 10:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 10:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4506 | WBS.2.2.6.1.3.1.4 | N | N | Planned | User Comparison | 2 | 2021-02-01 08:00 | 2021-02-01 10:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 10:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4508 | WBS.2.2.6.1.3.1.5 | N | N | Planned | Remove SAP_ALL If Assigned | 2 | 2021-02-01 10:00 | 2021-02-01 12:00 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4502 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 12:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4503 | WBS.2.2.6.1.3.1.6 | N | N | Planned | Prod Task - Execute Role Risk Analysis And Assign Mitigating Controls At Role Level | 8 | 2021-02-01 10:00 | 2021-02-01 18:00 | JEFF GRICE | JEFFREY.GRICE@GAPAC.COM | ANTHONY GORDON;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;SEC TEAM | ADGORDON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4502 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 18:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4504 | WBS.2.2.6.1.3.1.7 | N | N | Planned | Prod Task - Execute User Risk Analysis And Assign Mitigating Controls At User Level | 8 | 2021-02-01 18:00 | 2021-02-02 02:00 | JEFF GRICE | JEFFREY.GRICE@GAPAC.COM | ANTHONY GORDON;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;SEC TEAM | ADGORDON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4503 |  |  | * |  | 2021-02-01 18:00 | 2021-02-02 02:00 | SECURITY | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
37013 | WBS.2.2.6.1.3.1.9 | N | N | Planned | MC Task ¦ Set User Authentication To Users In BOBJ (WEBI and AFO) | 1 | 2021-02-01 08:00 | 2021-02-01 09:00 | ANTHONY GORDON | ADGORDON@GAPAC.COM | GREG CAPPS;SAI TEAM;CARLOS ROBELO TEJADA;SEC TEAM | GREG.CAPPS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4501,82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 09:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82749 | WBS.2.2.6.1.3.1.10 | N | N | Planned | Provide S/4HANA Production Access To Business Users - With Respective Business Roles | 6 | 2021-02-01 02:00 | 2021-02-01 08:00 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4500,4294,4326,93399,93404 |  |  | * |  | 2021-02-01 02:00 | 2021-02-01 08:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
37014 | WBS.2.2.6.1.3.1.12 | N | N | Planned | Load Users To ARIBA Realms | 4 | 2021-02-01 08:00 | 2021-02-01 12:00 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | CARLOS ROBELO TEJADA;SOUMYA PANDA;SAI TEAM;ANTHONY GORDON;SEC TEAM | CROBELOTEJADA@DELOITTE.COM;SOPANDA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 4501,4500,82749 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 12:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5799 | WBS.2.2.6.1.3.1.15 | N | N | Planned | Switch to operation mode "NORMAL" in MDG system | 0.5 | 2021-02-02 01:00 | 2021-02-02 01:30 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5690,5696,10030,5701,9660,9698,5763,5768,36505,94289,94331,96652,96751,96752,97524,97530,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 01:30 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5794 | WBS.2.2.6.1.3.1.16 | N | N | Planned | Switch to operation mode "NORMAL" in S/4HANA system | 0.5 | 2021-02-02 01:00 | 2021-02-02 01:33 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5690,5696,10030,5701,9660,9698,5763,5768,36505,94289,94331,96652,96751,96752,97524,97530,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 01:33 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5789 | WBS.2.2.6.1.3.1.17 | N | N | Planned | Backup S/4 HANA system - Post data load | 2.5 | 2021-02-02 01:00 | 2021-02-02 03:30 | SRINIVAS KAKUTURU | SKAKUTURU@DELOITTE.COM | US GP BASIS;SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;DEV TEAM | USGPBASIS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5690,5696,10030,5701,9660,9698,5763,5768,36505,94289,94331,96652,96751,96752,97524,97530,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 05:00 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5790 | WBS.2.2.6.1.3.1.18 | N | N | Planned | Backup MDG system - Post data load | 2 | 2021-02-02 01:00 | 2021-02-02 03:00 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;RICHARD HOWARD;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RLHOWARD@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5690,5696,10030,5701,9660,9698,5763,5768,36505,94289,94331,96652,96751,96752,97524,97530,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 03:00 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5825 | WBS.2.2.6.1.3.1.19 | N | N | Planned | Confirm all clients closed for manual configuration | 0.5 | 2021-02-02 01:30 | 2021-02-02 02:00 | PRASHANTH TUMMALA | PTUMMALA@DELOITTE.COM | SAI TEAM;DANI SIMMONS;NAVJOT SHARMA;BRIAN DOBASH;US GP BASIS;SUVENDU KUMAR;TED ZEIDLER;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DWSIMMON@GAPAC.COM;NASHARMA@DELOITTE.COM;BJDOBASH@GAPAC.COM;USGPBASIS@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;TED.ZEIDLER@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 5799 |  |  | * |  | 2021-02-02 01:30 | 2021-02-02 02:00 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
4430 | WBS.2.2.6.1.3.1.20 | N | N | Planned | Disable Super User IDs like DDIC and SAP* | 1 | 2021-02-01 20:00 | 2021-02-01 21:00 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | SAI TEAM;GREG CAPPS;SOUMYA PANDA;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 5833,36505,95152,95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 21:00 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93407 | WBS.2.2.6.1.3.1.21 | N | N | Planned | Prod/ UAT Task - SAI provides list of approved FF & SWAT team users | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | SAI | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93406 | WBS.2.2.6.1.3.1.22 | N | N | Planned | Security to provision FF Users in the system | 4 | 2021-01-31 17:30 | 2021-01-31 21:30 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | PALLAVI YELLAYI;SAI TEAM;GREG CAPPS;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM;SOUMYA PANDA | PYELLAYI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;SOPANDA@DELOITTE.COM | SECURITY | 93407,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 21:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95426 | WBS.2.2.6.1.3.1.23 | N | N | Planned | Unlock SCH users | 0.5 | 2021-02-01 18:16 | 2021-02-01 18:46 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM;JEREMY RAY;TOMMY NEFFENDORF | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | SECURITY | 82749,92995,92996 |  |  | * |  | 2021-02-01 18:16 | 2021-02-01 18:46 | SECURITY | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96763 | WBS.2.2.6.1.3.1.30 | N | N | Planned | Unlock RVG users | 0.5 | 2021-02-01 18:15 | 2021-02-01 18:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM;JENNIFER MCLEOD;JULI LEWIS | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | SECURITY | 82749,96379,96380,96528 |  |  | * |  | 2021-02-01 18:15 | 2021-02-01 18:45 | SECURITY | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96764 | WBS.2.2.6.1.3.1.31 | N | N | Planned | Unlock RNC users | 0.5 | 2021-02-01 18:15 | 2021-02-01 18:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM;JEREMY RAY;TOMMY NEFFENDORF | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | SECURITY | 82749,96383,96384 |  |  | * |  | 2021-02-01 18:15 | 2021-02-01 18:45 | SECURITY | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95425 | WBS.2.2.6.1.3.1.24 | N | N | Planned | Unlock PTH users | 0.5 | 2021-02-02 06:15 | 2021-02-02 06:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 82749,93344,93340,93339 |  |  | * |  | 2021-02-02 06:15 | 2021-02-02 06:45 | SECURITY | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95423 | WBS.2.2.6.1.3.1.26 | N | N | Planned | Unlock HBG users | 0.5 | 2021-02-02 01:15 | 2021-02-02 01:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 82749,93933,93932,95217 |  |  | * |  | 2021-02-02 01:15 | 2021-02-02 01:45 | SECURITY | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96632 | WBS.2.2.6.1.3.1.29 | N | N | Planned | Unlock BG users | 0.5 | 2021-02-02 02:15 | 2021-02-02 02:45 | KIRAN GANNAVARAPU | KGANNAVARAPU@DELOITTE.COM | ANTHONY GORDON;RYAN ORR;SWAMI RAJASEKAR;MELISSA OLSEN;MICHELLE AUSTIN-WILLARD;ANUPAM SHRIVASTAVA;CARLOS ROBELO TEJADA;DON ABBOTT;SAI TEAM;SEC TEAM;DEAN PIPER;LYNN MCMURDO | ADGORDON@GAPAC.COM;RDORR@GAPAC.COM;swaminath.rajasekar@kochgs.com ;MELISSA.OLSEN@GAPAC.COM;MICHELLE.AUSTIN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | SECURITY | 82749,96391 |  |  | * |  | 2021-02-02 02:15 | 2021-02-02 02:45 | SECURITY | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
83018 | WBS.2.2.6.1.3.1.28 | N | N | Planned | EDI - Remove SAP Down flag to open the gates | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | NAVEEN BODDU | NAVEEN.BODDU@KOCHTC.COM | DEV EDI TEAM;SAI TEAM;KELLY HINSON;GIRIJA SATPATHY;WILL COLEMAN;CYNTHIA LUBBERS | PATRICK.HERRING@GAPAC.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;IZKHAN@DELOITTE.COM;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM;CYNDI.HOTTENSTINE@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM;NAVEEN.BODDU@KOCHTC.COM;ABRADLEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;GIRIJA.SATPATHY@KOCHTC.COM;WCOLEMA@GAPAC.COM;CYNTHIA.LUBBERS@GAPAC.COM | EDI | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | EDI | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94616 | WBS.2.2.6.1.4 | N | N |  | FCW ¦ Multi-Team Plan Activities - EWM | 18 | 2021-01-31 01:15 | 2021-01-31 19:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 19:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94617 | WBS.2.2.6.1.4.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - EWM | 18 | 2021-01-31 01:15 | 2021-01-31 19:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 19:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94571 | WBS.2.2.6.1.4.1.1 | N | N | Planned | Provide EAI / Webmethods team with a list of all sites that may send D4 sites ASN data from Legacy systems | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94570 | WBS.2.2.6.1.4.1.2 | N | N | Planned | Setup parameters in Webmethods for D4 sites to receive ASN Data from Legacy sites | 1 | 2021-01-31 02:15 | 2021-01-31 03:15 | WILL COLEMAN | WCOLEMA@GAPAC.COM | SAI TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94571 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 03:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94567 | WBS.2.2.6.1.4.1.3 | N | N | Planned | Request Elixir team to setup D4 sites to receive ASN data from Elixir mills, so inbound deliveries can get created properly. | 1 | 2021-01-31 02:15 | 2021-01-31 03:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | SAI TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94571 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 03:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94568 | WBS.2.2.6.1.4.1.4 | N | N | Planned | Elixir team to setup D4 sites to receive ASN data from Elixir mills, so inbound deliveries can get created properly. | 1 | 2021-01-31 03:15 | 2021-01-31 04:15 | MINT VICKERY | MINT.VICKERY@GAPAC.COM | SAI TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94567 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 04:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94985 | WBS.2.2.6.1.4.1.11 | N | N | Planned | MFLE/MKLE - Update PPF condition records for warehouse task for parent roles and FG | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 4572,36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | EWM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90946 | WBS.2.2.6.1.5 | N | N |  | FCW ¦ Multi-Team Plan Activities - PTP | 33 | 2021-01-31 01:15 | 2021-02-01 10:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 10:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91723 | WBS.2.2.6.1.5.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - PTP | 33 | 2021-01-31 01:15 | 2021-02-01 10:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 10:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90892 | WBS.2.2.6.1.5.1.1 | N | N | Planned | Provide list of materials and order UOM's and conversion factors that need updates | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | DOROTHY RUSSELL;CASEY HERMANSEN;MIKE PUPILLO;DATA ETL TEAM;PTP TEAM;AMY EL-BASSIONI;YUDHAJIT MITRA;SAI TEAM;SHRISH MUDRI;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;MAPUPILL@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92743 | WBS.2.2.6.1.5.1.2 | N | N | Planned | Send report of all open STO's and PO's with sloc 9999 for sites being deployed (ME2n) | 1 | 2021-01-31 17:00 | 2021-01-31 18:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 18:00 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97449 | WBS.2.2.6.1.5.1.7 | N | N | Planned | Review all intercompany and ERS POs being converted to ensure the ERS and GR based IV indicators are flagged | 2 | 2021-02-01 08:15 | 2021-02-01 10:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;PTP TEAM;MIKE PUPILLO | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MAPUPILL@GAPAC.COM | PTP | 10852,5695 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 10:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94767 | WBS.2.2.6.1.6 | N | N |  | FCW ¦ Multi-Team Plan Activities - BATCH | 22.74 | 2021-02-01 09:01 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 09:01 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94768 | WBS.2.2.6.1.6.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - BATCH | 22.74 | 2021-02-01 09:01 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 09:01 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
92740 | WBS.2.2.6.1.6.1.1 | N | N | Planned | PTH - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 16:15 | 2021-02-01 17:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 90412,94781,93327 |  |  | * |  | 2021-02-01 16:15 | 2021-02-01 17:15 | BATCH | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95466 | WBS.2.2.6.1.6.1.3 | N | N | Planned | HBG - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 14:00 | 2021-02-01 15:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 93916,95282 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 15:00 | BATCH | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96633 | WBS.2.2.6.1.6.1.7 | N | N | Planned | BG - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 15:15 | 2021-02-01 16:15 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96478,96477 |  |  | * |  | 2021-02-01 15:15 | 2021-02-01 16:15 | BATCH | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95468 | WBS.2.2.6.1.6.1.5 | N | N | Planned | Run EWM FCW Batch Jobs After Gate 4 | 1 | 2021-02-02 03:45 | 2021-02-02 04:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 95119,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:45 | BATCH | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97154 | WBS.2.2.6.1.6.1.27 | N | N | Planned | PTH - Validate and sign off that 4Sight and Elixir are matching | 1 | 2021-02-02 06:45 | 2021-02-02 07:45 | CJ KAUTH | christopher.kauth@gapac.com | ROBBIE GARNER;KATIE PARKER;JAMES COWELL;SAI TEAM | Robbie.Garner2@gapac.com;Katie.Parker@gapac.com;James.Cowell@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 95425 |  |  | * |  | 2021-02-02 06:45 | 2021-02-02 07:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95465 | WBS.2.2.6.1.6.1.6 | N | N | Planned | SCH - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 09:01 | 2021-02-01 10:01 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 95197 |  |  | * |  | 2021-02-01 09:01 | 2021-02-01 10:01 | BATCH | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5793 | WBS.2.2.6.1.7 | N | N |  | FCW ¦ Multi-Team Plan Activities - LSA | 39.75 | 2021-01-31 01:15 | 2021-02-01 17:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 17:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91724 | WBS.2.2.6.1.7.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - LSA | 39.75 | 2021-01-31 01:15 | 2021-02-01 17:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 17:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97160 | WBS.2.2.6.1.7.1.19 | N | N | Planned | Communication to Converting Operators: PTH - Communication to Operators to start the new production S4 order/run | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | JERRY THOMAS | Jerry.Thomas2@gapac.com | JOHN CASABURRI;SAI TEAM;CJ KAUTH;ROBBIE GARNER;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 94798,94893,92262 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | ICPAQS OPERATIONS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96713 | WBS.2.2.6.1.7.1.7 | N | N | Planned | RNC - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96716 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | BATCH | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96714 | WBS.2.2.6.1.7.1.8 | N | N | Planned | RVG - Run EWM FCW Batch Jobs After Milestone 2 | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;JENNIFER MCLEOD;JULI LEWIS;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 96718 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | BATCH | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92576 | WBS.2.2.6.1.7.1.1 | N | N | Planned | Process ECC status 64 interim collected idocs 2 times. DESADV, ZMBGMCR, SHPMNT, ZPHYINVINT | 2 | 2021-01-31 19:15 | 2021-01-31 21:15 | SWAMI RAJASEKAR | swaminath.rajasekar@kochgs.com | GUNEET ARORA;BRIAN DOBASH;SAI TEAM;LSA TEAM;TED ZEIDLER | GUNEARORA@DELOITTE.COM;BJDOBASH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;TED.ZEIDLER@GAPAC.COM | LSA | 36505,95429,90653,95519,96904,97475 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 21:15 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92577 | WBS.2.2.6.1.7.1.2 | N | N | Planned | Set ECC partner profile S4PCLNT100 interim outbound interfaces to process immediately. DESADV, SHPMNT, ZMBGMCR, ZPHYINVINT | 0.25 | 2021-01-31 21:15 | 2021-01-31 21:30 | SWAMI RAJASEKAR | swaminath.rajasekar@kochgs.com | GUNEET ARORA;BRIAN DOBASH;SAI TEAM;LSA TEAM;TED ZEIDLER | GUNEARORA@DELOITTE.COM;BJDOBASH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;TED.ZEIDLER@GAPAC.COM | LSA | 92576 |  |  | * |  | 2021-01-31 21:15 | 2021-01-31 21:30 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94608 | WBS.2.2.6.1.7.1.3 | N | N | Planned | BG - DixieIT - PTM_I0271 - Point PendingTransactionsDisplay.exe to S4 instance/Test Communication | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | JOHN WHITE | JOHN.WHITE@GAPAC.COM | LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;DORESA WARD;MINT VICKERY | MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM | LSA | 96797 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | LSA | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94609 | WBS.2.2.6.1.7.1.4 | N | N | Planned | BG - DixieIT - PTM_I0270 - Point “LpnUploaderWinService.exe” to ICPAQS/Test Communication - send 1 Pilot LPN. | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | JOHN WHITE | JOHN.WHITE@GAPAC.COM | LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;DORESA WARD;MINT VICKERY | MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 96593,96598,97852 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | ICPAQS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96634 | WBS.2.2.6.1.7.1.6 | N | N | Planned | BG - DixieIT - Action - Turn on BG to ICPAQS Finshed Goods Integration - Set WinService_ActivityState to true from false. | 0.25 | 2021-01-31 03:45 | 2021-01-31 04:00 | JOHN WHITE | JOHN.WHITE@GAPAC.COM | LSA TEAM;SAI TEAM;SUSAN RIELS;TODD DAKINS;DEAN PIPER;LYNN MCMURDO;DORESA WARD;MINT VICKERY | MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94609 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 04:00 | ICPAQS | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97011 | WBS.2.2.6.1.7.1.11 | N | N | Planned | Update On AWS DynamoDb table “GP_TTN_CcsToWms_Queue" | 0.25 | 2021-01-31 19:30 | 2021-01-31 19:45 | ZAC HAMILTON | Zac.Hamilton@GAPAC.com | TISHA WEST;MAMIE TREZVANT;SAI TEAM;Akshay Kumar | TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKSHAY.KUMAR@KOCHTC.COM | LSA | 36505,94797 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 19:45 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97012 | WBS.2.2.6.1.7.1.12 | N | N | Planned | Delete existing trigger to GPTTN_CcsToWms_StreamSendToWms | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | ZAC HAMILTON | Zac.Hamilton@GAPAC.com | TISHA WEST;MAMIE TREZVANT;SAI TEAM;Akshay Kumar | TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKSHAY.KUMAR@KOCHTC.COM | LSA | 97011 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97013 | WBS.2.2.6.1.7.1.13 | N | N | Planned | Create new trigger to GPTTN_CcsToWms_StreamSendToWmsS4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | ZAC HAMILTON | Zac.Hamilton@GAPAC.com | TISHA WEST;MAMIE TREZVANT;SAI TEAM;Akshay Kumar | TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKSHAY.KUMAR@KOCHTC.COM | LSA | 97012 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97014 | WBS.2.2.6.1.7.1.9 | N | N | Planned | Validate traffic continues to flow to S4 | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | ZAC HAMILTON | Zac.Hamilton@GAPAC.com | TISHA WEST;MAMIE TREZVANT;SAI TEAM;Akshay Kumar | TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKSHAY.KUMAR@KOCHTC.COM | LSA | 97013,90704,94797 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97015 | WBS.2.2.6.1.7.1.14 | N | N | Planned | Validate response continues to flow to PLC (just the error code) | 0.25 | 2021-01-31 20:30 | 2021-01-31 20:45 | ZAC HAMILTON | Zac.Hamilton@GAPAC.com | TISHA WEST;MAMIE TREZVANT;SAI TEAM;Akshay Kumar | TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKSHAY.KUMAR@KOCHTC.COM | LSA | 97014 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 20:45 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97016 | WBS.2.2.6.1.7.1.16 | N | N | Planned | Shutdown all jobs in JDA except for data archiving jobs. Stop all interfacing jobs to external systems, shut off EMS reports to carriers, etc. | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | JEFF DUCKETT;TISHA WEST;MAMIE TREZVANT;SAI TEAM | JEFFREY.DUCKETT@GAPAC.COM;TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97017 | WBS.2.2.6.1.7.1.17 | N | N | Planned | 2. Shutdown outbound data senders when last updates sent to SAP. This will prevent JDA from trying to send any further data to SAP. | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | JEFF DUCKETT;TISHA WEST;MAMIE TREZVANT;SAI TEAM | JEFFREY.DUCKETT@GAPAC.COM;TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 97016 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97018 | WBS.2.2.6.1.7.1.18 | N | N | Planned | 3. Shutdown RGT JSA/CSS web services. Extra insurance that the interfacing is off. | 0.25 | 2021-01-31 01:45 | 2021-01-31 02:00 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | JEFF DUCKETT;TISHA WEST;MAMIE TREZVANT;SAI TEAM | JEFFREY.DUCKETT@GAPAC.COM;TISHA.WEST@GAPAC.com;MATREZVA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 97017 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:00 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97700 | WBS.2.2.6.1.7.1.20 | N | N | Planned | Update Outbound Delivery Due List variants for Atlanta MRO Central Storeroom | 0.5 | 2021-01-31 18:30 | 2021-01-31 19:00 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;SAI TEAM | KEPRADHAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | LSA | 95455,95453,90648 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:00 | LSA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90247 | WBS.2.2.6.1.8 | N | N |  | FCW ¦ Multi-Team Plan Activities - SCM | 16.75 | 2021-01-31 01:15 | 2021-01-31 18:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 18:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91725 | WBS.2.2.6.1.8.1 | N | N |  | FCW ¦ Multi-Team Plan Activities - SCM | 16.75 | 2021-01-31 01:15 | 2021-01-31 18:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 18:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92336 | WBS.2.2.6.1.8.1.1 | N | N | Planned | PCO Only: Communicate to IBP users to stay out of IBP for some down time during source ID changes | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | SANJAY JELAJI | SANJAY.JELAJI1@GAPAC.COM | JEFFREY GILLIAM;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JFGILLIA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | SCM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92340 | WBS.2.2.6.1.8.1.3 | N | N | Planned | Business Approval For File of Source ID Changes, Planning Unit changes & update the Capacity Expansion for Non-Live sites to 48 hours and also remove Manual Production Flag from Location Product in IBP | 2 | 2021-01-31 06:15 | 2021-01-31 08:15 | BRIDGET T LEE | BTLEE@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;JEFFREY GILLIAM;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;JFGILLIA@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92338 |  |  | * |  | 2021-01-31 06:15 | 2021-01-31 08:15 | SCM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92338 | WBS.2.2.6.1.8.1.4 | N | N | Planned | Remove capacity expansion in IBP for sites going live | 5 | 2021-01-31 01:15 | 2021-01-31 06:15 | SANJAY JELAJI | SANJAY.JELAJI1@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;JEFFREY GILLIAM;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;JFGILLIA@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 36505,10851 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 06:15 | SCM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4661 | WBS.2.2.6.1.8.1.6 | N | N | Planned | Maintain/Validate BRF+ parameter values for interfaces - PE | 0.25 | 2021-01-31 17:45 | 2021-01-31 18:00 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | ANUPAM SHRIVASTAVA;SAI TEAM;CHIRAG PARIKH;CHANDRA BALASUBRAMANIAN;JENNIFER LI;SCM TEAM;BRAD WYMAN | ANUPSHRIVASTAVA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;CBALASUBRAMANIAN@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM | SCM | 4084,36505,89641,96904,97475 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 18:00 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82959 | WBS.2.2.6.1.8.1.7 | N | N | Planned | Turn-off Stone Branch job for HCI, IBP and S/4HANA <Publish on Hold> | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36505,95142,95143,95145 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95411 | WBS.2.2.6.1.8.1.9 | N | N | Planned | Mock Only - Start Delivery Due List Job in S4 | 0.5 | 2021-01-31 17:30 | 2021-01-31 18:00 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 36505,94798,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:00 | BATCH | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97681 | WBS.2.2.6.1.9 |  |  |  | FCW ¦ Multi-Team Plan Activities - CMM | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97682 | WBS.2.2.6.1.9.2 |  |  |  | FCW ¦ Multi-Team Plan Activities - CMM | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97683 | WBS.2.2.6.1.9.2.12 | N | N | Planned | Turn on order replication jobs in Hybris | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | LEANNE EVANS | LEREVANS@gapac.com | JUDY LIGHTFOOT;SAI TEAM | JMLIGHTF@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | CMM | 96654 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | CMM | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91007 | WBS.2.2.7 | N | N |  | FCW ¦ Conversions | 52.5 | 2021-01-31 01:15 | 2021-02-02 05:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 05:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5680 | WBS.2.2.7.2 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data | 52.5 | 2021-01-31 01:15 | 2021-02-02 05:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 05:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
81151 | WBS.2.2.7.2.1 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data - Extractions | 5.25 | 2021-01-31 01:15 | 2021-01-31 06:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 06:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91570 | WBS.2.2.7.2.1.1 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data - Extractions - JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
8874 | WBS.2.2.7.2.1.1.1 | N | N | Planned | PTH - PTM_C0201 - Execute Inventory Extracts From Elixir | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DOUG STANISLAWSKI;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 8864,36505,68450 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94450 | WBS.2.2.7.2.1.1.2 | N | N | Planned | SCH - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DOUG STANISLAWSKI;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | DATA | 5231,36505,68450 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96719 | WBS.2.2.7.2.1.1.3 | N | N | Planned | RNC - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DOUG STANISLAWSKI;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | DATA | 36505,68450,96703 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96720 | WBS.2.2.7.2.1.1.4 | N | N | Planned | RVG - PTM_C0201 - Execute Inventory Extracts From JDA | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DOUG STANISLAWSKI;PMO TEAM;JENNIFER MCLEOD;JULI LEWIS | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | DATA | 36505,68450,96704 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91569 | WBS.2.2.7.2.1.2 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data - Extractions - AS8 | 3 | 2021-01-31 01:15 | 2021-01-31 04:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 04:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81154 | WBS.2.2.7.2.1.2.1 | N | N | Planned | Execute Final Cutover Extracts from AS8 - for PTM_C0201, ITR_0035, ITR_C0067 | 3 | 2021-01-31 01:15 | 2021-01-31 04:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JASON RAMSEY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 3968,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 04:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91568 | WBS.2.2.7.2.1.3 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data - Extractions - ECC | 5.25 | 2021-01-31 01:15 | 2021-01-31 06:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 06:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82715 | WBS.2.2.7.2.1.3.1 | N | N | Planned | Run ECC Open PO Dollar Amount report to be used for PO baseline data and upload to SharePoint | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;CASEY HERMANSEN;MIKE PUPILLO;SHRISH MUDRI;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;MAPUPILL@GAPAC.COM;SHRISH.MUDRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5246,36505,97813,97547 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97547 | WBS.2.2.7.2.1.3.9 | N | N | Planned | Validate execution of interco vendor balance write off program (Z0GLVC2GLACT) -typically scheduled for 6pm Sat (Job PFGLW006) | 0.25 | 2021-01-31 02:15 | 2021-01-31 02:30 | WENTAO TANG | WTANG@GAPAC.COM | BRETT DETTMERING;DONNA SMITH;LAURA FRY;SANDRA RICHARDS;DON ABBOTT;BOATENG LAWRENCE;RANJAI JOHN;RTR TEAM;SAI TEAM | BRETT.DETTMERING@GAPAC.COM;DONNA.SMITH@GAPAC.COM;LAURA.FRY@GAPAC.COM;SARICHARDS@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 36505,97813 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 02:30 | RTR - GL | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90006 | WBS.2.2.7.2.1.3.2 | N | N | Planned | Run baseline Report from ECC to be used for GR/IR baseline data and upload to SharePoint | 1 | 2021-01-31 02:30 | 2021-01-31 03:30 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | DONNA SMITH;LAURA FRY;SANDRA RICHARDS;DON ABBOTT;SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | DONNA.SMITH@GAPAC.COM;LAURA.FRY@GAPAC.COM;SARICHARDS@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36505,97547,97813 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 03:30 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95199 | WBS.2.2.7.2.1.3.4 | N | N | Planned | Provide Inventory snapshot at beginning of dark period | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LAURA FRY;LINDA GIBSON;RTR TEAM;SAI TEAM;DENISE MARSH;RANJAI JOHN;BOATENG LAWRENCE | LAURA.FRY@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DENISE.MARSH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81152 | WBS.2.2.7.2.1.3.5 | N | N | Planned | Execute Final Cutover Extracts from ECC - Small | 2.5 | 2021-01-31 02:30 | 2021-01-31 05:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;GRP_SAP BASIS TECHNICAL SERVICES;KELLY HINSON;KYNDAL CODY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;GRPSAPTECHNICALSERVICES@GAPAC.COM;KSHINSON@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 3964,3966,3967,3968,36505,95439,97813,97547 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 05:00 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81153 | WBS.2.2.7.2.1.3.6 | N | N | Planned | Execute Final Cutover Extracts from ECC - Large (Sales Orders, Pricing Records, Pricing Agrmts., Inventory) | 3.5 | 2021-01-31 02:30 | 2021-01-31 06:00 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;GRP_SAP BASIS TECHNICAL SERVICES;KELLY HINSON;KYNDAL CODY;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;GRPSAPTECHNICALSERVICES@GAPAC.COM;KSHINSON@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 3964,36505,95439,97813,97547 |  |  | * |  | 2021-01-31 02:30 | 2021-01-31 06:00 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82641 | WBS.2.2.7.2.1.3.7 | N | N | Planned | Use Legacy System Files to create Baseline File to be used in PO and GR/IR Conversions | 2 | 2021-01-31 03:30 | 2021-01-31 05:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;BRUCE KIRKLEWSKI;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 90005,90006,82716,82717,82715,94292 |  |  | * |  | 2021-01-31 03:30 | 2021-01-31 05:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92501 | WBS.2.2.7.2.1.3.8 | N | N | Planned | Review and signoff baseline file to be used in PO and GR/IR Conversions | 1 | 2021-01-31 05:30 | 2021-01-31 06:30 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | PTP TEAM;SAI TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 82641 |  |  | * |  | 2021-01-31 05:30 | 2021-01-31 06:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91572 | WBS.2.2.7.2.2 | N | N |  | FCW ¦ Conversions - Open Item Transactional Data - Conversion Objects | 52.5 | 2021-01-31 01:15 | 2021-02-02 05:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 05:45 |  | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5707 | WBS.2.2.7.2.2.1 | N | N |  | FCW ¦ Create Deliveries for Open Sales Orders | 18.5 | 2021-01-31 22:30 | 2021-02-01 17:00 | [8 empty] | * |  | 2021-01-31 22:30 | 2021-02-01 17:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92659 | WBS.2.2.7.2.2.1.1 | N | N | Planned | Start monitoring/fixing inbound shipment IDOC errors (TOPS to S4) in support of order conversion | 0.25 | 2021-02-01 10:31 | 2021-02-01 10:46 | JACOB OWENS | JACOB.OWENS@GAPAC.COM | ANDREW HELMANN;JOHN NATZKE;SAI TEAM;DOUG STANISLAWSKI;AQUIL HUSAIN;AVINASH TALREJA;EWM TEAM | Andrew.Helmann@kbxlogistics.com;JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;AVTALREJA@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 90104,96723,96724 |  |  | * |  | 2021-02-01 10:31 | 2021-02-01 10:46 | EWM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95094 | WBS.2.2.7.2.2.1.2 | N | N | Planned | PTH - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-01-31 23:00 | 2021-01-31 23:30 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;CJ KAUTH;ROBBIE GARNER | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com | Business | 94932 |  |  | * |  | 2021-01-31 23:00 | 2021-01-31 23:30 | OTC - KBX | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95092 | WBS.2.2.7.2.2.1.4 | N | N | Planned | HBG - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 16:30 | 2021-02-01 17:00 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com | Business | 94948 |  |  | * |  | 2021-02-01 16:30 | 2021-02-01 17:00 | OTC - KBX | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96636 | WBS.2.2.7.2.2.1.18 | N | N | Planned | BG - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 03:00 | 2021-02-01 03:30 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;LYNN MCMURDO;DEAN PIPER | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com | Business | 96635 |  |  | * |  | 2021-02-01 03:00 | 2021-02-01 03:30 | OTC - KBX | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90107 | WBS.2.2.7.2.2.1.6 | N | N | Planned | SCH - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 10:31 | 2021-02-01 11:01 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;JEREMY RAY;TOMMY NEFFENDORF | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | Business | 90104 |  |  | * |  | 2021-02-01 10:31 | 2021-02-01 11:01 | OTC - KBX | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96721 | WBS.2.2.7.2.2.1.20 | N | N | Planned | RNC - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 10:30 | 2021-02-01 11:00 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;JEREMY RAY;TOMMY NEFFENDORF | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | Business | 96723 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:00 | OTC - KBX | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96722 | WBS.2.2.7.2.2.1.21 | N | N | Planned | RVG - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 10:30 | 2021-02-01 11:00 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;JENNIFER MCLEOD;JULI LEWIS | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | Business | 96724 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:00 | OTC - KBX | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97124 | WBS.2.2.7.2.2.1.27 | N | N | Planned | SAT - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 05:00 | 2021-02-01 05:30 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;KELLY JANSSEN | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;MICHAEL.JANSSEN@GAPAC.COM | Business | 97128 |  |  | * |  | 2021-02-01 05:00 | 2021-02-01 05:30 | OTC - KBX | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97125 | WBS.2.2.7.2.2.1.28 | N | N | Planned | REX - Validate New S/4HANA DN's are finding and matching with old DN's and updating the load in TOPS and triggering a new ship doc in S4 on 1st group of loads sent through. | 0.5 | 2021-02-01 06:00 | 2021-02-01 06:30 | JOHN NATZKE | JOHN.NATZKE@KBXLOGISTICS.COM | TOM OLIVE;SAI TEAM;JOHN CASABURRI;ANDREW HELMANN;DANIEL ROSS | THOMAS.OLIVE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Andrew.Helmann@kbxlogistics.com;DANIEL.ROSS@GAPAC.COM | Business | 97129 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 06:30 | OTC - KBX | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90104 | WBS.2.2.7.2.2.1.7 | N | N | Planned | Manually run Delivery Due list for SCH | 0.5 | 2021-02-01 10:01 | 2021-02-01 10:31 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;JEREMY RAY;TOMMY NEFFENDORF;KYNDAL CODY;ONI BORCHERS | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 93401,92999,95197,95389 |  |  | * |  | 2021-02-01 10:01 | 2021-02-01 10:31 | OTC | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96723 | WBS.2.2.7.2.2.1.22 | N | N | Planned | Manually run Delivery Due list for RNC | 0.5 | 2021-02-01 10:00 | 2021-02-01 10:30 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;JEREMY RAY;TOMMY NEFFENDORF | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | OTC | 93401,96716,96923 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 10:30 | OTC | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96724 | WBS.2.2.7.2.2.1.23 | N | N | Planned | Manually run Delivery Due list for RVG | 0.5 | 2021-02-01 10:00 | 2021-02-01 10:30 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;JENNIFER MCLEOD;JULI LEWIS | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | OTC | 93401,96718,96924 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 10:30 | OTC | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94932 | WBS.2.2.7.2.2.1.8 | N | N | Planned | Manually run Delivery Due list for PTH | 0.5 | 2021-01-31 22:30 | 2021-01-31 23:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;KYNDAL CODY;ONI BORCHERS | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 94482 |  |  | * |  | 2021-01-31 22:30 | 2021-01-31 23:00 | OTC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96635 | WBS.2.2.7.2.2.1.17 | N | N | Planned | Manually run Delivery Due list for BG | 0.5 | 2021-02-01 02:30 | 2021-02-01 03:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;DEAN PIPER;LYNN MCMURDO | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | OTC | 93401,96690 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 03:00 | OTC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94948 | WBS.2.2.7.2.2.1.10 | N | N | Planned | Manually run Delivery Due list for HBG | 0.5 | 2021-02-01 16:00 | 2021-02-01 16:30 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;MELISSA KOTAREK;KYNDAL CODY;ONI BORCHERS | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;MELISSA.KOTAREK@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 93401,94405 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 16:30 | OTC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97128 | WBS.2.2.7.2.2.1.31 | N | N | Planned | Manually run Delivery Due list for SAT | 0.5 | 2021-02-01 04:30 | 2021-02-01 05:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;MELISSA KOTAREK;KELLY JANSSEN | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;MELISSA.KOTAREK@GAPAC.COM;MICHAEL.JANSSEN@GAPAC.COM | OTC | 93401,96668,96674 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 05:00 | OTC | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97129 | WBS.2.2.7.2.2.1.32 | N | N | Planned | Manually run Delivery Due list for REX | 0.5 | 2021-02-01 05:30 | 2021-02-01 06:00 | MICHELLE SADLER | BMSADLER@GAPAC.COM | JOHN NATZKE;SAI TEAM;OTC TEAM;KETAN PRADHAN;DAVE LEGOIS;MELISSA KOTAREK;DANIEL ROSS | JOHN.NATZKE@KBXLOGISTICS.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;KEPRADHAN@DELOITTE.COM;DAVID.LEGOIS@KBXLOGISTICS.COM;MELISSA.KOTAREK@GAPAC.COM;DANIEL.ROSS@GAPAC.COM | OTC | 93401,96672,97136 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 06:00 | OTC | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95405 | WBS.2.2.7.2.2.1.12 | N | N | Planned | SCH Update Delivery Due List Variant (1524) | 0.5 | 2021-02-01 10:31 | 2021-02-01 11:01 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 90104 |  |  | * |  | 2021-02-01 10:31 | 2021-02-01 11:01 | OTC | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96725 | WBS.2.2.7.2.2.1.24 | N | N | Planned | RNC Update Delivery Due List Variant (1460) | 0.5 | 2021-02-01 10:30 | 2021-02-01 11:00 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 96723 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:00 | OTC | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96726 | WBS.2.2.7.2.2.1.25 | N | N | Planned | RVG Update Delivery Due List Variant (1369) | 0.5 | 2021-02-01 10:30 | 2021-02-01 11:00 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;JENNIFER MCLEOD;JULI LEWIS;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 96724 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:00 | OTC | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95406 | WBS.2.2.7.2.2.1.13 | N | N | Planned | PTH Update Delivery Due List Variant (1034/5034) | 0.5 | 2021-01-31 23:00 | 2021-01-31 23:30 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 94932 |  |  | * |  | 2021-01-31 23:00 | 2021-01-31 23:30 | OTC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95408 | WBS.2.2.7.2.2.1.15 | N | N | Planned | HBG Update Delivery Due List Variant (1459/5459 | 0.5 | 2021-02-01 16:30 | 2021-02-01 17:00 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 94948 |  |  | * |  | 2021-02-01 16:30 | 2021-02-01 17:00 | OTC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96637 | WBS.2.2.7.2.2.1.19 | N | N | Planned | BG Update Delivery Due List Variant (1376/5376) | 0.5 | 2021-02-01 03:00 | 2021-02-01 03:30 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | OTC | 96635 |  |  | * |  | 2021-02-01 03:00 | 2021-02-01 03:30 | OTC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97132 | WBS.2.2.7.2.2.1.35 | N | N | Planned | SAT Update Delivery Due List Variant (1526) | 0.5 | 2021-02-01 05:00 | 2021-02-01 05:30 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;KELLY JANSSEN;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MICHAEL.JANSSEN@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 97128 |  |  | * |  | 2021-02-01 05:00 | 2021-02-01 05:30 | OTC | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97133 | WBS.2.2.7.2.2.1.36 | N | N | Planned | REX Update Delivery Due List Variant (1205) | 0.5 | 2021-02-01 06:00 | 2021-02-01 06:30 | LISA KOENIG | lisa.koenig@gapac.com | KETAN PRADHAN;OTC TEAM;SAI TEAM;DANIEL ROSS;KYNDAL CODY;ONI BORCHERS | KEPRADHAN@DELOITTE.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;KYNDAL.CODY@GAPAC.COM;OCBORCHE@GAPAC.COM | OTC | 97129 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 06:30 | OTC | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90502 | WBS.2.2.7.2.2.2 | N | N |  | FCW ¦ Inventory Conversion Prep Tasks | 34.25 | 2021-01-31 01:15 | 2021-02-01 11:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 11:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95417 | WBS.2.2.7.2.2.2.1 | N | N | Planned | PTH - Prepare List of items to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;DOUG STANISLAWSKI;RATUL CHAKRABORTY;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;ratchakraborty@deloitte.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | RTR | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | RTR - PC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96639 | WBS.2.2.7.2.2.2.53 | N | N | Planned | BG - Prepare List of items to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | Amanda Smith | Amanda.Smith@GAPAC.COM | NOEL CLARK;LINDA GIBSON;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;RANJAI JOHN;BOATENG LAWRENCE;LYNN MCMURDO;BG RTR TEAM;DOUG STANISLAWSKI;RATUL CHAKRABORTY | NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;DOUG.STANISLAWSKI@GAPAC.COM;ratchakraborty@deloitte.com | RTR | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | RTR - PC | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97415 | WBS.2.2.7.2.2.2.60 | N | N | Planned | HBG - Prepare List of items to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | AVIE LINDSEY | Avie.Lindsey@gapac.com | NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;RANJAI JOHN;BOATENG LAWRENCE;HOLLY KREUER;DOUG STANISLAWSKI;RATUL CHAKRABORTY;DENISE MARSH | NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;DOUG.STANISLAWSKI@GAPAC.COM;ratchakraborty@deloitte.com;DENISE.MARSH@GAPAC.COM | RTR | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | RTR - PC | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
21139 | WBS.2.2.7.2.2.2.4 | N | N | Planned | PTH - Build File and Load Inventory for Materials in SLOC 4500 in all Mills (e.g. Pulp, Logs, Chips, Tape, Stretch Wrap, Escrfina, etc.) | 2.5 | 2021-02-01 03:30 | 2021-02-01 06:00 | Uday Athwal | uathwal@deloitte.com | JEFFREY GOLDMUNTZ;EWM TEAM;AQUIL HUSAIN;DEEPAK SABNANI;SAI TEAM;DOUG STANISLAWSKI;MICHAEL MATTHEWS;DEEPA SAW | JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AQHUSAIN@DELOITTE.COM;DSABNANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;MMATTHEWS@DELOITTE.COM;DEESAW@DELOITTE.COM | EWM | 36505,90653,29571,93321,95417,96904,96892,95429,97475 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 06:00 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97418 | WBS.2.2.7.2.2.2.63 | N | N | Planned | BG - Build File and Load Inventory for Materials in SLOC 4500 in all Mills (e.g. Pulp, Logs, Chips, Tape, Stretch Wrap, Escrfina, etc.) | 2.5 | 2021-02-01 04:30 | 2021-02-01 07:00 | Uday Athwal | uathwal@deloitte.com | JEFFREY GOLDMUNTZ;EWM TEAM;AQUIL HUSAIN;DEEPAK SABNANI;SAI TEAM;DOUG STANISLAWSKI;MICHAEL MATTHEWS;DEEPA SAW | JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AQHUSAIN@DELOITTE.COM;DSABNANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;MMATTHEWS@DELOITTE.COM;DEESAW@DELOITTE.COM | EWM | 36505,90653,29571,96639,96631,96904,96892,95429,97475 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 07:00 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97419 | WBS.2.2.7.2.2.2.64 | N | N | Planned | HBG - Build File and Load Inventory for Materials in SLOC 4500 in all Mills (e.g. Pulp, Logs, Chips, Tape, Stretch Wrap, Escrfina, etc.) | 2.5 | 2021-02-01 03:30 | 2021-02-01 06:00 | Uday Athwal | uathwal@deloitte.com | JEFFREY GOLDMUNTZ;EWM TEAM;AQUIL HUSAIN;DEEPAK SABNANI;SAI TEAM;DOUG STANISLAWSKI;MICHAEL MATTHEWS;DEEPA SAW | JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;AQHUSAIN@DELOITTE.COM;DSABNANI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;MMATTHEWS@DELOITTE.COM;DEESAW@DELOITTE.COM | EWM | 36505,90653,29571,93904,96904,96892,95429,97415,97475 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 06:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95414 | WBS.2.2.7.2.2.2.5 | N | N | Planned | PTH - Validate Inventory in S4 for Materials to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-02-01 06:00 | 2021-02-01 07:00 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR | 21139 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 07:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96641 | WBS.2.2.7.2.2.2.55 | N | N | Planned | BG - Validate Inventory in S4 for Materials to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-02-01 07:00 | 2021-02-01 08:00 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;RTR TEAM;JOHN CASABURRI;RANJAI JOHN;BOATENG LAWRENCE;LYNN MCMURDO | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | RTR | 97418 |  |  | * |  | 2021-02-01 07:00 | 2021-02-01 08:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97416 | WBS.2.2.7.2.2.2.61 | N | N | Planned | HBG - Validate Inventory in S4 for Materials to be loaded in SLOC 4500 (e.g. Pulp, Logs, Chips, etc.) | 1 | 2021-02-01 06:00 | 2021-02-01 07:00 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 97419 |  |  | * |  | 2021-02-01 06:00 | 2021-02-01 07:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80925 | WBS.2.2.7.2.2.2.8 | N | N | Planned | Update Material Cross Reference (Xref) due to dual maintenance after initial conversion | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36505,94798,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
68331 | WBS.2.2.7.2.2.2.10 | N | N | Planned | PTH - Validate Moving Average Prices in S/4HANA For AS8 Materials | 3 | 2021-02-01 02:30 | 2021-02-01 05:30 | ANDRE GONZAQUE | ANDRE.GONZAQUE@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 29570 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 05:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92738 | WBS.2.2.7.2.2.2.11 | N | N | Planned | Start IBP Publish & PPDS sequencing job | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;RTR TEAM;BRAD WYMAN;KIM LADZINSKE;SATISH KUMAR B;ANUPAM SHRIVASTAVA;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 96903,92742 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
68428 | WBS.2.2.7.2.2.2.12 | N | N | Planned | Identify Pallet inventory for D4 sites and ZERO out from 9999 | 0.25 | 2021-01-31 19:30 | 2021-01-31 19:45 | Uday Athwal | uathwal@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;PRAJWAL K S | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;prajks@deloitte.com | EWM | 92738 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 19:45 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96334 | WBS.2.2.7.2.2.2.29 | N | N | Planned | SAT - Identify inventory for D4 sites and ZERO out from 9999 (Based on Date provided by RTR) | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | NIKHIL NEGI | nikhnegi@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;KAITLYN JANSEN;TRENT SCHICK | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | EWM | 36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | EWM | SAT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96322 | WBS.2.2.7.2.2.2.41 | N | N | Planned | REX - Identify inventory for D4 sites and ZERO out from 9999 (Based on Date provided by RTR) | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | NIKHIL NEGI | nikhnegi@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;DANIEL ROSS;SLADE HURST | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;DANIEL.ROSS@GAPAC.COM;SLADE.HURST@GAPAC.COM | EWM | 36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | EWM | REX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96642 | WBS.2.2.7.2.2.2.56 | N | N | Planned | BG - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 2.5 | 2021-01-31 18:00 | 2021-01-31 20:30 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RATUL CHAKRABORTY;PRAJWAL K S | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ratchakraborty@deloitte.com;prajks@deloitte.com | EWM | 92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:30 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94952 | WBS.2.2.7.2.2.2.14 | N | N | Planned | HBG - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 2.5 | 2021-01-31 18:00 | 2021-01-31 20:30 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;TEJAS THORAT;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TTHORAT@DELOITTE.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:30 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90499 | WBS.2.2.7.2.2.2.16 | N | N | Planned | PTH - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 2.5 | 2021-01-31 18:00 | 2021-01-31 20:30 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com | EWM | 92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96423 | WBS.2.2.7.2.2.2.65 | N | N | Planned | RNC - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 36505,92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96416 | WBS.2.2.7.2.2.2.66 | N | N | Planned | RVG - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 36505,92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92999 | WBS.2.2.7.2.2.2.67 | N | N | Planned | SCH - Identify inventory for D4 sites and scrap from SLOC 9999 (Based on Date provided by RTR) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;GAYATHRI BATTALA;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;GBATTALA@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 36505,92742,97402,10038 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82130 | WBS.2.2.7.2.2.2.17 | N | N | Planned | PTH - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 10:30 | 2021-02-01 11:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;KIM VANWYCHEN;JAMES COWELL | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;James.Cowell@gapac.com | EWM | 5690 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90505 | WBS.2.2.7.2.2.2.19 | N | N | Planned | HBG - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 07:30 | 2021-02-01 08:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;MELISSA KOTAREK;CHRIS ZUMWALT | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 95272 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 08:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96643 | WBS.2.2.7.2.2.2.57 | N | N | Planned | BG - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 2 | 2021-02-01 02:30 | 2021-02-01 04:30 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | DAVID HEILI;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;BEAU EARLS | DAVID.HEILI@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Beau.Earls@GAPAC.com | EWM | 96690 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94488 | WBS.2.2.7.2.2.2.21 | N | N | Planned | SCH - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 04:30 | 2021-02-01 05:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94515 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 05:30 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96741 | WBS.2.2.7.2.2.2.58 | N | N | Planned | RNC - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 04:30 | 2021-02-01 05:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96729 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 05:30 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96742 | WBS.2.2.7.2.2.2.59 | N | N | Planned | RVG - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 04:30 | 2021-02-01 05:30 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;JENNIFER MCLEOD;JULI LEWIS | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 96736 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 05:30 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96335 | WBS.2.2.7.2.2.2.28 | N | N | Planned | Update sloc for Inbound STO's to all go-live sites | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;RYAN D;SAYONI BANERJEE | CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM | SCM | 36505,92742,92743 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96333 | WBS.2.2.7.2.2.2.30 | N | N | Planned | SAT - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 02:00 | 2021-02-01 03:00 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | DAVID HEILI;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;DOUG STANISLAWSKI;KAITLYN JANSEN;TRENT SCHICK | DAVID.HEILI@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;Kaitlyn.Jansen@gapac.com;Trent.Schick@gapac.com | EWM | 36505,92742,96667 |  |  | * |  | 2021-02-01 02:00 | 2021-02-01 03:00 | EWM | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96321 | WBS.2.2.7.2.2.2.42 | N | N | Planned | REX - Move FG and Parent Roll inventory for D4 live sites to respective plant's interim 9999 sloc in ECC | 1 | 2021-02-01 02:00 | 2021-02-01 03:00 | DAVE BASCHE | DAVID.BASCHE@GAPAC.COM | DAVID HEILI;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;DOUG STANISLAWSKI;DANIEL ROSS;SLADE HURST | DAVID.HEILI@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;DANIEL.ROSS@GAPAC.COM;SLADE.HURST@GAPAC.COM | EWM | 36505,92742,96671 |  |  | * |  | 2021-02-01 02:00 | 2021-02-01 03:00 | EWM | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5686 | WBS.2.2.7.2.2.3 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory - Data Extractions | 16.75 | 2021-01-31 01:15 | 2021-01-31 18:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-01-31 18:00 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10039 | WBS.2.2.7.2.2.3.1 | N | N | Planned | PTH - PTM_C0201 - Extract E80 Storage Bins and Batches | 1 | 2021-01-31 03:30 | 2021-01-31 04:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 8874,89987,97835 |  |  | * |  | 2021-01-31 02:15 | 2021-01-31 03:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94452 | WBS.2.2.7.2.2.3.4 | N | N | Planned | PTM_C0201-Extract Storage bins and batches for all sources(PTH,RNC,RVG,SCH,HTB,BWG) | 2 | 2021-01-31 06:00 | 2021-01-31 08:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | DATA | 94450,8874,96719,96720,81154,81152,81153,97761 |  |  | * |  | 2021-01-31 06:00 | 2021-01-31 08:00 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10038 | WBS.2.2.7.2.2.3.5 | N | N | Planned | PTM_C0201 - Open the posting periods for Inventory conversion | 0.25 | 2021-01-31 17:30 | 2021-01-31 17:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;DONNA SMITH;SANDRA RICHARDS;SAI TEAM;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 10039,29564,94452,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 17:45 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97402 | WBS.2.2.7.2.2.3.14 | N | N | Planned | Provide posting date for inventory for D4 sites and scrap from SLOC 9999 | 0.25 | 2021-01-31 17:45 | 2021-01-31 18:00 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LAURA FRY;LINDA GIBSON;RTR TEAM;SAI TEAM;DENISE MARSH;RANJAI JOHN;BOATENG LAWRENCE | LAURA.FRY@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DENISE.MARSH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 10038 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 18:00 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
9091 | WBS.2.2.7.2.2.3.7 | N | N | Planned | PTM_C0201 - Upload Batch LSMW File | 0.75 | 2021-01-31 17:15 | 2021-01-31 18:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 9092,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
9092 | WBS.2.2.7.2.2.3.6 | N | N | Planned | PTM_C0201 - Extract and Prepare Batch LSMW File | 1 | 2021-01-31 08:00 | 2021-01-31 09:00 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 5230,5231,8864,10039,96703,96704,94452 |  |  | * |  | 2021-01-31 08:00 | 2021-01-31 09:00 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
89768 | WBS.2.2.7.2.2.3.8 | N | N | Planned | Run Inventory report for all items in Mill and DC | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | COURTNEY MORTON | COURTNEY.MORTON@GAPAC.COM | DOUG STANISLAWSKI;JOHN CASABURRI;SAI TEAM;PHILIP GAGLIA;JORDAN WASSON;CRAIG KASTNER;LYNN MCMURDO;ZACH HEFNER;MIKE BRUNNER;TOMMY NEFFENDORF;SCOTT TRAHAN;EWM TEAM | DOUG.STANISLAWSKI@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PHILIP.GAGLIA@GAPAC.COM;JORDAN.WASSON@GAPAC.COM;CRAIG.KASTNER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;ZACKERY.HEFNER@GAPAC.COM;MIKE.BRUNNER@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;SCOTT.TRAHAN@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95287 | WBS.2.2.7.2.2.4 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ HBG ¦ FG, Vitals & SFG | 30.25 | 2021-01-31 01:15 | 2021-02-01 07:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 07:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94630 | WBS.2.2.7.2.2.4.1 | N | N | Planned | HBG - PTM_C0201 - Provide manual load for for FG, Vitals and Semi-FG inventory | 2 | 2021-01-31 01:15 | 2021-01-31 03:15 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94631 | WBS.2.2.7.2.2.4.2 | N | N | Planned | HBG - PTM_C0201 - Convert manual load file into ISU format | 2 | 2021-01-31 03:15 | 2021-01-31 05:15 | NIKHIL NEGI | nikhnegi@deloitte.com | AVINASH TALREJA;SAI TEAM;EWM TEAM;MITCH DEATON;CHRIS ZUMWALT;SANTOSH KUPPILI;GLEN RICHARDSON | AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;VKUPPILI@DELOITTE.COM;GLEN.RICHARDSON@GAPAC.COM | EWM | 94630 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 05:15 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94954 | WBS.2.2.7.2.2.4.3 | N | N | Planned | HBG - PTM_C0201 - Manual Load of FG, Vitals & SFG Inventory | 2 | 2021-02-01 03:30 | 2021-02-01 05:30 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;TEJAS THORAT;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TTHORAT@DELOITTE.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94631,93904,93716,95429 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 05:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95272 | WBS.2.2.7.2.2.4.4 | N | N | Planned | HBG - PTM_C0201 - Validate Manual Load of FG, Vitals & SFG Inventory | 2 | 2021-02-01 05:30 | 2021-02-01 07:30 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94954 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 07:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97457 | WBS.2.2.7.2.2.43 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ BG ¦ Vitals | 30.25 | 2021-01-31 01:15 | 2021-02-01 07:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 07:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97458 | WBS.2.2.7.2.2.43.9 | N | N | Planned | BG - PTM_C0201 - Provide manual load file for Vitals | 2 | 2021-01-31 01:15 | 2021-01-31 03:15 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97459 | WBS.2.2.7.2.2.43.10 | N | N | Planned | BG - PTM_C0201 - Convert manual load file into ISU Format | 2 | 2021-01-31 03:15 | 2021-01-31 05:15 | Vinay Tawani | vtawani@deloitte.com | JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;EWM TEAM;SAI TEAM;FRANZ JURVA;PHIL RACINE | JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;FRANZ.JURVA@GAPAC.COM;phil.racine@gapac.com | EWM | 97458 |  |  | * |  | 2021-01-31 03:15 | 2021-01-31 05:15 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97460 | WBS.2.2.7.2.2.43.11 | N | N | Planned | BG - PTM_C0201 - Manual Load of Vitals Inventory | 2 | 2021-02-01 04:30 | 2021-02-01 06:30 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;SHREYA NARULA;TODD CALVERT;PHIL RACINE;FRANZ JURVA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;shrenarula@deloitte.com;todd.calvert@gapac.com;phil.racine@gapac.com;FRANZ.JURVA@GAPAC.COM | EWM | 97459,95429,96565,96631 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 06:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97461 | WBS.2.2.7.2.2.43.12 | N | N | Planned | BG - PTM_C0201 - Validate Manual Load of Vitals Inventory | 1 | 2021-02-01 06:30 | 2021-02-01 07:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;SAI TEAM;EWM TEAM | Beau.Earls@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97460 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 07:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96343 | WBS.2.2.7.2.2.6 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ IM Sites ¦ ECC ¦ Finished Goods | 9.5 | 2021-01-31 17:30 | 2021-02-01 03:00 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 03:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96347 | WBS.2.2.7.2.2.6.1 | N | N | Planned | IM Sites - PTM_C0201 - Execute Transform For ECC IM Inventory | 3 | 2021-01-31 17:30 | 2021-01-31 20:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DANIEL ROSS;KELLY JANSSEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;DANIEL.ROSS@GAPAC.COM;MICHAEL.JANSSEN@GAPAC.COM | DATA | 81153,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 20:30 | DATA | SAT,REX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96665 | WBS.2.2.7.2.2.6.10 | N | N | Planned | SAT - PTM_C0201 - Preload Validation and sign off for SAT SAP IM (ECC) Inventory | 2 | 2021-01-31 20:30 | 2021-01-31 22:30 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SLADE HURST;TRENT SCHICK;PATRICK BROWNING;SAI TEAM;EWM TEAM | SLADE.HURST@GAPAC.COM;Trent.Schick@gapac.com;PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96347 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 22:30 | EWM | SAT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96666 | WBS.2.2.7.2.2.6.11 | N | N | Planned | SAT - PTM_C0201 - Execute Load program for SAT SAP IM (ECC) Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;ZURI PETERSON;PMO TEAM;US GP BASIS;KELLY JANSSEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ZURI.PETERSON@DSCLOGISTICS.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;MICHAEL.JANSSEN@GAPAC.COM | DATA | 96665,95429 |  |  | * |  | 2021-01-31 22:30 | 2021-02-01 00:30 | DATA | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96667 | WBS.2.2.7.2.2.6.12 | N | N | Planned | SAT - PTM_C0201 - Validate Load for SAT SAP IM (ECC) Inventory | 1.5 | 2021-02-01 00:30 | 2021-02-01 02:00 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SLADE HURST;TRENT SCHICK;PATRICK BROWNING;SAI TEAM;EWM TEAM | SLADE.HURST@GAPAC.COM;Trent.Schick@gapac.com;PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96666 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:00 | EWM | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96668 | WBS.2.2.7.2.2.6.13 | N | N | Planned | SAT - PTM_C0201 - Business Sign-Off For ECC Load File | 1 | 2021-02-01 02:00 | 2021-02-01 03:00 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SLADE HURST;TRENT SCHICK;PATRICK BROWNING;SAI TEAM;EWM TEAM | SLADE.HURST@GAPAC.COM;Trent.Schick@gapac.com;PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96667 |  |  | * |  | 2021-02-01 02:00 | 2021-02-01 03:00 | EWM | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96669 | WBS.2.2.7.2.2.6.14 | N | N | Planned | REX - PTM_C0201 - Preload Validation and sign off for REX SAP IM (ECC) Inventory | 2 | 2021-01-31 20:30 | 2021-01-31 22:30 | JEFF BROWN | Jeff.martin@nfiindustries.com | DANIEL ROSS;SAI TEAM | DANIEL.ROSS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96347 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 22:30 | EWM | REX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96670 | WBS.2.2.7.2.2.6.15 | N | N | Planned | REX - PTM_C0201 - Execute Load program for REX SAP IM (ECC) Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;ZURI PETERSON;PMO TEAM;US GP BASIS;DANIEL ROSS | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ZURI.PETERSON@DSCLOGISTICS.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USGPBASIS@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM | DATA | 96669,95429 |  |  | * |  | 2021-01-31 22:30 | 2021-02-01 00:30 | DATA | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96671 | WBS.2.2.7.2.2.6.16 | N | N | Planned | REX - PTM_C0201 - Validate Load for REX SAP IM (ECC) Inventory | 1.5 | 2021-02-01 00:30 | 2021-02-01 02:00 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | JEFF BROWN;SAI TEAM | Jeff.martin@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96670 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:00 | EWM | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96672 | WBS.2.2.7.2.2.6.17 | N | N | Planned | REX - PTM_C0201 - Business Sign-Off For ECC Load File | 1 | 2021-02-01 02:00 | 2021-02-01 03:00 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | JEFF BROWN;SAI TEAM | Jeff.martin@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96671 |  |  | * |  | 2021-02-01 02:00 | 2021-02-01 03:00 | EWM | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90376 | WBS.2.2.7.2.2.7 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ BG ¦ SAP-WM | 8.5 | 2021-01-31 18:00 | 2021-02-01 02:30 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-02-01 02:30 |  | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97173 | WBS.2.2.7.2.2.7.12 | N | N | Planned | BG (FG/PR) - PTM_C0201 - Execute Transform for SAP-WM Inventory | 2.5 | 2021-01-31 18:00 | 2021-01-31 20:30 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10038,9091,96571 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:30 | DATA | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96688 | WBS.2.2.7.2.2.7.9 | N | N | Planned | BG (FG/SFG) - PTM_C0201 - Validate Pre-Load For SAP-WM FG/SFG Inventory | 2 | 2021-01-31 20:30 | 2021-01-31 22:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;SAI TEAM;DEAN PIPER;EWM TEAM | LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97173 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 22:30 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96689 | WBS.2.2.7.2.2.7.10 | N | N | Planned | BG (FG/SFG) - PTM_C0201 - Execute Load for SAP-WM FG/SFG Inventory | 2 | 2021-01-31 22:30 | 2021-02-01 00:30 | VENKATESH GANESHAN | VGANESHAN@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 96688,96565,95429 |  |  | * |  | 2021-01-31 22:30 | 2021-02-01 00:30 | DATA | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96690 | WBS.2.2.7.2.2.7.11 | N | N | Planned | BG (FG/SFG) - PTM_C0201 - Validate Load For SAP-WM FG/SFG Inventory | 2 | 2021-02-01 00:30 | 2021-02-01 02:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;SAI TEAM;DEAN PIPER;EWM TEAM | LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96689 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92613 | WBS.2.2.7.2.2.7.6 | N | N | Planned | Add 100,000 FLRS1 stock in all IM Live Sites | 0.25 | 2021-02-01 00:30 | 2021-02-01 00:45 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM | EWM | 96689 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 00:45 | EWM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90374 | WBS.2.2.7.2.2.8 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ HBG AND BG ¦ MP2 ¦ MRO | 20.75 | 2021-01-31 17:45 | 2021-02-01 14:30 | [8 empty] | * |  | 2021-01-31 17:45 | 2021-02-01 14:30 |  | HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94467 | WBS.2.2.7.2.2.8.1 | N | N | Planned | HBG and BG - PTM_C0201 - Execute Transform For ECC MRO Inventory | 2 | 2021-01-31 17:45 | 2021-01-31 19:45 | DEEPA SAW | DEESAW@DELOITTE.COM | SAI TEAM;MELISSA KOTAREK;DATA ETL TEAM;DEAN PIPER;LYNN MCMURDO | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 10038,94323,81153,96572,96903 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 19:45 | DATA | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94471 | WBS.2.2.7.2.2.8.2 | N | N | Planned | HBG - PTM_C0201 - Preload Validation and sign-off for ECC MRO Inventory | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94467 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94491 | WBS.2.2.7.2.2.8.4 | N | N | Planned | HBG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2021-02-01 03:30 | 2021-02-01 06:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;MELISSA KOTAREK | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MELISSA.KOTAREK@GAPAC.COM | DATA | 94471,92152,29567,29571,93904,95429 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 06:30 | DATA | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96753 | WBS.2.2.7.2.2.8.25 | N | N | Planned | HBG - PTM_C0201 - Validate Load for HBG ECC Inventory (MRO) | 2 | 2021-02-01 06:30 | 2021-02-01 08:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | LISA HAUSER;JOHN CASABURRI;SAI TEAM;EWM TEAM;MARK PETERSON;CHRIS ZUMWALT | LISA.HAUSER@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MARK.PETERSON1@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94491 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 08:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94509 | WBS.2.2.7.2.2.8.6 | N | N | Planned | HBG - PTM_C0201 - Business Sign-Off For ECC MRO Inventory Load | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96753 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94505 | WBS.2.2.7.2.2.8.8 | N | N | Planned | HBG - PTM_C0201 - Pre-Load Error File Resolution - Prepare Delta Load File For ECC MRO Inv | 2 | 2021-02-01 06:30 | 2021-02-01 08:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94467,94491 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 08:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94497 | WBS.2.2.7.2.2.8.14 | N | N | Planned | HBG - PTM_C0201 - Run Inventory Conversion For Delta Load File For ECC MRO Inv | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 94505 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94520 | WBS.2.2.7.2.2.8.16 | N | N | Planned | HBG - PTM_C0201 - Post Delta Load Validation For ECC MRO Inv | 0.27 | 2021-02-01 09:30 | 2021-02-01 09:46 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94497 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 09:46 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96681 | WBS.2.2.7.2.2.8.18 | N | N | Planned | BG - PTM_C0201 - Preload Validation and sign-off for ECC Inventory (MRO) | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 94467 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96685 | WBS.2.2.7.2.2.8.22 | N | N | Planned | BG - PTM_C0201 - Business Sign-Off For ECC MRO Inventory Load | 2 | 2021-02-01 09:30 | 2021-02-01 11:30 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 96683 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 11:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96687 | WBS.2.2.7.2.2.8.24 | N | N | Planned | BG - PTM_C0201 - Post Delta Load Validation For ECC MRO Inv | 0.25 | 2021-02-01 10:30 | 2021-02-01 10:45 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | EWM | 96686 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 10:45 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96682 | WBS.2.2.7.2.2.8.19 | N | N | Planned | BG - PTM_C0201 - Execute Load program for ECC Inventory (MRO) | 3 | 2021-02-01 04:30 | 2021-02-01 07:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 96681,92152,29567,29571,96631,95429 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 07:30 | DATA | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96683 | WBS.2.2.7.2.2.8.20 | N | N | Planned | BG - PTM_C0201 - Validate Load for BG ECC Inventory (MRO) | 2 | 2021-02-01 07:30 | 2021-02-01 09:30 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | MARK PETERSON;DEAN PIPER;LYNN MCMURDO;SAI TEAM;EWM TEAM | MARK.PETERSON1@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96682 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 09:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96684 | WBS.2.2.7.2.2.8.21 | N | N | Planned | BG - PTM_C0201 - Pre-Load Error File Resolution - Prepare Delta Load File For ECC MRO Inv | 2 | 2021-02-01 07:30 | 2021-02-01 09:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96682,94467 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 09:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96686 | WBS.2.2.7.2.2.8.23 | N | N | Planned | BG - PTM_C0201 - Run Inventory Conversion For Delta Load File For ECC MRO Inv | 1 | 2021-02-01 09:30 | 2021-02-01 10:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96684 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 10:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94640 | WBS.2.2.7.2.2.8.12 | N | N | Planned | Load MP2 BOM from Flat File | 1 | 2021-02-01 09:30 | 2021-02-01 10:30 | JOHN SIKES | JOHN.SIKES2@GAPAC.COM | ERIC REINDL;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO | ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 96683,96753 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 10:30 | AC | HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96986 | WBS.2.2.7.2.2.8.26 | N | N | Planned | HBG - ITR_C0020 - Verify Data With Compare Tool; Spot-Check SAP DATA Reflects Loaded Data (Convert BOM – Functional Location Conversion – MP2) | 4 | 2021-02-01 10:30 | 2021-02-01 14:30 | JEFF LEE | JAMES.LEE1@gapac.com | CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 94640 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 14:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90379 | WBS.2.2.7.2.2.10 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ PTH ¦ AS8 ¦ MRO | 19 | 2021-01-31 17:45 | 2021-02-01 12:45 | [8 empty] | * |  | 2021-01-31 17:45 | 2021-02-01 12:45 |  | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94469 | WBS.2.2.7.2.2.10.1 | N | N | Planned | PTH - PTM_C0201 - Execute Transform For AS8 MRO Inventory | 2 | 2021-01-31 17:45 | 2021-01-31 19:45 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 10038,81154,5230,96903 |  |  | * |  | 2021-01-31 17:45 | 2021-01-31 19:45 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94473 | WBS.2.2.7.2.2.10.2 | N | N | Planned | PTH - PTM_C0201 - Preload Validation and sign-off for AS8 Inventory (MRO) | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | CHARLES DUPRE | charles.dupre@gapac.com | LEM LANCASTER;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;MIKE LACEY;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | LEM.LANCASTER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;MICHAEL.LACEY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 94469 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97787 | WBS.2.2.7.2.2.10.27 | N | N | Planned | CSR - PTM_C0201 - Preload Validation and sign-off for AS8 Inventory (MRO) | 2 | 2021-01-31 19:45 | 2021-01-31 21:45 | Danny Dixon | Daniel.Dixon2@gapac.com | LEM LANCASTER;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;MIKE LACEY;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | LEM.LANCASTER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;MICHAEL.LACEY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 94469 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 21:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94493 | WBS.2.2.7.2.2.10.4 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for AS8 Inventory (MRO) | 4 | 2021-02-01 05:30 | 2021-02-01 09:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 29564,29570,68331,94473,92152,95429 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 09:30 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94511 | WBS.2.2.7.2.2.10.6 | N | N | Planned | PTH - PTM_C0201 - Business Sign-Off For AS8 Load File | 2 | 2021-02-01 09:30 | 2021-02-01 11:30 | CHARLES DUPRE | charles.dupre@gapac.com | LEM LANCASTER;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;MIKE LACEY;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | LEM.LANCASTER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;MICHAEL.LACEY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 94493 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 11:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94507 | WBS.2.2.7.2.2.10.8 | N | N | Planned | PTH - PTM_C0201 - Pre-Load Error File Resolution - Prepare Delta Load File For AS8 | 2 | 2021-02-01 09:30 | 2021-02-01 11:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94469,94493 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 11:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94499 | WBS.2.2.7.2.2.10.10 | N | N | Planned | PTH - PTM_C0201 - Run Inventory Conversion For Delta Load File For AS8 | 1 | 2021-02-01 11:30 | 2021-02-01 12:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94507 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 12:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94522 | WBS.2.2.7.2.2.10.12 | N | N | Planned | PTH - PTM_C0201 - Post Delta Load Validation For AS8 | 0.25 | 2021-02-01 12:30 | 2021-02-01 12:45 | CHARLES DUPRE | charles.dupre@gapac.com | LEM LANCASTER;SAI TEAM;ARNAB DEY;DOUG STANISLAWSKI;AQUIL HUSAIN;JEFFREY GOLDMUNTZ;MIKE LACEY;EWM TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | LEM.LANCASTER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;AQHUSAIN@DELOITTE.COM;JGOLDMUNTZ@DELOITTE.COM;MICHAEL.LACEY@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | EWM | 94499 |  |  | * |  | 2021-02-01 12:30 | 2021-02-01 12:45 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96691 | WBS.2.2.7.2.2.34 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ PTH ¦ Elixir ¦ Vitals, Finished Goods | 18 | 2021-01-31 18:00 | 2021-02-01 12:00 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-02-01 12:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90407 | WBS.2.2.7.2.2.34.1 | N | N | Planned | PTH - PTM_C0201 - Execute Transform For Elixir Inventory | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5231,9091,10038,8874,8864,96703,96704 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5671 | WBS.2.2.7.2.2.34.2 | N | N | Planned | PTH - PTM_C0201 - Preload Validation and sign off for Elixir Inventory | 1.5 | 2021-01-31 20:00 | 2021-01-31 21:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 90407 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 21:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
8883 | WBS.2.2.7.2.2.34.3 | N | N | Planned | PTH - PTM_C0201 - Execute Load program for Elixir Inventory | 5 | 2021-02-01 03:30 | 2021-02-01 08:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 5671,92152,93138,93321,95429,97618 |  |  | * |  | 2021-02-01 03:30 | 2021-02-01 08:30 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5690 | WBS.2.2.7.2.2.34.4 | N | N | Planned | PTH - PTM_C0201 - Validate Load for Elixir Inventory | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 8883 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94503 | WBS.2.2.7.2.2.34.12 | N | N | Planned | PTH - PTM_C0201 - Execute Pre-Load Error File Resolution - Prepare Delta Load File For Elixir | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE;JAMES COWELL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com;James.Cowell@gapac.com | EWM | 5671,8883 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94501 | WBS.2.2.7.2.2.34.13 | N | N | Planned | PTH - PTM_C0201 - Run Inventory Conversion For Delta Load File For Elixir | 1 | 2021-02-01 10:30 | 2021-02-01 11:30 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE;JAMES COWELL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com;James.Cowell@gapac.com | EWM | 94503,95429 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94513 | WBS.2.2.7.2.2.34.14 | N | N | Planned | PTH - PTM_C0201 - Post Delta Load Validation For Elixir | 0.5 | 2021-02-01 11:30 | 2021-02-01 12:00 | ANDY JONES | Gibson.Jones@gapac.com | DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;JAMES COWELL;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;James.Cowell@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 94501 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 12:00 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90412 | WBS.2.2.7.2.2.34.15 | N | N | Planned | PTH - PTM_C0201 - Business Sign-Off For Elixir Load File | 1 | 2021-02-01 10:30 | 2021-02-01 11:30 | CJ KAUTH | christopher.kauth@gapac.com | ROBBIE GARNER;SAI TEAM;EWM TEAM;ANDY JONES;DARRYL JOHNSON;HADYN HUGHES;JAMES COWELL;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | EWM | 5690 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94537 | WBS.2.2.7.2.2.19 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ PTH ¦ E80 ¦ Finished Goods | 6.5 | 2021-01-31 18:00 | 2021-02-01 00:30 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-02-01 00:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94476 | WBS.2.2.7.2.2.19.1 | N | N | Planned | PTH - PTM_C0201 - Execute preload for E80 Inventory Load file (FG) | 1 | 2021-01-31 18:00 | 2021-01-31 19:00 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 9091,10038,8864,10039 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 19:00 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94477 | WBS.2.2.7.2.2.19.2 | N | N | Planned | PTH - PTM_C0201 - Preload validation and sign-off for E80 FG Inventory | 0.5 | 2021-01-31 19:00 | 2021-01-31 19:30 | JAMES COWELL | James.Cowell@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;HADYN HUGHES;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.HUGHES@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | EWM | 94476 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94478 | WBS.2.2.7.2.2.19.3 | N | N | Planned | PTH - PTM_C0201 - Execute Load for E80 FG Inventory | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;KIM VANWYCHEN | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | DATA | 94477,95429 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94482 | WBS.2.2.7.2.2.19.4 | N | N | Planned | PTH - PTM_C0201 - Validate Load for E80 FG Inventory | 0.25 | 2021-01-31 22:15 | 2021-01-31 22:30 | ANDY JONES | Gibson.Jones@gapac.com | DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;JAMES COWELL;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;James.Cowell@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 94478,93138 |  |  | * |  | 2021-01-31 22:15 | 2021-01-31 22:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94480 | WBS.2.2.7.2.2.19.5 | N | N | Planned | PTH - PTM_C0201 - Business Sign-Off For E80 FG Inventory Load | 1 | 2021-01-31 22:30 | 2021-01-31 23:30 | JAMES COWELL | James.Cowell@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;HADYN HUGHES;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.HUGHES@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | EWM | 94482 |  |  | * |  | 2021-01-31 22:30 | 2021-01-31 23:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94481 | WBS.2.2.7.2.2.19.6 | N | N | Planned | PTH - PTM_C0201 - Execute Pre-Load Error File Resolution - Prepare Delta Load File For E80 FG | 2 | 2021-01-31 20:30 | 2021-01-31 22:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94478 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 22:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97360 | WBS.2.2.7.2.2.19.10 | N | N | Planned | HBG - PTM_C0202 - Validate Load - Convert Truck/Transportation Load Data | 0.5 | 2021-01-31 22:00 | 2021-01-31 22:30 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:30 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94485 | WBS.2.2.7.2.2.19.7 | N | N | Planned | PTH - PTM_C0201 - Run Inventory Conversion For Delta Load File For E80 FG | 1 | 2021-01-31 22:30 | 2021-01-31 23:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 94481 |  |  | * |  | 2021-01-31 22:30 | 2021-01-31 23:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97359 | WBS.2.2.7.2.2.19.9 | N | N | Planned | RVG - PTM_C0201 - Run Inventory Conversion For Delta Load File For E80 FG | 1 | 2021-01-31 22:30 | 2021-01-31 23:30 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 94481 |  |  | * |  | 2021-01-31 22:30 | 2021-01-31 23:30 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94483 | WBS.2.2.7.2.2.19.8 | N | N | Planned | PTH - PTM_C0201 - Post Delta Load Validation For E80 FG | 1 | 2021-01-31 23:30 | 2021-02-01 00:30 | JAMES COWELL | James.Cowell@gapac.com | CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;HADYN HUGHES;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;CHRISTOPHER.HUGHES@GAPAC.COM ; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | EWM | 97359 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 00:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90377 | WBS.2.2.7.2.2.18 | N | N |  | FCW ¦ PTM_C0201 Convert Inventory ¦ RNC, RVG AND SCH ¦ JDA ¦ Finished Goods | 13.51 | 2021-01-31 18:00 | 2021-02-01 07:31 | [8 empty] | * |  | 2021-01-31 18:00 | 2021-02-01 07:31 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96692 | WBS.2.2.7.2.2.18.16 | N | N | Planned | RNC, RVG AND SCH - PTM_C0201 - Execute Transform For JDA Inventory | 2 | 2021-01-31 18:00 | 2021-01-31 20:00 | DEEPA SAW | DEESAW@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;JEREMY RAY;TOMMY NEFFENDORF;JENNIFER MCLEOD;JULI LEWIS | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | DATA | 5231,9091,10038,8874,8864,96703,96704 |  |  | * |  | 2021-01-31 18:00 | 2021-01-31 20:00 | DATA | RNC,RVG,SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94479 | WBS.2.2.7.2.2.18.3 | N | N | Planned | PTM_C0201 - Preload Validation and sign off for JDA Inventory - SCH, RNC, RVG | 1.5 | 2021-01-31 20:00 | 2021-01-31 21:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 96692 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 21:30 | EWM | SCH,RNC,RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94486 | WBS.2.2.7.2.2.18.5 | N | N | Planned | SCH - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | DATA | 92152,94479,95429,95685,95686,95687 |  |  | * |  | 2021-01-31 21:30 | 2021-02-01 02:30 | DATA | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94515 | WBS.2.2.7.2.2.18.6 | N | N | Planned | SCH - PTM_C0201 - Validate Load for JDA Inventory | 2 | 2021-02-01 02:30 | 2021-02-01 04:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94486 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:30 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94502 | WBS.2.2.7.2.2.18.8 | N | N | Planned | SCH - PTM_C0201 - Execute Pre-Load Error File Resolution - Prepare Delta Load File For JDA | 1.5 | 2021-02-01 02:30 | 2021-02-01 04:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94479,94486 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:00 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94500 | WBS.2.2.7.2.2.18.9 | N | N | Planned | SCH - PTM_C0201 - Run Inventory Conversion For Delta Load File For JDA | 1 | 2021-02-01 04:00 | 2021-02-01 05:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94502 |  |  | * |  | 2021-02-01 04:00 | 2021-02-01 05:00 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94512 | WBS.2.2.7.2.2.18.10 | N | N | Planned | SCH - PTM_C0201 - Post Delta Load Validation For JDA | 0.5 | 2021-02-01 05:00 | 2021-02-01 05:31 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94500 |  |  | * |  | 2021-02-01 05:00 | 2021-02-01 05:31 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93044 | WBS.2.2.7.2.2.18.11 | N | N | Planned | SCH - PTM_C0201 - Business Sign-Off For JDA Inventory Load | 2 | 2021-02-01 05:31 | 2021-02-01 07:31 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94512 |  |  | * |  | 2021-02-01 05:31 | 2021-02-01 07:31 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96727 | WBS.2.2.7.2.2.18.17 | N | N | Planned | RNC - PTM_C0201 - Preload Validation and sign off for JDA Inventory | 1.5 | 2021-01-31 20:00 | 2021-01-31 21:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DAVID ALENCASTRO;JEREMY RAY;PMO TEAM;EWM TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96692 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 21:30 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96728 | WBS.2.2.7.2.2.18.18 | N | N | Planned | RNC - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM | DATA | 96727,92152,95429,95685,95686,95687 |  |  | * |  | 2021-01-31 21:30 | 2021-02-01 02:30 | DATA | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96729 | WBS.2.2.7.2.2.18.19 | N | N | Planned | RNC - PTM_C0201 - Validate Load for JDA Inventory | 2 | 2021-02-01 02:30 | 2021-02-01 04:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DAVID ALENCASTRO;EWM TEAM;JEREMY RAY;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96728 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:30 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96730 | WBS.2.2.7.2.2.18.12 | N | N | Planned | RNC - PTM_C0201 - Execute Pre-Load Error File Resolution - Prepare Delta Load File For JDA | 1.5 | 2021-02-01 02:30 | 2021-02-01 04:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96727,96728 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:00 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96731 | WBS.2.2.7.2.2.18.13 | N | N | Planned | RNC - PTM_C0201 - Run Inventory Conversion For Delta Load File For JDA | 1 | 2021-02-01 04:00 | 2021-02-01 05:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96730 |  |  | * |  | 2021-02-01 04:00 | 2021-02-01 05:00 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96732 | WBS.2.2.7.2.2.18.14 | N | N | Planned | RNC - PTM_C0201 - Post Delta Load Validation For JDA | 0.5 | 2021-02-01 05:00 | 2021-02-01 05:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;DAVID ALENCASTRO;EWM TEAM;JEREMY RAY;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JEREMY.RAY@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96731 |  |  | * |  | 2021-02-01 05:00 | 2021-02-01 05:30 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96733 | WBS.2.2.7.2.2.18.15 | N | N | Planned | RNC - PTM_C0201 - Business Sign-Off For JDA Inventory Load | 2 | 2021-02-01 05:30 | 2021-02-01 07:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY SIMS;DON ABBOTT;JOHN CASABURRI;SAI TEAM;PATRICK WEAVER;EWM TEAM;PMO TEAM;JEREMY RAY;DAVID ALENCASTRO | JEREMY.SIMS@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;PATRICK_WEAVER@RYDER.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96732 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 07:30 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96734 | WBS.2.2.7.2.2.18.23 | N | N | Planned | RVG - PTM_C0201 - Preload Validation and sign off for JDA Inventory | 1.5 | 2021-01-31 20:00 | 2021-01-31 21:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96692 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 21:30 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96735 | WBS.2.2.7.2.2.18.24 | N | N | Planned | RVG - PTM_C0201 - Execute Load program from JDA Inventory | 5 | 2021-01-31 21:30 | 2021-02-01 02:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;PMO TEAM;JENNIFER MCLEOD;JULI LEWIS | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | DATA | 96734,92152,95429,95685,95686,95687 |  |  | * |  | 2021-01-31 21:30 | 2021-02-01 02:30 | DATA | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96736 | WBS.2.2.7.2.2.18.25 | N | N | Planned | RVG - PTM_C0201 - Validate Load for JDA Inventory | 2 | 2021-02-01 02:30 | 2021-02-01 04:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96735 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:30 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96737 | WBS.2.2.7.2.2.18.26 | N | N | Planned | RVG - PTM_C0201 - Execute Pre-Load Error File Resolution - Prepare Delta Load File For JDA | 1.5 | 2021-02-01 02:30 | 2021-02-01 04:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 96734,96735 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96738 | WBS.2.2.7.2.2.18.20 | N | N | Planned | RVG - PTM_C0201 - Run Inventory Conversion For Delta Load File For JDA | 1 | 2021-02-01 04:00 | 2021-02-01 05:00 | ALOK BHATT | alobhatt@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;JENNIFER MCLEOD;JULI LEWIS | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 96737 |  |  | * |  | 2021-02-01 04:00 | 2021-02-01 05:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96739 | WBS.2.2.7.2.2.18.21 | N | N | Planned | RVG - PTM_C0201 - Post Delta Load Validation For JDA | 0.5 | 2021-02-01 05:00 | 2021-02-01 05:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96738 |  |  | * |  | 2021-02-01 05:00 | 2021-02-01 05:30 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96740 | WBS.2.2.7.2.2.18.22 | N | N | Planned | RVG - PTM_C0201 - Business Sign-Off For JDA Inventory Load | 2 | 2021-02-01 05:30 | 2021-02-01 07:30 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96739 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 07:30 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95717 | WBS.2.2.7.2.2.11 | N | N |  | FCW ¦ PTM_C0201 RTR Inventory Valuation | 23 | 2021-01-31 17:15 | 2021-02-01 16:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-01 16:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95150 | WBS.2.2.7.2.2.11.1 | N | N | Planned | MFLE/MKLE - Activation of E0428 Enhancement - Standard Cost Validation for Production Orders | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | KRISHNA SINGAREDDY;VISHNU CHIRALA;SANDRA RICHARDS;RTR TEAM;SUVENDU KUMAR;SAI TEAM;RANJAI JOHN;BOATENG LAWRENCE | ksingareddy@deloitte.com;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;SUVKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96645 | WBS.2.2.7.2.2.11.21 | N | N | Planned | BG - Inventory Validation – Non-Storeroom Valuation Classes | 3 | 2021-02-01 08:00 | 2021-02-01 11:00 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 68428,21139,96631,96690,96641,97418,97419,97461 |  |  | * |  | 2021-02-01 08:00 | 2021-02-01 11:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96647 | WBS.2.2.7.2.2.11.23 | N | N | Planned | BG - Business Sign-off Inventory Validation - Non-Storeroom Valuation Classes | 0.5 | 2021-02-01 11:00 | 2021-02-01 11:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 96645 |  |  | * |  | 2021-02-01 11:00 | 2021-02-01 11:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96646 | WBS.2.2.7.2.2.11.22 | N | N | Planned | BG - Inventory Validation – Storeroom Valuation Classes | 3 | 2021-02-01 11:30 | 2021-02-01 14:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 96685,96687 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 14:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96648 | WBS.2.2.7.2.2.11.24 | N | N | Planned | BG - Business Sign-off Inventory Validation – Storeroom Valuation Classes | 0.5 | 2021-02-01 14:30 | 2021-02-01 15:00 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER;NOEL CLARK;LINDA GIBSON | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 96646 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 15:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94779 | WBS.2.2.7.2.2.11.5 | N | N | Planned | PTH - Inventory Validation - Storeroom Valuation Classes (AS8) | 3 | 2021-02-01 12:45 | 2021-02-01 15:45 | ANDRE GONZAQUE | ANDRE.GONZAQUE@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR | 94522,94511 |  |  | * |  | 2021-02-01 12:45 | 2021-02-01 15:45 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94780 | WBS.2.2.7.2.2.11.6 | N | N | Planned | PTH - Inventory Validation - Non-Storeroom Valuation Classes (ECC/JDA) | 3 | 2021-02-01 12:00 | 2021-02-01 15:00 | ANDRE GONZAQUE | ANDRE.GONZAQUE@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 94483,94482,94513,5690,21139,68428,95414,97418,97419 |  |  | * |  | 2021-02-01 12:00 | 2021-02-01 15:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93327 | WBS.2.2.7.2.2.11.7 | N | N | Planned | PTH - Business Sign-off Inventory Validation - Storeroom Valuation Classes (AS8) | 0.5 | 2021-02-01 15:45 | 2021-02-01 16:15 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 94779 |  |  | * |  | 2021-02-01 15:45 | 2021-02-01 16:15 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94781 | WBS.2.2.7.2.2.11.8 | N | N | Planned | PTH - Business Sign-off Inventory Validation - All Valuation Classes except SR (ECC/JDA) | 0.5 | 2021-02-01 15:00 | 2021-02-01 15:30 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM;NOEL CLARK;LINDA GIBSON | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 94780 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94777 | WBS.2.2.7.2.2.11.13 | N | N | Planned | HBG - Inventory Validation – Non-Storeroom Valuation Classes | 3 | 2021-02-01 07:30 | 2021-02-01 10:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 68428,21139,95272,97418,97419,97416 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 10:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95281 | WBS.2.2.7.2.2.11.14 | N | N | Planned | HBG - Inventory Validation – Storeroom Valuation Classes | 3 | 2021-02-01 10:30 | 2021-02-01 13:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | RTR | 94520,94509 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 13:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93916 | WBS.2.2.7.2.2.11.15 | N | N | Planned | HBG - Business Sign-off Inventory Validation - Non-Storeroom Valuation Classes | 0.5 | 2021-02-01 10:30 | 2021-02-01 11:00 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 94777 |  |  | * |  | 2021-02-01 10:30 | 2021-02-01 11:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95282 | WBS.2.2.7.2.2.11.16 | N | N | Planned | HBG - Business Sign-off Inventory Validation - Storeroom Valuation Classes | 0.5 | 2021-02-01 13:30 | 2021-02-01 14:00 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM;NOEL CLARK;LINDA GIBSON | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM | Business | 95281 |  |  | * |  | 2021-02-01 13:30 | 2021-02-01 14:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95195 | WBS.2.2.7.2.2.11.19 | N | N | Planned | SCH - Inventory Validation - All Valuation Classes | 1 | 2021-02-01 07:31 | 2021-02-01 08:31 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF;RANJAI JOHN;BOATENG LAWRENCE | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94512,94515,93044 |  |  | * |  | 2021-02-01 07:31 | 2021-02-01 08:31 | RTR - PC | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95197 | WBS.2.2.7.2.2.11.20 | N | N | Planned | SCH - Business Sign-off Inventory Validation - All Valuation Classes | 0.5 | 2021-02-01 08:31 | 2021-02-01 09:01 | HEATHER HUTCHINS | HMHUTCHI@GAPAC.COM | KIM HECTOR;NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | KIMBERLY.HECTOR@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 95195 |  |  | * |  | 2021-02-01 08:31 | 2021-02-01 09:01 | RTR - PC | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96715 | WBS.2.2.7.2.2.11.33 | N | N | Planned | RNC - Inventory Validation - All Valuation Classes | 1 | 2021-02-01 07:30 | 2021-02-01 08:30 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;JEREMY RAY;TOMMY NEFFENDORF;RANJAI JOHN;BOATENG LAWRENCE | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96729,96732,96733 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 08:30 | RTR - PC | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96716 | WBS.2.2.7.2.2.11.34 | N | N | Planned | RNC - Business Sign-off Inventory Validation - All Valuation Classes | 0.5 | 2021-02-01 08:30 | 2021-02-01 09:00 | HEATHER HUTCHINS | HMHUTCHI@GAPAC.COM | KIM HECTOR;NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | KIMBERLY.HECTOR@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 96715 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:00 | RTR - PC | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96717 | WBS.2.2.7.2.2.11.35 | N | N | Planned | RVG - Inventory Validation - All Valuation Classes | 1 | 2021-02-01 07:30 | 2021-02-01 08:30 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;JENNIFER MCLEOD;JULI LEWIS;RANJAI JOHN;BOATENG LAWRENCE | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96736,96739,96740 |  |  | * |  | 2021-02-01 07:30 | 2021-02-01 08:30 | RTR - PC | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96718 | WBS.2.2.7.2.2.11.36 | N | N | Planned | RVG - Business Sign-off Inventory Validation - All Valuation Classes | 0.5 | 2021-02-01 08:30 | 2021-02-01 09:00 | HEATHER HUTCHINS | HMHUTCHI@GAPAC.COM | KIM HECTOR;NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | KIMBERLY.HECTOR@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 96717 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:00 | RTR - PC | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96679 | WBS.2.2.7.2.2.11.31 | N | N | Planned | SAT - Inventory Validation - All Valuation Classes | 1 | 2021-02-01 03:00 | 2021-02-01 04:00 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;KELLY JANSSEN;RANJAI JOHN;LAWRENCE BOATENG | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MICHAEL.JANSSEN@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96668 |  |  | * |  | 2021-02-01 03:00 | 2021-02-01 04:00 | RTR - PC | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96674 | WBS.2.2.7.2.2.11.26 | N | N | Planned | SAT - Business Sign-off Inventory Validation - All Valuation Classes | 0.5 | 2021-02-01 04:00 | 2021-02-01 04:30 | HEATHER HUTCHINS | HMHUTCHI@GAPAC.COM | KIM HECTOR;NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | KIMBERLY.HECTOR@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 96679 |  |  | * |  | 2021-02-01 04:00 | 2021-02-01 04:30 | RTR - PC | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96678 | WBS.2.2.7.2.2.11.30 | N | N | Planned | REX - Inventory Validation - All Valuation Classes | 1 | 2021-02-01 03:00 | 2021-02-01 04:00 | NOEL CLARK | NOEL.CLARK@GAPAC.COM | LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96672 |  |  | * |  | 2021-02-01 03:00 | 2021-02-01 04:00 | RTR - PC | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96673 | WBS.2.2.7.2.2.11.25 | N | N | Planned | REX - Business Sign-off Inventory Validation - All Valuation Classes | 0.5 | 2021-02-01 04:00 | 2021-02-01 04:30 | HEATHER HUTCHINS | HMHUTCHI@GAPAC.COM | KIM HECTOR;NOEL CLARK;LINDA GIBSON;LAURA FRY;DON ABBOTT;SAI TEAM;RTR TEAM;JOHN CASABURRI;PMO TEAM;DANIEL ROSS;RANJAI JOHN;LAWRENCE BOATENG | KIMBERLY.HECTOR@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LINDA.GIBSON@GAPAC.COM;LAURA.FRY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DANIEL.ROSS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | Business | 96678 |  |  | * |  | 2021-02-01 04:00 | 2021-02-01 04:30 | RTR - PC | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95719 | WBS.2.2.7.2.2.13 | N | N |  | FCW ¦ RTR Mark and Release Costs for Current Deployment - PTH - 1034/5034 | 4 | 2021-02-01 15:30 | 2021-02-01 19:30 | [8 empty] | * |  | 2021-02-01 15:30 | 2021-02-01 19:30 |  | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95651 | WBS.2.2.7.2.2.13.1 | N | N | Planned | GP00 - Mark cost estimates for MFLE Plants 1034 (PTH) | 0.25 | 2021-02-01 15:30 | 2021-02-01 15:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 94781 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 15:45 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95653 | WBS.2.2.7.2.2.13.2 | N | N | Planned | Mark GPGR/GPPC for MFLE Plants 1034 | 0.25 | 2021-02-01 15:45 | 2021-02-01 16:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95651 |  |  | * |  | 2021-02-01 15:45 | 2021-02-01 16:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95663 | WBS.2.2.7.2.2.13.3 | N | N | Planned | Cost Rolls for 5*series plants in GP00 - 5034 | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95653 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95738 | WBS.2.2.7.2.2.13.4 | N | N | Planned | Validate GP00 1034 = 5034 (PTH) | 0.5 | 2021-02-01 17:00 | 2021-02-01 17:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95663 |  |  | * |  | 2021-02-01 17:00 | 2021-02-01 17:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95665 | WBS.2.2.7.2.2.13.5 | N | N | Planned | Cost rolls GPGR/GPPC for 5* series Plants - 5034 | 1 | 2021-02-01 17:30 | 2021-02-01 18:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95738 |  |  | * |  | 2021-02-01 17:30 | 2021-02-01 18:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95664 | WBS.2.2.7.2.2.13.6 | N | N | Planned | GP00 - Mark cost estimates for 5* Series Plants - 5034 | 0.25 | 2021-02-01 18:30 | 2021-02-01 18:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95665 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 18:45 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95667 | WBS.2.2.7.2.2.13.7 | N | N | Planned | Mark GPGR/GPPC for 5* Series Plants - 5034 | 0.25 | 2021-02-01 18:30 | 2021-02-01 18:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95665 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 18:45 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95652 | WBS.2.2.7.2.2.13.8 | N | N | Planned | GP00 - Release cost estimates for MFLE Plant 1034 | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95664,95429 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95654 | WBS.2.2.7.2.2.13.9 | N | N | Planned | Release GPGR/GPPC for MFLE Plant 1034 | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95653,95667,95429 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95666 | WBS.2.2.7.2.2.13.10 | N | N | Planned | GP00 - Release cost estimates for 5* Series Plants - 5034 | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95653,95667,95429 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95668 | WBS.2.2.7.2.2.13.11 | N | N | Planned | Release GPGR/GPPC for 5* Series Plants - 5034 | 0.25 | 2021-02-01 18:45 | 2021-02-01 19:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95667,95653,95429 |  |  | * |  | 2021-02-01 18:45 | 2021-02-01 19:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95656 | WBS.2.2.7.2.2.13.12 | N | N | Planned | Cost rolls MF30 in MFLE PLANT 1034 - resolve errors | 0.5 | 2021-02-01 19:00 | 2021-02-01 19:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95654,95652 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 19:30 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95720 | WBS.2.2.7.2.2.14 | N | N |  | FCW ¦ RTR Mark and Release Costs for Current Deployment - HBG - 1459/5459 | 4 | 2021-02-01 11:00 | 2021-02-01 15:00 | [8 empty] | * |  | 2021-02-01 11:00 | 2021-02-01 15:00 |  | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95657 | WBS.2.2.7.2.2.14.1 | N | N | Planned | GP00 - Mark cost estimates for MFLE Plants 1459 (HBG) | 0.25 | 2021-02-01 11:00 | 2021-02-01 11:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 93916 |  |  | * |  | 2021-02-01 11:00 | 2021-02-01 11:15 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95659 | WBS.2.2.7.2.2.14.2 | N | N | Planned | Mark GPGR/GPPC for MFLE Plants 1459 | 0.25 | 2021-02-01 11:15 | 2021-02-01 11:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95657 |  |  | * |  | 2021-02-01 11:15 | 2021-02-01 11:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95669 | WBS.2.2.7.2.2.14.3 | N | N | Planned | Cost Rolls for 5*series plants in GP00 - 5459 | 1 | 2021-02-01 11:30 | 2021-02-01 12:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95659 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 12:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95739 | WBS.2.2.7.2.2.14.4 | N | N | Planned | Validate GP00 1459 = 5459 (HBG) | 0.5 | 2021-02-01 12:30 | 2021-02-01 13:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95669 |  |  | * |  | 2021-02-01 12:30 | 2021-02-01 13:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95671 | WBS.2.2.7.2.2.14.5 | N | N | Planned | Cost rolls GPGR/GPPC for 5* series Plants - 5459 | 1 | 2021-02-01 13:00 | 2021-02-01 14:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95739 |  |  | * |  | 2021-02-01 13:00 | 2021-02-01 14:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95670 | WBS.2.2.7.2.2.14.6 | N | N | Planned | GP00 - Mark cost estimates for 5* Series Plants - 5459 | 0.25 | 2021-02-01 14:00 | 2021-02-01 14:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95671 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 14:15 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95673 | WBS.2.2.7.2.2.14.7 | N | N | Planned | Mark GPGR/GPPC for 5* Series Plants - 5459 | 0.25 | 2021-02-01 14:00 | 2021-02-01 14:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95671 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 14:15 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95658 | WBS.2.2.7.2.2.14.8 | N | N | Planned | GP00 - Release cost estimates for MFLE Plant 1459 | 0.25 | 2021-02-01 14:15 | 2021-02-01 14:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95670,95429 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 14:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95660 | WBS.2.2.7.2.2.14.9 | N | N | Planned | Release GPGR/GPPC for MFLE Plant 1459 | 0.25 | 2021-02-01 14:15 | 2021-02-01 14:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95659,95673,95429 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 14:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95672 | WBS.2.2.7.2.2.14.10 | N | N | Planned | GP00 - Release cost estimates for 5* Series Plants - 5459 | 0.25 | 2021-02-01 14:15 | 2021-02-01 14:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95659,95673,95429 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 14:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95674 | WBS.2.2.7.2.2.14.11 | N | N | Planned | Release GPGR/GPPC for 5* Series Plants - 5459 | 0.25 | 2021-02-01 14:15 | 2021-02-01 14:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95673,95659,95429 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 14:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95662 | WBS.2.2.7.2.2.14.12 | N | N | Planned | Cost rolls MF30 in MFLE PLANT 1459 - resolve errors | 0.5 | 2021-02-01 14:30 | 2021-02-01 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;AVIE LINDSEY;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Avie.Lindsey@gapac.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95658,95660 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 15:00 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96539 | WBS.2.2.7.2.2.33 | N | N |  | FCW ¦ RTR Mark and Release Costs for Current Deployment - BG - 1376/5376 | 4 | 2021-02-01 11:30 | 2021-02-01 15:30 | [8 empty] | * |  | 2021-02-01 11:30 | 2021-02-01 15:30 |  | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96540 | WBS.2.2.7.2.2.33.25 | N | N | Planned | GP00 - Mark cost estimates for MFLE Plants 1376 (BG) | 0.25 | 2021-02-01 11:30 | 2021-02-01 11:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96647 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 11:45 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96541 | WBS.2.2.7.2.2.33.26 | N | N | Planned | Mark GPGR/GPPC for MFLE Plants 1376 | 0.25 | 2021-02-01 11:45 | 2021-02-01 12:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96540 |  |  | * |  | 2021-02-01 11:45 | 2021-02-01 12:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96542 | WBS.2.2.7.2.2.33.27 | N | N | Planned | Cost Rolls for 5*series plants in GP00 - 5376 | 1 | 2021-02-01 12:00 | 2021-02-01 13:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96541 |  |  | * |  | 2021-02-01 12:00 | 2021-02-01 13:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96543 | WBS.2.2.7.2.2.33.28 | N | N | Planned | Validate GP00 1376 = 5376 (BG) | 0.5 | 2021-02-01 13:00 | 2021-02-01 13:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96542 |  |  | * |  | 2021-02-01 13:00 | 2021-02-01 13:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96544 | WBS.2.2.7.2.2.33.29 | N | N | Planned | Cost rolls GPGR/GPPC for 5* series Plants - 5376 | 1 | 2021-02-01 13:30 | 2021-02-01 14:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96543 |  |  | * |  | 2021-02-01 13:30 | 2021-02-01 14:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96545 | WBS.2.2.7.2.2.33.30 | N | N | Planned | GP00 - Mark cost estimates for 5* Series Plants - 5376 | 0.25 | 2021-02-01 14:30 | 2021-02-01 14:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96544 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 14:45 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96546 | WBS.2.2.7.2.2.33.31 | N | N | Planned | Mark GPGR/GPPC for 5* Series Plants - 5376 | 0.25 | 2021-02-01 14:30 | 2021-02-01 14:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96544 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 14:45 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96547 | WBS.2.2.7.2.2.33.32 | N | N | Planned | GP00 - Release cost estimates for MFLE Plant 1376 | 0.25 | 2021-02-01 14:45 | 2021-02-01 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96545,95429 |  |  | * |  | 2021-02-01 14:45 | 2021-02-01 15:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96548 | WBS.2.2.7.2.2.33.33 | N | N | Planned | Release GPGR/GPPC for MFLE Plant 1376 | 0.25 | 2021-02-01 14:45 | 2021-02-01 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96541,96546,95429 |  |  | * |  | 2021-02-01 14:45 | 2021-02-01 15:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96549 | WBS.2.2.7.2.2.33.34 | N | N | Planned | GP00 - Release cost estimates for 5* Series Plants - 5376 | 0.25 | 2021-02-01 14:45 | 2021-02-01 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96541,96546,95429 |  |  | * |  | 2021-02-01 14:45 | 2021-02-01 15:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96550 | WBS.2.2.7.2.2.33.35 | N | N | Planned | Release GPGR/GPPC for 5* Series Plants - 5376 | 0.25 | 2021-02-01 14:45 | 2021-02-01 15:00 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96541,96546,95429 |  |  | * |  | 2021-02-01 14:45 | 2021-02-01 15:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96551 | WBS.2.2.7.2.2.33.36 | N | N | Planned | Cost rolls MF30 in MFLE PLANT 1376 - resolve errors | 0.5 | 2021-02-01 15:00 | 2021-02-01 15:30 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;DEAN PIPER;LYNN MCMURDO;Amanda Smith;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;Amanda.Smith@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 96547,96548 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:30 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95722 | WBS.2.2.7.2.2.16 | N | N |  | FCW ¦ RTR Mark and Release Costs - Deployed Plants D1/D2/D3 | 3 | 2021-01-31 19:15 | 2021-01-31 22:15 | [8 empty] | * |  | 2021-01-31 19:15 | 2021-01-31 22:15 |  | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95697 | WBS.2.2.7.2.2.16.1 | N | N | Planned | GP00 - Release cost estimates for MFLE Deployed Plants 1006, 1104, 1106, 1357, 1503, 1462, 1101-n/a for mock cutovers | 1 | 2021-01-31 19:15 | 2021-01-31 20:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,95696,92478,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 20:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95682 | WBS.2.2.7.2.2.16.2 | N | N | Planned | GP00 - Release cost estimates for 5* Series Plants - go-live plants | 0.5 | 2021-01-31 19:15 | 2021-01-31 19:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,92478,95683,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:45 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95684 | WBS.2.2.7.2.2.16.3 | N | N | Planned | Release GPGR/GPPC for 5* Series Plants - Deployed Plants (D1/D2/D3)-n/a for mock cutovers | 1 | 2021-01-31 19:15 | 2021-01-31 20:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,95683,92478,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 20:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95698 | WBS.2.2.7.2.2.16.4 | N | N | Planned | Release GPGR/GPPC for MFLE Deployed Plants 1006, 1104, 1106, 1357, 1503, 1462, 1101-n/a for mock cutovers | 1 | 2021-01-31 19:15 | 2021-01-31 20:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,95696,92478,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 20:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97549 | WBS.2.2.7.2.2.16.7 | N | N | Planned | Validate Deployed Plants - 1006, 1104, 1106, 1357, 1503, 1462, 1101 release GP00=GPGR=GPPC-n/a for mock cutovers | 1 | 2021-01-31 20:15 | 2021-01-31 21:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | TONY SMITH;SAI TEAM;DONNA SMITH;NOEL CLARK;SANDRA RICHARDS;RTR TEAM;PMO TEAM;RANJAI JOHN;BOATENG LAWRENCE | AJSMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95697,95698,95682,95684 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 21:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95700 | WBS.2.2.7.2.2.16.6 | N | N | Planned | Cost rolls MF30 in MFLE Deployed Plants 1006, 1104, 1106, 1357, 1503, 1462, 1101 - resolve errors-n/a for mock cutovers | 1 | 2021-01-31 21:15 | 2021-01-31 22:15 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95698,97549 |  |  | * |  | 2021-01-31 21:15 | 2021-01-31 22:15 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95723 | WBS.2.2.7.2.2.17 | N | N |  | FCW ¦ RTR Mark and Release Costs - Non-Deployed Plants | 0.5 | 2021-01-31 19:15 | 2021-01-31 19:45 | [8 empty] | * |  | 2021-01-31 19:15 | 2021-01-31 19:45 |  | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95689 | WBS.2.2.7.2.2.17.1 | N | N | Planned | GP00 - Release cost estimates for 5* Series and 1* Series Plants - Non-Deployed sites | 0.5 | 2021-01-31 19:15 | 2021-01-31 19:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,95690,92478,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:45 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95691 | WBS.2.2.7.2.2.17.2 | N | N | Planned | Release GPGR/GPPC for 5* Series and 1* Series Plants - Non-Deployed Sites | 0.5 | 2021-01-31 19:15 | 2021-01-31 19:45 | KRISHNA RAVI | KRISHNACHAITANYA.RAVI@GAPAC.COM | SAI TEAM;RTR TEAM;KRISHNA SINGAREDDY;NOEL CLARK;TONY SMITH;MANOJ ANNAJI;J NAGENDRABABU;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;ksingareddy@deloitte.com;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;MANOJ.ANNAJI@GAPAC.COM;nagendrababu.j@kochtc.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 95519,95429,95690,92478,92742 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:45 | RTR - PC | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29563 | WBS.2.2.7.2.2.20 | N | N |  | FCW ¦ PTM_C0201 Inventory Conversion/GL Reconciliation | 26.75 | 2021-01-31 01:15 | 2021-02-01 04:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 04:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
29564 | WBS.2.2.7.2.2.20.1 | N | N | Planned | Extract MAP (Moving Average Price) values from AS8 for Costing/AUP as of Cutoff date | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | US INDIA GP DATA;SAI TEAM;DATA ETL TEAM;PMO TEAM;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29565 | WBS.2.2.7.2.2.20.2 | N | N | Planned | Run Inventory report from AS8 | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | DENISE MARSH;SAI TEAM;DATA ETL TEAM;PMO TEAM | DENISE.MARSH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
80928 | WBS.2.2.7.2.2.20.3 | N | N | Planned | Provide preload file for AS8 MAP (Moving Average Price)/Inventory validation | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 29564,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29566 | WBS.2.2.7.2.2.20.4 | N | N | Planned | Pre-load validation of AS8 Inventory report (based on Access DB) | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | CHAD FLAGG;ERIC REINDL;SAI TEAM;JASON RAMSEY;CASEY HERMANSEN;NOEL CLARK;DENISE ROBINSON;DOROTHY RUSSELL;DATA ETL TEAM;PMO TEAM | CHAD.FLAGG@GAPAC.COM;ERIC.REINDL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;NOEL.CLARK@GAPAC.COM;DOROBINS@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 29565,80928 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29570 | WBS.2.2.7.2.2.20.5 | N | N | Planned | Load Moving Average Prices for AS8 | 6 | 2021-01-31 20:30 | 2021-02-01 02:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 29566,92152 |  |  | * |  | 2021-01-31 20:30 | 2021-02-01 02:30 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
29567 | WBS.2.2.7.2.2.20.6 | N | N | Planned | Extract MAP (Moving Average Price values) from ECC for Procured Materials as of cutoff date | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | US INDIA GP DATA;SAI TEAM;DATA ETL TEAM;PMO TEAM;AMY EL-BASSIONI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM | DATA | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:45 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82338 | WBS.2.2.7.2.2.20.7 | N | N | Planned | Provide RTR team the list of Capital materials that need pricing to be zero-ed out | 0.5 | 2021-02-01 02:30 | 2021-02-01 03:00 | MARCOS MIRANDA | MARCOS.MIRANDA@GAPAC.COM | SHANKAR RAMNARAYANAN;NOEL CLARK;DONNA COOPER;HOLLY KREUER;DENISE ROBINSON;SAI TEAM;DENISE MARSH;DATA ETL TEAM | SRAMNARAYANAN@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;DCOOPER@GAPAC.COM;HOLLY.KREUER@GAPAC.COM;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DENISE.MARSH@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 29566,29570 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 03:00 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94839 | WBS.2.2.7.2.2.20.8 | N | N | Planned | PTH - Run MR21 To Zero Capital MAP (AS8 per list provided) and any other materials, As Needed | 1 | 2021-02-01 03:00 | 2021-02-01 04:00 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | RTR | 82338 |  |  | * |  | 2021-02-01 03:00 | 2021-02-01 04:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80929 | WBS.2.2.7.2.2.20.10 | N | N | Planned | Provide preload file for ECC MAP (Moving Average Price)/Inventory validation | 2 | 2021-01-31 19:30 | 2021-01-31 21:30 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | SAI TEAM;DATA ETL TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com | DATA | 29567,96903,80928 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 21:30 | DATA | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29569 | WBS.2.2.7.2.2.20.11 | N | N | Planned | Execute Pre-load Validation for ECC MAP Extract from ECC for procured materials as of cut off date | 2 | 2021-01-31 21:30 | 2021-01-31 23:30 | LAURA FRY | LAURA.FRY@GAPAC.COM | SAI TEAM;RTR TEAM;PMO TEAM;DENISE MARSH;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DENISE.MARSH@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 80929 |  |  | * |  | 2021-01-31 21:30 | 2021-01-31 23:30 | RTR - PC | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29571 | WBS.2.2.7.2.2.20.12 | N | N | Planned | Load Moving Average Prices for ECC (procured material) | 2 | 2021-01-31 23:30 | 2021-02-01 01:30 | DEBRAJ PAL | DEBRPAL@DELOITTE.COM | SAI TEAM;DATA ETL TEAM;PMO TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 29569,92152 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 01:30 | DATA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5683 | WBS.2.2.7.2.2.21 | N | N |  | FCW ¦ PTM_C0202 - Convert Truck/Transportation Load Data (Transportation Unit) | 20.75 | 2021-01-31 01:45 | 2021-01-31 22:30 | [8 empty] | * |  | 2021-01-31 01:45 | 2021-01-31 22:30 |  | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94577 | WBS.2.2.7.2.2.21.1 | N | N | Planned | SCH - PTM_C0202 - Extract all Trailers from JDA | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93005 | WBS.2.2.7.2.2.21.2 | N | N | Planned | SCH - PTM_C0202 - Prepare Trailer Upload File | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 94577 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96745 | WBS.2.2.7.2.2.21.19 | N | N | Planned | RNC - PTM_C0202 - Extract all Trailers from JDA | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96746 | WBS.2.2.7.2.2.21.20 | N | N | Planned | RNC - PTM_C0202 - Prepare Trailer Upload File | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 96745 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96747 | WBS.2.2.7.2.2.21.21 | N | N | Planned | RVG - PTM_C0202 - Extract all Trailers from JDA | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JENNIFER MCLEOD;JULI LEWIS | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96748 | WBS.2.2.7.2.2.21.22 | N | N | Planned | RVG - PTM_C0202 - Prepare Trailer Upload File | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;JEFFREY GOLDMUNTZ;EWM TEAM;SAI TEAM;JENNIFER MCLEOD;JULI LEWIS | DAVID.BASCHE@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 96747 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96649 | WBS.2.2.7.2.2.21.15 | N | N | Planned | BG - PTM_C0202 - Extract Trailer file | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;SAI TEAM;DEAN PIPER;EWM TEAM | LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96650 | WBS.2.2.7.2.2.21.16 | N | N | Planned | BG - PTM_C0202 - Prepare Trailer Upload file | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | EWM TEAM;JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 96649 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94573 | WBS.2.2.7.2.2.21.5 | N | N | Planned | PTH - PTM_C0202 - Extract all Trailers from Elixir | 2 | 2021-01-31 01:45 | 2021-01-31 03:45 | ANDY JONES | Gibson.Jones@gapac.com | DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JAMES COWELL;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;James.Cowell@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 03:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94327 | WBS.2.2.7.2.2.21.6 | N | N | Planned | PTH - PTM_C0202 -Prepare Trailer Upload File | 2 | 2021-01-31 03:45 | 2021-01-31 05:45 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | EWM TEAM;JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;SAI TEAM;KIM VANWYCHEN | ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KIM.VANWYCHEN@GAPAC.COM | EWM | 94573 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97480 | WBS.2.2.7.2.2.21.11 | N | N | Planned | HBG - PTM_C0202 - Extract Trailer file | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:45 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97479 | WBS.2.2.7.2.2.21.27 | N | N | Planned | HBG - PTM_C0202 - Prepare Trailer Upload file | 2.5 | 2021-01-31 02:45 | 2021-01-31 05:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | EWM TEAM;JACOB OWENS;AVINASH TALREJA;AQUIL HUSAIN;SAI TEAM;DEAN PIPER;LYNN MCMURDO | ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;AVTALREJA@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | EWM | 97480 |  |  | * |  | 2021-01-31 02:45 | 2021-01-31 05:15 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96651 | WBS.2.2.7.2.2.21.17 | N | N | Planned | BG - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 1 | 2021-01-31 17:00 | 2021-01-31 18:00 | BEAU EARLS | Beau.Earls@GAPAC.com | SAI TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96650,96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 18:00 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93004 | WBS.2.2.7.2.2.21.8 | N | N | Planned | SCH - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 0.25 | 2021-01-31 05:45 | 2021-01-31 06:00 | TOM NEFFENDORF | tommy.neffendorf@gapac.com | PHIL RACINE;SAI TEAM;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL;EWM TEAM;FRANZ JURVA;ESSEX BRASSEL | phil.racine@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;FRANZ.JURVA@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM | EWM | 93005 |  |  | * |  | 2021-01-31 05:45 | 2021-01-31 06:00 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96749 | WBS.2.2.7.2.2.21.23 | N | N | Planned | RNC - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 0.25 | 2021-01-31 05:45 | 2021-01-31 06:00 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;DAVID ALENCASTRO;EWM TEAM | JEREMY.RAY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96746 |  |  | * |  | 2021-01-31 05:45 | 2021-01-31 06:00 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96750 | WBS.2.2.7.2.2.21.24 | N | N | Planned | RVG - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 0.25 | 2021-01-31 05:45 | 2021-01-31 06:00 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 96748 |  |  | * |  | 2021-01-31 05:45 | 2021-01-31 06:00 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94329 | WBS.2.2.7.2.2.21.9 | N | N | Planned | PTH - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 1 | 2021-01-31 05:45 | 2021-01-31 06:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 94327 |  |  | * |  | 2021-01-31 05:45 | 2021-01-31 06:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97478 | WBS.2.2.7.2.2.21.28 | N | N | Planned | HBG - PTM_C0202 - Validate and business sign of Trailer upload file - SCM MDM | 1.5 | 2021-01-31 05:15 | 2021-01-31 06:45 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM;EWM TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 97479 |  |  | * |  | 2021-01-31 05:15 | 2021-01-31 06:45 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5684 | WBS.2.2.7.2.2.21.10 | N | N | Planned | PTM_C0202 - Execute Load program - Convert Truck/Transportation Load Data | 3 | 2021-01-31 19:00 | 2021-01-31 22:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5218,92152,93004,94329,96651,96749,96750,97478 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 22:00 | DATA | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94289 | WBS.2.2.7.2.2.21.12 | N | N | Planned | SCH - PTM_C0202 - Validate Load - Convert Truck/Transportation Data | 0.25 | 2021-01-31 22:00 | 2021-01-31 22:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY;GIOVANY CARVAJAL | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:15 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96751 | WBS.2.2.7.2.2.21.25 | N | N | Planned | RNC - PTM_C0202 - Validate Load - Convert Truck/Transportation Data | 0.25 | 2021-01-31 22:00 | 2021-01-31 22:15 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | JEREMY RAY;DON ABBOTT;JOHN CASABURRI;SAI TEAM;EWM TEAM;DAVID ALENCASTRO | JEREMY.RAY@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:15 | EWM | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96752 | WBS.2.2.7.2.2.21.26 | N | N | Planned | RVG - PTM_C0202 - Validate Load - Convert Truck/Transportation Data | 0.25 | 2021-01-31 22:00 | 2021-01-31 22:15 | JULI LEWIS | JULI.LEWIS@GAPAC.COM | REBECCA MORRIS;SAI TEAM;JENNIFER MCLEOD;EWM TEAM | REBECCA.MORRIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:15 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96652 | WBS.2.2.7.2.2.21.18 | N | N | Planned | BG - PTM_C0202 - Validate Load - Convert Truck/Transportation Load Data | 0.5 | 2021-01-31 22:00 | 2021-01-31 22:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;SAI TEAM;DEAN PIPER;EWM TEAM | LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:30 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94331 | WBS.2.2.7.2.2.21.14 | N | N | Planned | PTH - PTM_C0202 - Validate Load - Convert Truck/Transportation Load Data | 0.5 | 2021-01-31 22:00 | 2021-01-31 22:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | EWM | 5684 |  |  | * |  | 2021-01-31 22:00 | 2021-01-31 22:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5692 | WBS.2.2.7.2.2.22 | N | N |  | FCW ¦ PTP_C0005 - Convert Open Purchase Orders / STOs - ECC | 36.5 | 2021-01-31 01:45 | 2021-02-01 14:15 | [8 empty] | * |  | 2021-01-31 01:45 | 2021-02-01 14:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82766 | WBS.2.2.7.2.2.22.1 | N | N | Planned | Update BODS user CONV_BOD_S4P for Parameter EVO | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | SOUMYA PANDA | SOPANDA@DELOITTE.COM | MOHAMMED ABDULLAHI;DON ABBOTT;SAI TEAM;SEC TEAM;PMO TEAM | MABDULLAHI@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 36505,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SECURITY | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90972 | WBS.2.2.7.2.2.22.2 | N | N | Planned | PTP_C0005 - Provide Supplement PO And Service PO List to Data | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;AVINASH TALREJA;SRUTHI SRINIVASAN;SAI TEAM;MIKE PUPILLO;DOROTHY RUSSELL;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;AVTALREJA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MAPUPILL@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5246,36505,95439 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:45 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
9656 | WBS.2.2.7.2.2.22.3 | N | N | Planned | Execute PO and GR change processes in ECC and S4 (ZGRA, ZSPN, ZA2A, ZLNG, ZING) | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;AVINASH TALREJA;SRUTHI SRINIVASAN;SAI TEAM;MIKE PUPILLO;DOROTHY RUSSELL;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;AVTALREJA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MAPUPILL@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5246,36505,95439,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91850 | WBS.2.2.7.2.2.22.4 | N | N | Planned | Execute DQ report to compare PO, Material and PIR units of measure | 1.5 | 2021-01-31 17:30 | 2021-01-31 19:00 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;PMO TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 89675,81152,90972,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:00 | DATA | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91849 | WBS.2.2.7.2.2.22.5 | N | N | Planned | Review DQ comparison report and update PIR UOM before PO conversion | 1 | 2021-01-31 19:00 | 2021-01-31 20:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;DOROTHY RUSSELL;MIKE PUPILLO;YUDHAJIT MITRA;SHRISH MUDRI;SAI TEAM;PMO TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 91850 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 20:00 | PTP | PTH,HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5693 | WBS.2.2.7.2.2.22.6 | N | N | Planned | PTP_C0005 - Execute Transform program - Convert Open Purchase Orders - ECC | 2 | 2021-01-31 22:15 | 2021-02-01 00:15 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 81152,89675,90894,90972,91849,90147 |  |  | * |  | 2021-01-31 22:15 | 2021-02-01 00:15 | DATA | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82646 | WBS.2.2.7.2.2.22.7 | N | N | Planned | PTP_C0005- Validate Preload Transform - POs for WBS and GL Accounts - ECC - RTR | 1.5 | 2021-02-01 00:15 | 2021-02-01 01:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;DEAN PIPER;LYNN MCMURDO;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 5693 |  |  | * |  | 2021-02-01 00:15 | 2021-02-01 01:45 | RTR - PS | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82340 | WBS.2.2.7.2.2.22.8 | N | N | Planned | ECC Preliminary GR/IR Conversion Review and Tie Off - Transform Stage | 5 | 2021-02-01 00:15 | 2021-02-01 05:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | MONICA CUEVAS;BRUCE KIRKLEWSKI;MIKE PUPILLO;LAURA FRY;SAI TEAM;YUDHAJIT MITRA;PTP TEAM;ERIC BARSTOW;DOUGLAS CARANGELO;PMO TEAM;Simon Lee | MONICA.CUEVAS@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MAPUPILL@GAPAC.COM;LAURA.FRY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;DOUGLAS.CARANGELO@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM | PTP | 5693,82641 |  |  | * |  | 2021-02-01 00:15 | 2021-02-01 05:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5694 | WBS.2.2.7.2.2.22.9 | N | N | Planned | PTP_C0005 - Validate Preload Transform - Convert Open Purchase Orders - ECC | 5 | 2021-02-01 00:15 | 2021-02-01 05:15 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | ERIC BARSTOW;NITIN GUPTA;CASEY HERMANSEN;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Mark Bernard | ERIC.BARSTOW@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM | PTP | 5693,82641 |  |  | * |  | 2021-02-01 00:15 | 2021-02-01 05:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92508 | WBS.2.2.7.2.2.22.10 | N | N | Planned | ECC PO Preload - Review the Prelim GR/IR Tie Out File (incl RTR) | 0.5 | 2021-02-01 05:15 | 2021-02-01 05:45 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;DOROTHY RUSSELL;SAI TEAM;MIKE PUPILLO;BRETT DETTMERING;DOUGLAS CARANGELO;PTP TEAM;DEAN PIPER;LYNN MCMURDO | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MAPUPILL@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;DOUGLAS.CARANGELO@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5694,82340 |  |  | * |  | 2021-02-01 05:15 | 2021-02-01 05:45 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5695 | WBS.2.2.7.2.2.22.11 | N | N | Planned | PTP_C0005 - Execute Load program - Convert Open Purchase Orders - ECC | 3 | 2021-02-01 05:15 | 2021-02-01 08:15 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 5694,82646,82766,92152,82340,90147 |  |  | * |  | 2021-02-01 05:15 | 2021-02-01 08:15 | DATA | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97451 | WBS.2.2.7.2.2.22.24 | N | N | Planned | Delete duplicated schedule lines on POs in S/4 - File provided by Data team | 0.5 | 2021-02-01 08:15 | 2021-02-01 08:45 | SANDEEP A | SANDEEP.A@KOCHGS.COM | MONICA CUEVAS;ERIC BARSTOW;PTP TEAM;MIKE PUPILLO;SRUTHI SRINIVASAN;DOUGLAS CARANGELO;SAI TEAM | MONICA.CUEVAS@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MAPUPILL@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;DOUGLAS.CARANGELO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 5695 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 08:45 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94291 | WBS.2.2.7.2.2.22.12 | N | N | Planned | Identify POs that have an order Price UOM on the PO Line that differs from the Unit of Purchase | 1 | 2021-02-01 08:15 | 2021-02-01 09:15 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | PTP TEAM;ERIC BARSTOW;SAI TEAM;PMO TEAM | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 5695 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 09:15 | PTP | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82652 | WBS.2.2.7.2.2.22.13 | N | N | Planned | PTP_C0005 - Validate Load - POs for WBS and GL Accounts - ECC - RTR | 1.5 | 2021-02-01 08:15 | 2021-02-01 09:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;DEAN PIPER;LYNN MCMURDO;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 5695 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 09:45 | RTR - PS | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82662 | WBS.2.2.7.2.2.22.14 | N | N | Planned | ECC Preliminary GR/IR Conversion Review and Tie Off - Load Stage | 3.5 | 2021-02-01 08:45 | 2021-02-01 12:15 | SANDEEP A | SANDEEP.A@KOCHGS.COM | MONICA CUEVAS;ERIC BARSTOW;PTP TEAM;MIKE PUPILLO;SRUTHI SRINIVASAN;DOUGLAS CARANGELO;SAI TEAM | MONICA.CUEVAS@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MAPUPILL@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;DOUGLAS.CARANGELO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 5695,97451 |  |  | * |  | 2021-02-01 08:45 | 2021-02-01 12:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5696 | WBS.2.2.7.2.2.22.15 | N | N | Planned | PTP_C0005 - Validate Load - Convert Open Purchase Orders - ECC | 4 | 2021-02-01 08:15 | 2021-02-01 12:15 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | ERIC BARSTOW;NITIN GUPTA;CASEY HERMANSEN;SAI TEAM;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Mark Bernard | ERIC.BARSTOW@GAPAC.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM | PTP | 5695 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 12:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92507 | WBS.2.2.7.2.2.22.16 | N | N | Planned | ECC PO Post Load - Review the Prelim GR/IR Tie Out File (incl RTR) | 0.5 | 2021-02-01 12:15 | 2021-02-01 12:45 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;DOROTHY RUSSELL;AMANDA WATZKA;SAI TEAM;MIKE PUPILLO;BRETT DETTMERING;PTP TEAM;DOUGLAS CARANGELO;DEAN PIPER;LYNN MCMURDO | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;AMANDA.WATZKA@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MAPUPILL@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;DOUGLAS.CARANGELO@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | PTP | 5696,82662 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 12:45 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82649 | WBS.2.2.7.2.2.22.17 | N | N | Planned | PTP_C0005 - ECC - Manually create / change Pos that Fall Out from PO Load | 1 | 2021-02-01 12:15 | 2021-02-01 13:15 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;SAI TEAM;DOROTHY RUSSELL;ERIC BARSTOW;PTP TEAM;PMO TEAM;Mark Bernard | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MARK.BERNARD@GAPAC.COM | PTP | 82652,5696 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 13:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82097 | WBS.2.2.7.2.2.22.18 | N | N | Planned | Run Mass Change Program To Reduce External Spend PO’s (Not STO’s) To Adjust PO Quantity To Received Level Using Transaction ME2N or ME80FN. Update PO Quantity, Save PO, Don't Send Update | 1 | 2021-02-01 12:15 | 2021-02-01 13:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;BRUCE KIRKLEWSKI;CASEY HERMANSEN;CHARLES BLUMREICH;YUDHAJIT MITRA;DON ABBOTT;SAI TEAM;PTP TEAM;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;YMITRA@DELOITTE.COM;DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5696 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 13:15 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80748 | WBS.2.2.7.2.2.22.19 | N | N | Planned | Run VL64 To Create Inbound Deliveries | 0.5 | 2021-02-01 12:15 | 2021-02-01 12:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | NITIN GUPTA;CASEY HERMANSEN;YUDHAJIT MITRA;SRUTHI SRINIVASAN;SAI TEAM;PTP TEAM;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5696,5701,82661 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 12:45 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
80747 | WBS.2.2.7.2.2.22.20 | N | N | Planned | Update PO Lines To Remove GR Based IV | 0.5 | 2021-02-01 12:15 | 2021-02-01 12:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | NITIN GUPTA;CASEY HERMANSEN;YUDHAJIT MITRA;SRUTHI SRINIVASAN;SAI TEAM;PTP TEAM;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;DEAN PIPER;LYNN MCMURDO;SANDEEP A | NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 5696,5701,82239,82661,82652 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 12:45 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82477 | WBS.2.2.7.2.2.22.21 | N | N | Planned | Send a PO Conv table to Datacap, Ariba, SPARC w/ POs, Reqs, Suppliers | 1 | 2021-02-01 13:15 | 2021-02-01 14:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;BRUCE KIRKLEWSKI;MIKE PUPILLO;CHARLES BLUMREICH;LAURA FRY;SAI TEAM;YUDHAJIT MITRA;PTP TEAM;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MAPUPILL@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;LAURA.FRY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 82658,82660,82649 |  |  | * |  | 2021-02-01 13:15 | 2021-02-01 14:15 | PTP | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92744 | WBS.2.2.7.2.2.22.22 | N | N | Planned | Reconcile vendor partners on converted PO's (OA's and PI's) | 1 | 2021-02-01 13:15 | 2021-02-01 14:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;PMO TEAM;MONICA CUEVAS;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 82658,82660,82649 |  |  | * |  | 2021-02-01 13:15 | 2021-02-01 14:15 | PTP | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96656 | WBS.2.2.7.2.2.22.23 | N | N | Planned | Update GP intercompany EDI processes (Corrugated/Bleached Board/Sterling/Webmethods/PO) | 1 | 2021-01-31 18:30 | 2021-01-31 19:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;PMO TEAM;MONICA CUEVAS;RON MASON;MICHELLE AGUIRRE;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;RONMASON@GAPAC.COM;Michelle.Aguirre@GAPAC.com ;SANDEEP.A@KOCHGS.COM | PTP | 9656 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5697 | WBS.2.2.7.2.2.23 | N | N |  | FCW ¦ PTP_C0005.1 - Convert Purchase Orders - AS8 (Open & Service POs) | 22.75 | 2021-01-31 17:30 | 2021-02-01 16:15 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 16:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
10027 | WBS.2.2.7.2.2.23.1 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Service Purchase Orders | 4 | 2021-01-31 17:30 | 2021-01-31 21:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 81155,82626,89675,81154,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 21:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5698 | WBS.2.2.7.2.2.23.2 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Transform program - Convert Open Purchase Orders | 3 | 2021-01-31 17:30 | 2021-01-31 20:30 | ANJALI SINHA | ANJASINHA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 81155,82626,89675,81154,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 20:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82341 | WBS.2.2.7.2.2.23.3 | N | N | Planned | PTP_C0005.1 - AS8 - Preliminary GR/IR Conversion Review and Tie Off - Transform Stage | 4 | 2021-01-31 20:30 | 2021-02-01 00:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;BRUCE KIRKLEWSKI;MIKE PUPILLO;CHARLES BLUMREICH;LAURA FRY;SAI TEAM;YUDHAJIT MITRA;PTP TEAM;JESSICA REED;KRISTINA KAUTH | ERIC.BARSTOW@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MAPUPILL@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;LAURA.FRY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;jessica.reed1@gapac.com;KRISTINA.KAUTH@GAPAC.COM | PTP | 5698,82641 |  |  | * |  | 2021-01-31 20:30 | 2021-02-01 00:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5699 | WBS.2.2.7.2.2.23.4 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Preload Transform - Convert Open Purchase Orders | 4 | 2021-01-31 20:30 | 2021-02-01 00:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;SAI TEAM;NITIN GUPTA;CASEY HERMANSEN;MIKE PUPILLO;PTP TEAM;PMO TEAM;JESSICA REED;KRISTINA KAUTH | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jessica.reed1@gapac.com;KRISTINA.KAUTH@GAPAC.COM | PTP | 5698,82641 |  |  | * |  | 2021-01-31 20:30 | 2021-02-01 00:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92502 | WBS.2.2.7.2.2.23.5 | N | N | Planned | AS8 Material PO Preload - Review the Prelim GR/IR Tie Out File (incl RTR) | 0.5 | 2021-02-01 00:30 | 2021-02-01 01:00 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;MARK BLOZINSKI;SAI TEAM;DOROTHY RUSSELL;BRETT DETTMERING;PTP TEAM;HANNA KATZ;KRISTINA KAUTH | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;HANNA.KATZ@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM | PTP | 5699,82341 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 01:00 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82657 | WBS.2.2.7.2.2.23.6 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Preload Transform - Convert Open Purchase Orders - Asset Suite POs for WBS and GL Accounts - RTR | 2 | 2021-01-31 20:30 | 2021-01-31 22:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 5698 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 22:30 | RTR - PS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10028 | WBS.2.2.7.2.2.23.7 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Preload Transform - Service Purchase Orders | 3 | 2021-01-31 21:30 | 2021-02-01 00:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;SAI TEAM;NITIN GUPTA;CASEY HERMANSEN;MARK BLOZINSKI;PTP TEAM;PMO TEAM;SRUTHI SRINIVASAN | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM | PTP | 10027,82641 |  |  | * |  | 2021-01-31 21:30 | 2021-02-01 00:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92506 | WBS.2.2.7.2.2.23.8 | N | N | Planned | AS8 Service PO Preload - Review PO Validation Tie Out File | 0.5 | 2021-02-01 00:30 | 2021-02-01 01:00 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;MARK BLOZINSKI;DOROTHY RUSSELL;SAI TEAM;SRUTHI SRINIVASAN;PTP TEAM | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10028 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 01:00 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82656 | WBS.2.2.7.2.2.23.9 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Preload Transform - Service Purchase Orders - Asset Suite POs for WBS and GL Accounts - RTR | 2 | 2021-01-31 21:30 | 2021-01-31 23:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 10027 |  |  | * |  | 2021-01-31 21:30 | 2021-01-31 23:30 | RTR - PS | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5700 | WBS.2.2.7.2.2.23.10 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Convert Open Purchase Orders | 6 | 2021-02-01 00:30 | 2021-02-01 06:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5699,82657,82766,92152 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 06:30 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
10029 | WBS.2.2.7.2.2.23.11 | N | N | Planned | PTP_C0005.1 - AS8 - Execute Load program - Service Purchase Orders | 2 | 2021-02-01 00:30 | 2021-02-01 02:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 10028,82656,82766,92152 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:30 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
89764 | WBS.2.2.7.2.2.23.12 | N | N | Planned | PTP_C0005.1 - AS8 - Turn on the enhancement | 0.5 | 2021-02-01 00:30 | 2021-02-01 01:00 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10028,82656 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 01:00 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5701 | WBS.2.2.7.2.2.23.13 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Load - Convert Open Purchase Orders | 3 | 2021-02-01 06:30 | 2021-02-01 09:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;SAI TEAM;NITIN GUPTA;CASEY HERMANSEN;MIKE PUPILLO;PTP TEAM;PMO TEAM;JESSICA REED;KRISTINA KAUTH | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jessica.reed1@gapac.com;KRISTINA.KAUTH@GAPAC.COM | PTP | 5700 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 09:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92503 | WBS.2.2.7.2.2.23.14 | N | N | Planned | AS8 Material PO Post Load - Review the Prelim GR/IR Tie Out File (incl RTR) | 0.5 | 2021-02-01 09:30 | 2021-02-01 10:00 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;MARK BLOZINSKI;SAI TEAM;DOROTHY RUSSELL;BRETT DETTMERING;PTP TEAM;HANNA KATZ;KRISTINA KAUTH | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;HANNA.KATZ@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM | PTP | 5701,82663 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 10:00 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82663 | WBS.2.2.7.2.2.23.15 | N | N | Planned | PTP_C0005.1 - AS8 - Preliminary GR/IR Conversion Review and Tie Off - Load Stage | 3 | 2021-02-01 06:30 | 2021-02-01 09:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;BRUCE KIRKLEWSKI;MIKE PUPILLO;CHARLES BLUMREICH;LAURA FRY;SAI TEAM;YUDHAJIT MITRA;PTP TEAM;JESSICA REED;KRISTINA KAUTH | ERIC.BARSTOW@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;MAPUPILL@GAPAC.COM;CHARLES.BLUMREICH@GAPAC.COM;LAURA.FRY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;jessica.reed1@gapac.com;KRISTINA.KAUTH@GAPAC.COM | PTP | 5700 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 09:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82661 | WBS.2.2.7.2.2.23.16 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Load - Convert Open Purchase Orders - Asset Suite POs for WBS and GL Accounts - RTR | 2 | 2021-02-01 06:30 | 2021-02-01 08:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 5700 |  |  | * |  | 2021-02-01 06:30 | 2021-02-01 08:30 | RTR - PS | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82660 | WBS.2.2.7.2.2.23.17 | N | N | Planned | PTP_C0005.1 - AS8 - Manually create / change Pos that Fall Out from PO Load | 1 | 2021-02-01 09:30 | 2021-02-01 10:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;PTP TEAM;PMO TEAM;JESSICA REED;KRISTINA KAUTH | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jessica.reed1@gapac.com;KRISTINA.KAUTH@GAPAC.COM | PTP | 82661,5701 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 10:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90287 | WBS.2.2.7.2.2.23.18 | N | N | Planned | Ensure PO Conversion Users Have Access To The Correct EIM Ariba Realm(s) | 2 | 2021-02-01 14:15 | 2021-02-01 16:15 | PAM NIX | PSNIX@GAPAC.COM | SAI TEAM;VIRGINIA SILICKIENE;PTP TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;VSILICK@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 21147,5699,10028,5694,82477 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 16:15 | EIM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95385 | WBS.2.2.7.2.2.23.19 | N | N | Planned | Ensure PO Conversion Suppliers are set up in the Correct EIM Ariba Realm(s) | 2 | 2021-02-01 14:15 | 2021-02-01 16:15 | RICHARD WORTMAN | RWORTMAN@GAPAC.COM | ERIC BARSTOW;PTP TEAM;PAM NIX;MASON DRAKE;SAI TEAM | ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;PSNIX@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 21147,5699,10028,5694,82477 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 16:15 | EIM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
10030 | WBS.2.2.7.2.2.23.20 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Load - Service Purchase Orders | 3 | 2021-02-01 02:30 | 2021-02-01 05:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | ERIC BARSTOW;SAI TEAM;NITIN GUPTA;CASEY HERMANSEN;MARK BLOZINSKI;PTP TEAM;PMO TEAM;SRUTHI SRINIVASAN | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM | PTP | 10029 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 05:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92505 | WBS.2.2.7.2.2.23.21 | N | N | Planned | AS8 Service PO Post Load - Review PO Validation Tie Out File | 0.5 | 2021-02-01 05:30 | 2021-02-01 06:00 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | MASON DRAKE;ERIC BARSTOW;MARK BLOZINSKI;DOROTHY RUSSELL;SAI TEAM;SRUTHI SRINIVASAN;PTP TEAM | MASON.DRAKE@GAPAC.COM;ERIC.BARSTOW@GAPAC.COM;MARK.BLOZINSKI@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 10030 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 06:00 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
89763 | WBS.2.2.7.2.2.23.22 | N | N | Planned | PTP_C0005.1 - AS8 - Turn off the enhancement | 0.5 | 2021-02-01 12:15 | 2021-02-01 12:45 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM | DATA | 10029,5696,10030 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 12:45 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82659 | WBS.2.2.7.2.2.23.23 | N | N | Planned | PTP_C0005.1 - AS8 - Validate Load - Service Purchase Orders - Asset Suite POs for WBS and GL Accounts - RTR | 1.5 | 2021-02-01 02:30 | 2021-02-01 04:00 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DONNA SMITH;SAI TEAM;RTR TEAM;PMO TEAM;BRETT DETTMERING | DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 10029 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 04:00 | RTR - PS | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82658 | WBS.2.2.7.2.2.23.24 | N | N | Planned | PTP_C0005.1 - AS8 Service Pos - Manually create / change Pos that Fall Out from PO Load | 1 | 2021-02-01 05:30 | 2021-02-01 06:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;SAI TEAM;ERIC BARSTOW;PTP TEAM;PMO TEAM;SRUTHI SRINIVASAN | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM | PTP | 82659,10030 |  |  | * |  | 2021-02-01 05:30 | 2021-02-01 06:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94595 | WBS.2.2.7.2.2.24 | N | N |  | FCW ¦ GR/IR Conversion Review and Tie Off | 2.5 | 2021-02-02 01:00 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-02-02 01:00 | 2021-02-02 03:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
80839 | WBS.2.2.7.2.2.24.25 | N | N | Planned | PTH - PTP_C0005.1 - AS8 & ECC - GR/IR Conversion Review and Tie Off | 2 | 2021-02-02 01:00 | 2021-02-02 03:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;PTP TEAM;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 5696,5701,9698 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 03:00 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97522 | WBS.2.2.7.2.2.24.32 | N | N | Planned | BG - PTP_C0005.1 - AS8 & ECC - GR/IR Conversion Review and Tie Off | 2 | 2021-02-02 01:00 | 2021-02-02 03:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;PTP TEAM;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 5696,5701,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 03:00 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97520 | WBS.2.2.7.2.2.24.30 | N | N | Planned | HBG - PTP_C0005.1 - AS8 & ECC - GR/IR Conversion Review and Tie Off | 2 | 2021-02-02 01:00 | 2021-02-02 03:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;PTP TEAM;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 5696,5701,97535 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 03:00 | RTR - GL | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93329 | WBS.2.2.7.2.2.24.26 | N | N | Planned | PTH - Validate/Sign Off on GR/IR Balance (Ledger and Subledger) loaded in S/4HANA | 0.5 | 2021-02-02 03:00 | 2021-02-02 03:30 | MARK HILL | JOHN.HILL1@GAPAC.COM | PTH RTR TEAM;CJ KAUTH;SAI TEAM;RTR TEAM | JOHN.HILL1@GAPAC.COM;ANNETTE.GONZALES@GAPAC.COM;andre.gonzaque@gapac.com;JEFFREY.ROBINSON@GAPAC.COM;DENISE.MARSH@GAPAC.com;laura.fry@gapac.com;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM | Business | 80839 |  |  | * |  | 2021-02-02 03:00 | 2021-02-02 03:30 | RTR - PC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93918 | WBS.2.2.7.2.2.24.1 | N | N | Planned | HBG - Validate/Sign Off on GR/IR Balance (Ledger and Subledger) loaded in S/4HANA | 0.5 | 2021-02-02 03:00 | 2021-02-02 03:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;LAURA FRY;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 97520 |  |  | * |  | 2021-02-02 03:00 | 2021-02-02 03:30 | RTR - PC | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96653 | WBS.2.2.7.2.2.24.3 | N | N | Planned | BG - Validate/Sign Off on GR/IR Balance (Ledger and Subledger) loaded in S4 | 0.5 | 2021-02-02 03:00 | 2021-02-02 03:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | BG RTR TEAM;SAI TEAM;LYNN MCMURDO;DEAN PIPER | AMANDA.SMITH@GAPAC.COM;JoAnna.Johnson@GAPAC.com;Steven.Smith4@GAPAC.com;David.Harber@GAPAC.com;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com | Business | 97522 |  |  | * |  | 2021-02-02 03:00 | 2021-02-02 03:30 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90779 | WBS.2.2.7.2.2.25 | N | N |  | FCW ¦ ITR_C0067 - Convert Scheduled Maintenance Plans – AS8 | 9 | 2021-01-31 17:30 | 2021-02-01 02:30 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 02:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5770 | WBS.2.2.7.2.2.25.1 | N | N | Planned | ITR_C0067 - Execute Transform program - Convert Scheduled Maintenance Plans – Asset suite | 4 | 2021-01-31 17:30 | 2021-01-31 21:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 81154,5476,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 21:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5771 | WBS.2.2.7.2.2.25.2 | N | N | Planned | ITR_C0067 - Validate Preload Transform - Convert Scheduled Maintenance Plans – Asset suite | 0.5 | 2021-01-31 21:30 | 2021-01-31 22:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5770 |  |  | * |  | 2021-01-31 21:30 | 2021-01-31 22:00 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5772 | WBS.2.2.7.2.2.25.3 | N | N | Planned | ITR_C0067 - Execute Load program - Convert Scheduled Maintenance Plans – Asset suite | 2 | 2021-01-31 22:00 | 2021-02-01 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5771,92152 |  |  | * |  | 2021-01-31 22:00 | 2021-02-01 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5773 | WBS.2.2.7.2.2.25.4 | N | N | Planned | ITR_C0067 - Validate Load - Convert Scheduled Maintenance Plans – Asset suite | 0.75 | 2021-02-01 | 2021-02-01 00:45 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5772,5768 |  |  | * |  | 2021-02-01 | 2021-02-01 00:45 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
89606 | WBS.2.2.7.2.2.25.5 | N | N | Planned | PTH - ITR_C0067 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Scheduled Maintenance Plans –AS8) | 0.75 | 2021-02-01 00:45 | 2021-02-01 01:30 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5773 |  |  | * |  | 2021-02-01 00:45 | 2021-02-01 01:30 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92081 | WBS.2.2.7.2.2.25.7 | N | N | Planned | Transfer inflight work orders to MRS | 1 | 2021-02-01 01:30 | 2021-02-01 02:30 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM | AC | 89606 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 02:30 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9699 | WBS.2.2.7.2.2.26 | N | N |  | FCW ¦ PTP_C0236 - Convert Goods Receipt for Open Invoice Reconciliation | 6.75 | 2021-02-01 12:15 | 2021-02-01 19:00 | [8 empty] | * |  | 2021-02-01 12:15 | 2021-02-01 19:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97548 | WBS.2.2.7.2.2.26.21 | N | N | Planned | Checkpoint Task to Confirm Path Forward for GR/IR | 0.5 | 2021-02-01 12:45 | 2021-02-01 13:15 | DON ABBOTT | DON.ABBOTT@GAPAC.COM | JOHN CASABURRI;SAI TEAM;CASEY HERMANSEN;MIKE PUPILLO;DONNA SMITH;NORMAN REYNOLDS;DENISE ROBINSON;MADAN ZOLLU | JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;MAPUPILL@GAPAC.COM;DONNA.SMITH@GAPAC.COM;norman.reynolds@gapac.com;DOROBINS@GAPAC.COM;MZOLLU@DELOITTE.COM | SAI | 92503,92507 |  |  | * |  | 2021-02-01 12:45 | 2021-02-01 13:15 | SAI | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
68402 | WBS.2.2.7.2.2.26.1 | N | N | Planned | PTP_C0236 - Activate NDR parameter in user data profile of CONV BODS ID (for Goods Receipt conversion) | 0.25 | 2021-02-01 12:15 | 2021-02-01 12:30 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | KIRAN GANNAVARAPU;CARLOS ROBELO TEJADA;SAI TEAM;ANTHONY GORDON;SEC TEAM;PMO TEAM | KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SECURITY | 5701,5696,36505 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 12:30 | SECURITY | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82480 | WBS.2.2.7.2.2.26.2 | N | N | Planned | PTP_C0236 - Provide Posting Date for Convert GR for Open Invoice reconciliation | 0.25 | 2021-02-01 12:45 | 2021-02-01 13:00 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;DONNA SMITH;PUNEET KUMAR;SAI TEAM;AMY EL-BASSIONI;DATA ETL TEAM;SANDRA RICHARDS;RTR TEAM;PMO TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;DONNA.SMITH@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5695,5700,80747,36505 |  |  | * |  | 2021-02-01 12:45 | 2021-02-01 13:00 | RTR - GL | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9657 | WBS.2.2.7.2.2.26.3 | N | N | Planned | PTP_C0236 - Execute Transform program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 13:00 | 2021-02-01 14:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 80747,82480,5701,5696,82661,82652,94291 |  |  | * |  | 2021-02-01 13:00 | 2021-02-01 14:00 | DATA | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82667 | WBS.2.2.7.2.2.26.4 | N | N | Planned | PTP_C0236 - Open the posting periods for GR conversion (GL & MM) for specific Co Codes | 0.25 | 2021-02-01 13:00 | 2021-02-01 13:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;DONNA SMITH;SANDRA RICHARDS;SAI TEAM;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82480 |  |  | * |  | 2021-02-01 13:00 | 2021-02-01 13:15 | RTR - GL | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9658 | WBS.2.2.7.2.2.26.5 | N | N | Planned | PTP_C0236 - Validate Preload Transform - Convert Goods Receipt for Open Invoice Reconciliation | 2 | 2021-02-01 14:00 | 2021-02-01 16:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 9657 |  |  | * |  | 2021-02-01 14:00 | 2021-02-01 16:00 | PTP | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9659 | WBS.2.2.7.2.2.26.6 | N | N | Planned | PTH - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9658,68402,80748,5696,5701,68331,92152,94779,94780 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | DATA | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9660 | WBS.2.2.7.2.2.26.7 | N | N | Planned | PTH - PTP_C0236 - Validate Load - Convert Goods Receipt for Open Invoice Reconciliation | 1.5 | 2021-02-01 17:00 | 2021-02-01 18:30 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 9659 |  |  | * |  | 2021-02-01 17:00 | 2021-02-01 18:30 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82361 | WBS.2.2.7.2.2.26.8 | N | N | Planned | PTH - PTP_C0236 - Confirm the GL account balances after the GRIR conversion load (PTP_C0236) | 0.5 | 2021-02-01 18:30 | 2021-02-01 19:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 9660 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 19:00 | RTR - GL | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97529 | WBS.2.2.7.2.2.26.18 | N | N | Planned | BG - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9658,68402,80748,5696,5701,92152,96645,96646 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | DATA | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97530 | WBS.2.2.7.2.2.26.19 | N | N | Planned | BG - PTP_C0236 - Validate Load - Convert Goods Receipt for Open Invoice Reconciliation | 1.5 | 2021-02-01 17:00 | 2021-02-01 18:30 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97529 |  |  | * |  | 2021-02-01 17:00 | 2021-02-01 18:30 | PTP | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97531 | WBS.2.2.7.2.2.26.20 | N | N | Planned | BG - PTP_C0236 - Confirm the GL account balances after the GRIR conversion load (PTP_C0236) | 0.5 | 2021-02-01 18:30 | 2021-02-01 19:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 97530 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 19:00 | RTR - GL | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97523 | WBS.2.2.7.2.2.26.12 | N | N | Planned | HBG - PTP_C0236 - Execute Load program - Convert Goods Receipt for Open Invoice Reconciliation | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9658,68402,80748,5696,5701,92152,95281,94777 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | DATA | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97524 | WBS.2.2.7.2.2.26.13 | N | N | Planned | HBG - PTP_C0236 - Validate Load - Convert Goods Receipt for Open Invoice Reconciliation | 1.5 | 2021-02-01 17:00 | 2021-02-01 18:30 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97523 |  |  | * |  | 2021-02-01 17:00 | 2021-02-01 18:30 | PTP | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97525 | WBS.2.2.7.2.2.26.14 | N | N | Planned | HBG - PTP_C0236 - Confirm the GL account balances after the GRIR conversion load (PTP_C0236) | 0.5 | 2021-02-01 18:30 | 2021-02-01 19:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;PMO TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 97524 |  |  | * |  | 2021-02-01 18:30 | 2021-02-01 19:00 | RTR - GL | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9700 | WBS.2.2.7.2.2.27 | N | N |  | FCW ¦ PTP_C0237 - Convert Goods Receipt Inventory Adjustment | 35.25 | 2021-01-31 18:30 | 2021-02-02 05:45 | [8 empty] | * |  | 2021-01-31 18:30 | 2021-02-02 05:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82481 | WBS.2.2.7.2.2.27.1 | N | N | Planned | PTP_C0237 - Provide Posting Date for Convert Goods Receipt Inventory Adjustment | 0.25 | 2021-02-01 16:00 | 2021-02-01 16:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;DONNA SMITH;PUNEET KUMAR;SAI TEAM;DATA ETL TEAM;SANDRA RICHARDS;AMY EL-BASSIONI;RTR TEAM;PMO TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;DONNA.SMITH@GAPAC.COM;PUNEKUMAR@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;SARICHARDS@DELOITTE.COM;AMY.EL-BASSIONI@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36505,9658 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 16:15 | RTR - GL | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9661 | WBS.2.2.7.2.2.27.2 | N | N | Planned | PTH - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-01 19:00 | 2021-02-01 20:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82361,82481,36505 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 20:00 | DATA | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9662 | WBS.2.2.7.2.2.27.3 | N | N | Planned | PTH - PTP_C0237 - Validate Preload Transform - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 20:00 | 2021-02-01 22:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 9661 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 22:00 | PTP | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
9663 | WBS.2.2.7.2.2.27.4 | N | N | Planned | PTH - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 22:00 | 2021-02-02 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 9662,9660,92152 |  |  | * |  | 2021-02-01 22:00 | 2021-02-02 | DATA | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
9698 | WBS.2.2.7.2.2.27.5 | N | N | Planned | PTH - PTP_C0237 - Validate Load - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-02 | 2021-02-02 01:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 9663,8883 |  |  | * |  | 2021-02-02 | 2021-02-02 01:00 | PTP | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97540 | WBS.2.2.7.2.2.27.31 | N | N | Planned | BG - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-01 19:00 | 2021-02-01 20:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82481,36505,97531 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 20:00 | DATA | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97541 | WBS.2.2.7.2.2.27.32 | N | N | Planned | BG - PTP_C0237 - Validate Preload Transform - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 20:00 | 2021-02-01 22:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97540 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 22:00 | PTP | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97542 | WBS.2.2.7.2.2.27.33 | N | N | Planned | BG - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 22:00 | 2021-02-02 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 97541,92152,97530 |  |  | * |  | 2021-02-01 22:00 | 2021-02-02 | DATA | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97543 | WBS.2.2.7.2.2.27.34 | N | N | Planned | BG - PTP_C0237 - Validate Load - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-02 | 2021-02-02 01:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97542 |  |  | * |  | 2021-02-02 | 2021-02-02 01:00 | PTP | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97532 | WBS.2.2.7.2.2.27.23 | N | N | Planned | HBG - PTP_C0237 - Execute Transform program - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-01 19:00 | 2021-02-01 20:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 82481,36505,97525 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 20:00 | DATA | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97533 | WBS.2.2.7.2.2.27.24 | N | N | Planned | HBG - PTP_C0237 - Validate Preload Transform - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 20:00 | 2021-02-01 22:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97532 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 22:00 | PTP | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97534 | WBS.2.2.7.2.2.27.25 | N | N | Planned | HBG - PTP_C0237 - Execute Load program - Convert Goods Receipt Inventory Adjustment | 2 | 2021-02-01 22:00 | 2021-02-02 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 97533,92152,97524 |  |  | * |  | 2021-02-01 22:00 | 2021-02-02 | DATA | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97535 | WBS.2.2.7.2.2.27.26 | N | N | Planned | HBG - PTP_C0237 - Validate Load - Convert Goods Receipt Inventory Adjustment | 1 | 2021-02-02 | 2021-02-02 01:00 | BRUCE KIRKLEWSKI | BRUCE.KIRKLEWSKI@GAPAC.COM | ERIC BARSTOW;SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM;PMO TEAM;Simon Lee;BRANDI LUCE | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SIMON.LEE@GAPAC.COM;brandi.luce@gapac.com | PTP | 97534 |  |  | * |  | 2021-02-02 | 2021-02-02 01:00 | PTP | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
68403 | WBS.2.2.7.2.2.27.7 | N | N | Planned | Deactivate NDR parameter in user data profile of CONV BODS ID | 1 | 2021-02-02 01:00 | 2021-02-02 02:00 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | KIRAN GANNAVARAPU;CARLOS ROBELO TEJADA;SAI TEAM;ANTHONY GORDON;SEC TEAM | KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 9660,9698,97524,97530,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 02:00 | SECURITY | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82360 | WBS.2.2.7.2.2.27.8 | N | N | Planned | PTH - PTP_C0237 - Validation of reversal of inventory receipt | 1 | 2021-02-02 01:00 | 2021-02-02 02:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 9698 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 02:00 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97546 | WBS.2.2.7.2.2.27.37 | N | N | Planned | BG - PTP_C0237 - Validation of reversal of inventory receipt | 1 | 2021-02-02 01:00 | 2021-02-02 02:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 02:00 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97544 | WBS.2.2.7.2.2.27.35 | N | N | Planned | HBG - PTP_C0237 - Validation of reversal of inventory receipt | 1 | 2021-02-02 01:00 | 2021-02-02 02:00 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE;BRENDA STAGGS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM | RTR | 97535 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 02:00 | RTR - GL | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82665 | WBS.2.2.7.2.2.27.11 | N | N | Planned | PTP_C0237 - Close the posting periods for Inventory Adjustment conversion (GL & MM) for specific Co Codes | 0.25 | 2021-02-02 02:00 | 2021-02-02 02:15 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;DONNA SMITH;SANDRA RICHARDS;SAI TEAM;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82360,97544,97546 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 02:15 | RTR - GL | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82380 | WBS.2.2.7.2.2.27.12 | N | N | Planned | Extract postings to Def Exp Account, Create JV Upload File, posting & validate results (ECC & AS8) | 2.5 | 2021-02-02 02:15 | 2021-02-02 04:45 | BRETT DETTMERING | BRETT.DETTMERING@GAPAC.COM | SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82665 |  |  | * |  | 2021-02-02 02:15 | 2021-02-02 04:45 | RTR - GL | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90845 | WBS.2.2.7.2.2.27.14 | N | N | Planned | DC confirmation control key | 1 | 2021-01-31 18:30 | 2021-01-31 19:30 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | ALBERT BAGUNA;DEEPAK SABNANI;AVINASH TALREJA;SAI TEAM;DOUG STANISLAWSKI;JEFFREY GOLDMUNTZ;EWM TEAM;PMO TEAM;JENNIFER LI;CHIRAG PARIKH;SANJAY JELAJI;KIM LADZINSKE;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | ABAGUNA@DELOITTE.COM;DSABNANI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;SANJAY.JELAJI1@GAPAC.COM;KDLADZIN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 21137 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 19:30 | EWM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
94295 | WBS.2.2.7.2.2.27.15 | N | N | Planned | Send one test output to AN/EIM, then validate the PO in EIM | 0.5 | 2021-02-02 01:00 | 2021-02-02 01:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SAI TEAM;PTP TEAM;MONICA CUEVAS;PMO TEAM;SANDEEP A | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 90845,82477,92744,97535,97543 |  |  | * |  | 2021-02-02 01:00 | 2021-02-02 01:30 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
92113 | WBS.2.2.7.2.2.27.16 | N | N | Planned | Update MKLE Facility/DC to 2000, Update WH to 5000 | 1 | 2021-01-31 19:30 | 2021-01-31 20:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | NITIN GUPTA;CASEY HERMANSEN;YUDHAJIT MITRA;SRUTHI SRINIVASAN;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;SRUSRINIVASAN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 82239,90845,92743,96904,97475 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:30 | PTP | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92364 | WBS.2.2.7.2.2.27.17 | N | N | Planned | Trigger SPED Output for Stock In Transit STO shipping from existing live EWM site to EWM Site that is going-live | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com | EWM | 92113,96904,97475 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:30 | EWM | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
36889 | WBS.2.2.7.2.2.27.18 | N | N | Planned | Manually Set PO and GR Outputs to Send in S/4HANA | 0.5 | 2021-02-02 01:30 | 2021-02-02 02:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MIKE PUPILLO;CASEY HERMANSEN;SAI TEAM;YUDHAJIT MITRA;PTP TEAM;SHRISH MUDRI;PMO TEAM;MONICA CUEVAS;SANDEEP A | MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 94295,97390 |  |  | * |  | 2021-02-02 01:30 | 2021-02-02 02:00 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82378 | WBS.2.2.7.2.2.27.19 | N | N | Planned | Block all conversion GL accounts (GRIR, Inventory acc, AR, WBS conversion acc - only deployed co.codes) | 1 | 2021-02-02 04:45 | 2021-02-02 05:45 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 82380 |  |  | * |  | 2021-02-02 04:45 | 2021-02-02 05:45 | RTR - GL | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82324 | WBS.2.2.7.2.2.27.20 | N | N | Planned | Manually maintain condition records for Freight PO data to TOPS - output conditions for ZSST | 0.25 | 2021-02-02 02:00 | 2021-02-02 02:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | YUDHAJIT MITRA;CASEY HERMANSEN;BRUCE KIRKLEWSKI;SAI TEAM;SHRISH MUDRI;PTP TEAM;MONICA CUEVAS;SANDEEP A | YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 36889 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 02:15 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
68448 | WBS.2.2.7.2.2.27.21 | N | N | Planned | Manually maintain condition records for Interim STO, PO output conditions ZUBT and ZINT | 0.25 | 2021-02-02 02:00 | 2021-02-02 02:15 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | SRUTHI SRINIVASAN;NITIN GUPTA;CASEY HERMANSEN;SAI TEAM;PTP TEAM;SHRISH MUDRI;MONICA CUEVAS;SANDEEP A | SRUSRINIVASAN@DELOITTE.COM;NITINGUPTA55@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SHRISH.MUDRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 36889,36505 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 02:15 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95493 | WBS.2.2.7.2.2.27.22 | N | N | Planned | Send Converted PO/GR to S4HANA EIM Realm | 3 | 2021-02-02 01:30 | 2021-02-02 04:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MONICA CUEVAS;SAI TEAM;PTP TEAM;SANDEEP A | MONICA.CUEVAS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 94295 |  |  | * |  | 2021-02-02 01:30 | 2021-02-02 04:30 | PTP | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
5485 | WBS.2.2.7.2.2.28 | N | N |  | FCW ¦ ITR_C0062 - Convert Work Order History - AS8 | 9.5 | 2021-01-31 17:30 | 2021-02-01 03:00 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 03:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5486 | WBS.2.2.7.2.2.28.1 | N | N | Planned | ITR_C0062 - Execute Transform Program - Convert Work Order History - AS8 | 2 | 2021-01-31 17:30 | 2021-01-31 19:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5393,5398,81155,81706,36505,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:30 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5487 | WBS.2.2.7.2.2.28.2 | N | N | Planned | ITR_C0062 - Validate Preload Transform - Convert Work Order History - AS8 | 0.75 | 2021-01-31 19:30 | 2021-01-31 20:15 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5486 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 20:15 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5488 | WBS.2.2.7.2.2.28.3 | N | N | Planned | ITR_C0062 - Execute Load Program - Convert Work Order History - AS8 | 2 | 2021-01-31 20:15 | 2021-01-31 22:15 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5487 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 22:15 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5489 | WBS.2.2.7.2.2.28.4 | N | N | Planned | ITR_C0062 - Validate Load - Convert Work Order History - AS8 | 0.75 | 2021-01-31 22:15 | 2021-01-31 23:00 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | CHAD FLAGG;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5488 |  |  | * |  | 2021-01-31 22:15 | 2021-01-31 23:00 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
81665 | WBS.2.2.7.2.2.28.5 | N | N | Planned | PTH - ITR_C0062 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Work order history - Asset Suite) | 4 | 2021-01-31 23:00 | 2021-02-01 03:00 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5489 |  |  | * |  | 2021-01-31 23:00 | 2021-02-01 03:00 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5764 | WBS.2.2.7.2.2.29 | N | N |  | FCW ¦ ITR_C0035 - Convert Open Notifications – AS8 | 4.08 | 2021-01-31 17:30 | 2021-01-31 21:35 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-01-31 21:35 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5765 | WBS.2.2.7.2.2.29.1 | N | N | Planned | ITR_C0035 - Execute Transform program - Convert Open Notifications – Asset Suite | 1.5 | 2021-01-31 17:30 | 2021-01-31 19:00 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5395,81154,5438,89987,94400,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 19:00 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5766 | WBS.2.2.7.2.2.29.2 | N | N | Planned | ITR_C0035 - Validate Preload Transform - Convert Open Notifications – Asset Suite | 0.33 | 2021-01-31 19:00 | 2021-01-31 19:20 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5765 |  |  | * |  | 2021-01-31 19:00 | 2021-01-31 19:20 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5767 | WBS.2.2.7.2.2.29.3 | N | N | Planned | ITR_C0035 - Execute Load program - Convert Open Notifications – Asset Suite | 1 | 2021-01-31 19:20 | 2021-01-31 20:20 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;PMO TEAM | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | DATA | 5766 |  |  | * |  | 2021-01-31 19:20 | 2021-01-31 20:20 | DATA | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5768 | WBS.2.2.7.2.2.29.4 | N | N | Planned | ITR_C0035 - Validate Load - Convert Open Notifications – Asset Suite | 1 | 2021-01-31 20:20 | 2021-01-31 21:20 | KELLY STRASSBURGER | KELLY.STRASSBURGER@GAPAC.COM | CHAD FLAGG;JASON RAMSEY;SAI TEAM;BRENNEN FRISQUE;AC TEAM;PMO TEAM | CHAD.FLAGG@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRENNEN.FRISQUE@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5767 |  |  | * |  | 2021-01-31 20:20 | 2021-01-31 21:20 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97750 | WBS.2.2.7.2.2.29.5 | N | N | Planned | PTH - ITR_C0035 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Work Requests – Asset Suite) | 0.25 | 2021-01-31 21:20 | 2021-01-31 21:35 | LONNIE MORRIS | Lonnie.Morris@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 5768 |  |  | * |  | 2021-01-31 21:20 | 2021-01-31 21:35 | AC | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92842 | WBS.2.2.7.2.2.30 | N | N |  | FCW ¦ ITR_C0062.1 Convert Work order history – MP2 | 7 | 2021-01-31 17:30 | 2021-02-01 00:30 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 00:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92840 | WBS.2.2.7.2.2.30.1 | N | N | Planned | Execute Preload ITR_C0062.1 Convert Work order history – MP2 | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 94412,36505,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | DATA | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92839 | WBS.2.2.7.2.2.30.2 | N | N | Planned | Validate Preload ITR_C0062.1 Convert Work order history – MP2 | 2 | 2021-01-31 18:30 | 2021-01-31 20:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92840 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 20:30 | AC | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92838 | WBS.2.2.7.2.2.30.3 | N | N | Planned | Execute Load ITR_C0062.1 Convert Work order history – MP2 | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92839 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:30 | DATA | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92837 | WBS.2.2.7.2.2.30.4 | N | N | Planned | Validate Load ITR_C0062.1 Convert Work order history – MP2 | 2 | 2021-01-31 21:30 | 2021-01-31 23:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92838 |  |  | * |  | 2021-01-31 21:30 | 2021-01-31 23:30 | AC | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96971 | WBS.2.2.7.2.2.30.6 | N | N | Planned | BG - ITR_C0062.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Work order history - MP2) | 1 | 2021-01-31 23:30 | 2021-02-01 00:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92837 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 00:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92836 | WBS.2.2.7.2.2.31 | N | N |  | FCW ¦ ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 10 | 2021-01-31 17:30 | 2021-02-01 03:30 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 03:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92834 | WBS.2.2.7.2.2.31.1 | N | N | Planned | Execute Preload ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 94412,36505,92877,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | DATA | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92833 | WBS.2.2.7.2.2.31.2 | N | N | Planned | Validate Preload ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 2 | 2021-01-31 18:30 | 2021-01-31 20:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92834 |  |  | * |  | 2021-01-31 18:30 | 2021-01-31 20:30 | AC | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92832 | WBS.2.2.7.2.2.31.3 | N | N | Planned | Execute Load ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 1 | 2021-01-31 20:30 | 2021-01-31 21:30 | JASPREET SINGH | JASPSINGH@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;TAJINDER KOHLI | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;TKOHLI@DELOITTE.COM | DATA | 92833 |  |  | * |  | 2021-01-31 20:30 | 2021-01-31 21:30 | DATA | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92831 | WBS.2.2.7.2.2.31.4 | N | N | Planned | Validate Load ITR_C0067.1 Convert Scheduled Maintenance Plans – MP2 | 2 | 2021-01-31 21:30 | 2021-01-31 23:30 | JASON RAMSEY | JCRAMSEY@GAPAC.COM | AC TEAM;SAI TEAM;TAJINDER KOHLI;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;TKOHLI@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 92832 |  |  | * |  | 2021-01-31 21:30 | 2021-01-31 23:30 | AC | HBG,BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92896 | WBS.2.2.7.2.2.31.6 | N | N | Planned | HBG - ITR_C0067.1 - Spot-check SAP DATA reflects loaded data (Convert Scheduled Maintenance Plans –MP2) | 4 | 2021-01-31 23:30 | 2021-02-01 03:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 92831 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 03:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96970 | WBS.2.2.7.2.2.31.7 | N | N | Planned | BG - ITR_C0067.1 - Verify data with compare tool; spot-check SAP DATA reflects loaded data (Convert Scheduled Maintenance Plans –MP2) | 1 | 2021-01-31 23:30 | 2021-02-01 00:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;SAI TEAM;AC TEAM;LYNN MCMURDO | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM | AC | 92831 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 00:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97470 | WBS.2.2.7.2.2.44 |  |  |  | FCW ¦ Current Meter Reading – MP2 | 5 | 2021-01-31 23:30 | 2021-02-01 04:30 | [8 empty] | * |  | 2021-01-31 23:30 | 2021-02-01 04:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97471 | WBS.2.2.7.2.2.44.9 | N | N | Planned | BG - Validate scheduled maintenance plans using IP24 - MP2 | 2 | 2021-01-31 23:30 | 2021-02-01 01:30 | JONATHAN STADNICKI VERHYEN | JONATHAN.STADNICKIVERHYEN@GAPAC.COM | KATHY MCMAHON;SAI TEAM;AC TEAM | kathleen.mcmahon@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | Business | 92831 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 01:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97472 | WBS.2.2.7.2.2.44.10 | N | N | Planned | BG - Manually schedule maintenance plans to generate work orders via MRS for week 1 post go-live | 3 | 2021-02-01 01:30 | 2021-02-01 04:30 | JONATHAN STADNICKI VERHYEN | JONATHAN.STADNICKIVERHYEN@GAPAC.COM | DOMINGO PEREZ;SAI TEAM;AC TEAM | DOMINGO.PEREZ@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | Business | 97471 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 04:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97473 | WBS.2.2.7.2.2.44.1 | N | N | Planned | HBG - Validate scheduled maintenance plans using IP24 - MP2 | 2 | 2021-01-31 23:30 | 2021-02-01 01:30 | JAMES LEE | JAMES.LEE1@gapac.com | GREGORY GIBBS;JERRY WHIDDON;SAI TEAM;AC TEAM | GREGORY.GIBBS@GAPAC.com;JERRY.WHIDDON@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | Business | 92831 |  |  | * |  | 2021-01-31 23:30 | 2021-02-01 01:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97474 | WBS.2.2.7.2.2.44.11 | N | N | Planned | HBG - Manually schedule maintenance plans to generate work orders via MRS for week 1 post go-live | 3 | 2021-02-01 01:30 | 2021-02-01 04:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | GREGORY GIBBS;JAMES LEE;SAI TEAM;AC TEAM | GREGORY.GIBBS@GAPAC.com;JAMES.LEE1@gapac.com ;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | Business | 97473 |  |  | * |  | 2021-02-01 01:30 | 2021-02-01 04:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91476 | WBS.2.2.8 | N | N |  | FCW ¦ Post Conversions Activity | 20.75 | 2021-01-31 17:30 | 2021-02-01 14:15 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 14:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91477 | WBS.2.2.8.1 | N | N |  | FCW ¦ Post Conversions Activity - Start-Up Tasks | 20.75 | 2021-01-31 17:30 | 2021-02-01 14:15 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 14:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92154 | WBS.2.2.8.1.1 | N | N |  | FCW ¦ Post Conversions Activity - Start-Up Tasks - SAP Systems | 20.75 | 2021-01-31 17:30 | 2021-02-01 14:15 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 14:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92707 | WBS.2.2.8.1.1.1 | N | N |  | FCW ¦ Post Conversion Activity - S4/HANA - EWM | 8 | 2021-01-31 17:30 | 2021-02-01 01:30 | [8 empty] | * |  | 2021-01-31 17:30 | 2021-02-01 01:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
4590 | WBS.2.2.8.1.1.1.1 | N | N | Planned | Create output condition for Shipments | 1 | 2021-01-31 17:30 | 2021-01-31 18:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com | EWM | 90836,95542,95539,95538,95536,95534,96561,96562,96697,96698,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 18:30 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
4589 | WBS.2.2.8.1.1.1.2 | N | N | Planned | Create output conditions for Deliveries | 8 | 2021-01-31 17:30 | 2021-02-01 01:30 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com | EWM | 90836,95542,95539,95538,95536,95534,96561,96562,96697,96698,96903 |  |  | * |  | 2021-01-31 17:30 | 2021-02-01 01:30 | EWM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
81219 | WBS.2.2.8.1.1.2 | N | N |  | FCW ¦ Post Conversion Activity - Start-Up Tasks - SAP Systems - Load Live Transaction Data - SAP IBP | 2 | 2021-02-01 12:15 | 2021-02-01 14:15 | [8 empty] | * |  | 2021-02-01 12:15 | 2021-02-01 14:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
81215 | WBS.2.2.8.1.1.2.1 | N | N | Planned | IBP - HCI Transfer of ALL transaction data for ALL sites into IBP from S/4HANA - IBP SP | 2 | 2021-02-01 12:15 | 2021-02-01 14:15 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;PMO TEAM;BRAD WYMAN;KIM LADZINSKE;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 5696,5690 |  |  | * |  | 2021-02-01 12:15 | 2021-02-01 14:15 | SCM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91013 | WBS.2.2.9 | N | N |  | FCW¦ Business Shutdown | 50.75 | 2021-01-31 01:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 04:00 |  | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
10730 | WBS.2.2.9.1 | N | N |  | FCW¦ Business Shutdown Activities | 50.75 | 2021-01-31 01:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 04:00 |  | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90121 | WBS.2.2.9.1.1 | N | N |  | FCW ¦ Enterprise Information Management - EIM | 39 | 2021-01-31 01:15 | 2021-02-01 16:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 16:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91735 | WBS.2.2.9.1.1.1 | N | N |  | FCW ¦ Enterprise Information Management - EIM | 39 | 2021-01-31 01:15 | 2021-02-01 16:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 16:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90124 | WBS.2.2.9.1.1.1.1 | N | N | Planned | Communicate new ship-to locations to Ariba Network suppliers | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;PAM NIX;SAI TEAM;PTP TEAM | MARK.BURGIN@GAPAC.COM;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EIM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90123 | WBS.2.2.9.1.1.1.2 | N | N | Planned | Move deployment facilities in MDM table from AS8/ECC to S/4HANA for EIM. Ensure SEGMENT is populated and inactivate any needed | 0.25 | 2021-01-31 17:00 | 2021-01-31 17:15 | TERESA FOWLER | TERESA.FOWLER@KBSLP.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36505,81871,96904,97475 |  |  | * |  | 2021-01-31 17:00 | 2021-01-31 17:15 | EIM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90122 | WBS.2.2.9.1.1.1.3 | N | N | Planned | Receive the PO conversion file from PTP and pull into Datacap | 2 | 2021-02-01 14:15 | 2021-02-01 16:15 | ROBBIE DEES | RTDEES@GAPAC.COM | CEDRICK SMITH;PAM NIX;CATHYE ROBINSON;SAI TEAM;PTP TEAM;FRANK CARDILLO | CLSMITH@GAPAC.COM;PSNIX@GAPAC.COM;CBROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ffcardil@gapac.com | PTP | 82477,21147 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 16:15 | EIM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95289 | WBS.2.2.9.1.1.1.4 | N | N | Planned | Update the modified facility tables on the Ariba Invoicing SharePoint | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | TERESA FOWLER | TERESA.FOWLER@KBSLP.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 90123 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | EIM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93342 | WBS.2.2.9.1.2 | N | N |  | FCW ¦ AC | 50.75 | 2021-01-31 01:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 04:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93341 | WBS.2.2.9.1.2.1 | N | N |  | FCW ¦ AC | 50.75 | 2021-01-31 01:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 04:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93795 | WBS.2.2.9.1.2.1.1 | N | N | Planned | HBG - MRO - Enter manually tracked activity post cutover MRO Work Orders | 1 | 2021-02-01 14:15 | 2021-02-01 15:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 10851,95284 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 15:15 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93219 | WBS.2.2.9.1.2.1.2 | N | N | Planned | PTH - MRO - Enter manually tracked activity post cutover MRO Work Orders | 8 | 2021-02-01 20:00 | 2021-02-02 04:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com ;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 21147,95155,95166 |  |  | * |  | 2021-02-01 20:00 | 2021-02-02 04:00 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96348 | WBS.2.2.9.1.2.1.5 | N | N | Planned | BG - MRO - CONVERTING Enter manually tracked activity post cutover MRO Work Orders | 2 | 2021-01-31 01:15 | 2021-01-31 03:15 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | AC | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
10761 | WBS.2.2.9.1.3 | N | N |  | FCW ¦ OTC | 25.5 | 2021-01-31 01:15 | 2021-02-01 02:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 02:45 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91747 | WBS.2.2.9.1.3.1 | N | N |  | FCW ¦ OTC | 25.5 | 2021-01-31 01:15 | 2021-02-01 02:45 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 02:45 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92965 | WBS.2.2.9.1.3.1.1 | N | N | Planned | SCH - Communicate to Warehouse Contact: Any nonconforming finished goods must be manually placed on Q-hold during blackout | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;JEREMY RAY;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM;Christopher.Jernigan@gapac.com | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | OTC - Quality | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96350 | WBS.2.2.9.1.3.1.2 | N | N | Planned | RNC - Communicate to Warehouse Contact: Any nonconforming finished goods must be manually placed on Q-hold during blackout | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | ELIZABETH JOHNSON | ELIZABETH.JOHNSON@GAPAC.COM | TOMMY NEFFENDORF;JEREMY RAY;SAI TEAM | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | OTC - Quality | RNC | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96349 | WBS.2.2.9.1.3.1.3 | N | N | Planned | RVG - Communicate to Warehouse Contact: Any nonconforming finished goods must be manually placed on Q-hold during blackout | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | OTC - Quality | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96361 | WBS.2.2.9.1.3.1.9 | N | N | Planned | SAT - Post File Load - Verify finished goods inventory from a Quality POV in S/4HANA | 2 | 2021-02-01 00:30 | 2021-02-01 02:30 | KAITLYN JANSEN | Kaitlyn.Jansen@gapac.com | SLADE HURST;TRENT SCHICK;PATRICK BROWNING;SAI TEAM | SLADE.HURST@GAPAC.COM;Trent.Schick@gapac.com;PWBROWNI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,96666 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:30 | TBD | SAT | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96357 | WBS.2.2.9.1.3.1.13 | N | N | Planned | REX - Blackout - Communicate to Warehouse: Any nonconforming finished goods must be manually placed on Q-hold | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;DILLON RAGHOONATHSINGH;SAI TEAM | duy.nguyen@nfiindustries.com;dillon.rsingh@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | TBD | REX | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96356 | WBS.2.2.9.1.3.1.14 | N | N | Planned | REX - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 0.25 | 2021-02-01 02:30 | 2021-02-01 02:45 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | DUY NGUYEN;SAI TEAM | duy.nguyen@nfiindustries.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,96355,96670 |  |  | * |  | 2021-02-01 02:30 | 2021-02-01 02:45 | TBD | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96355 | WBS.2.2.9.1.3.1.15 | N | N | Planned | REX - Post File Load - Verify finished goods inventory from a Quality POV in S/4HANA | 2 | 2021-02-01 00:30 | 2021-02-01 02:30 | DANIEL ROSS | DANIEL.ROSS@GAPAC.COM | SLADE HURST;SAI TEAM | SLADE.HURST@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,96670 |  |  | * |  | 2021-02-01 00:30 | 2021-02-01 02:30 | TBD | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
11097 | WBS.2.2.9.1.4 | N | N |  | FCW ¦ EWM | 36 | 2021-01-31 01:15 | 2021-02-01 13:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 13:15 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91749 | WBS.2.2.9.1.4.1 | N | N |  | FCW ¦ EWM | 36 | 2021-01-31 01:15 | 2021-02-01 13:15 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-01 13:15 |  | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97150 | WBS.2.2.9.1.4.1.46 | N | N | Planned | PTH - Lock End Users out of Elixir - Turn off Terminal Servers | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | JERRY LEBLANC | Jerry.Leblanc@gapac.com | Ryan Fitzek;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ryan.fitzek@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93268,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96038 | WBS.2.2.9.1.4.1.44 | N | N | Planned | BG - Point RFs to EWM | 4 | 2021-01-31 18:15 | 2021-01-31 22:15 | DEREK SARGENT | Derek.Sargent@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM;Jeron Wall;KELLY LEWIS;JOHN WHITE | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Jeron.wall@gapac.com;kelly.lewis@gapac.com;JOHN.WHITE@GAPAC.COM | Business | 96810,36505,81567 |  |  | * |  | 2021-01-31 18:15 | 2021-01-31 22:15 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96351 | WBS.2.2.9.1.4.1.2 | N | N | Planned | BG - Post File Load - Verify finished goods and materials inventory on Q-hold in S/4HANA | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 8883 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94404 | WBS.2.2.9.1.4.1.3 | N | N | Planned | HBG - Post File Load - Verify finished goods and materials inventory on Q-hold in S/4HANA | 0.5 | 2021-02-01 08:30 | 2021-02-01 09:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 8883 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93326 | WBS.2.2.9.1.4.1.4 | N | N | Planned | PTH - Start Task - Track any movements of FG's/RM/PR | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93913 | WBS.2.2.9.1.4.1.6 | N | N | Planned | HBG - Start Task - Track any movements of FG's/RM/PR | 0.5 | 2021-01-31 01:15 | 2021-01-31 01:45 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93865,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:45 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93325 | WBS.2.2.9.1.4.1.8 | N | N | Planned | PTH - Verify empty trailer upload file by counting the yard | 2 | 2021-01-31 01:15 | 2021-01-31 03:15 | MARCUS MARTINEZ | Marcus.Martinez@gapac.com | HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 03:15 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93914 | WBS.2.2.9.1.4.1.12 | N | N | Planned | HBG - Start Task - Record inbound/outbound Freight by using business continuity form - S2P | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93865,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93262 | WBS.2.2.9.1.4.1.13 | N | N | Planned | PTH - Start Task - Record inbound/outbound Freight by using business continuity form - S2P | 0.25 | 2021-01-31 01:15 | 2021-01-31 01:30 | LISA KOENIG | lisa.koenig@gapac.com | MARCUS MARTINEZ;HADYN HUGHES;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Marcus.Martinez@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 01:30 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93911 | WBS.2.2.9.1.4.1.16 | N | N | Planned | HBG - Blackout: Update all Emergency / Manual Documents (QHOLDs / Inventory, Outbounds, Inbounds, Trailers) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93865,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93324 | WBS.2.2.9.1.4.1.18 | N | N | Planned | PTH - Validate inventory accuracy in S/4HANA | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 8883 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92994 | WBS.2.2.9.1.4.1.21 | N | N | Planned | SCH - Blackout: Update all Emergency / Manual Documents (QHOLDs / Inventory, Outbounds, Inbounds, Trailers) | 4 | 2021-01-31 01:30 | 2021-01-31 05:39 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN;DANIELLE MULLIGAN;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com;Danielle.Mulligan@gapac.com;Tristan.Clark@nfiindustries.com | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 05:39 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93006 | WBS.2.2.9.1.4.1.22 | N | N | Planned | SCH - Point RFs to EWM | 2 | 2021-01-31 18:15 | 2021-01-31 20:15 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;GIOVANY CARVAJAL | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | Business | 81567 |  |  | * |  | 2021-01-31 18:15 | 2021-01-31 20:15 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92993 | WBS.2.2.9.1.4.1.23 | N | N | Planned | SCH - Blackout - Manually execute any Q-holds that occur during the blackout period & notify Quality | 2 | 2021-01-31 01:30 | 2021-01-31 03:30 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com;Tristan.Clark@nfiindustries.com | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 03:30 | EWM | SCH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93353 | WBS.2.2.9.1.4.1.24 | N | N | Planned | PTH - Ensure all locations are not in blocked status in EWM | 5 | 2021-02-01 08:15 | 2021-02-01 13:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 82553,21147 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 13:15 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93942 | WBS.2.2.9.1.4.1.26 | N | N | Planned | HBG - Ensure all locations are not in blocked status in EWM | 1 | 2021-02-01 08:15 | 2021-02-01 09:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,21147 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 09:15 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93940 | WBS.2.2.9.1.4.1.27 | N | N | Planned | HBG - Test printers SAP EWM | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93382 | WBS.2.2.9.1.4.1.32 | N | N | Planned | PTH - Verify the items on Q-hold are not available for shipping | 0.75 | 2021-01-31 01:30 | 2021-01-31 02:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:15 | EWM | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96372 | WBS.2.2.9.1.4.1.35 | N | N | Planned | BG - Start Task - Track any movements of FG's/RM/PR | 0.5 | 2021-01-31 01:30 | 2021-01-31 02:00 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 02:00 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96371 | WBS.2.2.9.1.4.1.36 | N | N | Planned | BG - Verify empty trailer upload file by counting the yard | 1.5 | 2021-01-31 03:45 | 2021-01-31 05:15 | BEAU EARLS | Beau.Earls@GAPAC.com | JORDAN BUNDY;LYNN MCMURDO;DEAN PIPER;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147,96649 |  |  | * |  | 2021-01-31 03:45 | 2021-01-31 05:15 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96370 | WBS.2.2.9.1.4.1.37 | N | N | Planned | BG - Start Task - Record inbound/outbound Freight by using business continuity form - S2P | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | LYNN MCMURDO | LYNN.MCMURDO@GAPAC.COM | BEAU EARLS;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96369 | WBS.2.2.9.1.4.1.38 | N | N | Planned | BG - Test printers SAP EWM | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | Jeron Wall | Jeron.wall@gapac.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM;DEREK SARGENT;KELLY LEWIS;JOHN WHITE | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Derek.Sargent@GAPAC.com;kelly.lewis@gapac.com;JOHN.WHITE@GAPAC.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96368 | WBS.2.2.9.1.4.1.39 | N | N | Planned | BG - Ensure all locations are not in blocked status in EWM | 0.5 | 2021-02-01 08:15 | 2021-02-01 08:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147,82553 |  |  | * |  | 2021-02-01 08:15 | 2021-02-01 08:45 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96367 | WBS.2.2.9.1.4.1.40 | N | N | Planned | BG - Verify with mill that all loads complete (not in process), dispatched, in ship start and "PGI", and/or segregated in marked area of yard | 1 | 2021-01-31 05:15 | 2021-01-31 06:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21147,95908,96371 |  |  | * |  | 2021-01-31 05:15 | 2021-01-31 06:15 | EWM | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96535 | WBS.2.2.9.1.4.1.41 | N | N | Planned | RVG - Blackout: Update all Emergency / Manual Documents (QHOLDs / Inventory, Outbounds, Inbounds, Trailers) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 10853,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96536 | WBS.2.2.9.1.4.1.42 | N | N | Planned | RVG - Point RFs to EWM | 1 | 2021-01-31 18:15 | 2021-01-31 19:15 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | JULI LEWIS;SAI TEAM;JENNIFER MCLEOD | JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM | Business | 36505,81567 |  |  | * |  | 2021-01-31 18:15 | 2021-01-31 19:15 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
96537 | WBS.2.2.9.1.4.1.43 | N | N | Planned | RVG - Blackout - Manually execute any Q-holds that occur during the blackout period | 1 | 2021-01-31 01:45 | 2021-01-31 02:45 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96349 |  |  | * |  | 2021-01-31 01:45 | 2021-01-31 02:45 | EWM | RVG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
36701 | WBS.2.2.9.1.5 | N | N |  | FCW ¦ RTR | 20.75 | 2021-01-31 19:15 | 2021-02-01 16:00 | [8 empty] | * |  | 2021-01-31 19:15 | 2021-02-01 16:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91750 | WBS.2.2.9.1.5.1 | N | N |  | FCW ¦ RTR | 20.75 | 2021-01-31 19:15 | 2021-02-01 16:00 | [8 empty] | * |  | 2021-01-31 19:15 | 2021-02-01 16:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97667 | WBS.2.2.9.1.5.1.2 | N | N | Planned | PTH - Zero out MAP for Price type V SFG (if any) in ECC new period as soon as system comes up (MR21 in P2) | 0.5 | 2021-02-01 15:30 | 2021-02-01 16:00 | WENTAO TANG | WTANG@GAPAC.COM | RANJAI JOHN;LAURA FRY;DENISE MARSH;NOEL CLARK;CJ KAUTH;AGNES DEBO;RTR TEAM;SAI TEAM | RANJAI.JOHN@KOCHTC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;christopher.kauth@gapac.com;ADEBO@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94781,97708 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 16:00 | RTR - PC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97657 | WBS.2.2.9.1.5.1.4 | N | N | Planned | BG - Zero out MAP for Price type V SFG (if any) in ECC new period as soon as system comes up (MR21 in P2) | 0.5 | 2021-02-01 11:30 | 2021-02-01 12:00 | WENTAO TANG | WTANG@GAPAC.COM | RANJAI JOHN;LAURA FRY;DENISE MARSH;NOEL CLARK;LYNN MCMURDO;DEAN PIPER;AGNES DEBO;RTR TEAM;SAI TEAM | RANJAI.JOHN@KOCHTC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;ADEBO@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96647,97709 |  |  | * |  | 2021-02-01 11:30 | 2021-02-01 12:00 | RTR - PC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97663 | WBS.2.2.9.1.5.1.10 | N | N | Planned | HBG - Zero out MAP for Price type V SFG (if any) in ECC new period as soon as system comes up (MR21 in P2) | 0.5 | 2021-02-01 11:00 | 2021-02-01 11:30 | WENTAO TANG | WTANG@GAPAC.COM | RANJAI JOHN;LAURA FRY;DENISE MARSH;NOEL CLARK;CHRIS ZUMWALT;AGNES DEBO;RTR TEAM;SAI TEAM | RANJAI.JOHN@KOCHTC.COM;LAURA.FRY@GAPAC.COM;DENISE.MARSH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;ADEBO@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93916,97710 |  |  | * |  | 2021-02-01 11:00 | 2021-02-01 11:30 | RTR - PC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97708 | WBS.2.2.9.1.5.1.12 | N | N | Planned | PTH - Provide list of price type V materials for zeroing of price type V MAP | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | LAURA FRY | LAURA.FRY@GAPAC.COM | NOEL CLARK;DENISE MARSH;CJ KAUTH;SAI TEAM | NOEL.CLARK@GAPAC.COM;DENISE.MARSH@GAPAC.COM;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | RTR | PTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97709 | WBS.2.2.9.1.5.1.13 | N | N | Planned | BG - Provide list of price type V materials for zeroing of price type V MAP | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | LAURA FRY | LAURA.FRY@GAPAC.COM | NOEL CLARK;DENISE MARSH;LYNN MCMURDO;DEAN PIPER;SAI TEAM | NOEL.CLARK@GAPAC.COM;DENISE.MARSH@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | RTR | BG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97710 | WBS.2.2.9.1.5.1.14 | N | N | Planned | HBG - Provide list of price type V materials for zeroing of price type V MAP | 0.25 | 2021-01-31 19:15 | 2021-01-31 19:30 | LAURA FRY | LAURA.FRY@GAPAC.COM | NOEL CLARK;DENISE MARSH;CHRIS ZUMWALT;SAI TEAM | NOEL.CLARK@GAPAC.COM;DENISE.MARSH@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 92467 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:30 | RTR | HBG | 2021-01-31 | 2021-01-31 | 3 | Shutdown
29838 | WBS.2.2.9.1.6 | N | N |  | FCW ¦ PTP | 34.75 | 2021-01-31 17:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-02 04:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91751 | WBS.2.2.9.1.6.1 | N | N |  | FCW ¦ PTP | 34.75 | 2021-01-31 17:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-02 04:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95913 | WBS.2.2.9.1.6.1.26 | N | N | Planned | BG - MRO - Operations confirms all system activities to perform prior to cutover have been completed | 2 | 2021-02-01 15:15 | 2021-02-01 17:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | GERONIMO ROMERO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | GERONIMO.ROMERO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 95932 |  |  | * |  | 2021-02-01 15:15 | 2021-02-01 17:15 | PTP | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95934 | WBS.2.2.9.1.6.1.24 | N | N | Planned | BG - Process Open Purchase Requisitions To Purchase Orders | 1 | 2021-02-01 15:00 | 2021-02-01 16:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 94780,81706 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 16:00 | PTP | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96779 | WBS.2.2.9.1.6.1.25 | N | N | Planned | BG -- STOP recording cycle counts in ECC | 0.5 | 2021-02-01 16:00 | 2021-02-01 16:30 | GERONIMO ROMERO | GERONIMO.ROMERO@GAPAC.COM | BRANDY MEREDITH;DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Brandy.Meredith@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 95934 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 16:30 | PTP - Procurement/Stores | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95932 | WBS.2.2.9.1.6.1.23 | N | N | Planned | BG - Start Task - Record all Procurement Transactions Using Business Continuity Forms | 0.25 | 2021-02-01 15:00 | 2021-02-01 15:15 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 94780,81706 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:15 | PTP - Procurement/Stores | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96375 | WBS.2.2.9.1.6.1.4 | N | N | Planned | BG - STOP Recording Purchase Requisitions (Direct & Indirect) on business continuity form - S2P | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 8860,9337,96473 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP - Procurement/Stores | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96374 | WBS.2.2.9.1.6.1.5 | N | N | Planned | BG - STOP Recording Procurement Transactions Manually; Begin entry into S4 | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | BRANDY MEREDITH | Brandy.Meredith@gapac.com | DEAN PIPER;LYNN MCMURDO;SAI TEAM;DOUG CARANGELLO;Mark Bernard | Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;*;MARK.BERNARD@GAPAC.COM | Business | 8860,9337,96473 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP - Procurement/Stores | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93362 | WBS.2.2.9.1.6.1.8 | N | N | Planned | PTH - STOP Recording Procurement Transactions Manually; Begin entry into S4 | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | NAWIETA HAMILTON-MATHIS | nawieta.hamilton-mathis@gapac.com | JERRY TIDMORE;CJ KAUTH;ROBBIE GARNER;SAI TEAM | jerry.tidmore@gapac.com ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 8860,9337,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93361 | WBS.2.2.9.1.6.1.9 | N | N | Planned | PTH - STOP Recording Storeroom Transactions Manually; Begin entry into S4 | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 8860,9337,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90464 | WBS.2.2.9.1.6.1.10 | N | N | Planned | ATL - Validate PO line item count and cross-reference received by Datacap | 0.5 | 2021-02-01 16:15 | 2021-02-01 16:45 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MIKE PUPILLO;CASEY HERMANSEN;SAI TEAM;YUDHAJIT MITRA;DOROTHY RUSSELL;MASON DRAKE;JOHN CASABURRI;MONICA CUEVAS;SANDEEP A | MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 90122 |  |  | * |  | 2021-02-01 16:15 | 2021-02-01 16:45 | PTP | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92639 | WBS.2.2.9.1.6.1.13 | N | N | Planned | Pull baseline report of invoices in S4 Ariba realm that are in awaiting reconcillation status | 1 | 2021-01-31 17:15 | 2021-01-31 18:15 | BETH MYERS | BETH.MYERS@GAPAC.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 90123 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 18:15 | EIM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95295 | WBS.2.2.9.1.6.1.15 | N | N | Planned | Determine the appropriate approval limits for new Ariba S/4 users for approvals that were occurring in AS8 | 0.5 | 2021-01-31 19:15 | 2021-01-31 19:45 | PAM NIX | PSNIX@GAPAC.COM | MYRA BATES;SAI TEAM;PTP TEAM | MYRA.BATES@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 91020 |  |  | * |  | 2021-01-31 19:15 | 2021-01-31 19:45 | EIM | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91020 | WBS.2.2.9.1.6.1.16 | N | N | Planned | Provide List of Users at Go-Live Facilities For Set-Up In The Correct EIM Ariba Realm | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | PAM NIX | PSNIX@GAPAC.COM | VIRGINIA SILICKIENE;SAI TEAM;PTP TEAM | VSILICK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 90123 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | EIM | ATL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
93895 | WBS.2.2.9.1.6.1.18 | N | N | Planned | HBG - STOP Recording Procurement Transactions Manually; Begin entry into S4 | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 8860,9337,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93894 | WBS.2.2.9.1.6.1.19 | N | N | Planned | HBG - STOP Recording Storeroom Transactions Manually; Begin entry into S4 | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 8860,9337,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91009 | WBS.2.2.10 | N | N |  | FCW ¦ Golden Transactions | 33.75 | 2021-01-31 17:15 | 2021-02-02 03:00 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-02 03:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90093 | WBS.2.2.10.1 | N | N |  | FCW ¦ Golden Transactions | 33.75 | 2021-01-31 17:15 | 2021-02-02 03:00 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-02-02 03:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
9796 | WBS.2.2.10.1.1 | N | N |  | FCW ¦ PTP Golden Transaction | 1 | 2021-02-02 02:00 | 2021-02-02 03:00 | [8 empty] | * |  | 2021-02-02 02:00 | 2021-02-02 03:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91721 | WBS.2.2.10.1.1.1 | N | N |  | FCW ¦ PTP Golden Transaction Activities | 1 | 2021-02-02 02:00 | 2021-02-02 03:00 | [8 empty] | * |  | 2021-02-02 02:00 | 2021-02-02 03:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
8860 | WBS.2.2.10.1.1.1.1 | N | N | Planned | Golden Transaction - PTP - Perform PR to PO to Invoice test (services) | 1 | 2021-02-02 02:00 | 2021-02-02 03:00 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | MIKE PUPILLO;CASEY HERMANSEN;SAI TEAM;YUDHAJIT MITRA;BRUCE KIRKLEWSKI;PTP TEAM;ALEX HANKINS;PMO TEAM | MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ALEX.HANKINS@KBSLP.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 9992,4250,36889,90878,36505,94295,97535,97543 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 03:00 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
9337 | WBS.2.2.10.1.1.1.2 | N | N | Planned | Golden Transaction - PTP - Perform PR to PO to Invoice test (material) | 1 | 2021-02-02 02:00 | 2021-02-02 03:00 | MIKE PUPILLO | MAPUPILL@GAPAC.COM | CASEY HERMANSEN;SAI TEAM;YUDHAJIT MITRA;DOROTHY RUSSELL;BRUCE KIRKLEWSKI;PTP TEAM;ALEX HANKINS;PMO TEAM | CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;ALEX.HANKINS@KBSLP.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 9992,4250,36889,90878,36505,94295,97535,97543 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 03:00 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90871 | WBS.2.2.10.1.2 | N | N |  | FCW ¦ AC Golden Transaction | 3.5 | 2021-02-01 00:45 | 2021-02-01 04:15 | [8 empty] | * |  | 2021-02-01 00:45 | 2021-02-01 04:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91736 | WBS.2.2.10.1.2.1 | N | N |  | FCW ¦ AC Golden Transaction | 3.5 | 2021-02-01 00:45 | 2021-02-01 04:15 | [8 empty] | * |  | 2021-02-01 00:45 | 2021-02-01 04:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
8853 | WBS.2.2.10.1.2.1.1 | N | N | Planned | Golden Transaction - AC | 3 | 2021-02-01 00:45 | 2021-02-01 03:45 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | JASON RAMSEY;SAI TEAM;AC TEAM;PMO TEAM;DEAN PIPER;LYNN MCMURDO | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | AC | 5768,9992,5403,5418,5398,5451,5471,5476,5379,5382,5385,5388,5393,5408,5430,5438,5489,5763,5773,89997,36505 |  |  | * |  | 2021-02-01 00:45 | 2021-02-01 03:45 | AC | PTH,HBG,BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
10233 | WBS.2.2.10.1.2.1.3 | N | N | Planned | MC Task ¦ Validate Catalog Integration (including SSO) - Work Order | 0.5 | 2021-02-01 03:45 | 2021-02-01 04:15 | CHAD FLAGG | CHAD.FLAGG@GAPAC.COM | SAI TEAM;CASEY HERMANSEN;DOROTHY RUSSELL;PTP TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;DOROTHY.RUSSELL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 4342,8853 |  |  | * |  | 2021-02-01 03:45 | 2021-02-01 04:15 | ARIBA | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
82186 | WBS.2.2.10.1.2.1.2 | N | N | Planned | Run script setting all PMRQs to Inactive for Converted MillS | 0.25 | 2021-02-01 03:45 | 2021-02-01 04:00 | BRENNEN FRISQUE | BRENNEN.FRISQUE@GAPAC.COM | PATRICK BOOMER;SAI TEAM;JASON RAMSEY;AC TEAM | PATRICK.BOOMER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM | ASSET SUITE | 8853,82188,82187 |  |  | * |  | 2021-02-01 03:45 | 2021-02-01 04:00 | ASSET SUITE | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5834 | WBS.2.2.10.1.3 | N | N |  | FCW ¦ SCM Golden Transaction | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91737 | WBS.2.2.10.1.3.1 | N | N |  | FCW ¦ SCM Golden Transaction | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5848 | WBS.2.2.10.1.3.1.1 | N | N | Planned | Execute CCR report -PPDS pv | 2 | 2021-01-31 17:15 | 2021-01-31 19:15 | FALKO KOEHLER | FKOEHLER@SCMO2.COM | CHANDRA BALASUBRAMANIAN;CHIRAG PARIKH;JENNIFER LI;SAI TEAM;SCM TEAM;PMO TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | CBALASUBRAMANIAN@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 19:15 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5843 | WBS.2.2.10.1.3.1.2 | N | N | Planned | Manual Regenerative planning run - PE pv | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | ANUPAM SHRIVASTAVA;JENNIFER LI;SAI TEAM;CHIRAG PARIKH;SCM TEAM;PMO TEAM;BRAD WYMAN | ANUPSHRIVASTAVA@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
8922 | WBS.2.2.10.1.3.1.3 | N | N | Planned | Removal of Live plant in BRF table | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | ANUPAM SHRIVASTAVA;CHIRAG PARIKH;SAI TEAM;JENNIFER LI;SCM TEAM;PMO TEAM;BRAD WYMAN | ANUPSHRIVASTAVA@DELOITTE.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JQLI@GAPAC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5850 | WBS.2.2.10.1.3.1.4 | N | N | Planned | Start master data interface batch jobs- PE | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | CHIRAG PARIKH | CPARIKH@DELOITTE.COM | JENNIFER LI;SAI TEAM;SCM TEAM;PMO TEAM;BRAD WYMAN;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5851 | WBS.2.2.10.1.3.1.5 | N | N | Planned | Start transaction data interface batch jobs- PE | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | JENNIFER LI;SAI TEAM;SCM TEAM;PMO TEAM;BRAD WYMAN;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5844 | WBS.2.2.10.1.3.1.6 | N | N | Planned | Manual Net change planning run -PE pv | 0.25 | 2021-01-31 17:30 | 2021-01-31 17:45 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | ANUPAM SHRIVASTAVA;JENNIFER LI;SAI TEAM;SCM TEAM;PMO TEAM;BRAD WYMAN | ANUPSHRIVASTAVA@DELOITTE.COM;JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 5843,9992,36505 |  |  | * |  | 2021-01-31 17:30 | 2021-01-31 17:45 | SCM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
9795 | WBS.2.2.10.1.4 | N | N |  | FCW ¦ RTR Golden Transaction | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
91738 | WBS.2.2.10.1.4.1 | N | N |  | FCW ¦ RTR Golden Transaction | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | [8 empty] | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 |  |  | 2021-01-31 | 2021-01-31 | 3 | Shutdown
8879 | WBS.2.2.10.1.4.1.1 | N | N | Planned | Smoke Test - RTR - GL | 0.25 | 2021-01-31 17:15 | 2021-01-31 17:30 | RICARDO OLIVEIRA | RICARDO.OLIVEIRA@GAPAC.COM | RANJAI JOHN;SAI TEAM;DONNA SMITH;SANDRA RICHARDS;RTR TEAM;BOATENG LAWRENCE | RANJAI.JOHN@KOCHTC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 9992,92742 |  |  | * |  | 2021-01-31 17:15 | 2021-01-31 17:30 | RTR - GL | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
5832 | WBS.2.2.10.1.5 | N | N |  | FCW ¦ EWM Golden Transaction | 11 | 2021-02-01 09:00 | 2021-02-01 20:00 | [8 empty] | * |  | 2021-02-01 09:00 | 2021-02-01 20:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91739 | WBS.2.2.10.1.5.1 | N | N |  | FCW ¦ EWM Golden Transaction | 11 | 2021-02-01 09:00 | 2021-02-01 20:00 | [8 empty] | * |  | 2021-02-01 09:00 | 2021-02-01 20:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5833 | WBS.2.2.10.1.5.1.1 | N | N | Planned | SCH - Process Golden Transactions in EWM | 1 | 2021-02-01 09:01 | 2021-02-01 10:01 | RASHI KUCHYA | rkuchya@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;SHREYA NARULA;GAYATHRI BATTALA;JEREMY RAY;TOMMY NEFFENDORF;GIOVANY CARVAJAL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;shrenarula@deloitte.com;GBATTALA@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | EWM | 9992,36505,93044,95197 |  |  | * |  | 2021-02-01 09:01 | 2021-02-01 10:01 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95155 | WBS.2.2.10.1.5.1.2 | N | N | Planned | PTH - Process Golden Transactions in EWM | 1 | 2021-02-01 19:00 | 2021-02-01 20:00 | GAYATHRI BATTALA | GBATTALA@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;AJIT GOLE;JAMES COWELL | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ajgole@deloitte.com;James.Cowell@gapac.com | EWM | 9992,36505,94781,90412,95654,95652,95666,95668 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 20:00 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95152 | WBS.2.2.10.1.5.1.4 | N | N | Planned | HBG - Process Golden Transactions in EWM | 1 | 2021-02-01 14:30 | 2021-02-01 15:30 | AJIT GOLE | ajgole@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;TEJAS THORAT;CHRIS ZUMWALT | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TTHORAT@DELOITTE.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 9992,36505,93916,95658,95660,95672,95674 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 15:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96378 | WBS.2.2.10.1.5.1.6 | N | N | Planned | RNC - Process Golden Transactions in EWM | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | Shefali Kushwaha | shefkushwaha@deloitte.com | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RASHI KUCHYA;GAYATHRI BATTALA;JEREMY RAY;TOMMY NEFFENDORF;DAVID ALENCASTRO | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;rkuchya@deloitte.com;GBATTALA@DELOITTE.COM;JEREMY.RAY@GAPAC.COM;TOMMY.NEFFENDORF@GAPAC.COM;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM | EWM | 9992,36505,96716,96733 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96377 | WBS.2.2.10.1.5.1.7 | N | N | Planned | RVG - Process Golden Transactions in EWM | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | SANTOSH KUPPILI | VKUPPILI@DELOITTE.COM | AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;ALOK BHAT;NIKHIL NEGI;JENNIFER MCLEOD;JULI LEWIS | AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;alobhatt@deloitte.com;nikhnegi@deloitte.com;JENNIFER.MCLEOD@GAPAC.COM;JULI.LEWIS@GAPAC.COM | EWM | 9992,36505,96718,96740 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96376 | WBS.2.2.10.1.5.1.8 | N | N | Planned | BG - Process Golden Transactions in EWM | 1 | 2021-02-01 15:00 | 2021-02-01 16:00 | SATYAM KUMAR | KSATYAM@DELOITTE.COM | SANTOSH KUPPILI;AVINASH TALREJA;KUMAR SATYAM;Mohaideen Feroze;SAI TEAM;DOUG STANISLAWSKI;EWM TEAM;RATUL CHAKRABORTY;PRAJWAL K S;BEAU EARLS | VKUPPILI@DELOITTE.COM;AVTALREJA@DELOITTE.COM;KSATYAM@DELOITTE.COM;FMOHAIDEEN@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ratchakraborty@deloitte.com;prajks@deloitte.com;Beau.Earls@GAPAC.com | EWM | 9992,36505,96547,96548,96549,96550,96645,96647 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 16:00 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91010 | WBS.2.2.11 | N | N |  | FCW ¦ Golden Finish Tracking | 50.25 | 2021-01-31 01:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 03:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82197 | WBS.2.2.11.1 | N | N |  | FCW ¦ Golden Finish Tracking | 50.25 | 2021-01-31 01:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 03:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90096 | WBS.2.2.11.1.1 | N | N |  | FCW ¦ Golden Finish Tracking | 50.25 | 2021-01-31 01:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 03:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91726 | WBS.2.2.11.1.1.1 | N | N |  | FCW ¦ Golden Finish Tracking | 50.25 | 2021-01-31 01:15 | 2021-02-02 03:30 | [8 empty] | * |  | 2021-01-31 01:15 | 2021-02-02 03:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
82243 | WBS.2.2.11.1.1.1.1 | N | N | Planned | Identify Golden Transactions for all Sites (Penny Transactions) | 1 | 2021-01-31 01:15 | 2021-01-31 02:15 | DOUG STANISLAWSKI | DOUG.STANISLAWSKI@GAPAC.COM | DAVE BASCHE;SAI TEAM;CRAIG HURST;JEFFREY GOLDMUNTZ;EWM TEAM;JACOB OWENS;BRIAN LEMOND | DAVID.BASCHE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CRAIG.HURST@GAPAC.COM;JGOLDMUNTZ@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;JACOB.OWENS@GAPAC.COM;BDLEMOND@GAPAC.COM | EWM | 36501,36505 |  |  | * |  | 2021-01-31 01:15 | 2021-01-31 02:15 | EWM | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
82339 | WBS.2.2.11.1.1.1.2 | N | N | Planned | Golden Finish | 0.5 | 2021-02-02 03:00 | 2021-02-02 03:30 | SAI TEAM | JVALLABHANENI@DELOITTE.COM |  | JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | SAI | 8853,8879,8860,9337,5843,5844,5848,5833,95152,95155 |  |  | * |  | 2021-02-02 03:00 | 2021-02-02 03:30 | SAI | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91011 | WBS.2.2.12 | N | N |  | FCW ¦ Pilot Transactions | 17.5 | 2021-02-01 14:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-02 07:45 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90094 | WBS.2.2.12.1 | N | N |  | FCW ¦ Pilot Transactions | 17.5 | 2021-02-01 14:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-02 07:45 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90097 | WBS.2.2.12.1.1 | N | N |  | FCW ¦ Pilot Transactions - HBG | 11.5 | 2021-02-01 20:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 20:15 | 2021-02-02 07:45 |  | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93907 | WBS.2.2.12.1.1.1 | N | N |  | FCW ¦ Pilot Transactions - HBG - AC | 1.5 | 2021-02-02 03:45 | 2021-02-02 05:15 | [8 empty] | * |  | 2021-02-02 03:45 | 2021-02-02 05:15 |  | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93921 | WBS.2.2.12.1.1.1.1 | N | N | Planned | HBG - Pilot Transaction: Generate Unplanned WO with Unplanned Goods Issue | 1 | 2021-02-02 03:45 | 2021-02-02 04:45 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 36505,82553,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:45 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93928 | WBS.2.2.12.1.1.1.2 | N | N | Planned | HBG - Pilot Transaction: WO with a service contract | 1.5 | 2021-02-02 03:45 | 2021-02-02 05:15 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 36505,82553,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 05:15 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93927 | WBS.2.2.12.1.1.1.3 | N | N | Planned | HBG - Pilot Transaction: Execute an operator inspection route | 0.75 | 2021-02-02 03:45 | 2021-02-02 04:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 36505,82553,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:30 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94665 | WBS.2.2.12.1.1.2 | N | N |  | FCW ¦ Pilot Transactions - HBG - EWM | 11.5 | 2021-02-01 20:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-01 20:15 | 2021-02-02 07:45 |  | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93906 | WBS.2.2.12.1.1.2.1 | N | N | Planned | HBG - Pilot Transaction: Identify/Receive using new STO number in S/4HANA | 4 | 2021-02-02 03:45 | 2021-02-02 07:45 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,95117,95152,95158 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 07:45 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93930 | WBS.2.2.12.1.1.2.2 | N | N | Planned | HBG - Pilot Transaction: Storeroom Pick, Issue and Cycle Count | 1 | 2021-02-02 03:45 | 2021-02-02 04:45 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM;KRISTINA KAUTH | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KRISTINA.KAUTH@GAPAC.COM | Business | 36505,82553,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:45 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93933 | WBS.2.2.12.1.1.2.3 | N | N | Planned | HBG - Pilot Transaction: Full converting process from staging to E80 pickup (PICK UP AT PLANT WRAPPER FOR HBG) | 5 | 2021-02-01 20:15 | 2021-02-02 01:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,95089 |  |  | * |  | 2021-02-01 20:15 | 2021-02-02 01:15 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93932 | WBS.2.2.12.1.1.2.4 | N | N | Planned | HBG - Pilot Transaction: stage and load outbound delivery | 3 | 2021-02-01 20:15 | 2021-02-01 23:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,95089 |  |  | * |  | 2021-02-01 20:15 | 2021-02-01 23:15 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95217 | WBS.2.2.12.1.1.2.5 | N | N | Planned | HBG - Pilot Transaction: Complete Pilot Outbound order, process order through staging, not loading or PGI | 4 | 2021-02-01 20:15 | 2021-02-02 00:15 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629,95089,95152,21147,82553 |  |  | * |  | 2021-02-01 20:15 | 2021-02-02 00:15 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94666 | WBS.2.2.12.1.1.3 | N | N |  | FCW ¦ Pilot Transactions - HBG - PTP | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 |  | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93929 | WBS.2.2.12.1.1.3.1 | N | N | Planned | HBG - Pilot Transaction: Generate Service PO Over $15k | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | BRETT WILBERDING | RICHARD.WILBERDING@GAPAC.com | KEN LITTLES;CHRIS ZUMWALT;SAI TEAM | Kenneth.Littles@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,82553,95117 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | PTP - Procurement/Stores | HBG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93331 | WBS.2.2.12.1.3 | N | N |  | FCW ¦ Pilot Transactions - PTH | 6.5 | 2021-02-02 01:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-02 01:15 | 2021-02-02 07:45 |  | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94672 | WBS.2.2.12.1.3.1 | N | N |  | FCW ¦ Pilot Transactions - PTH - AC | 2 | 2021-02-02 03:45 | 2021-02-02 05:45 | [8 empty] | * |  | 2021-02-02 03:45 | 2021-02-02 05:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95560 | WBS.2.2.12.1.3.1.2 | N | N | Planned | PTH - Pilot Transaction: Create a notification | 1.5 | 2021-02-02 03:45 | 2021-02-02 05:15 | DARRELL WATSON | Darrell.watson@gapac.com | TOMMY WOMACK;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS | tommy.womack@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com | Business | 82553,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 05:15 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95561 | WBS.2.2.12.1.3.1.3 | N | N | Planned | PTH - Pilot Transaction: Execute an operator inspection route | 0.75 | 2021-02-02 03:45 | 2021-02-02 04:30 | SEAN HERTZBURG | sean.hertzberg@gapac.com | JT THOMAS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS | Jerry.Thomas2@gapac.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com | Business | 82553,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:30 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95562 | WBS.2.2.12.1.3.1.4 | N | N | Planned | PTH - Pilot Transaction: Self Assign WO with material from Storeroom and execute work | 2 | 2021-02-02 03:45 | 2021-02-02 05:45 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com | Business | 82553,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 05:45 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95563 | WBS.2.2.12.1.3.1.5 | N | N | Planned | PTH - Pilot Transaction: Execute a lube route | 2 | 2021-02-02 03:45 | 2021-02-02 05:45 | PORTER CRAIG | Porter.Craig@gapac.com | RANDALL KNAPP;CJ KAUTH;ROBBIE GARNER;SAI TEAM;DANIEL HENDERSON;JERRY (JT) THOMAS | Randall.Knapp@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;daniel.henderson@gapac.com;jerry.thomas@gapac.com | Business | 82553,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 05:45 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94673 | WBS.2.2.12.1.3.2 | N | N |  | FCW ¦ Pilot Transactions - PTH - EWM | 6.5 | 2021-02-02 01:15 | 2021-02-02 07:45 | [8 empty] | * |  | 2021-02-02 01:15 | 2021-02-02 07:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93263 | WBS.2.2.12.1.3.2.1 | N | N | Planned | PTH - Pilot Transaction: Identify/Receive using new STO number in S/4HANA | 4 | 2021-02-02 03:45 | 2021-02-02 07:45 | KATIE PARKER | Katie.Parker@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON;HADYN HUGHES | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 36505,95119,95155,92427 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 07:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
92914 | WBS.2.2.12.1.3.2.2 | N | N | Planned | PTH - Pilot Transaction: Storeroom Pick, Issue and Cycle Count | 1 | 2021-02-02 03:45 | 2021-02-02 04:45 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER;KRISTINA KAUTH | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com;KRISTINA.KAUTH@GAPAC.COM | Business | 36505,82553,95119 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93344 | WBS.2.2.12.1.3.2.3 | N | N | Planned | PTH - Pilot Transaction: Complete Pilot Outbound order, process order through staging, not loading or PGI | 4 | 2021-02-02 01:15 | 2021-02-02 05:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 36505,82629,82553,21147,93346,95067,95155 |  |  | * |  | 2021-02-02 01:15 | 2021-02-02 05:15 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93340 | WBS.2.2.12.1.3.2.4 | N | N | Planned | PTH - Pilot Transaction: Full converting process from staging to E80 pickup | 5 | 2021-02-02 01:15 | 2021-02-02 06:15 | HADYN HUGHES | CHRISTOPHER.HUGHES@GAPAC.COM | ANDY JONES;DARRYL JOHNSON;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 82553,95067 |  |  | * |  | 2021-02-02 01:15 | 2021-02-02 06:15 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93339 | WBS.2.2.12.1.3.2.5 | N | N | Planned | PTH - Pilot Transaction: E80 stage and load outbound delivery | 3 | 2021-02-02 01:15 | 2021-02-02 04:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 82553,95067 |  |  | * |  | 2021-02-02 01:15 | 2021-02-02 04:15 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97812 | WBS.2.2.12.1.3.2.12 | N | N | Planned | PTH - Pilot Transaction: Check-in an empty trailer via Gate Pass Check-in and check it into CK01 location | 0.25 | 2021-02-02 01:15 | 2021-02-02 01:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 82553,95067 |  |  | * |  | 2021-02-02 01:15 | 2021-02-02 01:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97811 | WBS.2.2.12.1.3.2.11 | N | N | Planned | PTH - Pilot Transaction: Using Gate Pass (Update Existing Trailer) – Update the trailer to a Yard Location | 0.25 | 2021-02-02 01:30 | 2021-02-02 01:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97812 |  |  | * |  | 2021-02-02 01:30 | 2021-02-02 01:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97810 | WBS.2.2.12.1.3.2.10 | N | N | Planned | PTH - Pilot Transaction: Using Gate Pass (Create Spotter Move) – Create a spotter move to move the trailer to an open dock door | 0.25 | 2021-02-02 01:45 | 2021-02-02 02:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97811 |  |  | * |  | 2021-02-02 01:45 | 2021-02-02 02:00 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97809 | WBS.2.2.12.1.3.2.9 | N | N | Planned | PTH - Pilot Transaction: Work with 4Sight and confirm the SPOT transaction was recorded properly in 4Sight | 0.25 | 2021-02-02 02:00 | 2021-02-02 02:15 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97810 |  |  | * |  | 2021-02-02 02:00 | 2021-02-02 02:15 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97808 | WBS.2.2.12.1.3.2.8 | N | N | Planned | PTH - Pilot Transaction: Perform the move of the trailer to the dock door using the Yard Pilot Tablet | 0.25 | 2021-02-02 02:15 | 2021-02-02 02:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97809 |  |  | * |  | 2021-02-02 02:15 | 2021-02-02 02:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97807 | WBS.2.2.12.1.3.2.7 | N | N | Planned | PTH - Pilot Transaction: Confirm the trailer was successfully moved to the Dock Door in EWM | 0.25 | 2021-02-02 02:30 | 2021-02-02 02:45 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97808 |  |  | * |  | 2021-02-02 02:30 | 2021-02-02 02:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
97806 | WBS.2.2.12.1.3.2.6 | N | N | Planned | PTH - Pilot Transaction: Using Gate Pass Check-Out screen, Check the trailer out and confirm in YMS that the trailer was dispatched correctly. | 0.25 | 2021-02-02 02:45 | 2021-02-02 03:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;SAI TEAM;EWM TEAM | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | Business | 97807 |  |  | * |  | 2021-02-02 02:45 | 2021-02-02 03:00 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91728 | WBS.2.2.12.1.4 | N | N |  | FCW ¦ Pilot Transactions - SCH | 4 | 2021-02-01 14:16 | 2021-02-01 18:16 | [8 empty] | * |  | 2021-02-01 14:16 | 2021-02-01 18:16 |  | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94668 | WBS.2.2.12.1.4.1 | N | N |  | FCW ¦ Pilot Transactions - SCH - EWM | 4 | 2021-02-01 14:16 | 2021-02-01 18:16 | [8 empty] | * |  | 2021-02-01 14:16 | 2021-02-01 18:16 |  | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92996 | WBS.2.2.12.1.4.1.1 | N | N | Planned | SCH - Pilot Transaction: Identify/Receive using new STO number in S4 | 4 | 2021-02-01 14:16 | 2021-02-01 18:16 | ANDY KEOYOTHY | ANDY.KEOYOTHY@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Tristan.Clark@nfiindustries.com | Business | 21147,5833,93047,95164,95070 |  |  | * |  | 2021-02-01 14:16 | 2021-02-01 18:16 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92995 | WBS.2.2.12.1.4.1.2 | N | N | Planned | SCH - Pilot Transaction: Complete Pilot Outbound order, process order through staging, not loading or PGI | 3 | 2021-02-01 14:16 | 2021-02-01 17:16 | ANDY KEOYOTHY | ANDY.KEOYOTHY@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;Tristan.Clark@nfiindustries.com | Business | 21147,95070,5833 |  |  | * |  | 2021-02-01 14:16 | 2021-02-01 17:16 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96386 | WBS.2.2.12.1.5 | N | N |  | FCW ¦ Pilot Transactions - RNC | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96385 | WBS.2.2.12.1.5.1 | N | N |  | FCW ¦ Pilot Transactions - RNC - EWM | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96384 | WBS.2.2.12.1.5.1.1 | N | N | Planned | RNC - Pilot Transaction: Identify/Receive using new STO number in S4 | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 21147,96378,96419,96462,96453 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96383 | WBS.2.2.12.1.5.1.2 | N | N | Planned | RNC - Pilot Transaction: Complete Pilot Outbound order, process order through staging, not loading or PGI | 3 | 2021-02-01 14:15 | 2021-02-01 17:15 | DAVID ALENCASTRO | DAVID.ALENCASTRO@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;TOMMY NEFFENDORF;JEREMY RAY;FRANCISCO CHAVEZ;FABIAN RICHARDSON;JULIO RENTERIA | DAVID.ALENCASTRO@NFIINDUSTRIES.COM;MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;francisco.chavez1@gapac.com ;Fabian.Richardson@GAPAC.com ;Julio.Renteria@gapac.com | Business | 21147,96453,96378 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 17:15 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96382 | WBS.2.2.12.1.6 | N | N |  | FCW ¦ Pilot Transactions - RVG | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96381 | WBS.2.2.12.1.6.1 | N | N |  | FCW ¦ Pilot Transactions - RVG - EWM | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | [8 empty] | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96380 | WBS.2.2.12.1.6.1.1 | N | N | Planned | RVG - Pilot Transaction: Identify/Receive using new STO number in S4 | 4 | 2021-02-01 14:15 | 2021-02-01 18:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96377,96449 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 18:15 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96379 | WBS.2.2.12.1.6.1.2 | N | N | Planned | RVG - Pilot Transaction: Complete Pilot Outbound order, process order by assigning trailer, flow and stage to E80, loading, not PGI to include crossdock | 3 | 2021-02-01 14:15 | 2021-02-01 17:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96377,96449 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 17:15 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96528 | WBS.2.2.12.1.6.1.3 | N | N | Planned | RVG - Review and validate Customer Specific Requirements | 1 | 2021-02-01 14:15 | 2021-02-01 15:15 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96377,96449 |  |  | * |  | 2021-02-01 14:15 | 2021-02-01 15:15 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96397 | WBS.2.2.12.1.8 | N | N |  | FCW ¦ Pilot Transactions - BG | 7 | 2021-02-01 22:15 | 2021-02-02 05:15 | [8 empty] | * |  | 2021-02-01 22:15 | 2021-02-02 05:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96393 | WBS.2.2.12.1.8.2 | N | N |  | FCW ¦ Pilot Transactions - BG - EWM | 5.75 | 2021-02-01 22:15 | 2021-02-02 04:00 | [8 empty] | * |  | 2021-02-01 22:15 | 2021-02-02 04:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96392 | WBS.2.2.12.1.8.2.1 | N | N | Planned | BG - Pilot Transaction: Identify/Receive using new STO number in S/4HANA | 0.25 | 2021-02-02 03:45 | 2021-02-02 04:00 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | BEAU EARLS;LYNN MCMURDO;DEAN PIPER;SAI TEAM | Beau.Earls@GAPAC.com;LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,96473,96376,96478 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 04:00 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96391 | WBS.2.2.12.1.8.2.2 | N | N | Planned | BG - Pilot Transaction: Complete Pilot Outbound order, process order through staging, not loading or PGI | 4 | 2021-02-01 22:15 | 2021-02-02 02:15 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,82629,21147,96402,96404,96496 |  |  | * |  | 2021-02-01 22:15 | 2021-02-02 02:15 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96390 | WBS.2.2.12.1.8.3 | N | N |  | FCW ¦ Pilot Transactions - BG - PTP | 1.5 | 2021-02-02 03:45 | 2021-02-02 05:15 | [8 empty] | * |  | 2021-02-02 03:45 | 2021-02-02 05:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96387 | WBS.2.2.12.1.8.3.3 | N | N | Planned | BG - Pilot Transaction: WO with material from Ariba – this creates a PR for GPID | 1.5 | 2021-02-02 03:45 | 2021-02-02 05:15 | TODD BARKS | TABARKS@GAPAC.com | ROBBIE ISBELL;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Daniel.Isbell@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,82553,96473 |  |  | * |  | 2021-02-02 03:45 | 2021-02-02 05:15 | PTP - Procurement/Stores | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96791 | WBS.2.2.12.1.8.3.9 | N | N | Planned | BG - Pilot Transaction: Generate Purchase Requisition using short text | 0.5 | 2021-02-02 04:00 | 2021-02-02 04:30 | BRIAN RAYMER | BRIAN.RAYMER@GAPAC.COM | SARAH SANDERS;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BRANDY MEREDITH | Sarah.Sanders@gapac.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Brandy.Meredith@gapac.com | Business | 96375,96473 |  |  | * |  | 2021-02-02 04:00 | 2021-02-02 04:30 | PTP | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
96790 | WBS.2.2.12.1.8.3.8 | N | N | Planned | BG - Pilot Transaction: Approve Purchase requisition using short text | 0.5 | 2021-02-02 04:30 | 2021-02-02 05:00 | DAVID HARRER | DAVID.HARRER@GAPAC.COM | JEFF BOWLES;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BRANDY MEREDITH | JEFF.BOWLES@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Brandy.Meredith@gapac.com | Business | 96791,96473 |  |  | * |  | 2021-02-02 04:30 | 2021-02-02 05:00 | PTP | BG | 2021-02-02 | 2021-02-02 | 3 | Shutdown
91012 | WBS.2.2.13 | N | N |  | FCW ¦ Catch-Up Transactions | 47.5 | 2021-01-31 01:30 | 2021-02-02 01:00 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-02-02 01:00 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
90110 | WBS.2.2.13.1 | N | N |  | FCW ¦ Catch-Up Transactions | 47.5 | 2021-01-31 01:30 | 2021-02-02 01:00 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-02-02 01:00 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94618 | WBS.2.2.13.1.1 | N | N |  | FCW ¦ Production Catch-Up Transactions – PTH – EWM/ICPAQS/E80 | 6 | 2021-02-01 19:00 | 2021-02-02 01:00 | [8 empty] | * |  | 2021-02-01 19:00 | 2021-02-02 01:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94622 | WBS.2.2.13.1.1.1 | N | N |  | FCW ¦ Production Catch-up Transactions – PTH – EWM/ICPAQS/E80 | 6 | 2021-02-01 19:00 | 2021-02-02 01:00 | [8 empty] | * |  | 2021-02-01 19:00 | 2021-02-02 01:00 |  |  | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94856 | WBS.2.2.13.1.1.1.1 | N | N | Planned | PTH - EWM - Process Catch Up transactions (InventoryTransfer) - EWM | 3.5 | 2021-02-01 21:30 | 2021-02-02 01:00 | RAFI MOHAMMED | RAFIPASHA.MOHAMMED@GAPAC.COM | MICHAEL MATTHEWS;SAI TEAM;EWM TEAM;JAMES COWELL | MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;James.Cowell@gapac.com | EWM | 36505,94990 |  |  | * |  | 2021-02-01 21:30 | 2021-02-02 01:00 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94853 | WBS.2.2.13.1.1.1.2 | N | N | Planned | PTH - Process Catch Up transactions (ProduceHU) - EWM | 2 | 2021-02-01 21:30 | 2021-02-01 23:30 | RAFI MOHAMMED | RAFIPASHA.MOHAMMED@GAPAC.COM | MICHAEL MATTHEWS;SAI TEAM;EWM TEAM;JAMES COWELL | MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;James.Cowell@gapac.com | EWM | 36505,94858 |  |  | * |  | 2021-02-01 21:30 | 2021-02-01 23:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94990 | WBS.2.2.13.1.1.1.3 | N | N | Planned | PTH - E80 - Send Catch Up transactions to SAP (Inventory Transfers) | 0.5 | 2021-02-01 21:00 | 2021-02-01 21:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;CJ KAUTH;ROBBIE GARNER;STEPHANIE MOORE ;VIKTOR ZIVREV ;JAMES LANDRY ;EMANUEL VILLEGAS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;VILLEGAS.E@ELETTRIC80.IT | EWM | 94919 |  |  | * |  | 2021-02-01 21:00 | 2021-02-01 21:30 | E80 | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94858 | WBS.2.2.13.1.1.1.4 | N | N | Planned | PTH - E80 - Send Catch Up transactions to ICPAQs (ProduceHU) | 0.5 | 2021-02-01 21:00 | 2021-02-01 21:30 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;CJ KAUTH;ROBBIE GARNER;STEPHANIE MOORE ;VIKTOR ZIVREV ;JAMES LANDRY ;EMANUEL VILLEGAS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;VILLEGAS.E@ELETTRIC80.IT | EWM | 94915 |  |  | * |  | 2021-02-01 21:00 | 2021-02-01 21:30 | E80 | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94561 | WBS.2.2.13.1.1.1.5 | N | N | Planned | PTH - Stop Converting Lines | 0.5 | 2021-02-01 19:00 | 2021-02-01 19:30 | ANDY JONES | Gibson.Jones@gapac.com | DARRYL JOHNSON;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | DARRYL.JOHNSON@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90412,94483,94513,94480,94781,95652,95654,95666,95668 |  |  | * |  | 2021-02-01 19:00 | 2021-02-01 19:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93350 | WBS.2.2.13.1.1.1.6 | N | N | Planned | PTH - Validate PR Production from ICPAQ's to S4/EWM | 1 | 2021-02-01 20:45 | 2021-02-01 21:45 | JT THOMAS | Jerry.Thomas2@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 90616,90412,94483,94513,94480,94781,94554 |  |  | * |  | 2021-02-01 20:45 | 2021-02-01 21:45 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93349 | WBS.2.2.13.1.1.1.7 | N | N | Planned | PTH - Validate PR and Vital Consumption from ICPAQ's to S4/EWM | 1 | 2021-02-01 20:45 | 2021-02-01 21:45 | JT THOMAS | Jerry.Thomas2@gapac.com | JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 90616,90412,94483,94513,94480,94781,94554 |  |  | * |  | 2021-02-01 20:45 | 2021-02-01 21:45 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94554 | WBS.2.2.13.1.1.1.8 | N | N | Planned | PTH - Action - Turn on Transaction Service | 0.25 | 2021-02-01 20:30 | 2021-02-01 20:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS;JAMES COWELL;JERRY (JT) THOMAS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM;James.Cowell@gapac.com;jerry.thomas@gapac.com | ICPAQS | 90616,90412,94483,94513,94480,94781,95627,94893 |  |  | * |  | 2021-02-01 20:30 | 2021-02-01 20:45 | ICPAQS | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95628 | WBS.2.2.13.1.1.1.9 | N | N | Planned | PTH - Move Paper produced in FCW to true bin location in EWM | 1 | 2021-02-01 21:45 | 2021-02-01 22:45 | JAMES COWELL | James.Cowell@gapac.com | HADYN HUGHES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | CHRISTOPHER.HUGHES@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | Business | 93350 |  |  | * |  | 2021-02-01 21:45 | 2021-02-01 22:45 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95627 | WBS.2.2.13.1.1.1.10 | N | N | Planned | PTH - Move Vitals to Staging Lane for those manually staged during FCW/Update locations of consumed vitals in EWM – report from ICPAQS can be used to know LPN | 1 | 2021-02-01 19:30 | 2021-02-01 20:30 | JAMES COWELL | James.Cowell@gapac.com | HADYN HUGHES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;ANDY JONES;DARRYL JOHNSON | CHRISTOPHER.HUGHES@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | Business | 94561 |  |  | * |  | 2021-02-01 19:30 | 2021-02-01 20:30 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94919 | WBS.2.2.13.1.1.1.11 | N | N | Planned | PTH - Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-02-01 20:45 | 2021-02-01 21:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;JAMES COWELL;JERRY (JT) THOMAS | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;James.Cowell@gapac.com;jerry.thomas@gapac.com | ICPAQS | 94554 |  |  | * |  | 2021-02-01 20:45 | 2021-02-01 21:00 | ICPAQS | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94915 | WBS.2.2.13.1.1.1.12 | N | N | Planned | PTH - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-02-01 20:45 | 2021-02-01 21:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;JAMES COWELL;JERRY (JT) THOMAS | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;James.Cowell@gapac.com;jerry.thomas@gapac.com | ICPAQS | 94554 |  |  | * |  | 2021-02-01 20:45 | 2021-02-01 21:00 | ICPAQS | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93345 | WBS.2.2.13.1.1.1.13 | N | N | Planned | PTH - Validate Converting Staging Lane Inventory Level | 2 | 2021-02-01 21:45 | 2021-02-01 23:45 | JAMES COWELL | James.Cowell@gapac.com | JT THOMAS;CJ KAUTH;ROBBIE GARNER;SAI TEAM;EWM TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES;ANDY JONES;DARRYL JOHNSON | Jerry.Thomas2@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM ;Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM | EWM | 93349 |  |  | * |  | 2021-02-01 21:45 | 2021-02-01 23:45 | EWM | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94620 | WBS.2.2.13.1.3 | N | N |  | FCW ¦ Production Catch-Up Transactions – HBG – EWM/ICPAQS/E80 | 5.5 | 2021-02-01 14:30 | 2021-02-01 20:00 | [8 empty] | * |  | 2021-02-01 14:30 | 2021-02-01 20:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94624 | WBS.2.2.13.1.3.1 | N | N |  | FCW ¦ Production Catch-up Transactions – HBG – EWM/ICPAQS/E80 | 5.5 | 2021-02-01 14:30 | 2021-02-01 20:00 | [8 empty] | * |  | 2021-02-01 14:30 | 2021-02-01 20:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95246 | WBS.2.2.13.1.3.1.1 | N | N | Planned | HBG - EWM - Process Catch Up transactions (InventoryTransfer) | 3.5 | 2021-02-01 16:30 | 2021-02-01 20:00 | RAFI MOHAMMED | RAFIPASHA.MOHAMMED@GAPAC.COM | MICHAEL MATTHEWS;SAI TEAM;EWM TEAM;MELISSA KOTAREK;CHRIS ZUMWALT | MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MELISSA.KOTAREK@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 36505,94917 |  |  | * |  | 2021-02-01 16:30 | 2021-02-01 20:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95247 | WBS.2.2.13.1.3.1.2 | N | N | Planned | HBG - EWM - Process Catch Up transactions (ProduceHU) | 2 | 2021-02-01 16:45 | 2021-02-01 18:45 | RAFI MOHAMMED | RAFIPASHA.MOHAMMED@GAPAC.COM | MICHAEL MATTHEWS;SAI TEAM;EWM TEAM;MELISSA KOTAREK;CHRIS ZUMWALT | MMATTHEWS@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;MELISSA.KOTAREK@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com | EWM | 36505,94913 |  |  | * |  | 2021-02-01 16:45 | 2021-02-01 18:45 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94563 | WBS.2.2.13.1.3.1.5 | N | N | Planned | HBG - Stop Converting Lines | 0.5 | 2021-02-01 14:30 | 2021-02-01 15:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 36505,93916,95658,95660,95672,95674 |  |  | * |  | 2021-02-01 14:30 | 2021-02-01 15:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95630 | WBS.2.2.13.1.3.1.6 | N | N | Planned | HBG - Move Vitals to Staging Lane for those manually staged during FCW/Update locations of consumed vitals in EWM – report from ICPAQS can be used to know LPN | 1 | 2021-02-01 15:00 | 2021-02-01 16:00 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94563 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 16:00 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94393 | WBS.2.2.13.1.3.1.7 | N | N | Planned | HBG - Action - Turn on Transaction Service | 0.25 | 2021-02-01 16:00 | 2021-02-01 16:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616,94548,93916,95630 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 16:15 | ICPAQS | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94917 | WBS.2.2.13.1.3.1.8 | N | N | Planned | HBG - Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-02-01 16:15 | 2021-02-01 16:30 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94393 |  |  | * |  | 2021-02-01 16:15 | 2021-02-01 16:30 | ICPAQS | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94913 | WBS.2.2.13.1.3.1.9 | N | N | Planned | HBG - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-02-01 16:30 | 2021-02-01 16:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 94917 |  |  | * |  | 2021-02-01 16:30 | 2021-02-01 16:45 | ICPAQS | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93938 | WBS.2.2.13.1.3.1.10 | N | N | Planned | HBG - Validate PR and Vital Consumption from ICPAQ's to S4/EWM | 1 | 2021-02-01 16:15 | 2021-02-01 17:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94393 |  |  | * |  | 2021-02-01 16:15 | 2021-02-01 17:15 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93935 | WBS.2.2.13.1.3.1.11 | N | N | Planned | HBG - Validate Converting Staging Lane Inventory Level | 2 | 2021-02-01 17:15 | 2021-02-01 19:15 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM;EWM TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com | EWM | 93938 |  |  | * |  | 2021-02-01 17:15 | 2021-02-01 19:15 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96425 | WBS.2.2.13.1.5 | N | N |  | FCW ¦ Catch-Up Transactions - RNC | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96424 | WBS.2.2.13.1.5.1 | N | N |  | FCW ¦ Catch-Up Transactions - RNC - EWM | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96422 | WBS.2.2.13.1.5.1.2 | N | N | Planned | RNC - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Retail | 1 | 2021-02-01 10:00 | 2021-02-01 11:00 | ANA OLIVER | ANA.OLIVER@GAPAC.COM | MARIA MARQUEZ;SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;LILLIAN GARCIA;ELIZABETH PARDO;CASSANDRA OCHOA | MARIA.MARQUEZ@GAPAC.COM;MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;LILLIAN.GARCIA@GAPAC.COM;LILLIAN.GARCIA@NFIINDUSTRIES.COM;ELIZABETH.PARDO@GAPAC.COM ;CASSANDRA.OCHOA@GAPAC.COM | Business | 96378,82629,95868 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 11:00 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96421 | WBS.2.2.13.1.5.1.3 | N | N | Planned | RNC - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S4 | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 96378,82629,95868 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 | EWM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96420 | WBS.2.2.13.1.5.2 | N | N |  | FCW ¦ Catch-Up Transactions - RNC - OTC | 0.5 | 2021-02-01 10:00 | 2021-02-01 10:30 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 10:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96419 | WBS.2.2.13.1.5.2.1 | N | N | Planned | RNC - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 0.5 | 2021-02-01 10:00 | 2021-02-01 10:30 | TOMMY NEFFENDORF | TOMMY.NEFFENDORF@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;JEREMY.RAY@GAPAC.COM | Business | 96378,82629,95868 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 10:30 | OTC - Quality | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96418 | WBS.2.2.13.1.6 | N | N |  | FCW ¦ Catch-Up Transactions - RVG | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96417 | WBS.2.2.13.1.6.1 | N | N |  | FCW ¦ Catch-Up Transactions - RVG - EWM | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96415 | WBS.2.2.13.1.6.1.2 | N | N | Planned | RVG - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Retail | 1 | 2021-02-01 10:00 | 2021-02-01 11:00 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96377 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 11:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96414 | WBS.2.2.13.1.6.1.3 | N | N | Planned | RVG - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S4 | 4 | 2021-02-01 10:00 | 2021-02-01 14:00 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96377 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 14:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96413 | WBS.2.2.13.1.6.2 | N | N |  | FCW ¦ Catch-Up Transactions - RVG - OTC | 2 | 2021-02-01 10:00 | 2021-02-01 12:00 | [8 empty] | * |  | 2021-02-01 10:00 | 2021-02-01 12:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96529 | WBS.2.2.13.1.6.2.4 | N | N | Planned | RVG - Catch Up - Validate inventory that was shipped during shutdown | 2 | 2021-02-01 10:00 | 2021-02-01 12:00 | JENNIFER NEWBERRY | JENNIFER.NEWBERRY@GAPAC.COM | JENNIFER MCLEOD;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | EWM | 96377 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 12:00 | EWM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96412 | WBS.2.2.13.1.6.2.1 | N | N | Planned | RVG - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 0.5 | 2021-02-01 10:00 | 2021-02-01 10:30 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96377 |  |  | * |  | 2021-02-01 10:00 | 2021-02-01 10:30 | OTC - Quality | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96411 | WBS.2.2.13.1.7 | N | N |  | FCW ¦ Catch-Up Transactions - BG | 13.5 | 2021-02-01 08:30 | 2021-02-01 22:00 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-02-01 22:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96410 | WBS.2.2.13.1.7.1 | N | N |  | FCW ¦ Catch-Up Transactions - BG - AC | 5 | 2021-02-01 08:30 | 2021-02-01 13:30 | [8 empty] | * |  | 2021-02-01 08:30 | 2021-02-01 13:30 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96409 | WBS.2.2.13.1.7.1.1 | N | N | Planned | BG - Catch-Up: Converting Load and maintain Work Orders - ready for work (kitted), completed or in progress | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96408 | WBS.2.2.13.1.7.1.2 | N | N | Planned | BG - Catch-Up: Converting Using Warehouse tracking report issue all parts to work orders – completed, kitted to correct locations and ties to correct Work Order | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | ROBBIE ISBELL;DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Daniel.Isbell@GAPAC.com;Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96407 | WBS.2.2.13.1.7.1.3 | N | N | Planned | BG - Catch-Up: Converting Load fix-it myself and emergency work orders completed during outage | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | DEAN PIPER | Dean.Piper@gapac.com | ROBBIE ISBELL;SAI TEAM | Daniel.Isbell@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96406 | WBS.2.2.13.1.7.1.4 | N | N | Planned | BG - Catch-Up: Converting Load any repair work order confirmations completed during the outage | 1 | 2021-02-01 09:30 | 2021-02-01 10:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96407 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 10:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96803 | WBS.2.2.13.1.7.1.8 | N | N | Planned | BG - Catch-Up: Printing Load any repair work order confirmations completed during the outage | 4 | 2021-02-01 09:30 | 2021-02-01 13:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96407 |  |  | * |  | 2021-02-01 09:30 | 2021-02-01 13:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96802 | WBS.2.2.13.1.7.1.7 | N | N | Planned | BG - Catch-Up: Printing Load fix-it myself and emergency work orders completed during outage | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96801 | WBS.2.2.13.1.7.1.6 | N | N | Planned | BG - Catch-Up: Printing Using Warehouse tracking report issue all parts to work orders – completed, kitted to correct locations and ties to correct Work Order | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96800 | WBS.2.2.13.1.7.1.5 | N | N | Planned | BG - Catch-Up: Printing Load and maintain Work Orders - ready for work (kitted), completed or in progress | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | AC | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96405 | WBS.2.2.13.1.7.2 | N | N |  | FCW ¦ Production Catch-up Transactions – BG – EWM/ICPAQS | 7 | 2021-02-01 15:00 | 2021-02-01 22:00 | [8 empty] | * |  | 2021-01-31 19:45 | 2021-02-01 22:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96799 | WBS.2.2.13.1.7.2.12 | N | N | Planned | BG - Stop Converting Lines | 0.5 | 2021-02-01 15:00 | 2021-02-01 15:30 | KELLY LEWIS | kelly.lewis@gapac.com | DAVID HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BEAU EARLS | DAVID.HARRER@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Beau.Earls@GAPAC.com | Business | 96550,96647 |  |  | * |  | 2021-02-01 15:00 | 2021-02-01 15:30 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96797 | WBS.2.2.13.1.7.2.10 | N | N | Planned | BG -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-02-01 15:45 | 2021-02-01 16:00 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO;KELLY LEWIS;JOHN WHITE | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;kelly.lewis@gapac.com;JOHN.WHITE@GAPAC.COM | ICPAQS | 97605 |  |  | * |  | 2021-02-01 15:45 | 2021-02-01 16:00 | ICPAQS | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96796 | WBS.2.2.13.1.7.2.9 | N | N | Planned | BG - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-02-01 16:00 | 2021-02-01 16:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY;DEAN PIPER;LYNN MCMURDO;KELLY LEWIS;JOHN WHITE | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;kelly.lewis@gapac.com;JOHN.WHITE@GAPAC.COM | ICPAQS | 90616,89797,97605,96797 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 16:15 | ICPAQS | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96795 | WBS.2.2.13.1.7.2.8 | N | N | Planned | BG - Validate PR Production from ICPAQ's to S4/EWM | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BEAU EARLS | Jeana.Harrer@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Beau.Earls@GAPAC.com | Business | 96797 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | BG | 2021-02-01 | 2021-01-31 | 3 | Shutdown
96794 | WBS.2.2.13.1.7.2.7 | N | N | Planned | BG - Validate PR and Vital Consumption from ICPAQ's to S4/EWM | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BEAU EARLS | JORDAN.BUNDY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Beau.Earls@GAPAC.com | Business | 96797 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:45 | EWM | BG | 2021-02-01 | 2021-01-31 | 3 | Shutdown
96793 | WBS.2.2.13.1.7.2.6 | N | N | Planned | BG - Validate Converting Staging Lane Inventory Level | 2 | 2021-02-01 17:00 | 2021-02-01 19:00 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BEAU EARLS | JORDAN.BUNDY@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Beau.Earls@GAPAC.com | Business | 96794 |  |  | * |  | 2021-01-31 20:45 | 2021-01-31 22:45 | EWM | BG | 2021-02-01 | 2021-01-31 | 3 | Shutdown
96404 | WBS.2.2.13.1.7.2.1 | N | N | Planned | BG - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S/4HANA | 4 | 2021-02-01 18:00 | 2021-02-01 22:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,82629,21147,96376,96402 |  |  | * |  | 2021-02-01 18:00 | 2021-02-01 22:00 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96402 | WBS.2.2.13.1.7.2.3 | N | N | Planned | BG - Catch-Up: Enter (load start / end) all manual emergency loads | 2 | 2021-02-01 16:00 | 2021-02-01 18:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,82629,21147,96376 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 18:00 | EWM | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96399 | WBS.2.2.13.1.7.3 | N | N |  | FCW ¦ Catch-Up Transactions - BG - OTC | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | [8 empty] | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96398 | WBS.2.2.13.1.7.3.1 | N | N | Planned | BG - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 1 | 2021-02-01 16:00 | 2021-02-01 17:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96351,96376 |  |  | * |  | 2021-02-01 16:00 | 2021-02-01 17:00 | OTC - Quality | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92375 | WBS.2.2.13.1.8 | N | N |  | FCW ¦ E80 & iCPAQS Prep Activities | 39.75 | 2021-01-31 01:30 | 2021-02-01 17:15 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-02-01 17:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92376 | WBS.2.2.13.1.8.1 | N | N |  | FCW ¦ E80 & iCPAQS Prep Activities | 39.75 | 2021-01-31 01:30 | 2021-02-01 17:15 | [8 empty] | * |  | 2021-01-31 01:30 | 2021-02-01 17:15 |  |  | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91823 | WBS.2.2.13.1.8.1.1 | N | N | Planned | SCM validate Production orders from ICPAQ's | 1 | 2021-02-01 08:30 | 2021-02-01 09:30 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | MELISSA OLSEN;CHIRAG PARIKH;RAGHAVA GARRE;SCM TEAM;SAI TEAM;ANUPAM SHRIVASTAVA;PMO TEAM;BRAD WYMAN | MELISSA.OLSEN@GAPAC.COM;CPARIKH@DELOITTE.COM;RAGHAVA.GARRE@KOCHTC.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM | SCM | 82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 09:30 | SCM | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97600 | WBS.2.2.13.1.8.1.172 | N | N | Planned | MC TASK - Create MTH Paper Machine Data (1 day) | 0.25 | 2021-01-31 01:30 | 2021-01-31 01:45 | JACK MANFREDI | JACK.MANFREDI@GAPAC.COM | ALISON SMITH;MELISSA OLSEN;SAI TEAM;DORESA WARD;MINT VICKERY;SUSAN RIELS;TODD DAKINS | ALISON.SMITH@GAPAC.COM;MELISSA.OLSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DVWARD@GAPAC.COM;MINT.VICKERY@GAPAC.COM;SUSAN.RIELS@GAPAC.COM;TODD.DAKINS@GAPAC.COM | Business | 97590 |  |  | * |  | 2021-01-31 01:30 | 2021-01-31 01:45 | ICPAQS OPERATIONS | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97602 | WBS.2.2.13.1.8.1.174 | N | N | Planned | MTH - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97603 | WBS.2.2.13.1.8.1.175 | N | N | Planned | MTH -Validation - Transactions are being successfully sent to EWM / S4 | 0.25 | 2021-01-31 20:00 | 2021-01-31 20:15 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97602 |  |  | * |  | 2021-01-31 20:00 | 2021-01-31 20:15 | ICPAQS | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97604 | WBS.2.2.13.1.8.1.176 | N | N | Planned | MTH - Validation - EWM / S4 Transactions are being processed by ICPAQS | 0.25 | 2021-01-31 20:15 | 2021-01-31 20:30 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 97603 |  |  | * |  | 2021-01-31 20:15 | 2021-01-31 20:30 | ICPAQS | MTH | 2021-01-31 | 2021-01-31 | 3 | Shutdown
97606 | WBS.2.2.13.1.8.1.178 | N | N | Planned | Update workflows from sleep and put logic monitor or server or services from downtime to uptime (All sites (D1-D4) | 0.5 | 2021-02-01 16:45 | 2021-02-01 17:15 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 96954,97604,96956,96952,96950,96948,96946,96796,94913 |  |  | * |  | 2021-02-01 16:45 | 2021-02-01 17:15 | ICPAQS | CROSS | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97605 | WBS.2.2.13.1.8.1.177 | N | N | Planned | BG - Action - Turn on Transaction Service | 0.25 | 2021-02-01 15:30 | 2021-02-01 15:45 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616,96616,96799 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 15:45 | ICPAQS | BG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
90616 | WBS.2.2.13.1.8.1.2 | N | N | Planned | Check Gate - Prep for turning on Transaction Services | 0.25 | 2021-01-31 19:30 | 2021-01-31 19:45 | DORESA WARD | DVWARD@GAPAC.COM | TODD DAKINS;SAI TEAM;MINT VICKERY | TODD.DAKINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM | ICPAQS | 36505,94797,96904,96878,96877,97475 |  |  | * |  | 2021-01-31 19:30 | 2021-01-31 19:45 | ICPAQS | CROSS | 2021-01-31 | 2021-01-31 | 3 | Shutdown
90617 | WBS.2.2.13.1.8.1.3 | N | N | Planned | GP Validates middleware channel connection to E80 Live Server during EWM + ICPAQs downtime | 1 | 2021-01-31 06:30 | 2021-01-31 07:30 | RAMYA IYER | RAMYIYER@DELOITTE.COM | ANKIT SONI;SAI TEAM;EWM TEAM;HEMACHANDAN AS;PAYEL GHOSH;RADHIKA RASTOGI;SANDEEP THARWANI;SUVENDU KUMAR;DEV TEAM | ANKISONI@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;HEMACAS@DELOITTE.COM;PAYGHOSH@DELOITTE.COM;RADHRASTOGI@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 90478 |  |  | * |  | 2021-01-31 06:30 | 2021-01-31 07:30 | DEV | ALL | 2021-01-31 | 2021-01-31 | 3 | Shutdown
95592 | WBS.2.2.13.1.8.1.4 | N | N | Planned | PLT - Action - Turn on Transaction Service | 0.25 | 2021-01-31 19:45 | 2021-01-31 20:00 | DORESA WARD | DVWARD@GAPAC.COM | SAI TEAM;MINT VICKERY;TODD DAKINS | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MINT.VICKERY@GAPAC.COM;TODD.DAKINS@GAPAC.COM | ICPAQS | 90616,96967 |  |  | * |  | 2021-01-31 19:45 | 2021-01-31 20:00 | ICPAQS | PLT | 2021-01-31 | 2021-01-31 | 3 | Shutdown
92378 | WBS.2.2.13.1.9 | N | N |  | FCW ¦ Catch-Up Transactions - ATL | 5.51 | 2021-02-01 04:30 | 2021-02-01 10:01 | [8 empty] | * |  | 2021-02-01 04:30 | 2021-02-01 10:01 |  | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92910 | WBS.2.2.13.1.9.1 | N | N |  | FCW ¦ Catch-Up Transactions - ATL - OTC | 5.51 | 2021-02-01 04:30 | 2021-02-01 10:01 | [8 empty] | * |  | 2021-02-01 04:30 | 2021-02-01 10:01 |  | ALL | 2021-02-01 | 2021-02-01 | 3 | Shutdown
97136 | WBS.2.2.13.1.9.1.11 | N | N | Planned | ATL - FCW - Clear Order Blocks on DN/SD Converted Orders in S/4HANA – REX - PRO | 1 | 2021-02-01 04:30 | 2021-02-01 05:30 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 96673 |  |  | * |  | 2021-02-01 04:30 | 2021-02-01 05:30 | OTC - OM | REX | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95389 | WBS.2.2.13.1.9.1.3 | N | N | Planned | ATL - FCW - Clear Order Blocks on DN/SD Converted Orders in S/4HANA – SCH - RETAIL/PRO | 1 | 2021-02-01 09:01 | 2021-02-01 10:01 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 93401,92999,95197 |  |  | * |  | 2021-02-01 09:01 | 2021-02-01 10:01 | OTC - OM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96924 | WBS.2.2.13.1.9.1.29 | N | N | Planned | ATL - FCW - Clear Order Blocks on DN/SD Converted Orders in S/4HANA – Rivergate - RETAIL | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 93401,96718 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | OTC - OM | RVG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
96923 | WBS.2.2.13.1.9.1.28 | N | N | Planned | ATL - FCW - Clear Order Blocks on DN/SD Converted Orders in S/4HANA – Rancho - RETAIL/PRO | 1 | 2021-02-01 09:00 | 2021-02-01 10:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 93401,96716 |  |  | * |  | 2021-02-01 09:00 | 2021-02-01 10:00 | OTC - OM | RNC | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94684 | WBS.2.2.13.1.10 | N | N |  | FCW ¦ Catch-Up Transactions - PTH | 16 | 2021-02-01 08:30 | 2021-02-02 00:30 | [8 empty] | * |  | 2021-02-01 08:30 | 2021-02-02 00:30 |  | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
95237 | WBS.2.2.13.1.10.1 | N | N |  | FCW ¦ Catch-Up Transactions - PTH - AC | 16 | 2021-02-01 08:30 | 2021-02-02 00:30 | [8 empty] | * |  | 2021-02-01 08:30 | 2021-02-02 00:30 |  | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
92931 | WBS.2.2.13.1.10.1.1 | N | N | Planned | PTH - Catch-Up: Load and maintain Work Orders - ready for work (kitted), completed or in progress | 16 | 2021-02-01 08:30 | 2021-02-02 00:30 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 82629,82553 |  |  | * |  | 2021-02-01 08:30 | 2021-02-02 00:30 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
92930 | WBS.2.2.13.1.10.1.2 | N | N | Planned | PTH - Catch-Up: Using Warehouse tracking report issue all parts to work orders – completed, kitted to correct locations and ties to correct Work Order | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | AC | 82629,82553 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92929 | WBS.2.2.13.1.10.1.3 | N | N | Planned | PTH - Catch-Up: Load fix-it myself and emergency work orders completed during outage | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 82629,82553 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
92928 | WBS.2.2.13.1.10.1.4 | N | N | Planned | PTH - Catch-Up: Load any repair work order confirmations completed during the outage | 4 | 2021-02-01 08:30 | 2021-02-01 12:30 | RANDALL KNAPP | Randall.Knapp@gapac.com | DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | AC | 82629,82553 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 12:30 | AC | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94678 | WBS.2.2.13.1.10.2 | N | N |  | FCW ¦ Catch-Up Transactions - PTH - EWM | 4 | 2021-02-01 20:00 | 2021-02-02 | [8 empty] | * |  | 2021-02-01 20:00 | 2021-02-02 |  | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93352 | WBS.2.2.13.1.10.2.1 | N | N | Planned | PTH - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S/4HANA | 4 | 2021-02-01 20:00 | 2021-02-02 | ANDY JONES | Gibson.Jones@gapac.com | JAMES COWELL;DARRYL JOHNSON;HADYN HUGHES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | James.Cowell@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;CHRISTOPHER.HUGHES@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 93307,82553,82629,21147,95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-02 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93347 | WBS.2.2.13.1.10.2.2 | N | N | Planned | PTH - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Pro | 4 | 2021-02-01 20:00 | 2021-02-02 | ANDY JONES | Gibson.Jones@gapac.com | JANET QUEBEDEAUX;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | janet.quebedeaux@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 82553,82629,95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-02 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
93346 | WBS.2.2.13.1.10.2.3 | N | N | Planned | PTH - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Retail | 4 | 2021-02-01 20:00 | 2021-02-02 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | marshal.savage@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82553,82629,95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-02 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Shutdown
94696 | WBS.2.2.13.1.10.3 | N | N |  | FCW ¦ Catch-Up Transactions - PTH - OTC | 2 | 2021-02-01 20:00 | 2021-02-01 22:00 | [8 empty] | * |  | 2021-02-01 20:00 | 2021-02-01 22:00 |  | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94420 | WBS.2.2.13.1.10.3.1 | N | N | Planned | PTH - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 2 | 2021-02-01 20:00 | 2021-02-01 22:00 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;HAYDN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 93324,95155 |  |  | * |  | 2021-02-01 20:00 | 2021-02-01 22:00 | OTC - Quality | PTH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94686 | WBS.2.2.13.1.12 | N | N |  | FCW ¦ Catch-Up Transactions - HBG | 11 | 2021-02-01 08:30 | 2021-02-01 19:30 | [8 empty] | * |  | 2021-02-01 08:30 | 2021-02-01 19:30 |  | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
95235 | WBS.2.2.13.1.12.1 | N | N |  | FCW ¦ Catch-Up Transactions - HBG - AC | 3 | 2021-02-01 08:30 | 2021-02-01 11:30 | [8 empty] | * |  | 2021-02-01 08:30 | 2021-02-01 11:30 |  | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93926 | WBS.2.2.13.1.12.1.1 | N | N | Planned | HBG - Catch-Up : Load and maintain all work order types that were completed during outage. | 3 | 2021-02-01 08:30 | 2021-02-01 11:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 82553,82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 11:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93925 | WBS.2.2.13.1.12.1.2 | N | N | Planned | HBG - Catch-Up: Using Warehouse tracking report issue all parts to work orders – completed, kitted to correct locations and ties to correct Work Order | 2 | 2021-02-01 08:30 | 2021-02-01 10:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GREGORY.GIBBS@GAPAC.com | AC | 82553,82629 |  |  | * |  | 2021-02-01 08:30 | 2021-02-01 10:30 | AC | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94680 | WBS.2.2.13.1.12.2 | N | N |  | FCW ¦ Catch-Up Transactions - HBG - EWM | 4 | 2021-02-01 15:30 | 2021-02-01 19:30 | [8 empty] | * |  | 2021-02-01 15:30 | 2021-02-01 19:30 |  | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93941 | WBS.2.2.13.1.12.2.1 | N | N | Planned | HBG - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S/4HANA | 4 | 2021-02-01 15:30 | 2021-02-01 19:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93873,82553,82629,21147,95152 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 19:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93937 | WBS.2.2.13.1.12.2.2 | N | N | Planned | HBG - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Pro | 4 | 2021-02-01 15:30 | 2021-02-01 19:30 | RAYMOND BOND | RAYMOND.BOND@GAPAC.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 82629,95152 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 19:30 | EWM | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
91733 | WBS.2.2.13.1.12.3 | N | N |  | FCW ¦ Catch-Up Transactions - HBG - OTC | 0.5 | 2021-02-01 15:30 | 2021-02-01 16:00 | [8 empty] | * |  | 2021-02-01 15:30 | 2021-02-01 16:00 |  | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94405 | WBS.2.2.13.1.12.3.1 | N | N | Planned | HBG - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 0.5 | 2021-02-01 15:30 | 2021-02-01 16:00 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 94404,95152 |  |  | * |  | 2021-02-01 15:30 | 2021-02-01 16:00 | OTC - Quality | HBG | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94688 | WBS.2.2.13.1.13 | N | N |  | FCW ¦ Catch-Up Transactions - SCH | 4 | 2021-02-01 10:01 | 2021-02-01 14:01 | [8 empty] | * |  | 2021-02-01 10:01 | 2021-02-01 14:01 |  | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94682 | WBS.2.2.13.1.13.1 | N | N |  | FCW ¦ Catch-Up Transactions - SCH - EWM | 4 | 2021-02-01 10:01 | 2021-02-01 14:01 | [8 empty] | * |  | 2021-02-01 10:01 | 2021-02-01 14:01 |  | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93049 | WBS.2.2.13.1.13.1.2 | N | N | Planned | SCH - Catch-Up: Enter (load start / end) all manual emergency loads for non D1 sites - Retail | 1 | 2021-02-01 10:01 | 2021-02-01 11:01 | JORDAN ALLEN | Jordan.Allen@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CARLA PERKINS | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Carla.Perkins@gapac.com | Business | 5833,82629,93035 |  |  | * |  | 2021-02-01 10:01 | 2021-02-01 11:01 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93048 | WBS.2.2.13.1.13.1.3 | N | N | Planned | SCH - Catch-Up: Ensure Manual or Emergency QHOLDs, Inventory Moves / Changes, Trailer Moves, etc. are updated in EWM / S4 | 4 | 2021-02-01 10:01 | 2021-02-01 14:01 | CARLA PERKINS | Carla.Perkins@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;DANIELLE MULLIGAN;SHELLEY GRAHAM;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Danielle.Mulligan@gapac.com;Shelley.Graham@gapac.com;Tristan.Clark@nfiindustries.com | Business | 5833,82629,93035 |  |  | * |  | 2021-02-01 10:01 | 2021-02-01 14:01 | EWM | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
94693 | WBS.2.2.13.1.13.2 | N | N |  | FCW ¦ Catch-Up Transactions - SCH - OTC | 0.5 | 2021-02-01 10:01 | 2021-02-01 10:31 | [8 empty] | * |  | 2021-02-01 10:01 | 2021-02-01 10:31 |  | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
93047 | WBS.2.2.13.1.13.2.1 | N | N | Planned | SCH - Catch Up - Place finished goods on Q-hold that happened in blackout in restricted inventory in S/4 | 0.5 | 2021-02-01 10:01 | 2021-02-01 10:31 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN;DANIELLE MULLIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com;Danielle.Mulligan@gapac.com | Business | 5833,82629,93035 |  |  | * |  | 2021-02-01 10:01 | 2021-02-01 10:31 | OTC - Quality | SCH | 2021-02-01 | 2021-02-01 | 3 | Shutdown
5853 | WBS.2.3 | N | N |  | Ramp-Up ¦ Phase | 48.25 | 2021-02-02 08:15 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-05 08:30 |  | CROSS | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
91061 | WBS.2.3.2 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities | 4 | 2021-02-02 08:15 | 2021-02-02 12:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 12:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91535 | WBS.2.3.2.1 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities | 4 | 2021-02-02 08:15 | 2021-02-02 12:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 12:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91081 | WBS.2.3.2.1.1 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups | 4 | 2021-02-02 08:15 | 2021-02-02 12:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 12:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91083 | WBS.2.3.2.1.1.1 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - S/4HANA | 4 | 2021-02-02 08:15 | 2021-02-02 12:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 12:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91063 | WBS.2.3.2.1.1.1.1 | N | N | Planned | Backup S/4HANA System - Kick-Off Business Activities | 4 | 2021-02-02 08:15 | 2021-02-02 12:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 12:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91082 | WBS.2.3.2.1.1.2 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP BW | 1.5 | 2021-02-02 08:15 | 2021-02-02 09:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91062 | WBS.2.3.2.1.1.2.1 | N | N | Planned | Backup SAP BW System - Kick-Off Business Activities | 1.5 | 2021-02-02 08:15 | 2021-02-02 09:45 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:45 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91087 | WBS.2.3.2.1.1.3 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP CRM | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91067 | WBS.2.3.2.1.1.3.1 | N | N | Planned | Backup SAP CRM System - Kick-Off Business Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91088 | WBS.2.3.2.1.1.4 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP GRC | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91068 | WBS.2.3.2.1.1.4.1 | N | N | Planned | Backup SAP GRC System - Kick-Off Business Activities | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91086 | WBS.2.3.2.1.1.5 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP GW | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91066 | WBS.2.3.2.1.1.5.1 | N | N | Planned | Backup SAP GW System - Kick-Off Business Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;LOKESH KAMANA;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;LKAMANA@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91084 | WBS.2.3.2.1.1.6 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP MDG | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91064 | WBS.2.3.2.1.1.6.1 | N | N | Planned | Backup SAP MDG System - Kick-Off Business Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91085 | WBS.2.3.2.1.1.7 | N | N |  | Ramp Up ¦ Tech Activities – Kick-Off Business Activities – System Back-Ups - SAP PO | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91065 | WBS.2.3.2.1.1.7.1 | N | N | Planned | Backup SAP PO System - Kick-Off Business Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;NAVJOT SHARMA;DANI SIMMONS;SUVENDU KUMAR;PRASHANTH TUMMALA;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NASHARMA@DELOITTE.COM;DWSIMMON@GAPAC.COM;SUVKUMAR@DELOITTE.COM;PTUMMALA@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | DEV - INFRA | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
9871 | WBS.2.3.3 | N | N |  | Ramp-Up ¦ LSA Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
80969 | WBS.2.3.3.1 | N | N |  | Ramp-Up ¦ LSA Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90230 | WBS.2.3.3.1.1 | N | N |  | Ramp-Up ¦ LSA Tasks | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91762 | WBS.2.3.3.1.1.1 | N | N |  | Ramp-Up ¦ LSA Tasks | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
29808 | WBS.2.3.3.1.1.1.1 | N | N | Planned | Stop ECC to CPV or Fully Allocated cube/ CPV or Fully allocated cube to ECC interfaces for go-live sites | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | IMRAN NAZAKAT | IMRAN.NAZAKAT@GAPAC.COM | SAI TEAM;MAMIE TREZVANT;KELLY JANSSEN;LSA TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATREZVA@GAPAC.COM;MICHAEL.JANSSEN@GAPAC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM | LSA | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | LSA | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97421 | WBS.2.3.3.1.1.1.117 | N | N | Planned | ARBCIG - Create PTP batch job for Ariba invoice status and Ariba master data to Ariba | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | NNEKA MBA | NEMBA@GAPAC.COM | YUDHAJIT MITRA;ERIC BARSTOW;PTP TEAM;PAM NIX;MASON DRAKE;SAI TEAM;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | YMITRA@DELOITTE.COM;ERIC.BARSTOW@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;PSNIX@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | BATCH | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
81220 | WBS.2.3.4 | N | N |  | Ramp-Up ¦ Security Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90130 | WBS.2.3.4.1 | N | N |  | Ramp-Up ¦ Security Activities | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90231 | WBS.2.3.4.1.1 | N | N |  | Ramp-Up ¦ Security Tasks | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91773 | WBS.2.3.4.1.1.1 | N | N |  | Ramp-Up ¦ Security Tasks | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
7873 | WBS.2.3.4.1.1.1.1 | N | N | Planned | Remove Cutover Access to ABAP systems | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | PALLAVI YELLAYI | PYELLAYI@DELOITTE.COM | GREG CAPPS;SAI TEAM;SOUMYA PANDA;CARLOS ROBELO TEJADA;ANTHONY GORDON;SEC TEAM | GREG.CAPPS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SOPANDA@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;ADGORDON@GAPAC.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 5833,4430,82339,36654,36505,95152,95155 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | SECURITY | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
82282 | WBS.2.3.4.1.1.1.2 | N | N | Planned | Remove IBP Cutover Access | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | MOHAMMED ABDULLAHI | MABDULLAHI@DELOITTE.COM | SAI TEAM;SOUMYA PANDA;SEC TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SOPANDA@DELOITTE.COM;MABDULLAHI@DELOITTE.COM;GREG.CAPPS@GAPAC.COM;SOPANDA@DELOITTE.COM;PYELLAYI@DELOITTE.COM;KGANNAVARAPU@DELOITTE.COM;CROBELOTEJADA@DELOITTE.COM;VASAVA@DELOITTE.COM;mkim@deloitte.com | SECURITY | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | SECURITY | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89809 | WBS.2.3.5 | N | N |  | Ramp-Up ¦ Multi-Team Plan Activities | 33.25 | 2021-02-02 08:15 | 2021-02-04 09:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-04 09:30 |  |  | 2021-02-04 | 2021-02-04 | 3 | Ramp Up
5854 | WBS.2.3.5.1 | N | N |  | Ramp-Up ¦ SCM Activities | 0.5 | 2021-02-02 08:15 | 2021-02-02 08:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89818 | WBS.2.3.5.1.1 | N | N |  | Ramp-Up ¦ SCM Outage Transaction Processing | 0.5 | 2021-02-02 08:15 | 2021-02-02 08:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91774 | WBS.2.3.5.1.1.1 | N | N |  | Ramp-Up ¦ SCM Outage Transaction Processing | 0.5 | 2021-02-02 08:15 | 2021-02-02 08:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 08:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
5858 | WBS.2.3.5.1.1.1.1 | N | N | Planned | Validate PP related back ground Jobs for all the PP objects -PE | 0.5 | 2021-02-02 08:15 | 2021-02-02 08:45 | SATISH KUMAR B | BSATISHKUMAR@DELOITTE.COM | JENNIFER LI;SAI TEAM;SCM TEAM;BRAD WYMAN;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 8860,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:45 | SCM | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92687 | WBS.2.3.5.2 | N | N |  | Ramp-Up ¦ PTP Activities | 33 | 2021-02-02 08:30 | 2021-02-04 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-04 09:30 |  |  | 2021-02-04 | 2021-02-04 | 3 | Ramp Up
92689 | WBS.2.3.5.2.1 | N | N |  | Ramp-Up ¦ PTP Tasks | 33 | 2021-02-02 08:30 | 2021-02-04 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-04 09:30 |  |  | 2021-02-04 | 2021-02-04 | 3 | Ramp Up
92688 | WBS.2.3.5.2.1.1 | N | N |  | Ramp-Up ¦ PTP Tasks | 33 | 2021-02-02 08:30 | 2021-02-04 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-04 09:30 |  |  | 2021-02-04 | 2021-02-04 | 3 | Ramp Up
94294 | WBS.2.3.5.2.1.1.11 | N | N | Planned | Validate converted POs/GRs between EIM and S/4 and log incident for any missing POs/GRs | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | CHARLES BLUMREICH | CHARLES.BLUMREICH@GAPAC.COM | ERIC BARSTOW;SAI TEAM;PTP TEAM | ERIC.BARSTOW@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 90464,95493,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95495 | WBS.2.3.5.2.1.1.12 | N | N | Planned | Identify PO/GR failures in Middleware due to missing UOM mapping and create incident | 1 | 2021-02-02 09:30 | 2021-02-02 10:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | MIKE PUPILLO;CASEY HERMANSEN;SAI TEAM;YUDHAJIT MITRA;DOROTHY RUSSELL;MASON DRAKE;JOHN CASABURRI;MONICA CUEVAS;SANDEEP A | MAPUPILL@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;YMITRA@DELOITTE.COM;DOROTHY.RUSSELL@GAPAC.COM;MASON.DRAKE@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM | PTP | 94294,21148 |  |  | * |  | 2021-02-02 09:30 | 2021-02-02 10:30 | PTP | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92638 | WBS.2.3.5.2.1.1.14 | N | N | Planned | Run report of invoices in S4 Ariba realm that are in awaiting reconcillation status and compare with baseline report | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | BETH MYERS | BETH.MYERS@GAPAC.COM | PAM NIX;SAI TEAM;PTP TEAM | PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 9337,9698,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | EIM | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94738 | WBS.2.3.5.2.1.1.1 | N | N | Planned | Resend GR output to Ariba for all deployed POs | 32 | 2021-02-02 09:30 | 2021-02-04 09:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | PTP TEAM;MONICA CUEVAS;YUDHAJIT MITRA;SAI TEAM;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 36654,92638,21148 |  |  | * |  | 2021-02-02 09:30 | 2021-02-04 09:30 | PTP | ALL | 2021-02-04 | 2021-02-04 | 3 | Ramp Up
97382 | WBS.2.3.5.2.1.1.4 | N | N | Planned | ARBCIG - Validate new CIG batch jobs are setup | 0.25 | 2021-02-02 08:45 | 2021-02-02 09:00 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | CASEY HERMANSEN;YUDHAJIT MITRA;PTP TEAM;SAI TEAM;MONICA CUEVAS;SANDEEP A;PARUL CHOUDHARY | CASEY.HERMANSEN@GAPAC.COM;YMITRA@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;SANDEEP.A@KOCHGS.COM;parchoudhary@deloitte.com | PTP | 97421,21148 |  |  | * |  | 2021-02-02 08:45 | 2021-02-02 09:00 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95205 | WBS.2.3.5.2.1.1.2 | N | N | Planned | Confirm current legacy data (AS8 and ECC) is available in Slow Moving Inventory Dashboard | 1 | 2021-02-02 10:30 | 2021-02-02 11:30 | CASEY HERMANSEN | CASEY.HERMANSEN@GAPAC.COM | SAI TEAM;PTP TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 36654,94981 |  |  | * |  | 2021-02-02 10:30 | 2021-02-02 11:30 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95206 | WBS.2.3.5.2.1.1.3 | N | N | Planned | Set the Delivery Complete flag on converted ECC POs in ECC legacy system | 4 | 2021-02-02 08:30 | 2021-02-02 12:30 | ERIC BARSTOW | ERIC.BARSTOW@GAPAC.COM | PTP TEAM;MONICA CUEVAS;SAI TEAM;SANDEEP A | CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;MONICA.CUEVAS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SANDEEP.A@KOCHGS.COM | PTP | 36654,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 12:30 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97741 | WBS.2.3.5.2.1.1.28 | N | N | Planned | Identify source lists to be created for AS8 | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | DOROTHY RUSSELL | DOROTHY.RUSSELL@GAPAC.COM | BRUCE KIRKLEWSKI;PTP TEAM;SAI TEAM | BRUCE.KIRKLEWSKI@GAPAC.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | PTP | 36654,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | PTP | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95103 | WBS.2.3.5.3 | N | N |  | Ramp-Up ¦ CTM Activities | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95102 | WBS.2.3.5.3.1 | N | N |  | Ramp-Up ¦ CTM Activities | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95101 | WBS.2.3.5.3.1.1 | N | N |  | Ramp-Up ¦ CTM Activities | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95209 | WBS.2.3.5.3.1.1.5 | N | N | Planned | Move CTM Validity area Transport | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | US GP BASIS | USGPBASIS@DELOITTE.COM | SAI TEAM;CTM TEAM;DEV TEAM | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKWALL@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com; | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | DEV - INFRA | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89810 | WBS.2.3.5.4 | N | N |  | Ramp-Up ¦ RTR Activities | 22.25 | 2021-02-02 08:15 | 2021-02-03 14:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-03 14:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
90153 | WBS.2.3.5.4.1 | N | N |  | Ramp-Up ¦ RTR Tasks | 22.25 | 2021-02-02 08:15 | 2021-02-03 14:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-03 14:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
91775 | WBS.2.3.5.4.1.1 | N | N |  | Ramp-Up ¦ RTR Tasks | 14.25 | 2021-02-02 08:15 | 2021-02-03 06:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-03 06:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92302 | WBS.2.3.5.4.1.1.1 | N | N | Planned | Prepare Load File for Activity Rates (costing/tieout) for Product Costing | 1.5 | 2021-02-02 08:30 | 2021-02-02 10:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92291,36654 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:00 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92303 | WBS.2.3.5.4.1.1.6 | N | N | Planned | RTR_E0114 - Load Activity rates (costing/tieout) for all the Production/Work order cost centers only for go-live plants | 2 | 2021-02-02 10:00 | 2021-02-02 12:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92302 |  |  | * |  | 2021-02-02 10:00 | 2021-02-02 12:00 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92304 | WBS.2.3.5.4.1.1.7 | N | N | Planned | RTR_E0114 - Validate Load Activity rates (costing/tieout) | 1 | 2021-02-02 12:00 | 2021-02-02 13:00 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92303 |  |  | * |  | 2021-02-02 12:00 | 2021-02-02 13:00 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96916 | WBS.2.3.5.4.1.1.24 | N | N | Planned | Turn on batch jobs for mark, release and MF30 (costs rolls) | 0.25 | 2021-02-02 13:00 | 2021-02-02 13:15 | NNEKA MBA | NEMBA@GAPAC.COM | SAI TEAM;KELLY HINSON;SUNIL KORI;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;KSHINSON@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 95648,92304 |  |  | * |  | 2021-02-02 13:00 | 2021-02-02 13:15 | BATCH | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97712 | WBS.2.3.5.4.1.1.29 | N | N | Planned | ECC legacy batch job variants update after FCW | 1 | 2021-02-02 13:15 | 2021-02-02 14:15 | WENTAO TANG | WTANG@GAPAC.COM | AGNES DEBO;RICARDO OLIVEIRA;RANJAI JOHN;RTR TEAM;SAI TEAM | ADEBO@GAPAC.COM;RICARDO.OLIVEIRA@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 96916 |  |  | * |  | 2021-02-02 13:15 | 2021-02-02 14:15 | RTR-GL | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96427 | WBS.2.3.5.4.1.1.12 | N | N | Planned | BG - Prepare Prior Year spending balance load for Capital projects | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | Ryan Gietman | ryan.gietman@gapac.com | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | RTR - PS | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97659 | WBS.2.3.5.4.1.1.28 | N | N | Planned | BG- - Balance Sheet OIM reconciliation - Cutover (Mass JE process) After Cut over Puts the detail of in-transit or other OIM | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96426 | WBS.2.3.5.4.1.1.13 | N | N | Planned | BG - Prepare Current Year spending balance load for Capital and Capex projects | 2 | 2021-02-02 10:30 | 2021-02-02 12:30 | Ryan Gietman | ryan.gietman@gapac.com | Amanda Smith;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Amanda.Smith@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96427 |  |  | * |  | 2021-02-02 10:30 | 2021-02-02 12:30 | RTR - PS | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93372 | WBS.2.3.5.4.1.1.14 | N | N | Planned | PTH - Prepare Prior Year spending balance load for Capital, Turnaround and Annual Outage projects | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | DANIELLE RAMSEY | DANIELLE.RAMSEY@GAPAC.COM | Ryan Gietman;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ryan.gietman@gapac.com;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | RTR - PS | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93371 | WBS.2.3.5.4.1.1.15 | N | N | Planned | PTH - Prepare Current Year spending balance load for Capital, Turnaround, Annual Outage and Capex projects | 2 | 2021-02-02 10:30 | 2021-02-02 12:30 | DANIELLE RAMSEY | DANIELLE.RAMSEY@GAPAC.COM | Ryan Gietman;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ryan.gietman@gapac.com;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93372 |  |  | * |  | 2021-02-02 10:30 | 2021-02-02 12:30 | RTR - PS | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94758 | WBS.2.3.5.4.1.1.16 | N | N | Planned | Verify that settlement rules for all Capex Projects included in balance loads are updated per tasks 92136 and 92137 | 2 | 2021-02-02 12:30 | 2021-02-02 14:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DON ABBOTT;SAI TEAM;RTR TEAM;RANJAI JOHN;JOSHUA PENA | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;JOSHUA.PENA@GAPAC.COM | RTR | 93371,93965,96426 |  |  | * |  | 2021-02-02 12:30 | 2021-02-02 14:30 | RTR - PS | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
81801 | WBS.2.3.5.4.1.1.17 | N | N | Planned | Upload CY and PY spending for Capital, Turnaround, Annual Outage & Capex (CY only) projects. Settle projects, Validate | 5 | 2021-02-02 14:30 | 2021-02-02 19:30 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | DON ABBOTT;SAI TEAM;RTR TEAM;BRETT DETTMERING | DON.ABBOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 94758 |  |  | * |  | 2021-02-02 14:30 | 2021-02-02 19:30 | RTR - PS | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92290 | WBS.2.3.5.4.1.1.18 | N | N | Planned | Add LSMW For Misc. Prod Versions - Ramp up | 2 | 2021-02-02 20:30 | 2021-02-03 06:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | SAI TEAM;SANDRA RICHARDS;DONNA SMITH;VISHNU CHIRALA;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;VICHIRALA@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36654,8801 |  |  | * |  | 2021-02-02 20:30 | 2021-02-03 06:30 | RTR - PC | ALL | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92648 | WBS.2.3.5.4.1.1.19 | N | N | Planned | Reset the Status of WBS Elements from REL to TECO status that were changed for PO Conversion | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;SAI TEAM;RTR TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 36654,82652,82659,82661 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | RTR - PS | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93966 | WBS.2.3.5.4.1.1.20 | N | N | Planned | HBG - Prepare Prior Year spending balance load for Capital, Turnaround and Annual Outage projects | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | DANIELLE RAMSEY | DANIELLE.RAMSEY@GAPAC.COM | Kami Taylor;CHRIS ZUMWALT;SAI TEAM | kami.taylor@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | RTR - PS | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95194 | WBS.2.3.5.4.1.1.21 | N | N | Planned | Communicate to EcoSys timing related to balance upload for projects (Prod Cutover only) | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | BRENDA STAGGS | BRENDA.STAGGS@GAPAC.COM | SANDRA RICHARDS;DONNA SMITH;RTR TEAM;SAI TEAM;BRETT DETTMERING | SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;BRETT.DETTMERING@GAPAC.COM | RTR | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | RTR - PS | CROSS | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93965 | WBS.2.3.5.4.1.1.22 | N | N | Planned | HBG - Prepare Current Year spending balance load for Capital, Turnaround, Annual Outage and Capex projects | 2 | 2021-02-02 10:30 | 2021-02-02 12:30 | DANIELLE RAMSEY | DANIELLE.RAMSEY@GAPAC.COM | Kami Taylor;CHRIS ZUMWALT;SAI TEAM | kami.taylor@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 93966 |  |  | * |  | 2021-02-02 10:30 | 2021-02-02 12:30 | RTR - PS | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92299 | WBS.2.3.5.4.1.2 | N | N |  | Ramp Up ¦ RTR_E0113 - Maintenance of Planned Price Versions | 4.75 | 2021-02-02 08:30 | 2021-02-02 13:15 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 13:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92292 | WBS.2.3.5.4.1.2.1 | N | N | Planned | Preparation of load file for Planned prices | 4 | 2021-02-02 08:30 | 2021-02-02 12:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92291,36654 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 12:30 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92293 | WBS.2.3.5.4.1.2.2 | N | N | Planned | RTR_E0113 - Upload planned prices run program - Maintenance of planned price versions for std price, prior year average price, and forward looking price | 0.25 | 2021-02-02 12:30 | 2021-02-02 12:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92292 |  |  | * |  | 2021-02-02 12:30 | 2021-02-02 12:45 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92294 | WBS.2.3.5.4.1.2.3 | N | N | Planned | RTR_E0113 - Validate Load - for planned price versions - Maintenance of planned price versions for std price, prior year average price, and forward looking price | 0.5 | 2021-02-02 12:45 | 2021-02-02 13:15 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92293 |  |  | * |  | 2021-02-02 12:45 | 2021-02-02 13:15 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92300 | WBS.2.3.5.4.1.3 | N | N |  | Ramp Up ¦ RTR_E0276 - Automatic Update To Mixed Ratio Periodically By Production Version Based On Production Volume - Mill | 8 | 2021-02-03 06:30 | 2021-02-03 14:30 | [8 empty] | * |  | 2021-02-03 06:30 | 2021-02-03 14:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92295 | WBS.2.3.5.4.1.3.1 | N | N | Planned | RTR_E0276 - Provide load file - MFLE plants 1034, 1376, 1459 proc alternatives of GP01 and GPTO | 4 | 2021-02-03 06:30 | 2021-02-03 10:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92290 |  |  | * |  | 2021-02-03 06:30 | 2021-02-03 10:30 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92296 | WBS.2.3.5.4.1.3.2 | N | N | Planned | RTR_E0276 - Provide load file - mixed ratios of GP01 and GPTO - MFLE Plants 1034, 1376, 1459 | 2 | 2021-02-03 11:30 | 2021-02-03 13:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92291,92352 |  |  | * |  | 2021-02-03 11:30 | 2021-02-03 13:30 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92297 | WBS.2.3.5.4.1.3.3 | N | N | Planned | RTR_E0276 - Load mix ratio for GP01 & GPTO in MFLE Plants 1034, 1376, 1459 | 0.5 | 2021-02-03 13:30 | 2021-02-03 14:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92296 |  |  | * |  | 2021-02-03 13:30 | 2021-02-03 14:00 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92298 | WBS.2.3.5.4.1.3.4 | N | N | Planned | RTR_E0276 - Validate mixed costing for GP01 & GPTO in MFLE Plants 1034, 1376, 1459 | 0.5 | 2021-02-03 14:00 | 2021-02-03 14:30 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92297 |  |  | * |  | 2021-02-03 14:00 | 2021-02-03 14:30 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92351 | WBS.2.3.5.4.1.3.5 | N | N | Planned | RTR_E0276 - Load proc alternatives for GP01 and GPTO for MFLE Plants1034 1376, 1459 (E0276) | 0.25 | 2021-02-03 10:30 | 2021-02-03 10:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92295 |  |  | * |  | 2021-02-03 10:30 | 2021-02-03 10:45 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92352 | WBS.2.3.5.4.1.3.6 | N | N | Planned | RTR_E0276 - Valid proc alternatives for GP01 and GPTO - MFLE Plants 1034, 1376, 1459 (E0276) | 0.75 | 2021-02-03 10:45 | 2021-02-03 11:30 | TONY SMITH | AJSMITH@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;RTR TEAM;KRISHNA RAVI;KRISHNA SINGAREDDY;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;KRISHNACHAITANYA.RAVI@GAPAC.COM;ksingareddy@deloitte.com;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92351 |  |  | * |  | 2021-02-03 10:45 | 2021-02-03 11:30 | RTR - PC | CROSS | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
92307 | WBS.2.3.5.4.1.4 | N | N |  | Ramp Up ¦ PTM_C0080 - Convert Bill of Materials | 7 | 2021-02-02 08:15 | 2021-02-02 15:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 15:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
7882 | WBS.2.3.5.4.1.4.1 | N | N | Planned | Prepare load file for costing BOMs for current deployment | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92291,36654 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8788 | WBS.2.3.5.4.1.4.2 | N | N | Planned | PTM_C0080 - Execute Transform - Convert Costing BOMs | 2 | 2021-02-02 08:45 | 2021-02-02 10:45 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 7882 |  |  | * |  | 2021-02-02 08:45 | 2021-02-02 10:45 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8789 | WBS.2.3.5.4.1.4.3 | N | N | Planned | PTM_C0080 - Analyze and Resolve errors for Costing BOMs (Simulation load) | 0.5 | 2021-02-02 10:45 | 2021-02-02 11:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8788 |  |  | * |  | 2021-02-02 10:45 | 2021-02-02 11:15 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
5190 | WBS.2.3.5.4.1.4.4 | N | N | Planned | PTM_C0080 - Execute Load in S/4HANA - for Costing BOMS | 3 | 2021-02-02 11:15 | 2021-02-02 14:15 | PRADEEP CHEEDALLA | PCHEEDALLA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DENISE ROBINSON;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DOROBINS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 8789 |  |  | * |  | 2021-02-02 11:15 | 2021-02-02 14:15 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
5191 | WBS.2.3.5.4.1.4.5 | N | N | Planned | PTM_C0080 - Validate Load in S/4HANA - Costing BOMS | 1 | 2021-02-02 14:15 | 2021-02-02 15:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;CHIRAG PARIKH;JENNIFER LI;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CPARIKH@DELOITTE.COM;JQLI@GAPAC.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5190 |  |  | * |  | 2021-02-02 14:15 | 2021-02-02 15:15 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92454 | WBS.2.3.5.4.1.4.6 | N | N | Planned | Start ALL S4 (and related systems) Batch Jobs - after gate 10 (timing to be confirmed) | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | DON BIGALKE | DONALD.BIGALKE@KBSLP.COM | NNEKA MBA;SUNIL KORI;LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;KELLY HINSON;SURESH P;KESAVA BATTINA;PREETAM ROUT | NEMBA@GAPAC.COM;SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;KSHINSON@GAPAC.COM;suresh.p@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;preetam.rout@kochtc.com | BATCH | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 | BATCH | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92761 | WBS.2.3.5.4.1.4.7 | N | N | Planned | Enable Trigger for D4 Tasks | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | NNEKA MBA | NEMBA@GAPAC.COM | SUNIL KORI;LSA TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;KELLY HINSON;PREETAM ROUT;KESAVA BATTINA;SURESH P;JAYAKRISHNAN RADHAKRISHNAN | SUNIL.KORI@KOCHTC.COM;MATREZVA@GAPAC.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;KSHINSON@GAPAC.COM;preetam.rout@kochtc.com;KESAVAMANI.BATTINA@KOCHTC.COM;suresh.p@kochtc.com;JAYAKRISHNAN.RADHAKRISHNAN@KOCHTC.COM | BATCH | 92454 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | BATCH | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92309 | WBS.2.3.5.4.1.5 | N | N |  | Ramp Up ¦ PTM_C0085 - Convert Costing Production Versions | 5.25 | 2021-02-02 15:15 | 2021-02-02 20:30 | [8 empty] | * |  | 2021-02-02 15:15 | 2021-02-02 20:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
7886 | WBS.2.3.5.4.1.5.1 | N | N | Planned | Prepare load file for costing Prod versions | 1 | 2021-02-02 15:15 | 2021-02-02 16:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 5191,8794 |  |  | * |  | 2021-02-02 15:15 | 2021-02-02 16:15 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8797 | WBS.2.3.5.4.1.5.2 | N | N | Planned | PTM_C0085 - Execute Load program - Convert Costing Production Versions (Simulation Mode) | 2 | 2021-02-02 16:15 | 2021-02-02 18:15 | ANKIT AGARWAL | ANKITAGARWAL87@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 7886 |  |  | * |  | 2021-02-02 16:15 | 2021-02-02 18:15 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8798 | WBS.2.3.5.4.1.5.3 | N | N | Planned | PTM_C0085 - Analyze And Resolve Errors For Costing ProdVersion Data (Simulation Load) | 0.25 | 2021-02-02 18:15 | 2021-02-02 18:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8797 |  |  | * |  | 2021-02-02 18:15 | 2021-02-02 18:30 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8799 | WBS.2.3.5.4.1.5.4 | N | N | Planned | PTM_C0085 - Execute Load Program - Convert Costing Production Versions | 1 | 2021-02-02 18:30 | 2021-02-02 19:30 | PHANI GHANTASALA | PGHANTASALA@DELOITTE.COM | DATA ETL TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 8798 |  |  | * |  | 2021-02-02 18:30 | 2021-02-02 19:30 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8801 | WBS.2.3.5.4.1.5.5 | N | N | Planned | PTM_C0085 - Validate Load - Convert Costing Production Versions | 1 | 2021-02-02 19:30 | 2021-02-02 20:30 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8799 |  |  | * |  | 2021-02-02 19:30 | 2021-02-02 20:30 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92308 | WBS.2.3.5.4.1.6 | N | N |  | Ramp Up ¦ PTM_C0082 - Convert Routing Required | 3.75 | 2021-02-02 08:30 | 2021-02-02 12:15 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 12:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
7883 | WBS.2.3.5.4.1.6.1 | N | N | Planned | Prepare load file for costing Routings for current deployment | 0.5 | 2021-02-02 08:30 | 2021-02-02 09:00 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | NOEL CLARK;VISHNU CHIRALA;SAI TEAM;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | NOEL.CLARK@GAPAC.COM;VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92291,36654 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:00 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8790 | WBS.2.3.5.4.1.6.2 | N | N | Planned | PTM_C0082 - Execute Preload - Convert Costing Routing (Simulation Mode) | 1 | 2021-02-02 09:00 | 2021-02-02 10:00 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 7883 |  |  | * |  | 2021-02-02 09:00 | 2021-02-02 10:00 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8791 | WBS.2.3.5.4.1.6.3 | N | N | Planned | PTM_C0082 - Analyze and Resolve errors for Convert Costing Routing (Simulation load) | 0.25 | 2021-02-02 10:00 | 2021-02-02 10:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8790 |  |  | * |  | 2021-02-02 10:00 | 2021-02-02 10:15 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8792 | WBS.2.3.5.4.1.6.4 | N | N | Planned | PTM_C0082 - Execute Load program - Costing Routing | 1 | 2021-02-02 10:15 | 2021-02-02 11:15 | ANURAG ANAND | ANANAND@DELOITTE.COM | DATA ETL TEAM;DENISE ROBINSON;SAI TEAM;DEAN PIPER;LYNN MCMURDO | USINDIAGPDATA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;dorobins@gapac.com;DOROBINS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM | DATA | 8791 |  |  | * |  | 2021-02-02 10:15 | 2021-02-02 11:15 | DATA | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
8794 | WBS.2.3.5.4.1.6.5 | N | N | Planned | PTM_C0082 - Validate Load - Costing Routing | 1 | 2021-02-02 11:15 | 2021-02-02 12:15 | JACOB DENNIS | JACOB.DENNIS@GAPAC.COM | VISHNU CHIRALA;SAI TEAM;NOEL CLARK;TONY SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VICHIRALA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NOEL.CLARK@GAPAC.COM;AJSMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 8792 |  |  | * |  | 2021-02-02 11:15 | 2021-02-02 12:15 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89823 | WBS.2.3.5.5 | N | N |  | Ramp-Up ¦ AC Activities | 2.5 | 2021-02-02 08:15 | 2021-02-02 10:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90245 | WBS.2.3.5.5.1 | N | N |  | Ramp-Up ¦ AC Activities | 2.5 | 2021-02-02 08:15 | 2021-02-02 10:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91777 | WBS.2.3.5.5.1.1 | N | N |  | Ramp-Up ¦ AC Activities | 2.5 | 2021-02-02 08:15 | 2021-02-02 10:45 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 10:45 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
82288 | WBS.2.3.5.5.1.1.1 | N | N | Planned | Validate AC batch jobs have been scheduled | 1 | 2021-02-02 08:45 | 2021-02-02 09:45 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | JASON RAMSEY;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 21148,92761 |  |  | * |  | 2021-02-02 08:45 | 2021-02-02 09:45 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
9399 | WBS.2.3.5.5.1.1.2 | N | N | Planned | Create a notification from DMAPS to SAP | 2 | 2021-02-02 08:15 | 2021-02-02 10:15 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | CHAD FLAGG;KELLY STRASSBURGER;SAI TEAM;JASON RAMSEY;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | CHAD.FLAGG@GAPAC.COM;KELLY.STRASSBURGER@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 5763,5768,8853,5393,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 10:15 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90303 | WBS.2.3.5.5.1.1.3 | N | N | Planned | Get notification status changes from SAP to DMAPS | 0.25 | 2021-02-02 10:15 | 2021-02-02 10:30 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 9399 |  |  | * |  | 2021-02-02 10:15 | 2021-02-02 10:30 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90302 | WBS.2.3.5.5.1.1.4 | N | N | Planned | Get work order status changes from SAP to DMAPS (after the notification is associated to a work order) | 0.25 | 2021-02-02 10:30 | 2021-02-02 10:45 | BOB BROWN | ROBERT.BROWN4@GAPAC.COM | DAVID MCGINNIS;JASON RAMSEY;SAI TEAM;AC TEAM;GARY BENOIT;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | DAVID.MCGINNIS@GAPAC.COM;JCRAMSEY@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;GARY.BENOIT@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 90303 |  |  | * |  | 2021-02-02 10:30 | 2021-02-02 10:45 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
5871 | WBS.2.3.5.5.1.1.5 | N | N | Planned | Test Mobil devices connectivity at plants | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | PETER WILLIAMS | PETER.WILLIAMS@GAPAC.com | JASON RAMSEY;CHAD FLAGG;SAI TEAM;AC TEAM;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS;CHRIS TUFTS | JCRAMSEY@GAPAC.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com;CHRIS.TUFTS@GAPAC.COM | AC | 8853,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92096 | WBS.2.3.5.5.1.1.6 | N | N | Planned | Confirm MRS batch jobs are scheduled in StoneBranch | 1 | 2021-02-02 08:45 | 2021-02-02 09:45 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | JEY MURUGESH;AC TEAM;SAI TEAM;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | JMURUGESH@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 8853,36654,92761 |  |  | * |  | 2021-02-02 08:45 | 2021-02-02 09:45 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92095 | WBS.2.3.5.5.1.1.7 | N | N | Planned | Confirm PERNR assignment is aligned between MRS and S4 Work Centers | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | TAJINDER KOHLI | TKOHLI@DELOITTE.COM | RICHARD BLEVINS;AC TEAM;SAI TEAM;MATT BLOHM;DEAN PIPER;LYNN MCMURDO;GARY LORIMOR;DANIEL HENDERSON;JERRY (JT) THOMAS;JAMES LEE;GREGORY GIBBS | RICHARD.BLEVINS@GAPAC.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;MATTHEW.BLOHM@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;gary.lorimor@gapac.com;daniel.henderson@gapac.com;jerry.thomas@gapac.com ;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | AC | 8853,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | AC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90944 | WBS.2.3.5.6 | N | N |  | Ramp-Up ¦ DEV Activities | 8 | 2021-02-02 08:15 | 2021-02-02 16:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90943 | WBS.2.3.5.6.1 | N | N |  | Ramp-Up ¦ DEV Activities | 8 | 2021-02-02 08:15 | 2021-02-02 16:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91772 | WBS.2.3.5.6.1.1 | N | N |  | Ramp-Up ¦ DEV Activities | 8 | 2021-02-02 08:15 | 2021-02-02 16:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
81137 | WBS.2.3.5.6.1.1.1 | N | N | Planned | Disable Legacy EAI/ETL jobs and interfaces; webMethods/BODS | 8 | 2021-02-02 08:15 | 2021-02-02 16:15 | RON MASON | RONMASON@GAPAC.COM | TED ZEIDLER;BRIAN DOBASH;SAI TEAM;SUVENDU KUMAR;DEV TEAM;KELLY HINSON;WILL COLEMAN | TED.ZEIDLER@GAPAC.COM;BJDOBASH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;NASHARMA@DELOITTE.COM;STHARWANI@DELOITTE.COM;SUVKUMAR@DELOITTE.COM;BJDOBASH@GAPAC.COM;DWSIMMON@GAPAC.COM;ANKISONI@DELOITTE.COM;RAMYIYER@DELOITTE.COM;karavindkumar@deloitte.com;gunearora@deloitte.com;;KSHINSON@GAPAC.COM;WCOLEMA@GAPAC.COM | DEV | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 16:15 | INT | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94980 | WBS.2.3.5.7 | N | N |  | Ramp-Up ¦ Reporting | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95746 | WBS.2.3.5.7.1 | N | N |  | Ramp-Up ¦ Reporting | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95747 | WBS.2.3.5.7.1.1 | N | N |  | Ramp-Up ¦ Reporting | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94981 | WBS.2.3.5.7.1.1.1 | N | N | Planned | Refresh the data in eHANA sourced from the AS8 system | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | DWIGHT WORRELL | DLWORREL@GAPAC.COM | LISA HEROLD;ABHINAV SAXENA;SAI TEAM;RPT TEAM;PANKAJ SINGH;ATUL KUMAR AGNIHOTRI;CASEY HERMANSEN | LISA.HEROLD@GAPAC.COM;ABSAXENA@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ABSAXENA@DELOITTE.COM;ATAGNIHOTRI@DELOITTE.COM;SSANJEEV@DELOITTE.COM;BRIAN.RIDENHOUR@GAPAC.COM;DAVID.MILLER3@GAPAC.COM;DLWORREL@GAPAC.COM;LISA.HEROLD@GAPAC.COM;MARK.GILSON@GAPAC.COM;PANKASINGH@DELOITTE.COM;PANKASINGH@DELOITTE.COM;ATAGNIHOTRI@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM | RPT | 36654,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | RPT | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89642 | WBS.2.3.6 | N | N |  | Ramp-Up ¦ IBP Activities | 5.25 | 2021-02-02 08:15 | 2021-02-02 13:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 13:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
89816 | WBS.2.3.6.1 | N | N |  | Ramp-Up ¦ Demand Planning | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90137 | WBS.2.3.6.1.1 | N | N |  | Ramp-Up ¦ Demand Planning Tasks | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91769 | WBS.2.3.6.1.1.1 | N | N |  | Ramp-Up ¦ Demand Planning Tasks | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
82969 | WBS.2.3.6.1.1.1.1 | N | N | Planned | Turn-on Stone Branch job for HCI, IBP and S/4HANA - IBP DP | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | JEFFREY GILLIAM | JFGILLIA@GAPAC.COM | JENNIFER LI;CHIRAG PARIKH;SAI TEAM;SCM TEAM;BRAD WYMAN;KIM LADZINSKE;RYAN D;SAYONI BANERJEE;SATISH KUMAR B;ANUPAM SHRIVASTAVA | JQLI@GAPAC.COM;CPARIKH@DELOITTE.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;DGRUTAN@GAPAC.COM;bsatishkumar@deloitte.com;SANJAY.JELAJI1@GAPAC.COM;CPARIKH@DELOITTE.COM;cbalasubramanian@deloitte.com;BRAD.WYMAN@GAPAC.COM;KDLADZIN@GAPAC.COM;RDORR@GAPAC.COM;SAYONI.BANERJEE@KOCHTC.COM;BSATISHKUMAR@DELOITTE.COM;ANUPSHRIVASTAVA@DELOITTE.COM | SCM | 36654,5246,5251 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | SCM | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90127 | WBS.2.3.6.2 | N | N |  | Ramp-Up ¦ Validate Dependent Requirements in S/4HANA | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90139 | WBS.2.3.6.2.1 | N | N |  | Ramp-Up ¦ Validate Dependent Requirements in S/4HANA Tasks | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91766 | WBS.2.3.6.2.1.1 | N | N |  | Ramp-Up ¦ Validate Dependent Requirements in S/4HANA Tasks | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96428 | WBS.2.3.6.2.1.1.2 | N | N | Planned | BG - Validate Vital Inventory and vital and paper dependent requirements in S/4HANA (Resource Name) | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | JEANA HARRER | Jeana.Harrer@GAPAC.com | JORDAN BUNDY;JOHN J SMITH;LISA SZCZUREK;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JORDAN.BUNDY@GAPAC.COM;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | SCM - TTN | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93374 | WBS.2.3.6.2.1.1.4 | N | N | Planned | PTH - Validate Vital Inventory and vital and paper dependent requirements in S/4HANA - Tissue | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | MARSHAL SAVAGE | marshal.savage@gapac.com | JANET QUEBEDEAUX;CJ KAUTH;ROBBIE GARNER;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | janet.quebedeaux@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | SCM - TTN | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93373 | WBS.2.3.6.2.1.1.5 | N | N | Planned | PTH - Validate Vital Inventory and vital and paper dependent requirements in S/4HANA - Towel | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | JANET QUEBEDEAUX | janet.quebedeaux@gapac.com | MARSHAL SAVAGE;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | marshal.savage@gapac.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | SCM - TTN | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93964 | WBS.2.3.6.2.1.1.6 | N | N | Planned | HBG - Validate Vital Inventory and vital and paper dependent requirements in S/4HANA (Resource Name) | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;JOHN J SMITH;LISA SZCZUREK;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JOHNJ.SMITH@GAPAC.COM;LISA.SZCZUREK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | SCM - TTN | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
11119 | WBS.2.3.7 | N | N |  | Ramp-Up ¦ AC Business | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
90161 | WBS.2.3.7.1 | N | N |  | Ramp-Up ¦ AC Business Activities | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
90232 | WBS.2.3.7.1.1 | N | N |  | Ramp-Up ¦ AC Business Tasks | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
91765 | WBS.2.3.7.1.1.1 | N | N |  | Ramp-Up ¦ AC Business Tasks | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 |  |  | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
96782 | WBS.2.3.7.1.1.1.13 | N | N | Planned | BG - MRO - Printing Enter manually tracked activity post cutover MRO Work Orders | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM;ROBBIE ISBELL;Brad Collins | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Daniel.Isbell@GAPAC.com;Bradley.Collins@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | AC | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93920 | WBS.2.3.7.1.1.1.1 | N | N | Planned | HBG - ITR_C0062.1 - Spot-check SAP DATA reflects loaded data (Convert Work order history - MP2) | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;AC TEAM;JAMES LEE;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JCRAMSEY@GAPAC.COM;TKOHLI@DELOITTE.COM;JMURUGESH@DELOITTE.COM;GBHATIA@DELOITTE.COM;CHAD.FLAGG@GAPAC.COM;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96430 | WBS.2.3.7.1.1.1.4 | N | N | Planned | BG - Converting MRO - Provide final data for Resource constraints for each resource | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | STEPHEN GREENWOOD | Stephen.Greenwood@GAPAC.com | ROBBIE ISBELL;DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM;David Ennis;Brad Collins | Daniel.Isbell@GAPAC.com;Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Noel.Ennis@gapac.com;Bradley.Collins@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | AC | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96429 | WBS.2.3.7.1.1.1.5 | N | N | Planned | BG - Converting Final Work Order creation | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | ROBBIE ISBELL | Daniel.Isbell@GAPAC.com | DEAN PIPER;DARRIN WATKINS;BRIAN RAYMER;LYNN MCMURDO;SAI TEAM;David Ennis;Brad Collins | Dean.Piper@gapac.com;Darrin.Watkins@gapac.com;BRIAN.RAYMER@GAPAC.COM;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Noel.Ennis@gapac.com;Bradley.Collins@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | AC | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96804 | WBS.2.3.7.1.1.1.14 | N | N | Planned | BG - Printing Final Work Order creation | 4 | 2021-02-02 08:30 | 2021-02-02 12:30 | David Ennis | Noel.Ennis@gapac.com | Shane Grant;Jon Morrison;DEAN PIPER;LYNN MCMURDO;SAI TEAM;ROBBIE ISBELL;Brad Collins | Timothy.Grant@gapac.com;JON.MORRISON@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Daniel.Isbell@GAPAC.com;Bradley.Collins@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 12:30 | AC | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93378 | WBS.2.3.7.1.1.1.6 | N | N | Planned | PTH - MRO - Provide final data for Resource constraints for each resource | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;DANIEL HENDERSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;daniel.henderson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com ;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | AC | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93377 | WBS.2.3.7.1.1.1.7 | N | N | Planned | PTH - Final Work Order creation | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | DANIEL HENDERSON | daniel.henderson@gapac.com | TOMMY WOMACK;DARRELL WATSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;JERRY (JT) THOMAS | tommy.womack@gapac.com;Darrell.watson@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;jerry.thomas@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 | AC | PTH | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
93961 | WBS.2.3.7.1.1.1.9 | N | N | Planned | HBG - MRO - Provide final data for Resource constraints for each resource | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | RICHARD WILBERDING | Richard.Wilberding@gapac.com | GLEN RICHARDSON;JEFF LEE;CHRIS ZUMWALT;SAI TEAM;GREGORY GIBBS | GLEN.RICHARDSON@GAPAC.COM;JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;GREGORY.GIBBS@GAPAC.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93960 | WBS.2.3.7.1.1.1.10 | N | N | Planned | HBG - Final Work Order creation | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | JERRY WHIDDON | JERRY.WHIDDON@GAPAC.com | JEFF LEE;CHRIS ZUMWALT;SAI TEAM;JAMES LEE;GREGORY GIBBS | JAMES.LEE1@gapac.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JAMES.LEE1@gapac.com ;GREGORY.GIBBS@GAPAC.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | AC | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
80663 | WBS.2.3.8 | N | N |  | Ramp-Up ¦ EWM Business | 8.25 | 2021-02-02 08:15 | 2021-02-02 16:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:30 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90159 | WBS.2.3.8.1 | N | N |  | Ramp-Up ¦ EWM Business Activities | 8.25 | 2021-02-02 08:15 | 2021-02-02 16:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:30 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90233 | WBS.2.3.8.1.1 | N | N |  | Ramp-Up ¦ EWM Business Tasks | 8.25 | 2021-02-02 08:15 | 2021-02-02 16:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:30 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91757 | WBS.2.3.8.1.1.1 | N | N |  | Ramp-Up ¦ EWM Business Tasks | 8.25 | 2021-02-02 08:15 | 2021-02-02 16:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 16:30 |  | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93056 | WBS.2.3.8.1.1.1.4 | N | N | Planned | SCH - Verify the items on Q-hold in Sharepoint are not available for shipping in EWM | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | GIOVANY CARVAJAL | GIOVANY.CARVAJAL@NFIINDUSTRIES.COM | TOMMY NEFFENDORF;JEREMY RAY;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;CHRISTOPHER JERNIGAN;DANIELLE MULLIGAN;TRISTAN CLARK | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Christopher.Jernigan@gapac.com;Danielle.Mulligan@gapac.com;Tristan.Clark@nfiindustries.com | Business | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | EWM | SCH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93055 | WBS.2.3.8.1.1.1.5 | N | N | Planned | SCH - Validate inventory compare records between systems after mock cutover - review for necessary corrections | 8 | 2021-02-02 08:30 | 2021-02-02 16:30 | DANIELLE MULLIGAN | Danielle.Mulligan@gapac.com | TOMMY NEFFENDORF;JEREMY RAY;GIOVANY CARVAJAL;ESSEX BRASSEL;SAI TEAM;EWM TEAM;ANDY KEOYOTHY;AARON HISSONG;CHRISTOPHER JERNIGAN | TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;GIOVANY.CARVAJAL@NFIINDUSTRIES.COM;ESSEX.BRASSEL@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;ANDY.KEOYOTHY@NFIINDUSTRIES.COM;Aaron.Hissong@gapac.com;Christopher.Jernigan@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 16:30 | EWM | SCH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96440 | WBS.2.3.8.1.1.1.6 | N | N | Planned | BG - Start Task - Enter Stock Transport Orders by using business continuity form | 0.5 | 2021-02-02 08:30 | 2021-02-02 09:00 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:00 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96439 | WBS.2.3.8.1.1.1.7 | N | N | Planned | BG - Validate All inventory compare records between systems after mock cutover - review for necessary corrections | 4 | 2021-02-02 08:30 | 2021-02-02 12:30 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 12:30 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96438 | WBS.2.3.8.1.1.1.8 | N | N | Planned | BG - Verify the items on Q-hold are not available for shipping | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | BEAU EARLS | Beau.Earls@GAPAC.com | LYNN MCMURDO;DEAN PIPER;SAI TEAM | LYNN.MCMURDO@GAPAC.COM;Dean.Piper@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96437 | WBS.2.3.8.1.1.1.9 | N | N | Planned | BG - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation MRO | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | JORDAN BUNDY | JORDAN.BUNDY@GAPAC.COM | JEANA HARRER;DEAN PIPER;LYNN MCMURDO;SAI TEAM;BEAU EARLS | Jeana.Harrer@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Beau.Earls@GAPAC.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | EWM | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96436 | WBS.2.3.8.1.1.1.10 | N | N | Planned | RNC - Verify the items on Q-hold in Sharepoint are not available for shipping in JDA | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 36654,96421 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | EWM | RNC | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96435 | WBS.2.3.8.1.1.1.11 | N | N | Planned | RNC - Validate inventory compare records between systems after mock cutover - review for necessary corrections | 8 | 2021-02-02 08:30 | 2021-02-02 16:30 | MARIA MARQUEZ | MARIA.MARQUEZ@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY;RICHARD ROMO;DALIA MIRANDA;DERICK LOUGH | MARIA.MARQUEZ@NFIINDUSTRIES.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM;RICHARD.ROMO@GAPAC.COM;DALIA.MIRANDA@GAPAC.COM;DERICK.LOUGH@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 16:30 | EWM | RNC | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96434 | WBS.2.3.8.1.1.1.12 | N | N | Planned | RNC - Redirect RF units/tablets to EWM | 4 | 2021-02-02 08:30 | 2021-02-02 12:30 | STEVE TAYLOR | SSTAYLOR@GAPAC.COM | SAI TEAM;EWM TEAM;DAVID ALENCASTRO;TOMMY NEFFENDORF;JEREMY RAY | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;DAVID.ALENCASTRO@GAPAC.COM;DAVID.ALENCASTRO@NFIINDUSTRIES.COM;TOMMY.NEFFENDORF@GAPAC.COM;JEREMY.RAY@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 12:30 | EWM | RNC | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96433 | WBS.2.3.8.1.1.1.13 | N | N | Planned | RVG - Validate Qhold items are showing restricted in EWM | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | REBECCA MORRIS | REBECCA.MORRIS@GAPAC.COM | JENNIFER MCLEOD;JENNIFER NEWBERRY;JULI LEWIS;SAI TEAM | JENNIFER.MCLEOD@GAPAC.COM;JENNIFER.NEWBERRY@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96412,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | EWM | RVG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96432 | WBS.2.3.8.1.1.1.14 | N | N | Planned | RVG - Validate inventory compare records between E80 and EWM review for necessary corrections | 8 | 2021-02-02 08:15 | 2021-02-02 16:15 | JENNIFER MCLEOD | JENNIFER.MCLEOD@GAPAC.COM | JENNIFER NEWBERRY;REBECCA MORRIS;JULI LEWIS;SAI TEAM | JENNIFER.NEWBERRY@GAPAC.COM;REBECCA.MORRIS@GAPAC.COM;JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96735,36654 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 16:30 | EWM | RVG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96533 | WBS.2.3.8.1.1.1.33 | N | N | Planned | RVG - Turn on LGVs | 0.25 | 2021-02-02 08:15 | 2021-02-02 08:30 | JOSH NORTON | joshua.norton@gapac.com | JULI LEWIS;SAI TEAM;JENNIFER MCLEOD | JULI.LEWIS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JENNIFER.MCLEOD@GAPAC.COM | Business | 97642,36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 08:30 | EWM | RVG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96534 | WBS.2.3.8.1.1.1.34 | N | N | Planned | * Mock Only* RVG - Send Catch up Transactions to SAP (Inventory Transfers) | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | SAM MELNIK | MELNIK.S@ELETTRIC80.IT | SAI TEAM;EWM TEAM;EMANUEL VILLEGAS ;JAMES LANDRY ;STEPHANIE MOORE ;VIKTOR ZIVREV | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;ADEY@DELOITTE.COM;DOUG.STANISLAWSKI@GAPAC.COM;VKUPPILI@DELOITTE.COM;SMSHAH@DELOITTE.COM;KSATYAM@DELOITTE.COM;AQHUSAIN@DELOITTE.COM;alobhatt@deloitte.com;MAGUPTA@DELOITTE.COM;ATALREJA@deloitte.com;VILLEGAS.E@ELETTRIC80.IT ;LANDRY.J@ELETTRIC80.IT ;sttmoore@gapac.com ;ZIVREV.V@ELETTRIC80.IT | EWM | 36654 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | E80 | RVG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93384 | WBS.2.3.8.1.1.1.16 | N | N | Planned | PTH - Start Task - Enter Stock Transport Orders by using business continuity form | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | ANDY JONES | Gibson.Jones@gapac.com | DARRYL JOHNSON;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | DARRYL.JOHNSON@GAPAC.COM ;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93383 | WBS.2.3.8.1.1.1.17 | N | N | Planned | PTH - Validate inventory compare records between systems after mock cutover - review for necessary corrections | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | JAMES COWELL | James.Cowell@gapac.com | ANDY JONES;DARRYL JOHNSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ;HADYN HUGHES | Gibson.Jones@gapac.com;DARRYL.JOHNSON@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93380 | WBS.2.3.8.1.1.1.19 | N | N | Planned | PTH - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation MRO | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93379 | WBS.2.3.8.1.1.1.20 | N | N | Planned | PTH - Test printers SAP EWM | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | DARRYL JOHNSON | DARRYL.JOHNSON@GAPAC.COM | ANDY JONES;JAMES COWELL;HADYN HUGHES;CJ KAUTH;ROBBIE GARNER;SAI TEAM;CASSANDRA BROADWAY;JOE MATTHEWS;JACI ORTIZ | Gibson.Jones@gapac.com;James.Cowell@gapac.com;CHRISTOPHER.HUGHES@GAPAC.COM ;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM; Cassandra.Broadway@gapac.com;Joseph.Matthews@gapac.com; jaci.ortiz@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93959 | WBS.2.3.8.1.1.1.21 | N | N | Planned | HBG - Start Task - Enter Stock Transport Orders by using business continuity form | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | MITCH DEATON | MITCHELL.DEATON@GAPAC.com | RAYMOND BOND;CHRIS ZUMWALT;SAI TEAM | RAYMOND.BOND@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93958 | WBS.2.3.8.1.1.1.22 | N | N | Planned | HBG - Validate inventory compare records between systems after mock cutover - review for necessary corrections | 5 | 2021-02-02 08:30 | 2021-02-02 13:30 | CHRIS ZUMWALT | CHRISTOPHER.ZUMWALT@GAPAC.com | GLEN RICHARDSON;SAI TEAM | GLEN.RICHARDSON@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 13:30 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93957 | WBS.2.3.8.1.1.1.23 | N | N | Planned | HBG - Verify the items on Q-hold are not available for shipping | 0.75 | 2021-02-02 08:30 | 2021-02-02 09:15 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:15 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93956 | WBS.2.3.8.1.1.1.24 | N | N | Planned | HBG - Coordinate changes to receiving activities, ensure good capture of required information and control of documentation MRO | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | BOBBY WHITE | Bobby.White@gapac.com | MITCH DEATON;CHRIS ZUMWALT;SAI TEAM | MITCHELL.DEATON@GAPAC.com;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
10762 | WBS.2.3.9 | N | N |  | Ramp-Up ¦ OTC Business | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90160 | WBS.2.3.9.1 | N | N |  | Ramp-Up ¦ OTC Business Activities | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90234 | WBS.2.3.9.1.1 | N | N |  | Ramp-Up ¦ OTC Business Tasks | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91755 | WBS.2.3.9.1.1.1 | N | N |  | Ramp-Up ¦ OTC Business Tasks | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
29489 | WBS.2.3.9.1.1.1.2 | N | N | Planned | ATL - RETAIL/PRO - Ramp Up - Resume Releasing Customer orders from Deployment Facilities in S/4HANA | 0.5 | 2021-02-02 08:30 | 2021-02-02 09:00 | KATIE JACOBS | KATIE.JACOBS@GAPAC.COM | LAURA STEPHAN;JEFF WAGNER;DON ABBOTT;TERRIE GOKEY;JOHN CASABURRI;CHRIS FRENCH;SAI TEAM;NATE CLARK;MADISON MAY;CASSIE LEWIS;LINDSEY LONG | LAURA.STEPHAN@GAPAC.COM;JEFFREY.WAGNER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;THERESA.GOKEY@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;CFRENCH@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;NATHAN.CLARK2@GAPAC.COM;Madison.May@GAPAC.com;CASSANDRA.LEWIS@GAPAC.COM;Lindsey.Long@GAPAC.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:00 | OTC - OM | ATL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94421 | WBS.2.3.9.1.1.1.3 | N | N | Planned | ATL - Delete tops loads that did not match correctly during auto conversion process(add additional predecessor from Jeff W to create list) | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | DAVE LEGOIS | DAVID.LEGOIS@KBXLOGISTICS.COM | TOM OLIVE;JOHN NATZKE;OTC TEAM;SAI TEAM;ANDREW HELMANN | THOMAS.OLIVE@KBXLOGISTICS.COM;JOHN.NATZKE@KBXLOGISTICS.COM;PUNEKUMAR@DELOITTE.COM;KEPRADHAN@DELOITTE.COM;BRAD.WYMAN@GAPAC.COM;TBUDDHA@DELOITTE.COM;BMSADLER@GAPAC.COM;JEANNE.SCOTT@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;Andrew.Helmann@kbxlogistics.com | Business | 92459 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | OTC - KBX | ATL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
29696 | WBS.2.3.10 | N | N |  | Ramp-Up ¦ RTR Business | 3.25 | 2021-02-02 08:15 | 2021-02-02 11:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 11:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90157 | WBS.2.3.10.1 | N | N |  | Ramp-Up ¦ RTR Business Activities | 3.25 | 2021-02-02 08:15 | 2021-02-02 11:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 11:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90236 | WBS.2.3.10.1.1 | N | N |  | Ramp-Up ¦ RTR Business Tasks | 3.25 | 2021-02-02 08:15 | 2021-02-02 11:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 11:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91758 | WBS.2.3.10.1.1.1 | N | N |  | Ramp-Up ¦ RTR Business Tasks | 3.25 | 2021-02-02 08:15 | 2021-02-02 11:30 | [8 empty] | * |  | 2021-02-02 08:15 | 2021-02-02 11:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
95270 | WBS.2.3.10.1.1.1.3 | N | N | Planned | HBG - Balance Sheet OIM reconciliation - Cutover (Mass JE process) After Cut over Puts the detail of in-transit or other OIM | 0.5 | 2021-02-02 08:30 | 2021-02-02 09:00 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:00 | RTR - GL | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96443 | WBS.2.3.10.1.1.1.5 | N | N | Planned | BG - Manually accrue any materials or services received during the blackout in ECC final period | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96442 | WBS.2.3.10.1.1.1.6 | N | N | Planned | BG - Manually reverse the SAP accrual entries in the first month of using the S4 ledger | 2 | 2021-02-02 09:30 | 2021-02-02 11:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 96443 |  |  | * |  | 2021-02-02 09:30 | 2021-02-02 11:30 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96441 | WBS.2.3.10.1.1.1.7 | N | N | Planned | BG - Verify Receipt of In-transit internal items from blackout period | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | Amanda Smith | Amanda.Smith@GAPAC.COM | JoAnna Johnson;DEAN PIPER;LYNN MCMURDO;SAI TEAM | JoAnna.Johnson@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92139 | WBS.2.3.10.1.1.1.8 | N | N | Planned | Close Interim Engineering Support projects for deploying sites (after costs are settled) | 1 | 2021-02-02 08:15 | 2021-02-02 09:15 | LAKAYLA KILGORE | LAKAYLA.KILGORE@GAPAC.COM | VICKI IVEY;BRENDA STAGGS;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VLIVEY@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 36654,94759 |  |  | * |  | 2021-02-02 08:15 | 2021-02-02 09:15 | RTR - PS | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92140 | WBS.2.3.10.1.1.1.9 | N | N | Planned | Submit upload template for Engineering Support Projects for deploying sites to Central Accounting Services | 1 | 2021-02-02 09:15 | 2021-02-02 10:15 | DAMON KIENITZ | DAMON.KIENITZ@GAPAC.COM | CHARLEE VANG;BRENDA STAGGS;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL | CHARLEE.VANG@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM | Business | 92139 |  |  | * |  | 2021-02-02 09:15 | 2021-02-02 10:15 | RTR - PS | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92141 | WBS.2.3.10.1.1.1.10 | N | N | Planned | Upload template for Engineering Support Projects for deploying sites | 0.5 | 2021-02-02 10:15 | 2021-02-02 10:45 | LAKAYLA KILGORE | LAKAYLA.KILGORE@GAPAC.COM | VICKI IVEY;BRENDA STAGGS;SAI TEAM;SANDRA RICHARDS;DONNA SMITH;RTR TEAM;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL;RANJAI JOHN;BOATENG LAWRENCE | VLIVEY@GAPAC.COM;BRENDA.STAGGS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM;RANJAI.JOHN@KOCHTC.COM;LAWRENCE.BOATENG@GAPAC.COM | RTR | 92140 |  |  | * |  | 2021-02-02 10:15 | 2021-02-02 10:45 | RTR - PS | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
82224 | WBS.2.3.10.1.1.1.11 | N | N | Planned | ECC Inventory - WD1 11:59 pm PFGLM004 will execute to disallow back posting - Double check 9434, 9275, 9466 and 9447 to ensure flag is set. | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | VICKI IVEY | VLIVEY@GAPAC.COM | DANNY NGUYEN;SAI TEAM;JOHN CASABURRI;DEAN PIPER;LYNN MCMURDO;Brian Montgomery;MARK HILL | DANNY.NGUYEN@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;brian.montgomery@gapac.com;JOHN.HILL1@GAPAC.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | RTR - PC | PTH,HBG,BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
82223 | WBS.2.3.10.1.1.1.13 | N | N | Planned | ECC morning of CD1 or WD1 – Check OB52 settings for deployed company codes | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | RANJAI JOHN | RANJAI.JOHN@KOCHTC.COM | RICARDO OLIVEIRA;SANDRA RICHARDS;DONNA SMITH;LAURA FRY;BOATENG LAWRENCE;WENTAO TANG;RTR TEAM;SAI TEAM | RICARDO.OLIVEIRA@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;LAURA.FRY@GAPAC.COM;LAWRENCE.BOATENG@GAPAC.COM;WTANG@GAPAC.COM;SARICHARDS@DELOITTE.COM;DONNA.SMITH@GAPAC.COM;BRETT.DETTMERING@GAPAC.COM;NORMAN.REYNOLDS@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | RTR | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | RTR - GL | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93388 | WBS.2.3.10.1.1.1.14 | N | N | Planned | PTH - Start Manually reverse the SAP and AS8 accrual entries in the S/4HANA ledger period 1 | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93387 | WBS.2.3.10.1.1.1.17 | N | N | Planned | PTH - Verify - In-transit internal items from blackout period received in | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93386 | WBS.2.3.10.1.1.1.18 | N | N | Planned | PTH - Verify tracked material usage consumed against S4 production orders after system comes up at go-live | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | MARK HILL | JOHN.HILL1@GAPAC.COM | ANNETTE GONZALES;ANDRE GONZAQUE;JEFF ROBINSON;CJ KAUTH;ROBBIE GARNER;SAI TEAM | ANNETTE.GONZALES@GAPAC.COM;ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93954 | WBS.2.3.10.1.1.1.19 | N | N | Planned | HBG - Verify tracked material usage consumed against S4 production orders after system comes up at go-live | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
94237 | WBS.2.3.10.1.1.1.21 | N | N | Planned | HBG - Verify - In-transit internal items from blackout period received in | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | AVIE LINDSEY | Avie.Lindsey@gapac.com | HOLLY KREUER;CHRIS ZUMWALT;SAI TEAM | HOLLY.KREUER@GAPAC.COM;CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97666 | WBS.2.3.10.1.1.1.36 | N | N | Planned | PTH - Balance Sheet OIM reconciliation - Cutover (Mass JE process) After Cut over Puts the detail of in-transit or other OIM | 1 | 2021-02-02 08:30 | 2021-02-02 09:30 | ANNETTE GONZALES | ANNETTE.GONZALES@GAPAC.COM | ANDRE GONZAQUE;JEFF ROBINSON;MARK HILL;CJ KAUTH;SAI TEAM | ANDRE.GONZAQUE@GAPAC.COM;JEFFREY.ROBINSON@GAPAC.COM;JOHN.HILL1@GAPAC.COM;christopher.kauth@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 09:30 | RTR - GL | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92615 | WBS.2.3.10.1.1.1.37 | N | N | Planned | Provide names of Cost Controllers for deploying manufacturing sites | 0.06 | 2021-02-02 08:30 | 2021-02-02 08:34 | LAURA FRY | LAURA.FRY@GAPAC.COM | TONY SMITH;NOEL CLARK;SAI TEAM | AJSMITH@GAPAC.COM;NOEL.CLARK@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:34 | RTR - PC | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
92614 | WBS.2.3.10.1.1.1.38 | N | N | Planned | Update MBOM Workflow Table with name(s)of Cost Controller(s) at Deploying sites | 0.2 | 2021-02-02 08:34 | 2021-02-02 08:46 | ARLENE WALL | AKWALL@GAPAC.COM | SAI TEAM;CTM TEAM;RHONDA HODGE | JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;AKWALL@GAPAC.COM;AMY.EL-BASSIONI@GAPAC.COM;RAHODGE@GAPAC.COM | CTM | 92615 |  |  | * |  | 2021-02-02 08:34 | 2021-02-02 08:46 | CTM | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
29839 | WBS.2.3.11 | N | N |  | Ramp-Up ¦ PTP Business | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90156 | WBS.2.3.11.1 | N | N |  | Ramp-Up ¦ PTP Business Activities | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
90237 | WBS.2.3.11.1.1 | N | N |  | Ramp-Up ¦ PTP Business Tasks | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
91764 | WBS.2.3.11.1.1.1 | N | N |  | Ramp-Up ¦ PTP Business Tasks | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 |  |  | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
96446 | WBS.2.3.11.1.1.1.2 | N | N | Planned | BG - Enter Goods Movement by using business continuity form | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | JEANA HARRER | Jeana.Harrer@GAPAC.com | BEAU EARLS;DEAN PIPER;LYNN MCMURDO;SAI TEAM | Beau.Earls@GAPAC.com;Dean.Piper@gapac.com;LYNN.MCMURDO@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | EWM/SCM | BG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93397 | WBS.2.3.11.1.1.1.5 | N | N | Planned | PTH - Start Task - Enter Goods Movement by using business continuity form (MRO) | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | CHARLES DUPRE | charles.dupre@gapac.com | DONNA RABALAIS;JAMES COWELL;CJ KAUTH;ROBBIE GARNER;SAI TEAM;NAWIETA HAMILTON-MATHIS;PAUL CARTER | DONNA.RABALAIS@GAPAC.com;James.Cowell@gapac.com;christopher.kauth@gapac.com;Robbie.Garner2@gapac.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;nawieta.hamilton-mathis@gapac.com;PGCarter@gapac.com | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | EWM | PTH | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
83218 | WBS.2.3.11.1.1.1.6 | N | N | Planned | Start process of moving deployment facility invoices from the AS8/ECC to S/4 Ariba realm not in Paid or Paying Status | 2 | 2021-02-02 08:30 | 2021-02-02 10:30 | PAM NIX | PSNIX@GAPAC.COM | MYRA BATES;SANDEE LAUDRE;SAI TEAM;PTP TEAM | MYRA.BATES@GAPAC.COM;SANDRA.LAUNDRE@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 95493,21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 10:30 | EIM | ATL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
93952 | WBS.2.3.11.1.1.1.9 | N | N | Planned | HBG- Start Task - Enter Goods Movement by using business continuity form | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | GLEN RICHARDSON | GLEN.RICHARDSON@GAPAC.COM | CHRIS ZUMWALT;SAI TEAM | CHRISTOPHER.ZUMWALT@GAPAC.com;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | EWM | HBG | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
97168 | WBS.2.3.11.1.1.1.12 | N | N | Planned | Send the PO conversion list to enabled supplier asking they invoice against new POs. | 0.25 | 2021-02-02 08:30 | 2021-02-02 08:45 | BLAYNE GILLEN | blayne.gillen@gapac.com | MARK BURGIN;WILL STINSON;ABBY DREVIK;PAM NIX;SAI TEAM;PTP TEAM | MARK.BURGIN@GAPAC.COM;william.stinson@gapac.com ;abigail.drevik@gapac.com;PSNIX@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM;CASEY.HERMANSEN@GAPAC.COM;KRISTINA.KAUTH@GAPAC.COM;SRUSRINIVASAN@DELOITTE.COM;MASON.DRAKE@GAPAC.COM;MONICA.CUEVAS@GAPAC.COM;JEFFREY.SARTOR@GAPAC.COM;MAPUPILL@GAPAC.COM;YMITRA@DELOITTE.COM | PTP | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-02 08:45 | EIM | ALL | 2021-02-02 | 2021-02-02 | 3 | Ramp Up
36859 | WBS.2.3.12 | N | N |  | Ramp-Up ¦ MDM Business | 48 | 2021-02-02 08:30 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-05 08:30 |  |  | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
90155 | WBS.2.3.12.1 | N | N |  | Ramp-Up ¦ MDM Business Activities | 48 | 2021-02-02 08:30 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-05 08:30 |  |  | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
90238 | WBS.2.3.12.1.1 | N | N |  | Ramp-Up ¦ MDM Business Tasks | 48 | 2021-02-02 08:30 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-05 08:30 |  |  | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
91763 | WBS.2.3.12.1.1.1 | N | N |  | Ramp-Up ¦ MDM Business Tasks | 48 | 2021-02-02 08:30 | 2021-02-05 08:30 | [8 empty] | * |  | 2021-02-02 08:30 | 2021-02-05 08:30 |  |  | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
89663 | WBS.2.3.12.1.1.1.1 | N | N | Planned | Identify the Material Deltas for D4 facilities between the last data extract and current day and extend to the MDG plant code. | 24 | 2021-02-02 08:30 | 2021-02-03 16:30 | DA JIANG | DA.JIANG@GAPAC.COM | DAVID MILLER;DON ABBOTT;JOHN CASABURRI;SAI TEAM | DAVID.MILLER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 21148 |  |  | * |  | 2021-02-02 08:30 | 2021-02-03 16:30 | MDM - Purchased Goods | ALL | 2021-02-03 | 2021-02-03 | 3 | Ramp Up
89662 | WBS.2.3.12.1.1.1.2 | N | N | Planned | Review for any Catalog Deltas for D4 facilities and extend as needed. | 24 | 2021-02-03 16:30 | 2021-02-05 08:30 | DA JIANG | DA.JIANG@GAPAC.COM | DAVID MILLER;DON ABBOTT;JOHN CASABURRI;SAI TEAM | DAVID.MILLER@GAPAC.COM;DON.ABBOTT@GAPAC.COM;JOHN.CASABURRI@GAPAC.COM;JVALLABHANENI@DELOITTE.COM;JOHN.CASABURRI@GAPAC.COM;DON.ABBOTT@GAPAC.COM;ASUNILGANORKAR@DELOITTE.COM;ANKGOSWAMI@DELOITTE.COM;OCBORCHE@GAPAC.COM;SVC_DCCUTOVER2@GAPAC.COM;BERNHARD.MERTES@KOCHGS.COM;CKESSLER@DELOITTE.COM | Business | 89663 |  |  | * |  | 2021-02-03 16:30 | 2021-02-05 08:30 | MDM - Purchased Goods | ALL | 2021-02-05 | 2021-02-05 | 3 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up
[23 empty] | 00:00:00 | 00:00:00 | 7 | Ramp Up

## Object Dependency Info
RICEFW ID* | Description* | Freeze Period Conversion (D1) | In Scope | Process Area | Source Input | Load Mechanism | Revised Load Mechanism | Target System | Deployment 1 (D1) | Deployment 2 (D2) | New BODS Primary | KT | New ABAP Primary | BODS Primary | BODS Secondary | ABAP Primary | ABAP Secondary | D1 Volume | D2 Tentative Volume | D2-MC1 Volume | Comment | File Path n Name | D1 Load Time | D2 Estimated load time | D2-MC1 Load Time(hrs) | Server Usage (Instaces * Server) | Performance Improvement reqd | RFC to file based load | ETA - RFC to file based load | Complexity | Production/ Dev Central (Moved From) | QA Repo (Moved To) | Code Movement Status | Facility | D3 SCOPE | D2.5 SCOPE | D2 SCOPE - UPD 0827 | COMMENTS
ITR_C0016 | Convert Functional Locations - Asset Suite | No | Yes | ITR | Asset Suite - File | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Jaspreet Singh | Trupti | Ramesh Batra | Rajat Jain | FALSE | Ramesh Batra | Ravi Goyal | 7482 | 49000 |  | Load and Xref file will be provided Generate multiple files from BODS IDOC should be created status 64 to enable paralllel processing There are 6 hierarchy levels | No |  |  |  |  | Y |  |  | High | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
ITR_C0016.1 | Convert Functional Locations – MP2 | No | Yes | ITR | MP2- File | BODS (IDOC) | BODS (IDOC) | S/4 HANA | N | Y | Jaspreet Singh | Trupti | Ramesh Batra | Rajat Jain | FALSE | [5 empty] | Load and Xref file will be provided Generate multiple files from BODS IDOC should be created status 64 to enable paralllel processing There are 6 hierarchy levels | No |  |  |  |  | Y |  |  | High | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0018 | Convert equipment – Asset Suite | No | Yes | ITR | Asset Suite - File | Direct ABAP Load | BODS (File) | S/4 HANA | Y | Y |  |  | Anurag Anand | Ankit Agarwal | FALSE | Nikhila Isukapally | Ramesh Batra | 2127 | ~49000 |  | Load and Xref file will be provided Generate multiple files from BODS Direct ABAP load. XREF will be created by BODS but will be provided by AC team | Yes |  |  |  |  | Y |  |  | Very High | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
ITR_C0018.1 | Convert equipment – MP2 | No | Yes | ITR | MP2- File | Direct ABAP Load | BODS (File) | S/4 HANA | N | Y |  |  | Anurag Anand |  | TRUE | Nikhila Isukapally | Ramesh Batra |  |  |  | Load and Xref file will be provided Generate multiple files from BODS Direct ABAP load. XREF will be created by BODS but will be provided by AC team | Yes |  |  |  |  | Y |  |  | Very High | Dev Central | LR_DSQ4 | Completed | BG | Yes |  | No
ITR_C0020 | Convert BOM – Functional location Conversion – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Deepa Saw |  | Phani Ghantasala | Deepa Saw | TRUE | Phani Ghantasala | Ramesh Batra | 794 | 18000 | 32000 |  | No | 1 | 22.67 | 10 |  | Y | Yes |  | High | Dev Central | LR_DSQ3 | Completed | SAV | Yes | Yes | Yes
ITR_C0024 | Convert BOM - Material / Assemblies Conversion – Asset Suite | No | Yes | ITR | Asset Suite | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | Ankit Agarwal | FALSE | Phani Ghantasala | Ramesh Batra | 679 | 160000 |  |  | Yes | 0.8 | 188.5125 |  |  | ? |  |  | High | Dev Central | LR_DSQ2 | Completed | SAV | Yes | Yes | Yes
ITR_C0028 | Convert Equipment Classification Values – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Ayush Jain | Trupti | Ramesh Batra | Ayush Jain | TRUE | Ravi Goyal | Ramesh Batra | 539 | 14000 |  | Generate multiple files from BODS | Yes |  | 0 | [5 empty] | High | Dev Central | LR_DSQ2 | Completed | SAV | Yes | Yes | Yes
ITR_C0028.1 | Convert Equipment Classification Values – MP2 | No | No | ITR | MP2- File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | N | Y |  |  | Ramesh Batra |  | TRUE | Ravi Goyal | Ramesh Batra |  |  |  | Load ready File Generate multiple files from BODS | [8 empty] | High |  |  |  | BG | No |  | No
ITR_C0030 | Convert Functional Location Classification Values – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Anjali Sinha | Trupti | Ramesh Batra | Anjali Sinha | TRUE | Ravi Goyal | Ramesh Batra | 1202 | 14000 |  | Generate multiple files from BODS | No |  | 0 | [5 empty] | Medium | Dev Central | LR_DSQ | Completed | SAV | Yes | Yes | Yes
ITR_C0030.1 | Convert Classification Values - Functional Location – MP2 | No | No | ITR | MP2 - File | Direct ABAP Load | Direct ABAP Load | S/4 HANA |  | Y |  |  | Ramesh Batra |  | TRUE | [18 empty] | BG | No |  | No
ITR_C0032 | Convert Open work orders – Asset Suite | Yes | Yes | ITR | Asset Suite | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | Y | Anjali Sinha | Anurag Anand | Ramesh Batra | Anjali Sinha | TRUE | Ramesh Batra | Nikhila | 668 | 1500 | 2800 | RFC call is made for one order at a time | No | 0.5 | 1.1228 | 1 | 1 | ? | No | Low Volume | High | Dev Central | LR_DSQ5 | Completed | SAV | Yes | Yes | Yes
ITR_C0032.1 | Convert Open work orders – MP2 | Yes | Yes | ITR | MP2 | BODS (BAPI) | BODS (BAPI) | S/4 HANA | N | Y | Anjali Sinha | Anurag Anand | Ramesh Batra | Manish Kumar | FALSE | Ramesh Batra | Nikhila |  | 475 |  |  | No |  |  |  | 1 |  | No | Low Volume | High | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0035 | Convert Open Notifications – Asset Suite | Yes | Yes | ITR | Asset Suite | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | Y | Ayush Jain | Trupti | Ramesh Batra | Ayush Jain | TRUE | Ravi Goyal | Ramesh Batra | 895 | 1000 | 362 |  | Yes | 0.6 | 0.67039 | 0.4 | 1 |  | No | Low Volume | High | Dev Central | LR_DSQ2 | Completed | SAV | Yes | Yes | Yes
ITR_C0038 | Convert Task Lists – Functional Location Conversion - PTM | No | Yes | ITR | PTM | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Ankit Agarwal | Debraj Pal | Ramesh Batra | Ankit Agarwal | TRUE | Ramesh Batra | Ravi Goyal | 2 | 5555 | 900 | Generate multiple files from BODS RFC will be triggered in single instance | Yes | 0.001 | 2.7775 | 0.5 | 1 |  | Yes - Long Text - MC2 | 2019-07-23 | High | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
ITR_C0038.1 | Convert Task Lists – Functional Location Conversion – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Ankit Agarwal | Debraj Pal | Ramesh Batra | Ankit Agarwal | TRUE | Ramesh Batra | Ravi Goyal | 1488 | 6700 | 5262 | Generate multiple files from BODS RFC will be triggered in single instance | Yes | 3 | 13.5081 | 0.5 | 1*5 |  | Yes - Long Text - MC2 | 2019-07-23 | High | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
ITR_C0038.2 | Convert Task Lists – Functional Location Conversion - Maintelligence | No | Yes | ITR | Maintelligence | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Ankit Agarwal | Debraj Pal | Ramesh Batra | Ankit Agarwal | TRUE | Ramesh Batra | Ravi Goyal | 28 | 56453 |  | Generate multiple files from BODS RFC will be triggered in single instance | No | 0.05 | 100.8089 | [5 empty] | Low | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
ITR_C0038.6 | Convert Task Lists - General Conversion – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Charmaine Pereira | Debraj Pal | Ramesh Batra | Rajat Jain | FALSE | Ramesh Batra | Ravi Goyal | 146 | 6700 | 3161 | Generate multiple files from BODS RFC will be triggered in single instance | Yes | 0.45 | 20.6507 | 3 | 1 |  | Yes - Long Text - MC2 | 2019-07-23 | High | Dev Central | LR_DSQ | Completed | SAV | Yes | Yes | Yes
ITR_C0038.7 | Convert Task Lists - General Conversion – MP2 | No | Yes | ITR | MP2 | BODS (File) | BODS (File) | S/4 HANA | N | Y | Hawabi Mistry | Debraj Pal | Ramesh Batra | Rajat Jain | FALSE | Ramesh Batra | Ravi Goyal |  | 1067 | 1414 | Generate multiple files from BODS RFC will be triggered in single instance | No |  |  | 1 | 1 |  | Yes - Long Text - MC2 | 2019-07-23 | High | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0050 | Convert Maintenance Plans Conversion – Asset Suite | No | Yes | ITR | Asset Suite | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Charmaine Pereira |  | Anurag Anand | Rajat Jain | FALSE | Ramesh Batra | Anurag Anand | 1151 | 5000 |  | Generate multiple files from BODS | Yes |  | 0 | [5 empty] | Medium | Dev Central | LR_DSQ | Changes in Progress | SAV | Yes | Yes | Yes
ITR_C0050.1 | Convert Maintenance Plans Conversion - Maintelligence | No | Yes | ITR | Maintelligence | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Ayush Jain |  | Anurag Anand | Ayush Jain | TRUE | Ramesh Batra | Anurag Anand | 28 | 1181 |  | Generate multiple files from BODS | Yes |  | 0 | [5 empty] | High | Dev Central | LR_DSQ2 | Completed | SAV | Yes | Yes | Yes
ITR_C0050.2 | Convert Maintenance Plans Conversion – MP2 | No | Yes | ITR | MP2 | BODS (File) | BODS (File) | S/4 HANA | N | Y | Hawabi Mistry |  | Anurag Anand | Rajat Jain | FALSE | Ramesh Batra | Anurag Anand |  | 939 |  | Generate multiple files from BODS | No | [7 empty] | Medium | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0054 | Convert Measurement Documents – Maintelligence | No | No | ITR | Maintelligence | BODS (BAPI) | BODS (BAPI) | S/4 HANA | N | Y |  |  |  | Pranshu Wadhwa | FALSE | Phani Ghantasala | Ramesh Batra |  |  |  |  | No | [7 empty] | Low |  |  |  | SAV | No |  | No
ITR_C0055 | Convert Measuring Points (with catalogs) – Maintelligence | No | Yes | ITR | Maintelligence | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Amit Tiwari |  | Phani Ghantasala | Rajat Jain | FALSE | Ramesh Batra | Phani Ghantasala | 77 | 22334 | 18000 | Generate multiple files from BODS RFC will be triggered in single instance Long text might be a improvement candidate | No | 1 | 290.0519 | 1 |  | Y | Yes - Long Text - MC3 |  | Low | Dev Central | LR_DSQ | Completed | SAV | Yes | Yes | Yes
ITR_C0247 | NRX 3D Enterprise Document Conversion | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA |  | Phani Ghantasala |  | Trupti | Ramesh Batra | [20 empty] | SAV | Yes |  | Yes
ITR_C0055.1 | Convert Measuring Points (with catalogs) - Asset Suite | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Phani Ghantasala |  | TRUE | Ramesh Batra | Phani Ghantasala | [12 empty] | Low |  |  |  | SAV | Yes | Yes | Yes
ITR_C0058 | Convert Measuring Points (with catalogs) – MP2 | No | No | ITR | MP2 - File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | N | Y |  |  | Phani Ghantasala |  | TRUE | Ramesh Batra | Phani Ghantasala | [12 empty] | Low |  |  |  | BG | No |  | No | AC team will do this manually. Hence not in scope for DATA team.
ITR_C0059.1 | Convert Revisions Conversion – MP2 | No | No | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | N | Y |  |  |  |  | TRUE | Ravi Goyal | [13 empty] | High |  |  |  | BG | No |  | No
ITR_C0061 | Convert Work Center - HR Assignments Conversion | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Madan Zollu |  | TRUE | Sanath | Nikhila | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
ITR_C0062 | Convert Work order history - Asset Suite | Yes | Yes | ITR | Asset Suite | BODS Table Copy | BODS Table Copy | Ent HANA | Y | Y | Hawabi Mistry |  | Debraj Pal | Rajat Jain | FALSE |  |  | 49655 | 250000 |  |  | Yes | 1 | 5.0347 |  |  | Y |  |  | High | Dev Central | LR_DSQ3 | Changes in Progress | SAV | Yes | Yes | Yes
ITR_C0062.1 | Convert Work order history – MP2 | Yes | Yes | ITR | MP2 | BODS Table Copy | BODS Table Copy | Ent HANA | N | Y | Ankit Agarwal |  |  | Ankit Agarwal | TRUE |  |  |  | 35877 |  |  | Yes |  |  |  |  | Y |  |  | Medium | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0064 | Convert Code and Code groups | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Ramesh Batra | Prathamesh | [12 empty] | Medium |  |  |  |  | Yes | Yes | Yes
ITR_C0065 | Convert Documents (Document Management System) - MP2 | No | Yes | ITR | MP2 | BODS (BAPI) | BODS (File) | S/4 HANA | N | Y | Ayush Jain | Anurag Anand | Ramesh Batra | Ayush Jain | TRUE | Ramesh Batra | Ravi Goyal |  | 264 | 410 | RFC call might require to change in load file approach | No |  |  | 0.25 |  | Y | Yes |  | Medium | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite | Yes | Yes | ITR | Asset Suite | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | Y | Ayush Jain | Trupti | Ramesh Batra | Rajat Jain | FALSE | Ramesh Batra | Surya Rajendran | 1128 | 1000 | 737 |  | Yes |  | 0 | 0.75 | 1 |  | No | Low Volume | Medium | Dev Central | LR_DSQ3 | Changes in Progress | SAV | Yes | Yes | Yes
ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite - Delta | Yes | Yes | ITR | Asset Suite | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | Y | Ayush Jain | Trupti | Ramesh Batra | [21 empty] | Yes |  | Yes
ITR_C0067.1 | Convert Scheduled Maintenance Plans – MP2 | Yes | Yes | ITR | MP2 | BODS (BAPI) | BODS (BAPI) | S/4 HANA | N | Y | Ayush Jain | Trupti | Ramesh Batra | Ayush Jain, Ramesh Batra | FALSE | Ravi Goyal |  |  | 939 | 696 |  | No |  |  | 0.5 | 1 |  | No | Low Volume | Medium | Dev Central | LR_DSQ2 | Completed | BG | Yes |  | No
ITR_C0067.1 | Convert Scheduled Maintenance Plans – MP2 - Delta | Yes | Yes | ITR | MP2 | BODS (BAPI) | BODS (BAPI) | S/4 HANA | N | Y | Ayush Jain | Trupti | Ramesh Batra | [21 empty] | Yes |  | No
ITR_C0069 | Convert Classes | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Ravi Goyal | Ramesh Batra | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
ITR_C0070 | Convert Characteristics | No | Yes | ITR | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Ravi Goyal | Ramesh Batra | [12 empty] | Medium |  |  |  |  | Yes | Yes | Yes
ITR_C0071 | Convert Documents (Document Management System) - Asset Suite | No | Yes | ITR | Asset Suite | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Ankit Agarwal | Anurag Anand | Ramesh Batra | Ankit Agarwal | TRUE | Ramesh Batra | Ravi Goyal | 1241 | 35000 | 7400 | RFC call might require to change in load file approach | Yes | 0.5 | 14.1015 | 2 |  | Y | Yes |  | Medium | Dev Central | LR_DSQ2 | Completed | SAV | Yes | Yes | Yes
ITR_C0175 | Convert Measuring documents - Maintelligence | No | Yes | ITR | Maintelligence | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Jaspreet Singh | Anurag Anand | Ramesh Batra | Ankit Agarwal | FALSE | Phani Ghantasala | Ramesh Batra | 0 | 147 | 111 | RFC call might require to change in load file approach | No |  |  | 0.25 |  | Y | Yes |  | Medium | Dev Central | LR_DSQ4 | Completed | SAV | Yes | Yes | Yes
DAT_C0232 | Qualifications from AS8 (TTN) and MP2 (Dixie) | No | No | DATA | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Anurag Anand | Nikhila | [12 empty] | Very High |  |  |  | Both | Yes |  | Yes | In scope only if data is available. Part of Cutover Plan but most likely no data.
DAT_C0234 | Conversion of Non-Employees (Contractors) | No | Yes | DATA | File | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Gul Ansari |  | Anurag Anand | Ayush Jain | FALSE | Surya Rajendran | Nikhila |  |  |  |  | No | [7 empty] | Medium | LR_DSP1 | LR_DSQ | Completed |  | Yes | Yes | Yes
MDG_C0098 | Asset Suite Material Master | No | Yes | DATA | SAP ECC, Asset Suite, File | BODS (File) | BODS (File) | MDG | Y | Y | Deepa Saw |  | Debraj Pal | Arijit Banerjee, Amit Tiwari | FALSE | Debraj Pal | Phani Ghantasala | 43634 | TBD |  | Basic View | No | [6 empty] | already file based | Medium | Dev Central | LR_DSQ3 | Completed | SAV | Yes | Yes | Yes
MDG_C0098 | Asset Suite Material Master - Delta | No | Yes | DATA | Asset Suite | BODS (File) | BODS (File) | MDG |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Manual File - Consumer | No | Yes | DATA | Manual File | BODS (File) | BODS (File) | MDG |  |  | Charmaine Pereira |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Manual File - SPECS | No | Yes | DATA | File | BODS (File) | BODS (File) | MDG |  |  | Charmaine Pereira |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Material Master - Classification | No | Yes | DATA | Asset Suite | BODS (File) | BODS (File) | MDG |  |  | Amit Tiwari |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Manual File - Material Classification | No | Yes | DATA | Manual File | BODS (File) | BODS (File) | MDG |  |  | Amit Tiwari |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Material - Moving Average Price - ECC | No | Yes | DATA | SAP ECC | BODS (File) | BODS (File) | MDG |  |  | Arkodeb Chakraborty |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Material - Moving Average Price - Asset Suite | No | Yes | DATA | Asset Suite | BODS (File) | BODS (File) | MDG |  |  | Arkodeb Chakraborty |  | Debraj Pal | [21 empty] | Yes |  | Yes
MDG_C0098 | Material Master - Asset Suite - Post Load Validation | No | Yes | DATA | [6 empty] | Anjali Sinha | [23 empty] | Yes |  | Yes
MDG_C0098 | Material Master - Manual Files - Post Load Validation | No | Yes | DATA | [6 empty] | Charmaine Pereira | [23 empty] | Yes |  | Yes
MDG_C0098 | Material Master - Replication | No | Yes | DATA |  | IDOC Based | IDOC Based | S/4 HANA |  |  |  |  | Phani Ghantasala | [21 empty] | Yes |  | Yes
MDG_C0098 | Material Master - Replication Validation | No | Yes | DATA | [6 empty] | Ayush Jain | [23 empty] | Yes |  | Yes
NTO_C0156 | Convert Claims from ECC - S4 | Yes | Yes | NTO | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Arkodeb Chakraborty, Ankit Agarwal |  | Madan Zollu | Rajat Jain | FALSE | Ramesh Batra | Nikhila | TBD | TBD | 211000 - 60,00,000 |  | No |  |  | 50 |  |  | Yes - Executed in MC1 |  | Medium | Dev Central | LR_DSQ4 | Completed |  | No | Yes | Yes
NTO_C0156 | Convert Claims from ECC - S4 - Delta | Yes | Yes | NTO | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Arkodeb Chakraborty, Ankit Agarwal |  | Madan Zollu | [21 empty] | No |  | Yes
NTO_C0157 | Convert Inventory Pooling from ECC - S4 | Yes | Yes | NTO | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Anjali Sinha |  | Anurag Anand | Anjali Sinha | TRUE | Anurag Anand | Surya Rajendran | TBD | TBD | 1400000 | MC4: 38,635 records, 2 hours | No |  |  | 5 |  |  | Yes |  | Medium | Dev Central | LR_DSQ5 | Completed |  | No | Yes | Yes
NTO_C0170 | Open Deductions | Yes | Yes | NTO | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Phani Ghantasala |  | TRUE | Surya Rajendran | Sanath | [12 empty] | Medium |  |  |  |  | No | Yes | Yes
NTO_C0222 | Upload the history of data sources that are pertinent to Customer Program's calculations | No | Yes | NTO | SAP ECC | BODS (IDOC) | BODS (IDOC) | S/4 HANA | N | Y | Arkodeb Chakraborty |  | Madan Zollu | Arkodeb Chakraborty | TRUE | Phani Ghantasala | Debraj Pal |  |  |  |  | No | [7 empty] | Very High | Dev Central | LR_DSQ | Completed |  | No | Yes | Yes
NTO_C0230 | PROS Transaction History Table | No | Yes | NTO | PROS | BODS Table Copy | BODS Table Copy | Ent HANA | Y | Y | Deepa Saw |  | Debraj Pal | Deepa Saw | TRUE | [6 empty] | No | [7 empty] | Medium | Dev Central | LR_DSQ3 | Completed |  | No | Yes | Yes
NTO_C0231 | Broker Commission Conditions | No | No | NTO | SAP ECC | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | Y |  |  |  | Gul Ansari | FALSE | Ramesh Batra | Nikhila |  |  |  |  | No | [7 empty] | High |  |  |  |  | No |  | No
OTC_C0079 | Open Sales Order conversion | Yes | Yes | OTC | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Deepa Saw |  | Madan Zollu | Deepa Saw | TRUE | Anurag Anand | Madan | TBD | 11000 | 2500 | MC4: 135 orders, 2 hours | No |  |  | 6 | 2*5 |  | Yes - Volume TestIn Progress 8/1 | 2019-08-06 | Low | Dev Central | LR_DSQ3 | Completed |  | No | Yes | Yes
OTC_C0079 | Open Sales Order conversion - Post Load Validation | Yes | Yes | OTC |  |  |  |  | Y | Y | Deepa Saw | [23 empty] | No |  | Yes
OTC_C0164 | Convert Open AR Invoices from ECC to S/4 | Yes | Yes | OTC | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Arkodeb Chakraborty |  | Phani Ghantasala | Arkodeb Chakraborty | TRUE | Phani Ghantasala | Subbu/Surya | TBD | TBD | 74096 | MC4: 3,276 records, 3 hours | No |  |  | 4.5 |  |  | Yes |  | High | Dev Central | LR_DSQ | Completed |  | No | Yes | Yes
OTC_C0166.1 | Convert Open collections Activity from Get Paid to S/4 | Yes | Yes | OTC | File | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Amit Tiwari |  | Madan Zollu | Amit Tiwari | TRUE | Surya Rajendran | Debarshi | TBD | TBD | 5000 | MC4: 120 records, 2 hours | Yes |  |  | 5 |  |  | Yes |  | Medium | Dev Central | LR_DSQ | Completed |  | No | Yes | Yes
PTM_C0079 | Convert Work center objects from ECC to S4HANA platform | No | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Debarshi Banerjee | Anurag Anand | [12 empty] | Low |  |  |  |  | Yes | Yes | Yes
PTM_C0080 | M-BOMs | No | Yes | PTM | File | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | Ayush Jain | FALSE | Sanath | Debraj Pal |  |  |  |  | Yes | [7 empty] | Medium | Dev Central | LR_DSQ2 | Completed |  | Yes | Yes | Yes
PTM_C0080 | BOM - Costing | No | Yes | PTM | File | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | [21 empty] | Yes |  | Yes
PTM_C0080 | BOM - Repetitive Manufacturing | No | Yes | PTM | File | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | [21 empty] | Yes |  | Yes
PTM_C0082 | Routings | No | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Debarshi Banerjee | Anurag Anand | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
PTM_C0082 | Routings - Costing | No | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand | [21 empty] | Yes |  | Yes
PTM_C0082 | Routings - Repetitive Manufacturing | No | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand | [21 empty] | Yes |  | Yes
PTM_C0085 | Production versions | No | Yes | PTM | File | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Charmaine Pereira |  | Trupti Koushik | Aarthi Somasekharan | FALSE | Debarshi Banerjee | Subbu | 10443 | TBD | 2000 | PV, SubCon PV, Costing PV, ~3 hours | Yes | 3 |  | 0.5 |  |  | Yes |  | Medium | Dev Central | LR_DSQ2 | Completed |  | Yes | Yes | Yes
PTM_C0085 | Production versions - Costing | No | Yes | PTM | File | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Hawabi Mistry |  | Trupti Koushik | [21 empty] | Yes |  | Yes
PTM_C0085 | Production versions - Repetitive Manufacturing | No | Yes | PTM | File | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Hawabi Mistry |  | Trupti Koushik | [21 empty] | Yes |  | Yes
PTM_C0092 | Convert Product Cost Collectors | No | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Trupti Koushik |  | TRUE | Nikhila Isukapally | Phani Ghantasala | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
PTM_C0201 | Inventory - MP2 | Yes | Yes | PTM | SAP ECC, Asset Suite, JDA, High Jump, Elixir, RGL | BODS (File) | BODS (File) | S/4 HANA | Y | Y | Deepa Saw |  | Debraj Pal | Deepa Saw | TRUE | Debraj Pal | Sanath | TBD | TBD | AS8 - 22555 - 3 hrs DSC - non HU - 62 - 4 hrs DSC - Rest - 67979 - 4 hrs JDA EWM - 80888 - 5 hrs JDA E80 - 10342 - 3 hrs MP2 EWM - 3298 - 2 hrs SAP EWM - 9200 - 2 hrs SAP IM - 30 - 2hrs | based on ECC IM Inventory volume | No |  |  | AS8 - 22555 - 3 hrs DSC - non HU - 62 - 4 hrs DSC - Rest - 67979 - 4 hrs JDA EWM - 80888 - 5 hrs JDA E80 - 10342 - 3 hrs MP2 EWM - 3298 - 2 hrs SAP EWM - 9200 - 2 hrs SAP IM - 30 - 2hrs (Continue with RFC) |  |  | Yes - Executed in MC1 |  | Medium | Dev Central | LR_DSQ3 | Completed | Both | Yes | Yes | No
PTM_C0201 | Inventory - Asset Suite | Yes | Yes | PTM | Asset Suite | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | Yes
PTM_C0201 | Inventory - JDA E-80 | Yes | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA |  |  |  |  | Debraj Pal | [21 empty] | Yes |  | Yes
PTM_C0201 | Inventory - JDA | Yes | Yes | PTM | JDA | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | Yes | JDA(Xfm) and JDA E-80 (Direct load file)
PTM_C0201 | Inventory - DSC | Yes | Yes | PTM | DSC | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | Yes | Jacksonville is a plant in DSC
PTM_C0201 | Inventory - SAP WM | Yes | Yes | PTM | SAP WM | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | No
PTM_C0201 | Inventory - SAP IM | Yes | Yes | PTM | SAP IM | BODS (BAPI) | BODS (BAPI) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | Yes
PTM_C0201 | Inventory - High Jump | Yes | Yes | PTM | High Jump | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | No
PTM_C0201 | Inventory - SPG | Yes | Yes | PTM | SPG | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | No
PTM_C0201 | Inventory - Elixir | Yes | Yes | PTM | Elixir | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | No
PTM_C0201 | Inventory - RGL | Yes | Yes | PTM | RGL | BODS (File) | BODS (File) | S/4 HANA |  |  | Deepa Saw |  | Debraj Pal | [21 empty] | Yes |  | No
PTM_C0202 | Convert Truck/Transportation Load Data (Transportation Unit) | Yes | Yes | PTM | File | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Madan Zollu |  | TRUE | Anurag Anand | Phani Ghantasala | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
PTM_C0205 | Convert Product Master | No | Yes | PTM | File | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Charmaine Pereira |  | Madan Zollu | Charmaine Pereria | FALSE | Madan Zollu | Phani Ghantasala | 49444 | TBD | 169000 | 1 hour | No | 1 |  | 4 |  |  | Yes |  | High | Dev Central | LR_DSQ | Completed |  | Yes | Yes | Yes
PTP_C0001 | Convert PTP Contracts - ECC | No | Yes | PTP | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | Richa Bhardwaj | TRUE | Ramesh Batra | Ravi Goyal | 335 | TBD | 48 | 5 hours, Complex: Header, Item, Account Assignment, Scales | Yes | 5 |  | 0.5 |  |  | Yes - Will recheck if it is required via file | 2019-07-23 | Medium | Dev Central | LR_DSQ5 | Completed | Both | Yes |  | Yes
PTP_C0005 | Convert Open Purchase Orders - ECC | Yes | Yes | PTP | SAP ECC | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Jaspreet Singh |  | Phani Ghantasala | Jaspreet Singh | TRUE | Ravi Goyal | Phani Ghantasala | TBD | TBD | 600 | DR3: 11,548 POs, 3 hours | Yes |  |  | 1.5 |  |  | Yes - Will recheck if it is required via file | 2019-07-25 | High | Dev Central | LR_DSQ4 | Completed | Both | Yes |  | Yes
PTP_C0005.1 | Convert Open Purchase Orders - Asset Suite | Yes | Yes | PTP | Asset Suite | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Richa Bhardwaj |  | Phani Ghantasala | Harshit Misra, Anjali Sinha | FALSE | Ravi Goyal | Phani Ghantasala | TBD | TBD | Open - 1046 Service - 606 | DR3: 291 + 189 = 480 Pos | No |  |  | Open - 1.15 Service - 4 |  |  | Yes - Will recheck if it is required via file | 2019-07-25 | High | Dev Central | LR_DSQ5 | Changes in Progress | SAV | Yes | Yes | Yes
PTP_C0005.1 | Convert Service Purchase Orders - Asset Suite | Yes | Yes | PTP | Asset Suite | BODS (BAPI) | BODS (File) | S/4 HANA | Y | Y | Anjali Sinha |  | Phani Ghantasala | [21 empty] | Yes |  | Yes
PTP_C0007 | Convert Output Condition Records - ECC | No | No | PTP | File | BODS (BAPI) | BODS (BAPI) | S/4 HANA | Y | N | Gul Ansari |  | Phani Ghantasala | Manish Kumar | FALSE | Ramesh Batra | Ravi Goyal | 245 | TBD |  | 1.5 hours | No | 1.5 |  |  |  |  | Yes |  | Low |  |  |  |  | No |  | No
PTP_C0008 | Convert Purchase Info Record - ECC | No | Yes | PTP | SAP ECC | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Charmaine Pereira |  | Phani Ghantasala | Charmaine Pereria | FALSE | Phani Ghantasala | Anurag Anand |  |  |  |  | Yes | [7 empty] | Low | Dev Central | LR_DSQ | Completed | Both | Yes |  | Yes
PTP_C0008.1 | Convert Purchase Info Record - Asset Suite | No | Yes | PTP | Asset Suite | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Hawabi Mistry |  | Phani Ghantasala | Hawabi Mistry | TRUE | Phani Ghantasala | Anurag Anand |  |  |  |  | No | [7 empty] | High | Dev Central | LR_DSQ | FUT in Progress | SAV | Yes | Yes | Yes
PTP_C0200 | AS8 Source List Conversion | No | Yes | PTP | Asset Suite | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Hawabi Mistry |  | Phani Ghantasala | Hawabi Mistry | TRUE | Phani Ghantasala | Anurag Anand |  |  |  |  | No | [7 empty] | High | Dev Central | LR_DSQ | FUT in Progress | SAV | Yes | Yes | Yes
PTP_C0200.1 | Convert Source List - ECC | No | Yes | PTP | SAP ECC | BODS (IDOC) | BODS (IDOC) | S/4 HANA | Y | Y | Amit Tiwari |  | Phani Ghantasala | Amit Tiwari | TRUE | Phani Ghantasala | Anurag Anand |  |  |  |  | No | [7 empty] | Low | Dev Central | LR_DSQ | Completed | Both | Yes |  | Yes
PTP_C0236 | Convert Goods Receipt | Yes | Yes | PTP | S/4 HANA | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Ravi Goyal | Sanath | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
PTP_C0237 | Convert Goods Receipt Inventory Adjustment | Yes | Yes | PTP | S/4 HANA | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Anurag Anand |  | TRUE | Debarshi Banerjee | Sanath | [12 empty] | High |  |  |  |  | Yes | Yes | Yes
NTO_C0244 | In-flight/unpaid promotions | No | Yes | NTO | S/4 HANA | BODS (File) | BODS (File) | S/4 HANA | N | Y | Jaspreet Singh |  | Debraj Pal | [21 empty] | No | Yes | Yes
RTR_C0246 | Upload apportionment structure for co-products | No | Yes | RTR | S/4 HANA | Direct ABAP Load | Direct ABAP Load | S/4 HANA | N | Y |  | Phani | Ramesh Batra | [21 empty] | Yes | Yes | Yes
PTM_C0245 | TAPPI ID conversion of entries | No | Yes | PTM | S/4 HANA | Direct ABAP Load | Direct ABAP Load | S/4 HANA | N | Y | Arkodeb Chakraborty |  | Anurag Anand | [21 empty] | Yes | Yes | Yes
PTM_C0204 | EWM Packaging Specification | No | Yes | PTM | S/4 HANA | Direct ABAP Load | Direct ABAP Load | S/4 HANA | Y | Y |  |  | Phani Ghantasala | SAV |  | Yes | [17 empty] | SAV | Yes | Yes | Yes

## Status
Unnamed: 0 | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6
WIP task | 1 |  | Defects
|  |  | 0 | Activities with Defects : ETA not today | 0
|  |  |  | Activities with Defects : ETA today : DATA | 0
Activities with Defects : ETA today : Process
|  |  |  | Loads in Progress | 1
Yet to receive task | 244
Big 3 | Total Activity | Done | WIP | #issue | Yet To Receive | %Percentage Competion
Material | 46 | 0 | 0 | 0 | 46 | 0
Customer | 3 | 0 | 0 | 0 | 3 | 0
Vendor | 1 | 0 | 0 | 0 | 1 | 0
Big 3 | Total Activity | Done | WIP | #issue | Yet To Receive | %Percentage Competion
Material | 46 | 0 | 0 | 0 | 46 | 0
Customer | 3 | 0 | 0 | 0 | 3 | 0
Vendor | 1 | 0 | 0 | 0 | 1 | 0

## Pivot
Finish Date | Unnamed: 1 | Unnamed: 2 | Tag Status | #done | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | Unnamed: 9 | Unnamed: 10 | Unnamed: 11 | Unnamed: 12 | Unnamed: 13 | Unnamed: 14 | Unnamed: 15 | Unnamed: 16 | Unnamed: 17 | Unnamed: 18 | Unnamed: 19 | Unnamed: 20 | Unnamed: 21 | Unnamed: 22 | Unnamed: 23 | Unnamed: 24 | Unnamed: 25 | Unnamed: 26 | Unnamed: 27 | Unnamed: 28 | Unnamed: 29 | Unnamed: 30 | Unnamed: 31 | Unnamed: 32 | Unnamed: 33 | Unnamed: 34 | Unnamed: 35 | Unnamed: 36 | Unnamed: 37 | Unnamed: 38 | Unnamed: 39 | Unnamed: 40 | Unnamed: 41 | Unnamed: 42 | Unnamed: 43 | Unnamed: 44 | Unnamed: 45 | Unnamed: 46 | Unnamed: 47 | Unnamed: 48 | Unnamed: 49 | Unnamed: 50 | Unnamed: 51 | Unnamed: 52 | Unnamed: 53 | Unnamed: 54 | Unnamed: 55 | Unnamed: 56 | Unnamed: 57 | Unnamed: 58 | Unnamed: 59 | Unnamed: 60 | Unnamed: 61 | Unnamed: 62 | Unnamed: 63 | Unnamed: 64 | Unnamed: 65 | Unnamed: 66 | Unnamed: 67 | Unnamed: 68 | Unnamed: 69 | Unnamed: 70 | Unnamed: 71 | Unnamed: 72 | Unnamed: 73 | Unnamed: 74 | Unnamed: 75 | Unnamed: 76 | Unnamed: 77 | Unnamed: 78 | Unnamed: 79 | Unnamed: 80 | Unnamed: 81 | Unnamed: 82 | Unnamed: 83 | Unnamed: 84 | Unnamed: 85 | Unnamed: 86 | Unnamed: 87 | Unnamed: 88 | Unnamed: 89 | Unnamed: 90 | Unnamed: 91 | Unnamed: 92 | Unnamed: 93 | Unnamed: 94 | Unnamed: 95 | Unnamed: 96 | Unnamed: 97 | Unnamed: 98 | Unnamed: 99 | Unnamed: 100 | Unnamed: 101 | Unnamed: 102 | Unnamed: 103 | Unnamed: 104 | Unnamed: 105 | Unnamed: 106 | Unnamed: 107 | Unnamed: 108 | Unnamed: 109 | Unnamed: 110 | Unnamed: 111 | Unnamed: 112 | Unnamed: 113 | Unnamed: 114 | Unnamed: 115 | Unnamed: 116 | Unnamed: 117 | Unnamed: 118 | Unnamed: 119 | Unnamed: 120 | Unnamed: 121 | Unnamed: 122 | Unnamed: 123 | Unnamed: 124 | Unnamed: 125 | Unnamed: 126 | Unnamed: 127 | Unnamed: 128 | Unnamed: 129 | Unnamed: 130 | Unnamed: 131 | Unnamed: 132 | Unnamed: 133 | Unnamed: 134 | Unnamed: 135 | Unnamed: 136 | Unnamed: 137 | Unnamed: 138 | Unnamed: 139 | Unnamed: 140 | Unnamed: 141 | Unnamed: 142 | Unnamed: 143 | Unnamed: 144 | Unnamed: 145 | Unnamed: 146 | Unnamed: 147 | Unnamed: 148 | Unnamed: 149 | Unnamed: 150 | Unnamed: 151 | Unnamed: 152 | Unnamed: 153 | Unnamed: 154 | Unnamed: 155 | Unnamed: 156 | Unnamed: 157 | Unnamed: 158 | Unnamed: 159 | Unnamed: 160 | Unnamed: 161 | Unnamed: 162 | Unnamed: 163 | Unnamed: 164 | Unnamed: 165 | Unnamed: 166 | Unnamed: 167 | Unnamed: 168 | Unnamed: 169 | Unnamed: 170 | Unnamed: 171 | Unnamed: 172 | Unnamed: 173 | Unnamed: 174 | Unnamed: 175 | Unnamed: 176 | Unnamed: 177 | Unnamed: 178 | Unnamed: 179 | Unnamed: 180 | Unnamed: 181
Row Labels | Count of UID |  | Row Labels | Count of UID |  | #Total | #Done
30-Nov | 39 |  | 30-Nov | 39 |  | 39 | 39
1-Dec | 30 |  | 1-Dec | 30 |  | 30 | 30
2-Dec | 27 |  | 2-Dec | 27 |  | 27 | 27
3-Dec | 32 |  | 3-Dec | 32 |  | 32 | 32
4-Dec | 28 |  | 4-Dec | 28 |  | 28 | 28
5-Dec | 3 |  | 5-Dec | 3 |  | 3 | 3
7-Dec | 10 |  | 7-Dec | 10 |  | 10 | 10
8-Dec | 1 |  | 8-Dec | 1 |  | 1 | 1
9-Dec | 1 |  |  |  |  | 1 | 0
10-Dec | 1 |  |  |  |  | 1 | 0
11-Dec | 13 |  |  |  |  | 13 | 0
12-Dec | 41 |  |  |  |  | 41 | 0
14-Dec | 3 |  |  |  |  | 3 | 0
15-Dec | 10 |  |  |  |  | 10 | 0
16-Dec | 3 |  |  |  |  | 3 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 242 | 170
Big 3 | Total Activity | Done | WIP | #issue | Yet To Receive | %Percentage Competion
Material | 46 | 0 | 0 | 0 | 46 | 0
Customer | 3 | 0 | 0 | 0 | 3 | 0
Vendor | 1 | 0 | 0 | 0 | 1 | 0
Column Labels
| 2020-11-29 23:23 | 2020-11-29 23:22 | 2020-11-29 23:24 | 2020-11-30 00:23 | 2020-11-30 06:31 | 2020-11-30 05:54 | 2020-11-30 06:28 | 2020-11-30 06:14 | 2020-11-30 09:31 | 2020-11-30 06:47 | 2020-11-30 08:15 | 2020-11-30 06:07 | 2020-11-30 09:38 | 2020-11-30 06:58 | 2020-11-30 09:47 | 2020-11-30 14:22 | 2020-11-30 12:51 | 2020-11-30 13:37 | 2020-11-30 12:55 | 2020-11-30 10:42 | 2020-11-30 10:03 | 2020-11-30 10:10 | 2020-11-30 12:38 | 2020-11-30 12:37 | 2020-11-30 12:50 | 2020-11-30 12:58 | 2020-11-30 13:21 | 2020-11-30 13:06 | 2020-12-01 05:00 | 2020-12-01 01:38 | 2020-11-30 11:34 | 2020-11-30 14:48 | 2020-12-01 01:41 | 2020-12-01 07:31 | 2020-12-01 07:18 | 2020-12-01 09:18 | 2020-11-30 16:11 | 2020-12-01 07:55 | 2020-12-01 09:39 | 2020-12-01 10:00 | 2020-12-01 09:37 | 2020-12-01 09:41 | 2020-12-01 09:40 | 2020-12-01 09:34 | 2020-12-01 08:32 | 2020-12-01 12:09 | 2020-12-01 14:23 | 2020-12-01 13:48 | 2020-12-01 11:28 | 2020-12-01 07:10 | 2020-12-01 13:05 | 2020-12-01 15:15 | 2020-12-02 04:07 | 2020-12-01 08:19 | 2020-12-01 14:13 | 2020-12-01 14:30 | 2020-12-01 15:20 | 2020-12-02 00:18 | 2020-12-01 13:18 | 2020-12-01 12:21 | 2020-12-02 02:57 | 2020-12-01 23:36 | 2020-12-02 00:03 | 2020-12-02 07:57 | 2020-12-02 02:33 | 2020-12-02 02:35 | 2020-12-02 02:34 | 2020-12-01 15:24 | 2020-12-02 10:27 | 2020-12-02 08:09 | 2020-12-03 | 2020-11-30 10:06 | 2020-12-02 10:42 | 2020-12-02 10:47 | 2020-12-02 14:02 | 2020-12-02 14:26 | 2020-12-02 14:58 | 2020-12-02 14:21 | 2020-12-02 11:25 | 2020-12-02 09:48 | 2020-12-02 12:21 | 2020-12-03 02:31 | 2020-12-03 00:20 | 2020-12-02 14:00 | 2020-12-02 17:46 | 2020-12-04 06:30 | 2020-12-01 16:35 | 2020-12-08 09:45 | 2020-12-10 15:15 | 2020-12-10 19:15 | 2020-12-10 19:45 | 2020-12-10 20:15 | 2020-12-11 04:30 | 2020-12-11 09:00 | 2020-12-11 11:00 | 2020-12-11 09:15 | 2020-12-11 09:30 | 2020-12-11 10:30 | 2020-12-11 10:50 | 2020-12-11 11:30 | 2020-12-11 11:45 | 2020-12-11 12:00 | 2020-12-11 13:00 | 2020-12-11 13:15 | 2020-12-11 13:30 | 2020-12-11 14:00 | 2020-12-11 15:00 | 2020-12-11 16:00 | 2020-12-11 16:15 | 2020-12-11 19:00 | 2020-12-11 20:00 | 2020-12-11 21:00 | 2020-12-11 23:15 | 2020-12-12 06:15 | 2020-12-12 07:00 | 2020-12-12 07:15 | 2020-12-12 10:00 | 2020-12-12 12:15 | 2020-12-03 06:54 | 2020-12-03 15:48 | 2020-12-03 07:32 | 2020-12-03 08:19 | 2020-12-03 10:43 | 2020-12-03 09:59 | 2020-12-03 09:58 | 2020-12-03 09:57 | 2020-12-03 10:00 | 2020-12-03 09:56 | 2020-12-03 10:51 | 2020-12-03 12:07 | 2020-12-03 13:16 | 2020-12-03 13:32 | 2020-12-03 13:42 | 2020-12-03 13:28 | 2020-12-03 15:25 | 2020-12-03 14:19 | 2020-12-03 12:51 | 2020-12-03 15:12 | 2020-12-03 15:32 | 2020-12-03 12:14 | 2020-12-03 16:29 | 2020-12-03 20:43 | 2020-12-03 21:36 | 2020-12-08 16:45 | 2020-12-04 01:20 | 2020-12-04 02:09 | 2020-12-04 06:21 | 2020-12-04 00:47 | 2020-12-04 02:12 | 2020-12-04 08:21 | 2020-12-04 07:10 | 2020-12-04 11:24 | 2020-12-04 07:09 | 2020-12-04 09:22 | 2020-12-04 10:08 | 2020-12-04 09:58 | 2020-12-04 09:54 | 2020-12-04 10:18 | 2020-12-04 13:26 | 2020-12-04 12:35 | 2020-12-04 14:43 | 2020-12-04 12:47 | 2020-12-04 12:16 | 2020-12-04 09:55 | 2020-12-04 12:46 | 2020-12-05 11:36 | 2020-12-04 14:42 | 2020-12-04 15:35 | 2020-12-04 12:57 | 2020-12-04 12:01 | 2020-12-04 12:12 | 2020-12-05 01:33 | 2020-12-04 15:43 | 2020-12-04 16:04 | 2020-12-07 08:00 | 2020-12-07 00:27 | 2020-12-07 11:00 | 2020-12-07 13:15 | 2020-12-07 14:45 | 2020-12-07 19:45 | Grand Total
Count of UID | 3 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 3 | 2 | 1 | 11 | 2 | 2 | 4 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 236
Count of UID | Column Labels
Row Labels | 2020-11-29 23:23 | 2020-11-29 23:22 | 2020-11-29 23:24 | 2020-11-30 00:23 | 2020-11-30 06:31 | 2020-11-30 05:54 | 2020-11-30 06:28 | 2020-11-30 06:14 | 2020-11-30 09:31 | 2020-11-30 06:47 | 2020-11-30 08:15 | 2020-11-30 06:07 | 2020-11-30 09:38 | 2020-11-30 06:58 | 2020-11-30 09:47 | 2020-11-30 14:22 | 2020-11-30 12:51 | 2020-11-30 13:37 | 2020-11-30 12:55 | 2020-11-30 10:42 | 2020-11-30 10:03 | 2020-11-30 10:10 | 2020-11-30 12:38 | 2020-11-30 12:37 | 2020-11-30 12:50 | 2020-11-30 12:58 | 2020-11-30 13:21 | 2020-11-30 13:06 | 2020-12-01 05:00 | 2020-12-01 01:38 | 2020-11-30 11:34 | 2020-11-30 14:48 | 2020-12-01 01:41 | 2020-12-01 07:31 | 2020-12-01 07:18 | 2020-12-01 09:18 | 2020-11-30 16:11 | 2020-12-01 07:55 | 2020-12-01 09:39 | 2020-12-01 10:00 | 2020-12-01 09:37 | 2020-12-01 09:41 | 2020-12-01 09:40 | 2020-12-01 09:34 | 2020-12-01 08:32 | 2020-12-01 12:09 | 2020-12-01 14:23 | 2020-12-01 13:48 | 2020-12-01 11:28 | 2020-12-01 07:10 | 2020-12-01 13:05 | 2020-12-01 15:15 | 2020-12-02 04:07 | 2020-12-01 08:19 | 2020-12-01 14:13 | 2020-12-01 14:30 | 2020-12-01 15:20 | 2020-12-02 00:18 | 2020-12-01 13:18 | 2020-12-01 12:21 | 2020-12-02 02:57 | 2020-12-01 23:36 | 2020-12-02 00:03 | 2020-12-02 07:57 | 2020-12-02 02:33 | 2020-12-02 02:35 | 2020-12-02 02:34 | 2020-12-01 15:24 | 2020-12-02 10:27 | 2020-12-02 08:09 | 2020-12-03 | 2020-11-30 10:06 | 2020-12-02 10:42 | 2020-12-02 10:47 | 2020-12-02 14:02 | 2020-12-02 14:26 | 2020-12-02 14:58 | 2020-12-02 14:21 | 2020-12-02 11:25 | 2020-12-02 09:48 | 2020-12-02 12:21 | 2020-12-03 02:31 | 2020-12-03 00:20 | 2020-12-02 14:00 | 2020-12-02 17:46 | 2020-12-04 06:30 | 2020-12-01 16:35 | 2020-12-08 09:45 | 2020-12-10 15:15 | 2020-12-10 19:15 | 2020-12-10 19:45 | 2020-12-10 20:15 | 2020-12-11 04:30 | 2020-12-11 09:00 | 2020-12-11 11:00 | 2020-12-11 09:15 | 2020-12-11 09:30 | 2020-12-11 10:30 | 2020-12-11 10:50 | 2020-12-11 11:30 | 2020-12-11 11:45 | 2020-12-11 12:00 | 2020-12-11 13:00 | 2020-12-11 13:15 | 2020-12-11 13:30 | 2020-12-11 14:00 | 2020-12-11 15:00 | 2020-12-11 16:00 | 2020-12-11 16:15 | 2020-12-11 19:00 | 2020-12-11 20:00 | 2020-12-11 21:00 | 2020-12-11 23:15 | 2020-12-12 06:15 | 2020-12-12 07:00 | 2020-12-12 07:15 | 2020-12-12 10:00 | 2020-12-12 12:15 | 2020-12-03 06:54 | 2020-12-03 15:48 | 2020-12-03 07:32 | 2020-12-03 08:19 | 2020-12-03 10:43 | 2020-12-03 09:59 | 2020-12-03 09:58 | 2020-12-03 09:57 | 2020-12-03 10:00 | 2020-12-03 09:56 | 2020-12-03 10:51 | 2020-12-03 12:07 | 2020-12-03 13:16 | 2020-12-03 13:32 | 2020-12-03 13:42 | 2020-12-03 13:28 | 2020-12-03 15:25 | 2020-12-03 14:19 | 2020-12-03 12:51 | 2020-12-03 15:12 | 2020-12-03 15:32 | 2020-12-03 12:14 | 2020-12-03 16:29 | 2020-12-03 20:43 | 2020-12-03 21:36 | 2020-12-08 16:45 | 2020-12-04 01:20 | 2020-12-04 02:09 | 2020-12-04 06:21 | 2020-12-04 00:47 | 2020-12-04 02:12 | 2020-12-04 08:21 | 2020-12-04 07:10 | 2020-12-04 11:24 | 2020-12-04 07:09 | 2020-12-04 09:22 | 2020-12-04 10:08 | 2020-12-04 09:58 | 2020-12-04 09:54 | 2020-12-04 10:18 | 2020-12-04 13:26 | 2020-12-04 12:35 | 2020-12-04 14:43 | 2020-12-04 12:47 | 2020-12-04 12:16 | 2020-12-04 09:55 | 2020-12-04 12:46 | 2020-12-05 11:36 | 2020-12-04 14:42 | 2020-12-04 15:35 | 2020-12-04 12:57 | 2020-12-04 12:01 | 2020-12-04 12:12 | 2020-12-05 01:33 | 2020-12-04 15:43 | 2020-12-04 16:04 | 2020-12-07 08:00 | 2020-12-07 00:27 | 2020-12-07 11:00 | 2020-12-07 13:15 | 2020-12-07 14:45 | 2020-12-07 19:45 | Grand Total
ANJALI SINHA | 3 | 1 | 1 | [6 empty] | 1 | [11 empty] | 1 | [11 empty] | 1 | 1 |  |  | 1 | [5 empty] | 1 | 1 | [11 empty] | 1 | [7 empty] | 1 | 1 | 1 | [12 empty] | 1 | [7 empty] | 1 |  | 7 | 3 |  |  | 2 | [40 empty] | 1 |  |  |  | 1 | [11 empty] | 2 |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 | 1 | 1 |  |  | 2 |  | 1 |  |  |  | 45
ANKIT AGARWAL |  |  |  |  | 1 | [35 empty] | 1 |  | 1 | [6 empty] | 1 | [11 empty] | 2 | [8 empty] | 2 | 1 | [16 empty] | 1 |  |  |  |  | 3 | [6 empty] | 1 | 1 |  |  | 1 | [21 empty] | 2 | [10 empty] | 1 |  | 1 | [22 empty] | 1 |  |  |  |  | 1 | [10 empty] | 1 |  | 23
ANURAG ANAND | [10 empty] | 1 |  |  |  |  | 1 |  | 2 |  |  |  | 1 | [8 empty] | 1 | [19 empty] | 1 |  |  |  | 1 |  |  | 1 | 1 | [10 empty] | 2 | [7 empty] | 1 | 1 | [6 empty] | 1 | [11 empty] | 1 | [16 empty] | 1 |  | 1 | [32 empty] | 1 | [30 empty] | 19
DEBRAJ PAL | [28 empty] | 1 | [9 empty] | 1 | [6 empty] | 1 |  | 1 | [7 empty] | 1 | [6 empty] | 1 | [13 empty] | 1 | [14 empty] | 1 |  |  | 1 |  | 1 |  |  |  |  | 1 | 3 |  | 1 |  | 1 |  |  | 2 | 1 | 2 | [20 empty] | 1 | 1 |  | 1 | [7 empty] | 1 | [29 empty] | 1 | [6 empty] | 26
DEEPA SAW | [8 empty] | 1 |  |  |  | 1 | [9 empty] | 1 |  | 1 | 1 | 1 | 1 | [37 empty] | 1 | [25 empty] | 1 |  | 2 |  | 2 | 3 | [9 empty] | 2 | [20 empty] | 1 | [19 empty] | 1 | [15 empty] | 1 |  |  | 1 |  | 1 | [11 empty] | 23
JASPREET SINGH |  |  |  | 1 |  | 4 | 1 |  | 1 | [7 empty] | 1 |  | 1 | [10 empty] | 1 |  | 1 | [9 empty] | 1 | [21 empty] | 1 | [10 empty] | 1 | [6 empty] | 1 | [11 empty] | 2 |  |  |  |  | 1 |  |  | 1 | [6 empty] | 1 |  |  |  | 1 | [10 empty] | 1 |  |  |  |  | 1 | [16 empty] | 1 |  |  | 1 | [6 empty] | 1 | [8 empty] | 1 | [9 empty] | 1 | 1 |  |  |  |  | 29
PHANI GHANTASALA | [26 empty] | 1 | [5 empty] | 1 | [19 empty] | 1 | [6 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  | 1 |  |  |  |  | 1 |  |  | 1 | 1 |  | 1 | [5 empty] | 1 | [6 empty] | 1 |  |  |  | 1 |  |  |  | 3 | [5 empty] | 1 |  | 1 |  | 1 | 1 |  | 1 |  | 1 | [6 empty] | 1 | [10 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1 | [20 empty] | 1 |  |  |  |  | 2 |  | 1 | 31
PRADEEP CHEEDALLA | [7 empty] | 1 |  |  |  | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  | 1 | [11 empty] | 1 | [12 empty] | 1 | [7 empty] | 1 |  |  |  | 1 | [6 empty] | 1 |  |  |  |  | 2 | [9 empty] | 2 | [10 empty] | 2 | 1 | [26 empty] | 1 |  |  |  | 1 | [28 empty] | 1 |  |  |  |  | 1 | [20 empty] | 22
SHANKAR RAMNARAYANAN | [141 empty] | 1 | 1 | [37 empty] | 2
VENKATESH GANESHAN | [20 empty] | 1 | [15 empty] | 1 |  |  | 1 | [6 empty] | 1 |  |  |  |  | 1 |  | 1 | [51 empty] | 1 | [13 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | [7 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  | 1 | [19 empty] | 16
Grand Total | 3 | 1 | 1 | 1 | 1 | 4 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 3 | 2 | 1 | 11 | 2 | 2 | 4 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 2 | 1 | 3 | 3 | 1 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 1 | 1 | 236

## Misc
OLD | NEW | COMPARE | Unnamed: 3
94411 | 82574 | 82574 | 94411
3968 | 82575 | 82575 | 3968
3967 | 82561 | 82561 | 3967
3966 | 82566 | 82566 | 3966
3964 | 82567 | 82567 | 3964
82569 | 82569 | 82569 | 82569
82566 | 82570 | 82570 | 82566
82567 | 82565 | 82565 | 82567
82574 | 3967 | 3967 | 82574
82575 | 3968 | 3968 | 82575
82561 | 3966 | 3966 | 82561
10137 | 94411 | 94411 | 10137
82570 | 3964 | 3964 | 82570
89984 | 89674 | 89674 | 89984
92780 | 10137 | 10137 | 92780
5390 | 5084 | 5084 | 5390
89675 | 90888 | 90888 | 89675
82565 | 10492 | 10492 | 82565
89674 | 10138 | 10138 | 89674
5084 | 10493 | 10493 | 5084
90888 | 10494 | 10494 | 90888
89982 | 10495 | 10495 | 89982
5387 | 10496 | 10496 | 5387
5381 | 9174 | 9174 | 5381
5233 | 83323 | 83323 | 5233
5243 | 90055 | 90055 | 5243
5392 | 90890 | 90890 | 5392
5384 | 83325 | 83325 | 5384
92778 | 5090 | 5090 | 92778
10116 | 10498 | 10498 | 10116
9174 | 5096 | 5096 | 9174
10138 | 9148 | 9148 | 10138
10492 | 83324 | 83324 | 10492
95364 | 9149 | 9149 | 95364
10493 | 9150 | 9150 | 10493
10494 | 10499 | 10499 | 10494
5235 | 10526 | 10526 | 5235
92785 | 10501 | 10501 | 92785
83323 | 9151 | 9151 | 83323
10495 | 90767 | 90767 | 10495
10496 | 9928 | 9928 | 10496
8807 | 10502 | 10502 | 8807
82903 | 5100 | 5100 | 82903
5427 | 90765 | 90765 | 5427
92787 | 10528 | 10528 | 92787
5405 | 90052 | 90052 | 5405
90055 | 5121 | 5121 | 90055
83325 | 89712 | 89712 | 83325
90890 | 89711 | 89711 | 90890
5090 | 5122 | 5122 | 5090
82901 | 10503 | 10503 | 82901
5440 | 89766 | 89766 | 5440
92806 | 80859 | 80859 | 92806
5407 | 80860 | 80860 | 5407
5096 | 95038 |  | 5096
10498 | 90959 | 90959 | 10498
9148 | 90960 | 90960 | 9148
83324 | 82771 | 82771 | 83324
5429 | 82772 | 82772 | 5429
92808 | 82773 | 82773 | 92808
10118 | 82777 | 82777 | 10118
10472 | 82778 | 82778 | 10472
10526 | 90681 | 90681 | 10526
9149 | 82779 | 82779 | 9149
5177 | 90679 | 90679 | 5177
5453 | 82798 | 82798 | 5453
10473 | 90677 | 90677 | 10473
90767 | 82799 | 82799 | 90767
68443 | 82804 | 82804 | 68443
68444 | 5395 | 5395 | 68444
9150 | 5397 | 5397 | 9150
10499 | 5415 | 5415 | 10499
10120 | 5417 | 5417 | 10120
90765 | 5400 | 5400 | 90765
95508 | 5402 | 5402 | 95508
5455 | 5448 | 5448 | 5455
82908 | 5450 | 5450 | 82908
9151 | 5468 | 5468 | 9151
10501 | 5470 | 5470 | 10501
94770 | 5473 | 5473 | 94770
10110 | 5475 | 5475 | 10110
9798 | 94770 | 94770 | 9798
89712 | 9798 | 9798 | 89712
5478 | 10110 | 10110 | 5478
95506 | 90050 | 90050 | 95506
5100 | 9800 | 9800 | 5100
10502 | 5183 | 5183 | 10502
9928 | 5186 | 5186 | 9928
89711 | 90049 | 90049 | 89711
5480 | 10023 | 10023 | 5480
82906 | 5193 | 5193 | 82906
10528 | 95613 | 95613 | 10528
10023 | 9804 | 9804 | 10023
9804 | 82854 | 82854 | 9804
5121 | 10022 | 10022 | 5121
90050 | 5201 | 5201 | 90050
9800 | 5215 | 5215 | 9800
5183 | 10032 | 10032 | 5183
5193 | 5229 | 5229 | 5193
82854 | 5233 | 5233 | 82854
10503 | 5235 | 5235 | 10503
5122 | 5243 | 5243 | 5122
5415 | 95364 | 95364 | 5415
89766 | 5245 | 5245 | 89766
5395 | 5248 | 5248 | 5395
5248 | 5250 | 5250 | 5248
5448 | 5253 | 5253 | 5448
92867 | 5255 | 5255 | 92867
5468 | 5258 | 5258 | 5468
80859 | 5260 | 5260 | 80859
5186 | 4971 | 4971 | 5186
92869 | 4973 | 4973 | 92869
5450 | 5390 | 5390 | 5450
5470 | 5392 | 5392 | 5470
5397 | 92780 | 92780 | 5397
5250 | 92778 | 92778 | 5250
90049 | 92785 | 92785 | 90049
10114 | 92787 | 92787 | 10114
92874 | 92806 | 92806 | 92874
10022 | 92808 | 92808 | 10022
9810 | 92813 | 92813 | 9810
92876 | 92815 | 92815 | 92876
5417 | 10112 | 10112 | 5417
5201 | 5437 | 5437 | 5201
10112 | 92867 | 92867 | 10112
5473 | 92869 | 92869 | 5473
5437 | 92874 | 92874 | 5437
80860 | 92876 | 92876 | 80860
10032 | 8807 | 8807 | 10032
5400 | 5440 | 5440 | 5400
5475 | 5760 | 5760 | 5475
90052 | 5762 | 5762 | 90052
90959 | 82903 | 82903 | 90959
5402 | 82901 | 82901 | 5402
5253 | 5453 | 5453 | 5253
5245 | 5455 | 5455 | 5245
90960 | 5478 | 5478 | 90960
5255 | 5480 | 5480 | 5255
5229 | 5427 | 5427 | 5229
5215 | 5429 | 5429 | 5215
5258 | 10472 | 10472 | 5258
5260 | 10473 | 10473 | 5260
4971 | 68443 | 68443 | 4971
4973 | 68444 | 68444 | 4973
10474 | 10474 | 10474 | 10474
5378 | 5378 | 5378 | 5378
89987 | 5387 | 5387 | 89987
82771 | 89993 | 89993 | 82771
95613 | 89994 | 89994 | 95613
94400 | 5384 | 5384 | 94400
92846 | 5381 | 5381 | 92846
94357 | 5405 | 5405 | 94357
5760 | 5407 | 5407 | 5760
89993 | 82908 | 82908 | 89993
92844 | 82906 | 82906 | 92844
82772 | 10116 | 10116 | 82772
89994 | 10118 | 10118 | 89994
94355 | 5177 | 5177 | 94355
5762 | 10120 | 10120 | 5762
92813 | 95508 | 95508 | 92813
82773 | 95506 | 95506 | 82773
92815 | 10114 | 10114 | 92815
82777 | 9810 | 9810 | 82777
82778 | 89984 | 89984 | 82778
90681 | 89982 | 89982 | 90681
82779 | 94357 | 94357 | 82779
90679 | 94355 | 94355 | 90679
82798 | 92846 | 92846 | 82798
90677 | 92844 | 92844 | 90677
82799 | 89675 | 89675 | 82799
82804 | 94400 | 94400 | 82804
81155 | 89987 | 89987 | 81155
94412 | 81155 | 81155 | 94412
81154 | 97821 |  | 81154
96720 | 94412 | 94412 | 96720
8874 | 97761 |  | 8874
94450 | 92169 | 92169 | 94450
29564 | 90894 | 90894 | 29564
96719 | 90147 | 90147 | 96719
29567 | 90896 | 90896 | 29567
10039 | 92172 | 92172 | 10039
81152 | 92396 | 92396 | 81152
81153 | 8874 | 8874 | 81153
94452 | 94450 | 94450 | 94452
92169 | 96719 | 96719 | 92169
80925 | 96720 | 96720 | 80925
5770 | 81154 | 81154 | 5770
92840 | 81152 | 81152 | 92840
5486 | 81153 | 81153 | 5486
80928 | 80925 | 80925 | 80928
91850 | 10039 | 10039 | 91850
5698 | 94452 | 94452 | 5698
10027 | 96347 | 96347 | 10027
5765 | 96666 | 96666 | 5765
92834 | 96670 | 96670 | 92834
96347 | 97173 | 97173 | 96347
94469 | 96689 | 96689 | 94469
94467 | 94467 | 94467 | 94467
94476 | 94491 | 94491 | 94476
90407 | 96682 | 96682 | 90407
97173 | 94469 | 94469 | 97173
96692 | 94493 | 94493 | 96692
5684 | 90407 | 90407 | 5684
90147 | 8883 | 8883 | 90147
5767 | 94476 | 94476 | 5767
80929 | 94478 | 94478 | 80929
94478 | 96692 | 96692 | 94478
90894 | 94486 | 94486 | 90894
5488 | 96728 | 96728 | 5488
92832 | 96735 | 96735 | 92832
92838 | 29564 | 29564 | 92838
29570 | 80928 | 80928 | 29570
94486 | 29570 | 29570 | 94486
96728 | 29567 | 29567 | 96728
96735 | 80929 | 80929 | 96735
5772 | 29571 | 29571 | 5772
5693 | 5684 | 5684 | 5693
96670 | 91850 | 91850 | 96670
96666 | 5693 | 5693 | 96666
96689 | 5695 | 5695 | 96689
29571 | 10027 | 10027 | 29571
10029 | 5698 | 5698 | 10029
89764 | 5700 | 5700 | 89764
5700 | 10029 | 10029 | 5700
94491 | 89764 | 89764 | 94491
8883 | 89763 | 89763 | 8883
96682 | 5770 | 5770 | 96682
5695 | 5772 | 5772 | 5695
94493 | 9657 | 9657 | 94493
89763 | 9659 | 9659 | 89763
9657 | 97529 | 97529 | 9657
90896 | 97523 | 97523 | 90896
97523 | 9661 | 9661 | 97523
97529 | 9663 | 9663 | 97529
9659 | 97540 | 97540 | 9659
92172 | 97542 | 97542 | 92172
92396 | 97532 | 97532 | 92396
97532 | 97534 | 97534 | 97532
97540 | 5486 | 5486 | 97540
9661 | 5488 | 5488 | 9661
97542 | 5765 | 5765 | 97542
97534 | 5767 | 5767 | 97534
9663 | 92840 | 92840 | 9663
8788 | 92838 | 92838 | 8788
8790 | 92834 | 92834 | 8790
8792 | 92832 | 92832 | 8792
5190 | 8788 | 8788 | 5190
8797 | 5190 | 5190 | 8797
8799 | 8797 | 8797 | 8799
| 8799 | 8799
| 8790 | 8790
| 8792 | 8792

## Object Status
Sl. No | Object ID | Description | Process Area | Transform Task ID | Load Task ID | Extract & Transform Status | ET Planned End Date | ET Defects | ET Comments | Load Status | Load Planned End Date | Load Defects | Load Comments
24 | DAT_C0232 | Qualifications from AS8 (TTN) and MP2 (Dixie) | DAT | 21156 | 4963
18 | DAT_C0234 | Conversion of Non-Employees (Contractors) | DAT | 4971 | 4973 | Yet to receive | 2021-01-25 13:15 | 0 | 0 | Yet to receive | 2021-01-25 13:30 | 0 | 0
16 | ITR_C0016 | Convert Functional Locations - Asset Suite | ITR | 5390 | 5392 | Yet to receive | 2021-01-18 09:30 | 0 | 0 | Yet to receive | 2021-01-18 11:00 | 0 | 0
17 | ITR_C0016.1 | Convert Functional Locations – MP2 | ITR | 92780 | 92778 | Yet to receive | 2021-01-18 09:30 | 0 | 0 | Yet to receive | 2021-01-18 11:30 | 0 | 0
3 | ITR_C0018 | Convert equipment – Asset Suite | ITR | 5395 | 5397 | Yet to receive | 2021-01-21 11:00 | 0 | 0 | Yet to receive | 2021-01-21 12:00 | 0 | 0
4 | ITR_C0018.1 | Convert equipment – MP2 | ITR | 92785 | 92787 | Yet to receive | 2021-01-18 16:30 | 0 | 0 | Yet to receive | 2021-01-18 18:30 | 0 | 0
48 | ITR_C0020 | Convert BOM – Functional location Conversion – Asset Suite | ITR | 5415 | 5417 | Yet to receive | 2021-01-21 11:00 | 0 | 0 | Yet to receive | 2021-01-21 16:45 | 0 | 0
61 | ITR_C0024 | Convert BOM - Material / Assemblies Conversion – Asset Suite | ITR | 5400 | 5402 | Yet to receive | 2021-01-22 09:15 | 0 | 0 | Yet to receive | 2021-01-22 10:15 | 0 | 0
46 | ITR_C0028 | Convert Equipment Classification Values – Asset Suite | ITR | 10112 | 5437 | Yet to receive | 2021-01-21 20:00 | 0 | 0 | Yet to receive | 2021-01-21 20:20 | 0 | 0
47 | ITR_C0028.1 | Convert Equipment Classification Values – MP2 | ITR | 82865 | 82863
1 | ITR_C0030 | Convert Functional Location Classification Values – Asset Suite | ITR | 8807 | 5440 | Yet to receive | 2021-01-18 20:30 | 0 | 0 | Yet to receive | 2021-01-18 21:00 | 0 | 0
67 | ITR_C0032 | Convert Open work orders – Asset Suite | ITR | 5760 | 5762 | Yet to receive | 2021-01-26 12:15 | 0 | 0 | Yet to receive | 2021-01-26 13:15 | 0 | 0
68 | ITR_C0032.1 | Convert Open work orders – MP2 | ITR | 92846 | 92844 | Yet to receive | 2021-01-26 10:45 | 0 | 0 | Yet to receive | 2021-01-26 12:15 | 0 | 0
65 | ITR_C0035 | Convert Open Notifications – Asset Suite | ITR | 5765 | 5767 | Yet to receive | 2021-01-31 19:00 | 0 | 0 | Yet to receive | 2021-01-31 19:20 | 0 | 0
25 | ITR_C0038 | Convert Task Lists – Functional Location Conversion - PTM | ITR | 82903 | 82901 | Yet to receive | 2021-01-18 20:30 | 0 | 0 | Yet to receive | 2021-01-18 21:00 | 0 | 0
26 | ITR_C0038.1 | Convert Task Lists – Functional Location Conversion – Asset Suite | ITR | 5448 | 5450 | Yet to receive | 2021-01-21 09:00 | 0 | 0 | Yet to receive | 2021-01-21 10:00 | 0 | 0
2 | ITR_C0038.2 | Convert Task Lists – Functional Location Conversion - Maintelligence | ITR | 5453 | 5455 | Yet to receive | 2021-01-19 14:30 | 0 | 0 | Yet to receive | 2021-01-19 16:30 | 0 | 0
43 | ITR_C0038.6 | Convert Task Lists - General Conversion – Asset Suite | ITR | 5468 | 5470 | Yet to receive | 2021-01-21 09:00 | 0 | 0 | Yet to receive | 2021-01-21 10:45 | 0 | 0
44 | ITR_C0038.7 | Convert Task Lists - General Conversion – MP2 | ITR | 92867 | 92869 | Yet to receive | 2021-01-21 08:00 | 0 | 0 | Yet to receive | 2021-01-21 10:00 | 0 | 0
52 | ITR_C0050 | Convert Maintenance Plans Conversion – Asset Suite | ITR | 5473 | 5475 | Yet to receive | 2021-01-21 22:00 | 0 | 0 | Yet to receive | 2021-01-22 08:00 | 0 | 0
53 | ITR_C0050.1 | Convert Maintenance Plans Conversion - Maintelligence | ITR | 5478 | 5480 | Yet to receive | 2021-01-20 06:15 | 0 | 0 | Yet to receive | 2021-01-20 07:45 | 0 | 0
54 | ITR_C0050.2 | Convert Maintenance Plans Conversion – MP2 | ITR | 92874 | 92876 | Yet to receive | 2021-01-21 14:00 | 0 | 0 | Yet to receive | 2021-01-21 16:00 | 0 | 0
36 | ITR_C0055 | Convert Measuring Points (with catalogs) – Maintelligence | ITR | 5427 | 5429 | Yet to receive | 2021-01-18 20:30 | 0 | 0 | Yet to receive | 2021-01-19 06:30 | 0 | 0
37 | ITR_C0055 | Measuring Points - Classification | ITR | 10472 | 10473 | Yet to receive | 2021-01-19 10:30 | 0 | 0 | Yet to receive | 2021-01-19 10:30 | 0 | 0
38 | ITR_C0055 | Measuring Points - Entry List | ITR | 68443 | 68444 | Yet to receive | 2021-01-19 12:30 | 0 | 0 | Yet to receive | 2021-01-19 12:30 | 0 | 0
39 | ITR_C0055.1 | Convert Measuring Points (with catalogs) - Asset Suite | ITR | 82879 | 82877
22 | ITR_C0058 | Convert Measuring Points (with catalogs) – MP2 | ITR | 82890 | 82888
21 | ITR_C0061 | Convert Work Center - HR Assignments Conversion | ITR | 10474 | 5378 | Yet to receive | 2021-01-25 19:00 | 0 | 0 | Yet to receive | 2021-01-25 19:20 | 0 | 0
63 | ITR_C0062 | Convert Work order history - Asset Suite | ITR | 5486 | 5488 | Yet to receive | 2021-01-31 19:30 | 0 | 0 | Yet to receive | 2021-01-31 20:15 | 0 | 0
64 | ITR_C0062.1 | Convert Work order history – MP2 | ITR | 92840 | 92838 | Yet to receive | 2021-01-31 18:30 | 0 | 0 | Yet to receive | 2021-01-31 20:30 | 0 | 0
9 | ITR_C0064 | Convert Code and Code groups | ITR | 5387 | 5387 | Yet to receive | 2021-01-18 11:00 | 0 | 0 | Yet to receive | 2021-01-18 10:00 | 0 | 0
20 | ITR_C0065 | Convert Documents (Document Management System) - MP2 | ITR | 92806 | 92808 | Yet to receive | 2021-01-19 06:30 | 0 | 0 | Yet to receive | 2021-01-19 07:15 | 0 | 0
67 | ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite | ITR | 89993 | 89994 | Yet to receive | 2021-01-26 12:15 | 0 | 0 | Yet to receive | 2021-01-26 12:35 | 0 | 0
66 | ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite (T-4) | ITR | 89993 | 89994 | Yet to receive | 2021-01-26 12:15 | 0 | 0 | Yet to receive | 2021-01-26 12:35 | 0 | 0
67 | ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite | ITR | 5770 | 5772 | Yet to receive | 2021-01-31 21:30 | 0 | 0 | Yet to receive | 2021-01-31 22:00 | 0 | 0
62 | ITR_C0067.1 | Convert Scheduled Maintenance Plans – MP2 | ITR | 92834 | 92832 | Yet to receive | 2021-01-31 18:30 | 0 | 0 | Yet to receive | 2021-01-31 20:30 | 0 | 0
14 | ITR_C0069 | Convert Classes | ITR | 5384 | 5384 | Yet to receive | 2021-01-18 12:30 | 0 | 0 | Yet to receive | 2021-01-18 11:30 | 0 | 0
10 | ITR_C0070 | Convert Characteristics | ITR | 5381 | 5381 | Yet to receive | 2021-01-18 11:00 | 0 | 0 | Yet to receive | 2021-01-18 10:00 | 0 | 0
32 | ITR_C0071 | Convert Documents (Document Management System) - Asset Suite | ITR | 5405 | 5407 | Yet to receive | 2021-01-18 21:00 | 0 | 0 | Yet to receive | 2021-01-18 21:30 | 0 | 0
55 | ITR_C0175 | Convert Measuring documents - Maintelligence | ITR | 82908 | 82906 | Yet to receive | 2021-01-19 18:30 | 0 | 0 | Yet to receive | 2021-01-20 08:00 | 0 | 0
85 | MDG_C0098 | Asset Suite Material Master - Delta | MDG | 82772 | 82778 | Yet to receive | 2021-01-26 16:30 | 0 | 0 | Yet to receive | 2021-01-27 10:00 | 0 | 0
83 | MDG_C0098 | MAP - Asset Suite | MDG | 80928 | 29570 | Yet to receive | 2021-01-31 19:30 | 0 | 0 | Yet to receive | 2021-01-31 20:30 | 0 | 0
84 | MDG_C0098 | MAP - ECC | MDG | 80929 | 29571 | Yet to receive | 2021-01-31 21:30 | 0 | 0 | Yet to receive | 2021-01-31 23:30 | 0 | 0
75 | MDG_C0098 | Asset Suite - Basic View | MDG | 10492 | 10498 | Yet to receive | 2021-01-18 13:45 | 0 | 0 | Yet to receive | 2021-01-19 06:00 | 0 | 0
76 | MDG_C0098 | Asset Suite - Purchasing/MRP View | MDG | 10493 | 10499 | Yet to receive | 2021-01-18 14:45 | 0 | 0 | Yet to receive | 2021-01-19 14:00 | 0 | 0
77 | MDG_C0098 | Asset Suite - Accounting View | MDG | 10494 | 10499 | Yet to receive | 2021-01-18 15:45 | 0 | 0 | Yet to receive | 2021-01-19 14:00 | 0 | 0
78 | MDG_C0098 | Asset Suite - Storage View | MDG | 10495 | 10501 | Yet to receive | 2021-01-18 16:45 | 0 | 0 | Yet to receive | 2021-01-19 18:00 | 0 | 0
79 | MDG_C0098 | Asset Suite - Sales View | MDG | 10496 | 10502 | Yet to receive | 2021-01-18 17:45 | 0 | 0 | Yet to receive | 2021-01-19 21:00 | 0 | 0
80 | MDG_C0098 | Asset Suite - Classification View | MDG | 10526 | 10528 | Yet to receive | 2021-01-19 10:00 | 0 | 0 | Yet to receive | 2021-01-20 09:30 | 0 | 0
81 | MDG_C0098 | Manual File - SPECS Semi Finished Goods | MDG | 9174 | 83325 | #done | 2021-01-18 15:45 | 0 | 0 | Yet to receive | 2021-01-18 20:00 | 0 | 0
82 | MDG_C0098 | Manual File - Consumer Units File | MDG | 90888 | 90890 | Yet to receive | 2021-01-18 11:15 | 0 | 0 | Yet to receive | 2021-01-18 20:00 | 0 | 0
15 | NTO_C0156 | Convert Claims from ECC - S4 | NTO | 5741 | 90108
11 | NTO_C0157 | Convert Inventory Pooling from ECC - S4 | NTO | 5736 | 5738
27 | NTO_C0170 | Open Deductions | NTO | 5746 | 5748
70 | NTO_C0222 | Upload the history of data sources that are pertinent to Customer Program's calculations | NTO | 68505 | 68507
8 | NTO_C0230 | PROS Transaction History Table | NTO | 81783 | 81781
12 | OTC_C0079 | Open Sales Order conversion | OTC | 5708 | 5710
19 | OTC_C0164 | Convert Open AR Invoices from ECC to S/4 | OTC | 5716 | 5718
28 | OTC_C0166.1 | Convert Open collections Activity from Get Paid to S/4 | OTC | 5721 | 5723
13 | PTM_C0079 | Convert Work center objects from ECC to S4HANA platform | PTM | 10116 | 10120 | Yet to receive | 2021-01-18 13:00 | 0 | 0 | Yet to receive | 2021-01-19 14:15 | 0 | 0
41 | PTM_C0080 | Convert Repetitive Manufacturing BOMs | PTM | 9798 | 9800 | Yet to receive | 2021-01-20 08:15 | 0 | 0 | Yet to receive | 2021-01-20 12:45 | 0 | 0
40 | PTM_C0080 | Convert MBOMs | PTM | 10110 | 5183 | Yet to receive | 2021-01-20 11:15 | 0 | 0 | Yet to receive | 2021-01-20 12:45 | 0 | 0
42 | PTM_C0080 | Convert Costing BOMs | PTM | 8788 | 5190 | Yet to receive | 2021-02-02 10:45 | 0 | 0 | Yet to receive | 2021-02-02 11:15 | 0 | 0
33 | PTM_C0082 | Convert Routings | PTM | 10023 | 5193 | Yet to receive | 2021-01-20 12:00 | 0 | 0 | Yet to receive | 2021-01-20 13:00 | 0 | 0
34 | PTM_C0082 | Convert Repetitive Manufacturing Routings | PTM | 9804 | 82854 | Yet to receive | 2021-01-20 13:00 | 0 | 0 | Yet to receive | 2021-01-20 14:00 | 0 | 0
35 | PTM_C0082 | Convert Costing Routings | PTM | 8790 | 8792 | Yet to receive | 2021-02-02 10:00 | 0 | 0 | Yet to receive | 2021-02-02 10:15 | 0 | 0
50 | PTM_C0085 | Convert Production Versions - Repetitive Manufacturing | PTM | 10114 | 9810 | Yet to receive | 2021-01-21 14:30 | 0 | 0 | Yet to receive | 2021-01-21 14:45 | 0 | 0
49 | PTM_C0085 | Convert Production Versions | PTM | 10022 | 5201 | Yet to receive | 2021-01-21 16:00 | 0 | 0 | Yet to receive | 2021-01-21 18:00 | 0 | 0
51 | PTM_C0085 | Convert Production Versions - Costing | PTM | 8797 | 8799 | Yet to receive | 2021-02-02 18:15 | 0 | 0 | Yet to receive | 2021-02-02 18:30 | 0 | 0
69 | PTM_C0092 | Convert Product Cost Collectors | PTM | 5215 | 5215 | Yet to receive | 2021-01-22 18:00 | 0 | 0 | Yet to receive | 2021-01-22 17:00 | 0 | 0
56 | PTM_C0201 | PTM_C0201 GBB - JDA Inventory | PTM | 90407 | 8883 | Yet to receive | 2021-01-31 20:00 | 0 | 0 | Yet to receive | 2021-02-01 03:30 | 0 | 0
57 | PTM_C0201 | PTM_C0201 HUT - JDA Inventory | PTM | 90407 | 94486 | Yet to receive | 2021-01-31 20:00 | 0 | 0 | Yet to receive | 2021-01-31 21:30 | 0 | 0
59 | PTM_C0201 | PTM_C0201 GBB - AS8 MRO Inventory | PTM | 94469 | 94493 | Yet to receive | 2021-01-31 19:45 | 0 | 0 | Yet to receive | 2021-02-01 05:30 | 0 | 0
60 | PTM_C0201 | PTM_C0201 GBD - AS8 MRO Inventory | PTM | 94469 | 94492 | Yet to receive | 2021-01-31 19:45 | 0 | 0
58 | PTM_C0201 | PTM_C0201 GBP - ECC MRO Inventory | PTM | 94467 | 94491 | Yet to receive | 2021-01-31 19:45 | 0 | 0 | Yet to receive | 2021-02-01 03:30 | 0 | 0
59 | PTM_C0201 | PTM_C0201 LVP - ECC MRO Inventory | PTM | 94467 | 94490 | Yet to receive | 2021-01-31 19:45 | 0 | 0
60 | PTM_C0201 | PTM_C0201 GBB - E80 FG Inventory | PTM | 94476 | 94478 | Yet to receive | 2021-01-31 19:00 | 0 | 0 | Yet to receive | 2021-01-31 19:30 | 0 | 0
58 | PTM_C0201 | PTM_C0201 GBP - SPG FG Inventory | PTM | 94604 | 94602
59 | PTM_C0201 | PTM_C0201 GBD - SAP WM FG Inventory | PTM | 94461 | 94599
60 | PTM_C0201 | PTM_C0201 LVP - SAP WM FG/SFG Inventory | PTM | 94461 | 93695
58 | PTM_C0201 | PTM_C0201 MCD - DSC Inventory | PTM | 94459 | 93120
23 | PTM_C0202 | Convert Truck/Transportation Load Data (Transportation Unit) | PTM | 5684 | 5684 | Yet to receive | 2021-01-31 22:00 | 0 | 0 | Yet to receive | 2021-01-31 19:00 | 0 | 0
45 | PTM_C0205 | Convert Product Master | PTM | 10032 | 5229 | Yet to receive | 2021-01-22 11:00 | 0 | 0 | Yet to receive | 2021-01-22 16:00 | 0 | 0
7 | PTP_C0001 | Convert PTP Contracts - ECC | PTP | 5233 | 5235 | Yet to receive | 2021-01-18 12:45 | 0 | 0 | Yet to receive | 2021-01-18 14:45 | 0 | 0
29 | PTP_C0005 | Convert Open Purchase Orders - ECC | PTP | 5693 | 5695 | Yet to receive | 2021-02-01 00:15 | 0 | 0 | Yet to receive | 2021-02-01 05:15 | 0 | 0
30 | PTP_C0005.1 | Convert Open Purchase Orders - AS8 Open PO | PTP | 5698 | 5700 | Yet to receive | 2021-01-31 20:30 | 0 | 0 | Yet to receive | 2021-02-01 00:30 | 0 | 0
31 | PTP_C0005.1 | Convert Open Purchase Orders - AS8 Service PO | PTP | 10027 | 10029 | Yet to receive | 2021-01-31 21:30 | 0 | 0 | Yet to receive | 2021-02-01 00:30 | 0 | 0
5 | PTP_C0008 | Convert Purchase Info Record - ECC | PTP | 5243 | 5245 | Yet to receive | 2021-01-18 11:45 | 0 | 0 | Yet to receive | 2021-01-22 11:00 | 0 | 0
6 | PTP_C0008.1 | Convert Purchase Info Record - Asset Suite | PTP | 5248 | 5250 | Yet to receive | 2021-01-21 10:00 | 0 | 0 | Yet to receive | 2021-01-21 12:00 | 0 | 0
71 | PTP_C0200 | AS8 Source List Conversion | PTP | 5253 | 5255 | Yet to receive | 2021-01-22 13:00 | 0 | 0 | Yet to receive | 2021-01-22 14:00 | 0 | 0
72 | PTP_C0200.1 | Convert Source List - ECC | PTP | 5258 | 5260 | Yet to receive | 2021-01-22 19:00 | 0 | 0 | Yet to receive | 2021-01-22 20:00 | 0 | 0
73 | PTP_C0236 | Convert Goods Receipt | PTP | 9657 | 9659 | Yet to receive | 2021-02-01 14:00 | 0 | 0 | Yet to receive | 2021-02-01 16:00 | 0 | 0
74 | PTP_C0237 | Convert Goods Receipt Inventory Adjustment | PTP | 9661 | 9663 | Yet to receive | 2021-02-01 20:00 | 0 | 0 | Yet to receive | 2021-02-01 22:00 | 0 | 0

## Objects
RICEFW ID* | Description*
ITR_C0016 | Convert Functional Locations - Asset Suite
ITR_C0016.1 | Convert Functional Locations – MP2
ITR_C0018 | Convert equipment – Asset Suite
ITR_C0018.1 | Convert equipment – MP2
ITR_C0020 | Convert BOM – Functional location Conversion – Asset Suite
ITR_C0024 | Convert BOM - Material / Assemblies Conversion – Asset Suite
ITR_C0028 | Convert Equipment Classification Values – Asset Suite
ITR_C0028.1 | Convert Equipment Classification Values – MP2
ITR_C0030 | Convert Functional Location Classification Values – Asset Suite
ITR_C0032 | Convert Open work orders – Asset Suite
ITR_C0032.1 | Convert Open work orders – MP2
ITR_C0035 | Convert Open Notifications – Asset Suite
ITR_C0038 | Convert Task Lists – Functional Location Conversion - PTM
ITR_C0038.1 | Convert Task Lists – Functional Location Conversion – Asset Suite
ITR_C0038.2 | Convert Task Lists – Functional Location Conversion - Maintelligence
ITR_C0038.6 | Convert Task Lists - General Conversion – Asset Suite
ITR_C0038.7 | Convert Task Lists - General Conversion – MP2
ITR_C0050 | Convert Maintenance Plans Conversion – Asset Suite
ITR_C0050.1 | Convert Maintenance Plans Conversion - Maintelligence
ITR_C0050.2 | Convert Maintenance Plans Conversion – MP2
ITR_C0055 | Convert Measuring Points (with catalogs) – Maintelligence
ITR_C0055.1 | Convert Measuring Points (with catalogs) - Asset Suite
ITR_C0058 | Convert Measuring Points (with catalogs) – MP2
ITR_C0061 | Convert Work Center - HR Assignments Conversion
ITR_C0062 | Convert Work order history - Asset Suite
ITR_C0062.1 | Convert Work order history – MP2
ITR_C0064 | Convert Code and Code groups
ITR_C0065 | Convert Documents (Document Management System) - MP2
ITR_C0067 | Convert Scheduled Maintenance Plans – Asset suite
ITR_C0067.1 | Convert Scheduled Maintenance Plans – MP2
ITR_C0069 | Convert Classes
ITR_C0070 | Convert Characteristics
ITR_C0071 | Convert Documents (Document Management System) - Asset Suite
ITR_C0175 | Convert Measuring documents - Maintelligence
DAT_C0232 | Qualifications from AS8 (TTN) and MP2 (Dixie)
DAT_C0234 | Conversion of Non-Employees (Contractors)
MDG_C0098 | Asset Suite Material Master
NTO_C0156 | Convert Claims from ECC - S4
NTO_C0157 | Convert Inventory Pooling from ECC - S4
NTO_C0170 | Open Deductions
NTO_C0222 | Upload the history of data sources that are pertinent to Customer Program's calculations
NTO_C0230 | PROS Transaction History Table
OTC_C0079 | Open Sales Order conversion
OTC_C0164 | Convert Open AR Invoices from ECC to S/4
OTC_C0166.1 | Convert Open collections Activity from Get Paid to S/4
PTM_C0079 | Convert Work center objects from ECC to S4HANA platform
PTM_C0080 | Convert Bill of Materials required from ECC to S4HANA platform
PTM_C0082 | Convert Routing required for Planning & Execution from ECC systems to S4HANA platform
PTM_C0085 | Convert Production versions required for Planning & Execution from ECC to S4HANA platform
PTM_C0092 | Convert Product Cost Collectors
PTM_C0201 | Convert EWM / IM Inventory (HU & Non HU)(Unrestricted, Quality, Blocked)
PTM_C0202 | Convert Truck/Transportation Load Data (Transportation Unit)
PTM_C0205 | Convert Product Master
PTP_C0001 | Convert PTP Contracts - ECC
PTP_C0005 | Convert Open Purchase Orders - ECC
PTP_C0005.1 | Convert Open Purchase Orders - Asset Suite (2 types)
PTP_C0008 | Convert Purchase Info Record - ECC
PTP_C0008.1 | Convert Purchase Info Record - Asset Suite
PTP_C0200 | AS8 Source List Conversion
PTP_C0200.1 | Convert Source List - ECC
PTP_C0236 | Convert Goods Receipt
PTP_C0237 | Convert Goods Receipt Inventory Adjustment